## READ ME
GENERAL NOTES:
1. | REQUIRED TO BE SENT TO WBOA LAND PROGRAM MANAGER, THE 1ST WEEK OF EVERY MONTH THROUGHOUT THE PROJECT
2. | ENTER PROJECT AND CONSULTANT FIRM INFORMATION UNDER "FILE…PRINT…PAGE SETUP... AND HEADER"
3. | ENTER APPROPIATE MONTH UNDER EACH HEADING (ROW 2 AND ROW 9)
4. | POPULATE CELLS (THAT ARE NOT LOCKED) FOR PROJECT PROGESS ITEMS
5. | SOME CELLS MAY NOT BE RELEVANT TO THE PROJECT. ENTER N/A OR --- ACCORDINGLY
6. | ADD ROWS, AS NECESSARY, FOR ADDITIONAL PARCEL(S)

## PROJ. NO XXXX
Project Tracking
Month of XXXXX
Project |  |  | HazMat Phase 1 | HazMat Phase 2-4 | Ag Impact Statement | Arch/Hist Study | Section 106 Review | Field Reconn | Mapped Record | Land Acquisition Proposal | Exhibit A Map - Proposed Land Acquisition | Land Surveys | Relocation Order Filed with Co. Clerk | Relocation Order Updates | Final Land Acquisition Report | Exhibit A Map - Final Land Acquisition | Updated BOA Land Inventory Spreadsheet | Final Land Acquisition - Exhibit 'A' Map (Sponsor's Signature Included) | Status, Comments, or Action Steps
Parcel Tracking
f
Parcel No. | Interest Type (Fee, AE, or CZE & AE) | Owner | Relocation Plan Completed | Relocation Plan Approved | Records Research & Title Work Requested | Title Work Received | Property Surveys | Conveyance Documents & Maps | Brochure & Introduction Letter Mailed | Apprasial | Appraisal Review | Appraisal Revisions | Approved Offer & Recommended Purchase Price | Replacement Housing Payment Determination Completed | Replacement Housing Payment Approved | Appraisal Offer & Offer to Purchase Letter Issued | Initiation of Negotiations | Relocation Eligibility Benefits Presented & 90-Day Assurance Issued | 60-Day Deadline Date for Owner Appraisal | Revised Offer | Administrative Settlement Report | Signed Conveyance | Check Voucher Recorded | Conveyance Document Recorded | Jurisdictional Offer | Payment Issued | Lis Pendens | Award of Damages Recorded | 2 - Year Appeal Start Date | 2 - Year Appeal End Date | 90-Day Vacate Notice Issued | 30-Day Vacate Notice Issued | Vacate Date | Parcel Filed | Parcel Closed | Acquisition Amount | Date Acquired | Recorded Document | Status, Comments, or Action Steps