## TaskList
2017-05-18 | [13 empty] | Improvement Type | [11 empty] | Total Effort Needed (hrs) | [6 empty] | Clerical/Administration | [8 empty] | Construction Engineer | [8 empty] | Construction Project Manager | [8 empty] | Construction Specialist/Professional | [8 empty] | Construction Technician | [8 empty] | Design Engineer | [8 empty] | Design Project Manager | [8 empty] | Design Specialist/Professional | [8 empty] | Design Technician | [8 empty] | Environmental Engineer | [8 empty] | Environmental Project Manager | [8 empty] | Environmental Specialist/Professional | [8 empty] | Maintenance Engineer | [8 empty] | Maintenance Project Manager | [8 empty] | Maintenance Specialist/Professional | [8 empty] | Maintenance Technician | [8 empty] | Manager/Director | [8 empty] | Materials/Pavements Engineer | [8 empty] | Materials/Pavements Project Manager | [8 empty] | Materials/Pavements Specialist/Professional | [8 empty] | Materials/Pavements Technician | [8 empty] | Planning Engineer | [8 empty] | Planning Project Manager | [8 empty] | Planning Specialist/Professional | [8 empty] | Real Estate Project Manager | [8 empty] | Real Estate Specialist/Professional | [8 empty] | Structure Engineer | [8 empty] | Structure Project Manager | [8 empty] | Structure Specialist/Professional | [8 empty] | Structure Technician | [8 empty] | Survey Project Manager | [8 empty] | Survey Specialist/Professional | [8 empty] | Survey Technician | [8 empty] | Traffic Engineer | [8 empty] | Traffic Project Manager | [8 empty] | Traffic Specialist/Professional | [8 empty] | Traffic Technician | [8 empty] | Utilities Engineer | [8 empty] | Utilities Project Manager | [8 empty] | Utilities Specialist/Professional
Outline | Activity Task | Activity Task Description | [23 empty] | Low | Medium | High | Clerical/Administration - Entry | Clerical/Administration - Entry | Clerical/Administration - Entry | Clerical/Administration - Mid | Clerical/Administration - Mid | Clerical/Administration - Mid | Clerical/Administration - High | Clerical/Administration - High | Clerical/Administration - High | Construction Engineer - Entry | Construction Engineer - Entry | Construction Engineer - Entry | Construction Engineer - Mid | Construction Engineer - Mid | Construction Engineer - Mid | Construction Engineer - High | Construction Engineer - High | Construction Engineer - High | Construction Project Manager - Entry | Construction Project Manager - Entry | Construction Project Manager - Entry | Construction Project Manager - Mid | Construction Project Manager - Mid | Construction Project Manager - Mid | Construction Project Manager - High | Construction Project Manager - High | Construction Project Manager - High | Construction Specialist/Professional - Entry | Construction Specialist/Professional - Entry | Construction Specialist/Professional - Entry | Construction Specialist/Professional - Mid | Construction Specialist/Professional - Mid | Construction Specialist/Professional - Mid | Construction Specialist/Professional - High | Construction Specialist/Professional - High | Construction Specialist/Professional - High | Construction Technician - Entry | Construction Technician - Entry | Construction Technician - Entry | Construction Technician - Mid | Construction Technician - Mid | Construction Technician - Mid | Construction Technician - High | Construction Technician - High | Construction Technician - High | Design Engineer - Entry | Design Engineer - Entry | Design Engineer - Entry | Design Engineer - Mid | Design Engineer - Mid | Design Engineer - Mid | Design Engineer - High | Design Engineer - High | Design Engineer - High | Design Project Manager - Entry | Design Project Manager - Entry | Design Project Manager - Entry | Design Project Manager - Mid | Design Project Manager - Mid | Design Project Manager - Mid | Design Project Manager - High | Design Project Manager - High | Design Project Manager - High | Design Specialist/Professional - Entry | Design Specialist/Professional - Entry | Design Specialist/Professional - Entry | Design Specialist/Professional - Mid | Design Specialist/Professional - Mid | Design Specialist/Professional - Mid | Design Specialist/Professional - High | Design Specialist/Professional - High | Design Specialist/Professional - High | Design Technician - Entry | Design Technician - Entry | Design Technician - Entry | Design Technician - Mid | Design Technician - Mid | Design Technician - Mid | Design Technician - High | Design Technician - High | Design Technician - High | Environmental Engineer - Entry | Environmental Engineer - Entry | Environmental Engineer - Entry | Environmental Engineer - Mid | Environmental Engineer - Mid | Environmental Engineer - Mid | Environmental Engineer - High | Environmental Engineer - High | Environmental Engineer - High | Environmental Project Manager - Entry | Environmental Project Manager - Entry | Environmental Project Manager - Entry | Environmental Project Manager - Mid | Environmental Project Manager - Mid | Environmental Project Manager - Mid | Environmental Project Manager - High | Environmental Project Manager - High | Environmental Project Manager - High | Environmental Specialist/Professional - Entry | Environmental Specialist/Professional - Entry | Environmental Specialist/Professional - Entry | Environmental Specialist/Professional - Mid | Environmental Specialist/Professional - Mid | Environmental Specialist/Professional - Mid | Environmental Specialist/Professional - High | Environmental Specialist/Professional - High | Environmental Specialist/Professional - High | Maintenance Engineer - Entry | Maintenance Engineer - Entry | Maintenance Engineer - Entry | Maintenance Engineer - Mid | Maintenance Engineer - Mid | Maintenance Engineer - Mid | Maintenance Engineer - High | Maintenance Engineer - High | Maintenance Engineer - High | Maintenance Project Manager - Entry | Maintenance Project Manager - Entry | Maintenance Project Manager - Entry | Maintenance Project Manager - Mid | Maintenance Project Manager - Mid | Maintenance Project Manager - Mid | Maintenance Project Manager - High | Maintenance Project Manager - High | Maintenance Project Manager - High | Maintenance Specialist/Professional - Entry | Maintenance Specialist/Professional - Entry | Maintenance Specialist/Professional - Entry | Maintenance Specialist/Professional - Mid | Maintenance Specialist/Professional - Mid | Maintenance Specialist/Professional - Mid | Maintenance Specialist/Professional - High | Maintenance Specialist/Professional - High | Maintenance Specialist/Professional - High | Maintenance Technician - Entry | Maintenance Technician - Entry | Maintenance Technician - Entry | Maintenance Technician - Mid | Maintenance Technician - Mid | Maintenance Technician - Mid | Maintenance Technician - High | Maintenance Technician - High | Maintenance Technician - High | Manager/Director - Entry | Manager/Director - Entry | Manager/Director - Entry | Manager/Director - Mid | Manager/Director - Mid | Manager/Director - Mid | Manager/Director - High | Manager/Director - High | Manager/Director - High | Materials/Pavements Engineer - Entry | Materials/Pavements Engineer - Entry | Materials/Pavements Engineer - Entry | Materials/Pavements Engineer - Mid | Materials/Pavements Engineer - Mid | Materials/Pavements Engineer - Mid | Materials/Pavements Engineer - High | Materials/Pavements Engineer - High | Materials/Pavements Engineer - High | Materials/Pavements Project Manager - Entry | Materials/Pavements Project Manager - Entry | Materials/Pavements Project Manager - Entry | Materials/Pavements Project Manager - Mid | Materials/Pavements Project Manager - Mid | Materials/Pavements Project Manager - Mid | Materials/Pavements Project Manager - High | Materials/Pavements Project Manager - High | Materials/Pavements Project Manager - High | Materials/Pavements Specialist/Professional - Entry | Materials/Pavements Specialist/Professional - Entry | Materials/Pavements Specialist/Professional - Entry | Materials/Pavements Specialist/Professional - Mid | Materials/Pavements Specialist/Professional - Mid | Materials/Pavements Specialist/Professional - Mid | Materials/Pavements Specialist/Professional - High | Materials/Pavements Specialist/Professional - High | Materials/Pavements Specialist/Professional - High | Materials/Pavements Technician - Entry | Materials/Pavements Technician - Entry | Materials/Pavements Technician - Entry | Materials/Pavements Technician - Mid | Materials/Pavements Technician - Mid | Materials/Pavements Technician - Mid | Materials/Pavements Technician - High | Materials/Pavements Technician - High | Materials/Pavements Technician - High | Planning Engineer - Entry | Planning Engineer - Entry | Planning Engineer - Entry | Planning Engineer - Mid | Planning Engineer - Mid | Planning Engineer - Mid | Planning Engineer - High | Planning Engineer - High | Planning Engineer - High | Planning Project Manager - Entry | Planning Project Manager - Entry | Planning Project Manager - Entry | Planning Project Manager - Mid | Planning Project Manager - Mid | Planning Project Manager - Mid | Planning Project Manager - High | Planning Project Manager - High | Planning Project Manager - High | Planning Specialist/Professional - Entry | Planning Specialist/Professional - Entry | Planning Specialist/Professional - Entry | Planning Specialist/Professional - Mid | Planning Specialist/Professional - Mid | Planning Specialist/Professional - Mid | Planning Specialist/Professional - High | Planning Specialist/Professional - High | Planning Specialist/Professional - High | Real Estate Project Manager - Entry | Real Estate Project Manager - Entry | Real Estate Project Manager - Entry | Real Estate Project Manager - Mid | Real Estate Project Manager - Mid | Real Estate Project Manager - Mid | Real Estate Project Manager - High | Real Estate Project Manager - High | Real Estate Project Manager - High | Real Estate Specialist/Professional - Entry | Real Estate Specialist/Professional - Entry | Real Estate Specialist/Professional - Entry | Real Estate Specialist/Professional - Mid | Real Estate Specialist/Professional - Mid | Real Estate Specialist/Professional - Mid | Real Estate Specialist/Professional - High | Real Estate Specialist/Professional - High | Real Estate Specialist/Professional - High | Structure Engineer - Entry | Structure Engineer - Entry | Structure Engineer - Entry | Structure Engineer - Mid | Structure Engineer - Mid | Structure Engineer - Mid | Structure Engineer - High | Structure Engineer - High | Structure Engineer - High | Structure Project Manager - Entry | Structure Project Manager - Entry | Structure Project Manager - Entry | Structure Project Manager - Mid | Structure Project Manager - Mid | Structure Project Manager - Mid | Structure Project Manager - High | Structure Project Manager - High | Structure Project Manager - High | Structure Specialist/Professional - Entry | Structure Specialist/Professional - Entry | Structure Specialist/Professional - Entry | Structure Specialist/Professional - Mid | Structure Specialist/Professional - Mid | Structure Specialist/Professional - Mid | Structure Specialist/Professional - High | Structure Specialist/Professional - High | Structure Specialist/Professional - High | Structure Technician - Entry | Structure Technician - Entry | Structure Technician - Entry | Structure Technician - Mid | Structure Technician - Mid | Structure Technician - Mid | Structure Technician - High | Structure Technician - High | Structure Technician - High | Survey Project Manager - Entry | Survey Project Manager - Entry | Survey Project Manager - Entry | Survey Project Manager - Mid | Survey Project Manager - Mid | Survey Project Manager - Mid | Survey Project Manager - High | Survey Project Manager - High | Survey Project Manager - High | Survey Specialist/Professional - Entry | Survey Specialist/Professional - Entry | Survey Specialist/Professional - Entry | Survey Specialist/Professional - Mid | Survey Specialist/Professional - Mid | Survey Specialist/Professional - Mid | Survey Specialist/Professional - High | Survey Specialist/Professional - High | Survey Specialist/Professional - High | Survey Technician - Entry | Survey Technician - Entry | Survey Technician - Entry | Survey Technician - Mid | Survey Technician - Mid | Survey Technician - Mid | Survey Technician - High | Survey Technician - High | Survey Technician - High | Traffic Engineer - Entry | Traffic Engineer - Entry | Traffic Engineer - Entry | Traffic Engineer - Mid | Traffic Engineer - Mid | Traffic Engineer - Mid | Traffic Engineer - High | Traffic Engineer - High | Traffic Engineer - High | Traffic Project Manager - Entry | Traffic Project Manager - Entry | Traffic Project Manager - Entry | Traffic Project Manager - Mid | Traffic Project Manager - Mid | Traffic Project Manager - Mid | Traffic Project Manager - High | Traffic Project Manager - High | Traffic Project Manager - High | Traffic Specialist/Professional - Entry | Traffic Specialist/Professional - Entry | Traffic Specialist/Professional - Entry | Traffic Specialist/Professional - Mid | Traffic Specialist/Professional - Mid | Traffic Specialist/Professional - Mid | Traffic Specialist/Professional - High | Traffic Specialist/Professional - High | Traffic Specialist/Professional - High | Traffic Technician - Entry | Traffic Technician - Entry | Traffic Technician - Entry | Traffic Technician - Mid | Traffic Technician - Mid | Traffic Technician - Mid | Traffic Technician - High | Traffic Technician - High | Traffic Technician - High | Utilities Engineer - Entry | Utilities Engineer - Entry | Utilities Engineer - Entry | Utilities Engineer - Mid | Utilities Engineer - Mid | Utilities Engineer - Mid | Utilities Engineer - High | Utilities Engineer - High | Utilities Engineer - High | Utilities Project Manager - Entry | Utilities Project Manager - Entry | Utilities Project Manager - Entry | Utilities Project Manager - Mid | Utilities Project Manager - Mid | Utilities Project Manager - Mid | Utilities Project Manager - High | Utilities Project Manager - High | Utilities Project Manager - High | Utilities Specialist/Professional - Entry | Utilities Specialist/Professional - Entry | Utilities Specialist/Professional - Entry | Utilities Specialist/Professional - Mid | Utilities Specialist/Professional - Mid | Utilities Specialist/Professional - Mid | Utilities Specialist/Professional - High | Utilities Specialist/Professional - High | Utilities Specialist/Professional - High
|  |  | Guidance | COLD10 | COLD20 | COLD30 | RSRF10 | RSRF20 | RSRF30 | RCND10 | RCND20 | PSRS10 | PSRS20 | PSRS30 | PSRS40 | PVRPLA | PVRP_O | RECST | RECSTE | BRNEW | BRRHB | BRELIM | BRRPLE | BRRPL | UNITS |  |  |  | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High | Low | Meduim | High
1 |  | Project Management
1.1 |  | Scope, Schedule and Change Management
1.1.1 | 886 | Develop Project Scope
1.1.1.1 | 886 | Develop Project Scope - Scoping task | FDM 2-20-5.3, Chapter 3
1.1.1.2 | 886.1 | Develop and review project concept definition | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.3 | 886.2 | Define purpose and need | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.4 | 886.3 | Define study area and logical termini | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.5 | 886.4 | Conduct field review | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [45 empty] | 1 | 4 | 8 | [9 empty] | 1 | 4 | 8 | bar: COLD10 to PSRS40
1.1.1.6 | 886.5 | Identify and define design deficiencies | [13 empty] | X | X | X | X | X | X | X | X | X | project | 4 | 12 | 24 | [57 empty] | 4 | 12 | 24 | bar: COLD10 to PSRS40
1.1.1.7 | 886.6 | Identify design issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 8 | 16 | 36 | [45 empty] | 4 | 8 | 10 | [9 empty] | 4 | 8 | 26 | bar: COLD10 to PSRS40
1.1.1.8 | 886.7 | Identify geotechnical issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [57 empty] | 1 | 4 | 12 | [105 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.9 | 886.8 | Identify pavement issues
1.1.1.10 | 886.9 | Identify utility issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.11 | 886.1 | Identify railroad issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.12 | 886.11 | Identify environmental issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.13 | 886.12 | Identify storm water/drainage issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [57 empty] | 2 | 8 | 24 | bar: COLD10 to PSRS40
1.1.1.14 | 886.13 | Identify traffic issues (capacity-safety/crash) | [13 empty] | X | X | X | X | X | X | X | X | X | project | 4 | 12 | 24 | [57 empty] | 2 | 6 | 12 | [249 empty] | 2 | 6 | 12 | bar: COLD10 to PSRS40
1.1.1.15 | 886.14 | Identify real estate issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [57 empty] | 2 | 8 | 16 | bar: COLD10 to PSRS40
1.1.1.16 | 886.15 | Identify airport issues | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [57 empty] | 2 | 8 | 16 | bar: COLD10 to PSRS40
1.1.1.17 | 886.16 | Determine street lighting and traffic signal needs | [13 empty] | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [57 empty] | 4 | 8 | 24 | bar: COLD10 to PSRS40
1.1.1.18 | 886.17 | Determine ITS needs for project | [13 empty] | X | X | X | X | X | X | X | X | X | project | 4 | 12 | 24 | [57 empty] | 4 | 12 | 24 | bar: COLD10 to PSRS40
1.1.1.19 | 886.18 | Determine structure needs | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [57 empty] | 1 | 4 | 12 | [186 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.20 | 886.19 | Determine complete streets needs for project (bike-pedestrian-transit) | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [57 empty] | 2 | 4 | 8 | [141 empty] | 0 | 4 | 8 | bar: COLD10 to PSRS40
1.1.1.21 | 886.2 | Determine public involvement needs (PIM-Hearings) | [13 empty] | X | X | X | X | X | X | X | X | X | project | 1 | 4 | 12 | [57 empty] | 1 | 4 | 12 | bar: COLD10 to PSRS40
1.1.1.22 | 886.21 | Determine aesthetic needs (landscaping-streetscaping-CSS) | [13 empty] | X | X | X | X | X | X | X | X | X | project | 0 | 0 | 0 | bar: COLD10 to PSRS40
1.1.1.23 | 886.22 | Determine construction traffic control needs (staged or detour) | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [57 empty] | 2 | 8 | 24 | bar: COLD10 to PSRS40
1.1.1.24 | 886.23 | Determine local participation | [13 empty] | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [57 empty] | 2 | 8 | 24 | bar: COLD10 to PSRS40
1.1.2 | 887 | Manage Project Scope and Schedule
1.1.2.1 | 887 | Manage Project Scope and Schedule - Scoping task | FDM2-20-5.3&4
1.1.2.2 | 887.1 | Create project schedule | [13 empty] | x | x | x | x | x | x | x | x | x | project | 2 | 6 | 12 | [57 empty] | 2 | 6 | 12 | bar: COLD10 to PSRS40
1.1.2.3 | 887.2 | Update and Track project progress/percent complete | [13 empty] | x | x | x | x | x | x | x | x | x | month | 1 | 2 | 4 | [57 empty] | 1 | 2 | 4 | bar: COLD10 to PSRS40
1.1.2.4 | 887.3 | Prepare/attend scope and schedule meetings / conference calls | [13 empty] | x | x | x | x | x | x | x | x | x | month | 1 | 2 | 4 | [48 empty] | 1 | 2 | 4 | bar: COLD10 to PSRS40
1.1.2.5 | 887.4 | Prepare/attend 30% Plan review meeting | [13 empty] | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [48 empty] | 4 | 15 | 20 | [6 empty] | 4 | 15 | 20 | bar: COLD10 to PSRS40
1.1.2.6 | 887.5 | Prepare/attend 60% Plan review meeting | [13 empty] | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [48 empty] | 4 | 15 | 20 | [6 empty] | 4 | 15 | 20 | bar: COLD10 to PSRS40
1.1.2.7 | 887.6 | Prepare/attend 90% Plan review meeting | [13 empty] | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [48 empty] | 4 | 15 | 20 | [6 empty] | 4 | 15 | 20 | bar: COLD10 to PSRS40
1.1.2.8 | 887.7 | Develop and maintain financial plan | [15 empty] | x | x | x |  |  |  |  | project | 8 | 16 | 24 | [57 empty] | 8 | 16 | 24
1.1.3 | 884 | Manage Change
1.1.3.1 | 884 | Manage Change - Scoping task | FDM 2-20-15.2.2
1.1.3.2 | 884.1 | Change management process and plan |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 24 | 120 | 200 | [45 empty] | 4 | 8 | 12 | 4 | 8 | 12 | [6 empty] | 16 | 92 | 152 | [87 empty] | 0 | 8 | 16 | 0 | 4 | 8
1.1.3.3 | 884.2 | Rebalance program |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | rebalance | 8 | 24 | 40 | [45 empty] | 4: 0; 8: 4; 12: 8 | [6 empty] | 8 | 18 | 26 | [87 empty] | 0 | 2 | 4
1.1.3.4 | 884.3 | Coordinate construction timing with other projects & completion restrictions |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | change | 4 | 10 | 40 | [57 empty] | 4 | 10 | 40
1.1.3.5 | 884.4 | Monitor funding resources (local-state-federal) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | change | 2 | 16 | 30 | [201 empty] | 2 | 16 | 30
1.1.3.6 | 884.5 | Analyze and review contractor change order and claims request |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | change | 4 | 8 | 35 | [45 empty] | 4: 0; 8: 4; 12: 9 | [6 empty] | 4 | 4 | 24 | [87 empty] | 0 | 0 | 2
1.2 |  | Budget, Cost, Procurement and Resource Management
1.2.1 | 888 | Manage Project Delivery
1.2.1.1 | 888 | Manage Project Delivery - Scoping task | FDM 2-20-5.5
1.2.1.2 | 888.1 | Develop and manage project human resources | [22 empty] | project | 10 | 40 | 80 | [57 empty] | 10 | 36 | 70 | [87 empty] | 0 | 4 | 10
1.2.1.3 | 888.2 | Develop initial project delivery cost estimate | [22 empty] | project | 8 | 12 | 16 | [57 empty] | 8 | 12 | 16
1.2.1.4 | 888.3 | Review and develop revised and final project delivery cost estimate | [22 empty] | project | 3 | 10 | 20 | [57 empty] | 3 | 10 | 20
1.2.2 | 883 | Manage Consultant Selection
1.2.2.1 | 883 | Manage Consultant Selection - Scoping task | FDM 8-5
1.2.2.2 | 883.1 | Prepare solicitation package |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | package | 16 | 24 | 40 | .5 | .5 | 1 | [54 empty] | 12 | 24 | 40
1.2.2.3 | 883.2 | Review solicitation package |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | package | 2 | 2 | 4 | .5 | .5 | 1 | [54 empty] | .5 | .5 | 1 | bar: 4 to 12
1.2.2.4 | 883.3 | Review NOIs |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | per NOI per person | 0.5 | 0.5 | 1 | [57 empty] | 16 | 20 | 30
1.2.2.5 | 883.4 | Conduct and evaluate consultant interviews |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | per interview per person |  |  | 5 | [57 empty] | 0 | 0 | 20 | [87 empty] | 0 | 0 | 5
1.2.2.6 | 883.5 | Make final selection |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | package per person | 2 | 4 | 6 | .5 | .5 | 1 | [54 empty] | 1 | 2 | 3 | [87 empty] | 1 | 2 | 3
1.2.2.7 | 883.6 | Review final selection |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | package | 2.5 | 2.5 | 4.5 | [57 empty] | .5 | .5 | 1 | [87 empty] | .5 | .5 | 1 | .5 | .5 | .5 | bar: 4 to 12
1.2.2.8 | 883.7 | Prepare/attend consultant scoping meeting |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | person | 2 | 6 | 8 | [57 empty] | 2 | 6 | 8
1.2.2.9 | 883.8 | Negotiate contract |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | contract | 16 | 30 | 60 | [57 empty] | 16 | 30 | 60
1.2.2.10 | 883.9 | Prepare and review consultant contract documents |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | contract | 6 | 10 | 16 | 2 | 4 | 5 | [54 empty] | 1 | 2 | 3
1.2.3 | 773 | Manage Consultant Contract
1.2.3.1 | 773 | Manage Consultant Contract - Scoping task | FDM 8-25 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x
1.2.3.2 | 773.1 | Prepare consultant invoice and supporting documents |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | invoice | 4 | 6 | 12 | 1 | 1 | 2 | [54 empty] | 3 | 5 | 8 | [87 empty] | 0 | 0 | 2
1.2.3.3 | 773.2 | Review consultant invoices |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | invoice | 1 | 3 | 5 | .5 | 1.5 | 2.5 | [54 empty] | .5 | 1.5 | 2.5
1.2.3.4 | 773.3 | Review and negotiate contract amendments |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | amendment | 2 | 8 | 16 | [57 empty] | 2 | 8 | 12 | [87 empty] | 0 | 0 | 4
1.2.3.5 | 773.4 | Review errors and omissions/disputes |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | issue | 2 | 4 | 12 | [57 empty] | 2 | 4 | 8 | [87 empty] | 0 | 0 | 4
1.2.3.6 | 773.5 | Setting up CARS roles - Region administrator |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | contract | 1 | 1 | 1 | 1 | 1 | 1
1.2.3.7 | 773.6 | Evaluate performance of contract |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | contract | 1 | 2 | 3 | [57 empty] | 1 | 2 | 3
1.2.4 | 889 | Manage Project Non-Delivery Cost
1.2.4.1 | 889 | Manage Project Non-Delivery Cost - Scoping task | FDM 19-5
1.2.4.2 | 889.1 | Manage and review construction project cost estimate |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | estimate | 10 | 20 | 40 | [45 empty] | 2 | 6 | 10 | 4 | 8 | 22 | [6 empty] | 4 | 6 | 8
1.2.4.3 | 889.2 | Manage and review R/W costs |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | parcel | 4 | 10 | 24 | [45 empty] | 4: 2; 8: 6; 12: 14 | [6 empty] | 2 | 4 | 10
1.2.4.4 | 889.3 | Mange and review Utility costs |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | utility company | 4 | 10 | 24 | [45 empty] | 4: 2; 8: 6; 12: 14 | [6 empty] | 2 | 4 | 10
1.2.4.5 | 889.4 | Mange and review "supplied by WisDOT" costs (signals, cabinets, etc.) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | location | 4 | 10 | 24 | [45 empty] | 4: 2; 8: 6; 12: 14 | [6 empty] | 2 | 4 | 10
1.2.5 | 892 | Manage Procurement of Goods and/or Services
1.2.5.1 | 892 | Manage Procurement of Goods and/or Services - Scoping task
1.2.5.2 | 892.1 | Purchasing
1.2.5.3 | 892.1.1 | Develop and manage simplified bid | http://dotnet/purchasing/guidelines.htm | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | quote | 8 | 10 | 12 | [45 empty] | 4: 8; 8: 10; 12: 12
1.2.5.4 | 892.1.2 | Develop and manage RFB/RFI | http://dotnet/purchasing/guidelines.htm | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | purchase item | 24 | 40 | 80 | [45 empty] | 4: 24; 8: 40; 12: 80
1.2.5.5 | 892.1.3 | Develop and manage RFP | http://dotnet/purchasing/guidelines.htm | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | purchase item | 24 | 40 | 80 | [45 empty] | 4: 24; 8: 40; 12: 80
1.2.5.6 | 892.1.4 | Develop and manage Sole Source purchase | http://dotnet/purchasing/guidelines.htm | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | purchase item | 8 | 10 | 12 | [45 empty] | 4: 8; 8: 10; 12: 12
1.2.5.7 | 892.2 | Coordinate "supply by WisDOT" orders |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 10 | 12 | [45 empty] | 4: 8; 8: 10; 12: 12
1.2.5.8 | 892.3 | Pay invoices for purchased items |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | invoice | 8 | 8 | 8 | [45 empty] | 4: 8; 8: 8; 12: 8
1.3 |  | Quality and Risk Management
1.3.1 | 890 | Manage Project Quality
1.3.1.1 | 890 | Manage Project Quality - Scoping task | FDM 2-20-5.6
1.3.1.2 | 890.1 | Prepare/attend oversight meetings |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 2 | 4 | 8 | [57 empty] | 2 | 4 | 8
1.3.1.3 | 890.2 | Review project documentation/reports/plans and documents
1.3.1.4 | 890.2.1 | Review 30% project plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 76 | 144 | 212 | [45 empty] | 4: 60; 8: 112; 12: 164 | [6 empty] | 16 | 32 | 48
1.3.1.5 | 890.2.2 | Review 60% project plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 144 | 212 | 280 | [45 empty] | 4: 112; 8: 164; 12: 216 | [6 empty] | 32 | 48 | 64
1.3.1.6 | 890.2.3 | Review 90% project plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 212 | 280 | 348 | [45 empty] | 4: 164; 8: 216; 12: 268 | [6 empty] | 48 | 64 | 80
1.3.1.7 | 890.2.4 | Review special provisions and supporting documents |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 46 | 92 | 160 | [45 empty] | 4: 16; 8: 32; 12: 48 | [6 empty] | 30 | 60 | 112
1.3.1.8 | 890.3 | Specialty - Technical construction expert | [15 empty] | x | x | x |  | x | x | x | project | * | * | *
1.3.1.9 | 890.4 | Specialty - Value engineering | [15 empty] | x | x | x |  | x | x | x | project | * | * | *
1.3.2 | 894 | Manage Project Risks
1.3.2.1 | 894 | Manage Project Risks - Scoping task | FDM 2-20-5.9
1.3.2.2 | 894.1 | Develop and define risk register |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | per project per person | 2 | 4 | 8 | [57 empty] | 2 | 4 | 8
1.3.2.3 | 894.2 | Evaluate risk |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | per project per person | 2 | 4 | 8 | [57 empty] | 2 | 4 | 8
1.3.2.4 | 894.3 | Prepare risk management plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | per project per person | 2 | 4 | 8 | [57 empty] | 2 | 4 | 8
1.3.2.5 | 894.4 | Manage risk |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | month | 1 | 2 | 3 | [57 empty] | 1 | 2 | 3
1.4 |  | Communication and Stakeholder Management
1.4.1 | 743 | Manage Project Stakeholders
1.4.1.1 | 743 | Manage Project Stakeholders - Scoping task | FDM 2-20-1.3, 2-20-5.11
1.4.1.2 | 743.1 | Respond to inquiries (public, government, media) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | month | 1 | 4 | 8 | [45 empty] | 4: 0; 8: 0; 12: 2 | [6 empty] | 2 | 4 | 6
1.4.1.3 | 743.2 | Develop public involvement plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 4 | 16 | 40 | [45 empty] | 4: 1; 8: 8; 12: 8 | [6 empty] | 3 | 8 | 32
1.4.1.4 | 743.3 | Prepare and maintain public involvement log/comment database |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | month | 1 | 2 | 4 | [45 empty] | 4: 0; 8: 1; 12: 2 | [6 empty] | 1 | 1 | 2
1.4.1.5 | 743.4 | Notify property owners |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 3 | 5 | 9 | 1 | 1 | 1 | [42 empty] | 4: 1; 8: 2; 12: 4 | [231 empty] | 1 | 2 | 4
1.4.1.6 | 743.5 | Pre-meeting (PIM PAC TAC)
1.4.1.7 | 743.5.1 | Develop and maintain contact mailing list (email/address) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 4 | 12 | 24 | 1 | 1 | 1 | [42 empty] | 4: 1; 8: 8; 12: 16 | [6 empty] | 1 | 1 | 3 | [222 empty] | 1 | 2 | 4
1.4.1.8 | 743.5.2 | Plan pre-meeting and meeting arrangements |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 2 | 2 | 2 | 1 | 1 | 1 | bar: 4 to 12
1.4.1.9 | 743.5.3 | Prepare/print/mail/email meeting invites |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 4 | 6 | 8 | 1 | 2 | 3 | [42 empty] | 4: 2; 8: 3; 12: 4 | [6 empty] | 1 | 1 | 1
1.4.1.10 | 743.5.4 | Prepare news release |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 2 | 2 | 2 | 1 | 1 | 1 | bar: 4 to 12
1.4.1.11 | 743.5.5 | Prepare/Review/Revise meeting materials (handouts, exhibits, presentation) PIM, PAC, TAC |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 32 | 50 | 80 | 2 | 2 | 2 | [42 empty] | 4 | 6 | 12 | 16 | 20 | 32 | [6 empty] | 4 | 16 | 24 | [12 empty] | 6 | 6 | 10
1.4.1.12 | 743.5.6 | Attend PIM, PAC, TAC |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 4 | 8 | 15 | [45 empty] | 0 | 0 | 5 | 0 | 4 | 5 | [6 empty] | 4 | 4 | 5
1.4.1.13 | 743.5.7 | Prepare/Review PIM, PAC, TAC meeting minutes or summary |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 2 | 4 | 6 | [45 empty] | 0 | 0 | 2 | 1 | 3 | 3 | [6 empty] | 1 | 1 | 1
1.4.1.14 | 743.6 | General Project Meeting
1.4.1.15 | 743.6.1 | Prepare for, attend, and summarize meeting |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 5 | 8 | 10 | [45 empty] | 0 | 0 | 2 | 1 | 4 | 4 | [6 empty] | 4 | 4 | 4
1.4.2 | 893 | Manage Project Communications
1.4.2.1 | 893 | Manage Project Communications - Scoping task |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
1.4.2.2 | 893.1 | Develop/Prepare materials, update and manage project website |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | X | exhibit | 2 | 2 | 4 | [45 empty] | 1 | 0 | 0 | 1 | 1 | 2
1.4.2.3 | 893.2 | Develop project pamphlet/brochure/newsletter |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | X | exhibit | 2 | 4 | 8 | 0 | 1 | 1 | [42 empty] | 1 | 1 | 1 | 1 | 2 | 4
1.4.2.4 | 893.3 | Manage news media releases and social media |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | X | response | 1 | 1 | 3 | [45 empty] | 0 | 0 | 1 | 1 | 1 | 1
1.4.2.5 | 893.4 | Regional communication manager coordination |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | interaction | 1 | 1 | 3 | [45 empty] | 0 | 0 | 1 | 1 | 1 | 1
1.4.3 | 266 | Coordinate Local Public Agency (LPA)
1.4.3.1 | 266 | Coordinate Local Public Agency (LPA) - Scoping task
1.4.3.2 | 266.1 | Develop SMA |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | municipality | 4 | 40 | 500
1.4.3.3 | 266.2 | LPA coordination |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 20 | 160
2 |  | Preliminary and Final Design
2.1 |  | Pavement and Soils Design
2.1.1 | 208 | Design Soils & Earthwork
2.1.1.1 | 208 | Design Soils & Earthwork - Scoping task | FDM Chapter 11
2.1.1.2 | 208.1 | Roadway
2.1.1.3 | 208.1.1 | Review available geotechnical and design information |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 12 | [156 empty] | 4 | 8 | 10 | [6 empty] | 0 | 0 | 2
2.1.1.4 | 208.1.2 | Develop subsurface exploration program |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 12 | [156 empty] | 4 | 8 | 10 | [6 empty] | 0 | 0 | 2
2.1.1.5 | 208.1.3 | Complete subsurface investigation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | 1 mile urban or 2.5 mile rural | 12 | 20 | 30 | [183 empty] | 12 | 20 | 30
2.1.1.6 | 208.1.4 | Additional Resources for Subsurface Investigation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | 1 mile urban or 2.5 mile rural | 4 | 25 | 40 | [156 empty] | 0 | 5 | 5 | [6 empty] | 0 | 0 | 5 | [15 empty] | 4 | 20 | 30
2.1.1.7 | 208.1.5 | Perform laboratory testing and evaluate results |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | 1 mile urban or 2.5 mile rural | 4 | 8 | 13 | [156 empty] | 1 | 2 | 3 | [24 empty] | 3 | 6 | 10
2.1.1.8 | 208.1.6 | Complete analysis and develop soils report |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | 1 mile urban or 2.5 mile rural | 12 | 16 | 20 | [156 empty] | 8 | 10 | 12 | [6 empty] | 4 | 6 | 8
2.1.1.9 | 208.2 | Structures
2.1.1.10 | 208.2.1 | Review available geotechnical and design information | [17 empty] | X | X | X | X | X | structure | 2 | 4 | 8 | [156 empty] | 1 | 4 | 6 | [6 empty] | 0 | 0 | 2
2.1.1.11 | 208.2.2 | Develop subsurface exploration program | [17 empty] | X | X |  | X | X | structure | 2 | 4 | 6 | [156 empty] | 2 | 4 | 4 | [6 empty] | 0 | 0 | 2
2.1.1.12 | 208.2.3 | Complete subsurface investigation | [17 empty] | X | X |  | X | X | structure | 30 | 40 | 120 | [183 empty] | 30 | 40 | 120
2.1.1.13 | 208.2.4 | Additional Resources for Subsurface Investigation | [17 empty] | X | X |  | X | X | structure | 4 | 40 | 120 | [147 empty] | 0 | 0 | 4 | [6 empty] | 0 | 4 | 8 | [6 empty] | 0 | 0 | 8 | [15 empty] | 4 | 36 | 100
2.1.1.14 | 208.2.5 | Perform laboratory testing and evaluate results | [17 empty] | X | X |  | X | X | structure | 5 | 12 | 20 | [147 empty] | 0 | 1 | 2 | [6 empty] | 2 | 4 | 5 | [6 empty] | 1 | 2 | 3 | [15 empty] | 2 | 5 | 10
2.1.1.15 | 208.2.6 | Complete analysis and develop soils report | [17 empty] | X | X |  | X | X | structure | 20 | 40 | 60 | [147 empty] | 0 | 5 | 10 | [6 empty] | 10 | 15 | 20 | [6 empty] | 10 | 20 | 30
2.1.1.16 | 208.3 | Miscellaneous
2.1.1.17 | 208.3.1 | Review available geotechnical and design information | [13 empty] | X | X | X | X | X |  | X | X | X | feature | 4 | 8 | 24 | [156 empty] | 4 | 8 | 20 | [6 empty] | 0 | 0 | 4
2.1.1.18 | 208.3.2 | Develop subsurface exploration program |  |  |  | X | X | X | X | X |  | X | X | X | X | X | X | X | X | X |  | X | X | X | feature | 4 | 8 | 16 | [156 empty] | 4 | 8 | 12 | [6 empty] | 0 | 0 | 4
2.1.1.19 | 208.3.3 | Complete subsurface investigation | [13 empty] | X | X | X | X | X |  | X | X | X | feature | 20 | 40 | 120 | [183 empty] | 20 | 40 | 120
2.1.1.20 | 208.3.4 | Additional Resources for Subsurface Investigation | [13 empty] | X | X | X | X | X |  | X | X | X | feature | 0 | 20 | 80 | [156 empty] | 0 | 4 | 15 | [6 empty] | 0 | 0 | 5 | [15 empty] | 0 | 16 | 60
2.1.1.21 | 208.3.5 | Perform laboratory testing and evaluate results | [13 empty] | X | X | X | X | X |  | X | X | X | feature | 10 | 20 | 40 | [156 empty] | 2 | 4 | 6 | [6 empty] | 0 | 2 | 4 | [15 empty] | 8 | 8 | 8 | 0 | 4 | 18
2.1.1.22 | 208.3.6 | Complete analysis and develop soils report | [13 empty] | X | X | X | X | X |  | X | X | X | feature | 10 | 20 | 45 | [156 empty] | 2 | 4 | 6 | [6 empty] | 5 | 10 | 20
2.1.1.23 | 208.4 | Identify possible waste, borrow, and aggregate sources | [182 empty] | 5 | 5 | 10
2.1.1.24 | 208.5 | Analyze select material in subgrade
2.1.1.25 | 208.6 | Specialty - Subsurface exploration drilling and field operations/testing services
2.1.1.26 | 208.7 | Specialty - Geotechnical engineering
2.1.2 | 277 | Design Pavement Structure
2.1.2.1 | 277 | Design Pavement Structure - Scoping task | FDM 14-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X
2.1.2.2 | 277.1 | Conduct site investigation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | project | 5 | 8 | 12 | [45 empty] | 4: 4; 8: 6; 12: 8 | [24 empty] | 1 | 2 | 4
2.1.2.3 | 277.2 | Develop Preliminary Pavement Design Recommendation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | project | 5 | 11 | 19 | [45 empty] | 4: 4; 8: 8; 12: 14 | [6 empty] | 0 | 1 | 1 | [15 empty] | 1 | 2 | 4
2.1.2.4 | 277.3 | Review information |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | project | 7 | 11 | 14 | [45 empty] | 4: 5; 8: 10; 12: 10 | [24 empty] | 1 | 2 | 4
2.1.2.5 | 277.4 | Perform pavement structural calculations/evaluations |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | project | 6 | 12 | 42 | [45 empty] | 4: 6; 8: 12; 12: 42
2.1.2.6 | 277.5 | Perform LCCA calculations/evaluations |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | project | 0 | 12 | 20 | [45 empty] | 0 | 3 | 4 | 0 | 9 | 16
2.1.2.7 | 277.6 | Prepare Draft and Final pavement design report |  | X | X | X | X | X | X | X | X |  | X | X | X | X | X | X | X | X | X |  | X | X | project | 9 | 18 | 37 | [45 empty] | 4: 6; 8: 12; 12: 30 | [6 empty] | 1 | 2 | 3 | [15 empty] | 2 | 4 | 4
2.1.2.8 | 277.7 | Specialty - FWD and GPR data collection and/or analysis | [15 empty] | X | X | [5 empty] | mile | 2 | 3 | 4
2.2 |  | Engineering and Plan Development
2.2.1 | 268 | Develop and Manage Access Control
2.2.1.1 | 268 | Develop and Manage Access Control - Scoping task | FDM Chapter 7
2.2.1.2 | 268.1 | Determine land development and access |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 2 | 4 | 8 | [45 empty] | 1 | 1 | 2 | 0 | 1 | 2 | [24 empty] | 1 | 1 | 2 | [204 empty] | 0 | 1 | 2
2.2.1.3 | 268.2 | Analyze access locations |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 4 | 8 | 16 | [45 empty] | 4: 2; 8: 4; 12: 6 | [6 empty] | 1 | 2 | 4 | [15 empty] | 1 | 2 | 4
2.2.1.4 | 268.3 | Identify access management recommendations (moving-removing-consolidation) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | parcel | 2 | 16 | 40 | 0 | 2 | 4 | [42 empty] | 4: 1; 8: 6; 12: 16 | [6 empty] | 1 | 2 | 8 | [15 empty] | 0 | 6 | 12
2.2.1.5 | 268.4 | Develop service road/emergency access feasibility |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | each | 8 | 40 | 80 | [45 empty] | 1 | 4 | 8 | 4 | 20 | 40 | [6 empty] | 1 | 8 | 16 | [15 empty] | 2 | 8 | 16
2.2.1.6 | 268.5 | Develop multi-modal overpass/underpass justification |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | each | 16 | 80 | 160 | [45 empty] | 2 | 8 | 16 | 8 | 40 | 80 | [6 empty] | 2 | 16 | 40 | [15 empty] | 3 | 12 | 16 | [69 empty] | 1 | 4 | 8
2.2.1.7 | 268.6 | Specialty - Reasonable access studies
2.2.2 | 778 | Design Drainage
2.2.2.1 | 778 | Design Drainage - Scoping task | FDM Chapter 13; FDM 10-25/30/35/40. WisDOT Drainage SharePoint
2.2.2.2 | 778.1 | Identify existing drainage structures/systems, drainage patterns | FDM 13-5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | outfall | 2 | 4 | 6 | [44 empty] | 0-0-0 | 4: 1; 8: 3; 12: 5 | [6 empty] | 1 | 1 | 1
2.2.2.3 | 778.2 | Identify existing land use, land cover, soil types, imperviousness (CN, C) | FDM 13-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | acre | 1 | 2 | 4 | [44 empty] | 0-0-0 | 4: 1; 8: 1; 12: 3 | [7 empty] | 1 | 1
2.2.2.4 | 778.3 | Establish existing drainage areas, time of concentration (tc) flow paths, flow rates | FDM 13-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | outfall | 3 | 5 | 8 | [44 empty] | 1-2-3 | 1 | 2 | 33 | 1 | 2 | 3 | [6 empty] | 1 | 1 | 1
2.2.2.5 | 778.4 | Identify existing deficiencies/concerns |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | outfall | 1 | 3 | 6 | [44 empty] | 0-0-0 | 4: 1; 8: 2; 12: 5 | [7 empty] | 1 | 1
2.2.2.6 | 778.5 | Prepare Existing Condition Drainage Area Exhibits |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | sheet | 4 | 6 | 8 | [44 empty] | 3-4-6 | 3 | 4 | 6 | 1 | 2 | 2
2.2.2.7 | 778.6 | Establish and evaluate proposed drainage flow path/time of concentration/peak discharge | FDM 13-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | outfall | 2 | 6 | 10 | [44 empty] | 0-2-3 |  | 2 | 3 | 1 | 3 | 6 | [6 empty] | 1 | 1 | 1
2.2.2.8 | 778.7 | Design storm sewer system, size pipes, and inlet spacing | FDM 13-25 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | station | 2 | 4 | 8 | [44 empty] | 0-1-2 |  | 1 | 2 | 1 | 2 | 5 | [6 empty] | 1 | 1 | 1
2.2.2.9 | 778.8 | Design temporary drainage for staged construction |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | station | 1 | 2 | 3 | [44 empty] | 0-0-0 | 4: 1; 8: 2; 12: 2 | [8 empty] | 1
2.2.2.10 | 778.9 | Analyze hydraulics and design culvert pipes | FDM 13-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | each | 2 | 4 | 6 | [44 empty] | 0-1-1 |  | 1 | 1 | 2 | 2 | 4 | [7 empty] | 1 | 1
2.2.2.11 | 778.1 | Analyze hydraulics and design ditches | FDM 13-30 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 3 | 5 | 8 | [44 empty] | 2-3-4 | 2 | 3 | 4 | 1 | 2 | 2 | [8 empty] | 2
2.2.2.12 | 778.11 | Perform hydraulic analysis for navigable/floodzone bridges/culverts | FDM 13-20 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | each | 30 | 45 | 60 | [44 empty] | 5-10-15 | 5 | 10 | 15 | 22 | 30 | 35 | [6 empty] | 3 | 5 | 10
2.2.2.13 | 778.12 | Design channel relocation |  |  |  | X | X | X | X | X |  | X | X | X | X | x | x | x | x | x |  | x | x | x | mile | n/a | n/a | 80 | [44 empty] | 0-0-0 | [12 empty] | 30 | 40 | 50
2.2.2.14 | 778.13 | Perform water quality calculations | FDM 10-25, 10-30 | [12 empty] | x | x | x | x | x |  | x | x | x | outfall | 0 | 2 | 4 | [44 empty] | 0-1-1 |  | 1 | 1 |  | 1 | 2 | [8 empty] | 1
2.2.2.15 | 778.14 | Design detention pond(s) and outlet control structure(s) | FDM 10-35 | [12 empty] | x | x | x | x | [5 empty] | each | 60 | 75 | 90 | [44 empty] | 20-30-40 | 20 | 30 | 40 | 34 | 37 | 40 | [6 empty] | 6 | 8 | 10
2.2.2.16 | 778.15 | Water Quality/Stormwater Control Measure Design | FDM 10-35 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | each | 60 | 75 | 90 | [44 empty] | 15-25-35 | 15 | 25 | 35 | 39 | 42 | 45 | [6 empty] | 6 | 8 | 10
2.2.2.17 | 778.16 | Stormwater-Drainage-Water Quality (WQ) Spreadsheets | FDM 10-25/30/35, 13-1-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | outfall | 2 | 3 | 4 | [44 empty] | 0-0-0 | 4: 1; 8: 2; 12: 3 | [6 empty] | 1 | 1 | 1
2.2.2.18 | 778.17 | Prepare Proposed Drainage Area Exhibits |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | sheet | 2 | 3 | 4 | [44 empty] | 2-2-2 | 2 | 2 | 2 |  | 1 | 2
2.2.2.19 | 778.18 | Complete Stormwater Report | FDM 10-25 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 16 | 30 | 60 | [44 empty] | 2-6-15 | 2 | 6 | 15 | 13 | 21 | 39 | [6 empty] | 1 | 3 | 6
2.2.2.20 | 778.19 | Complete Hydraulic Report | FDM 13-20 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | structure | 12 | 24 | 40 | [44 empty] | 2-6-16 | 2 | 6 | 15 | 9 | 16 | 20 | [6 empty] | 1 | 2 | 4
2.2.3 | 768 | Design Erosion Control and Landscaping
2.2.3.1 | 768 | Design Erosion Control and Landscaping - Scoping task
2.2.3.2 | 768.1 | Analyze existing erosion control conditions | FDM 10-5, 10-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 16 | 32 | 48 | [45 empty] | 6 | 12 | 18 | 8 | 16 | 24 | [6 empty] | 2 | 4 | 6
2.2.3.3 | 768.2 | Determine temporary erosion control features | FDM 10-5, 10-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 32 | 64 | 96 | [45 empty] | 16 | 32 | 48 | 12 | 24 | 36 | [6 empty] | 4 | 8 | 12
2.2.3.4 | 768.3 | Determine permanent erosion control features | FDM 10-5, 10-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 32 | 64 | 96 | [45 empty] | 16 | 32 | 48 | 12 | 24 | 36 | [6 empty] | 4 | 8 | 12
2.2.3.5 | 768.4 | Erosion control plan preparation | FDM 10-5, 10-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | sheet | 8 | 16 | 32 | [45 empty] | 4: 2; 8: 4; 12: 8 | [6 empty] | 1 | 2 | 4 | [15 empty] | 5 | 10 | 20
2.2.3.6 | 768.5 | Review & define landscaping parameters | None | [12 empty] | x | x | x | x | x |  |  |  |  | mile | 40 | 200 | 400 | [45 empty] | 4: 3; 8: 12; 12: 24 | [6 empty] | 1 | 8 | 16 |  |  |  | 20 | 100 | 200 | 16 | 80 | 160
2.2.3.7 | 768.6 | Landscaping plan preparation | None | [12 empty] | x | x | x | x | x |  |  |  |  | sheet | 8 | 20 | 40 | [45 empty] | 4: 2; 8: 5; 12: 10 | [6 empty] | 1 | 3 | 6 | [15 empty] | 5 | 12 | 24
2.2.4 | 776 | Design Geometrics and Details
2.2.4.1 | 776 | Design Geometrics and Details - Scoping task | FDM Chapter 11
2.2.4.2 | 776.1 | Determine and document design criteria |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 20 | 40
2.2.4.3 | 776.2 | Analyze existing geometrics |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 6 | 12 | 30
2.2.4.4 | 776.3 | Develop preliminary horizontal alignments |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 2 | 6 | 12
2.2.4.5 | 776.4 | Develop preliminary vertical alignments | [13 empty] | X | X | X | X | X | X | X | X | X | mile | 8 | 24 | 48
2.2.4.6 | 776.5 | Develop preliminary intersection design |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 80 | 100
2.2.4.7 | 776.6 | Develop preliminary interchange design | [15 empty] | X | X | X |  |  |  |  | each | 200 | 400 | 600
2.2.4.8 | 776.7 | Analyze and document geometric alternatives |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 80 | 120
2.2.4.9 | 776.8 | Finalize preliminary geometrics |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 100 | 200 | 400
2.2.4.10 | 776.9 | Create basic templates |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 8 | 24 | 40
2.2.4.11 | 776.1 | Develop preliminary surface models | [22 empty] | each
2.2.4.12 | 776.10.1 | Roadway |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 40 | 80 | 120
2.2.4.13 | 776.10.2 | Intersection |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 80 | 160 | 240
2.2.4.14 | 776.10.3 | Interchange |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 200 | 320 | 480
2.2.4.15 | 776.10.4 | Roundabout |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 100 | 180 | 280
2.2.4.16 | 776.10.5 | Construction staging |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 20 | 40 | 60
2.2.4.17 | 776.10.6 | Miscellaneous |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 20 | 40 | 60
2.2.4.18 | 776.11 | Perform airway/railway/highway clearance analysis |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 40 | 80
2.2.4.19 | 776.12 | Determine need for design exception |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 20 | 40
2.2.4.20 | 776.13 | Design aesthetic & Community Sensitive Design Features | [13 empty] | X | X | X | X | X |  |  | X | X | project | 100 | 250 | 400
2.2.4.21 | 776.14 | Beamguard calculations and geometrics |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 8 | 16 | 40
2.2.4.22 | 776.15 | Develop preliminary roadside design elements |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 40 | 80 | 160
2.2.4.23 | 776.16 | Update intersection geometrics and details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 60 | 120 | 200
2.2.4.24 | 776.17 | Update interchange geometrics and details |  | X | X | X | X | X | X | X |  |  |  |  | X | X | X | X | X | X |  |  |  |  | each | 300 | 500 | 800
2.2.4.25 | 776.18 | Develop final horizontal alignments (mainline and side road) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 16 | 36 | 72
2.2.4.26 | 776.19 | Develop final vertical alignments (mainline, side road, and driveway) | [13 empty] | X | X | X | X | X | X | X | X | X | mile | 24 | 54 | 96
2.2.4.27 | 776.2 | Develop final intersection design |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | each | 80 | 120 | 160
2.2.4.28 | 776.21 | Develop final interchange design | [15 empty] | X | X | X |  |  |  |  | each | 400 | 600 | 800
2.2.4.29 | 776.22 | Finalize geometrics |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 600 | 800 | 1000
2.2.4.30 | 776.23 | Refine and finalize surface models |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | project | 200 | 400 | 800
2.2.4.30 | 776.24 | Design Documentation
2.2.4.31 | 776.24.1 | Prepare and review interchange access justification report (IAJR) | FDM 7-45 | [14 empty] | x | x | [5 empty] | report | 280 | 480 | 700 | 16 | 32 | 42 | [42 empty] | 64 | 112 | 152 | 80 | 140 | 200 | [6 empty] | 24 | 48 | 72 | [12 empty] | 10 | 16 | 24 | 40 | 56 | 78 | 32 | 48 | 80 | [66 empty] | 4 | 8 | 16 | 2 | 4 | 8 | [84 empty] | 4 | 8 | 16 | [42 empty] | 4 | 8 | 12
2.2.4.32 | 776.24.2 | Develop and document Encroachment Report | FDM 12-1-20 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | report | 16 | 32 | 60 | 1 | 2 | 4 | [42 empty] | 8 | 16 | 30 | 2 | 5 | 8 | [6 empty] | 1 | 1 | 2 | [12 empty] | 4 | 8 | 16
2.2.4.33 | 776.24.3 | Develop and document Roadside Hazards Report | FDM 11-45-3 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | report | 6 | 16 | 40 | [45 empty] | 3 | 8 | 20 | 2 | 6 | 16 | [6 empty] | 1 | 2 | 4
2.2.4.34 | 776.24.4 | Develop and document Design Study Report | FDM 3-15-25.4 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | report | 60 | 80 | 120 | 4 | 8 | 12 | [42 empty] | 24 | 32 | 48 | 12 | 16 | 30 | [6 empty] | 2 | 4 | 8 | [18 empty] | 16 | 16 | 16 | [156 empty] | 2 | 4 | 6
2.2.4.35 | 776.24.5 | Prepare addendum to the Design Study Report | FDM 3-15-25.4 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | addendum | 16 | 24 | 40 | 1 | 2 | 2 | [42 empty] | 6 | 8 | 14 | 6 | 8 | 16 | [6 empty] | 1 | 2 | 4 | [18 empty] | 2 | 4 | 4
2.2.4.36 | 776.24.6 | Develop and prepare Design Exceptions Report | FDM 11-1 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | exception | 32 | N/A | 80 | 2 | 0 | 6 | [42 empty] | 10 | 0 | 24 | 12 | 0 | 32 | [6 empty] | 1 | 0 | 3 | [18 empty] | 5 | 0 | 10 | [156 empty] | 2 | 0 | 5
2.2.4.37 | 776.24.7 | Develop and prepare Programmatic Exceptions to Standards Report | FDM 11-40-4 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | [7 empty] | exception | 16 | N/A | 32 | 1 | 0 | 2 | [42 empty] | 8 | 0 | 16 | 4 | 0 | 8 | [6 empty] | 1 | 0 | 2 | [18 empty] | 2 | 0 | 4
2.2.4.38 | 776.24.8 | Perform Value Engineering evaluation | FDM 1-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | VE evaluation | 280 | 400 | 600 | 24 | 36 | 60 | [18 empty] | 24 | 32 | 40 | [21 empty] | 4: 48; 8: 72; 12: 108 | [6 empty] | 60 | 92 | 160 | [15 empty] | 12 | 18 | 32 | 24 | 36 | 48 |  |  |  | 24 | 32 | 40 | [60 empty] | 8 | 10 | 16 | 4 | 8 | 16 |  |  |  | 16 | 16 | 16 | [78 empty] | 24 | 32 | 40 | [42 empty] | 12 | 16 | 24
2.2.4.39 | 776.24.9 | Prepare Technical memorandum for design related issues | None | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | memo | 8 | 20 | 40 | 1 | 4 | 6 | [42 empty] | 4: 4; 8: 8; 12: 20 | [6 empty] | 2 | 4 | 8 | [18 empty] | 1 | 4 | 6
2.2.4.40 | 776.25 | Plan Preparation
2.2.4.41 | 776.25.1 | Title sheet |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 14 | 16 | 24 | [45 empty] | 4: 6; 8: 8; 12: 8 | [24 empty] | 4 | 4 | 8
2.2.4.42 | 776.25.2 | General notes |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 14 | 16 | 24 | [45 empty] | 4: 6; 8: 8; 12: 10 | [6 empty] | 4 | 4 | 8 | [15 empty] | 4 | 4 | 8
2.2.4.43 | 776.25.3 | Project Overview |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 16 | 24 | 40 | [45 empty] | 4: 7; 8: 10; 12: 20 | [6 empty] | 4 | 4 | 6 | [15 empty] | 6 | 8 | 12
2.2.4.44 | 776.25.4 | Typical sections |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | section | 14 | 16 | 20 | [45 empty] | 4: 7; 8: 8; 12: 12 | [6 empty] | 3 | 6 | 8 | [15 empty] | 4 | 4 | 4
2.2.4.45 | 776.25.5 | Construction details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | detail | 6 | 32 | 48 | [45 empty] | 4: 2; 8: 14; 12: 20 | [6 empty] | 3 | 4 | 4 | [15 empty] | 4 | 14 | 20
2.2.4.46 | 776.25.6 | Building and site clearance details | [15 empty] | X | X | X |  |  |  |  | sheet | 16 | 32 | 40 | [45 empty] | 4: 7; 8: 14; 12: 18 | [6 empty] | 0 | 4 | 8 | [15 empty] | 7 | 14 | 18
2.2.4.47 | 776.25.7 | Jointing details | [13 empty] | X | X | X | X | X | X | X | X | X | detail | 6 | 10 | 16 | [45 empty] | 4: 3; 8: 4; 12: 6 | [6 empty] | 2 | 4 | 4 | [15 empty] | 2 | 5 | 8
2.2.4.48 | 776.25.8 | Driveway details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | detail | 6 | 10 | 20 | [45 empty] | 4: 3; 8: 4; 12: 8 | [6 empty] | 1 | 1 | 2 | [15 empty] | 2 | 5 | 10
2.2.4.49 | 776.25.9 | Curb ramp details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | detail | 0 | 6 | 20 | [45 empty] | 4: 0; 8: 2; 12: 6 | [6 empty] | 1 | 1 | 2 | [15 empty] | 0 | 2 | 12
2.2.4.50 | 776.25.10 | Plan / paving details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 28 | 40 | 52 | [45 empty] | 4: 10; 8: 16; 12: 14 | [6 empty] | 0 | 1 | 2 | [15 empty] | 14 | 20 | 28 | [69 empty] | 0 | 0 | 4
2.2.4.51 | 776.25.11 | Intersection details |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | intersection | 40 | 60 | 80 | [45 empty] | 4: 22; 8: 36; 12: 42 | [6 empty] | 4 | 4 | 6 | [15 empty] | 14 | 18 | 36 | [69 empty] | 0 | 0 | 4
2.2.4.52 | 776.25.12 | Interchange details | [15 empty] | X | X | X |  |  |  |  | sheet | 40 | 60 | 80 | [45 empty] | 4: 22; 8: 36; 12: 42 | [6 empty] | 4 | 6 | 8 | [15 empty] | 14 | 18 | 36 | [69 empty] | 0 | 0 | 4
2.2.4.53 | 776.25.13 | Storm Sewer and Utilities details | [13 empty] | X | X | X | X | X |  |  |  |  | sheet | 42 | 64 | 100 | [45 empty] | 4: 22; 8: 32; 12: 44 | [6 empty] | 4 | 6 | 8 | [15 empty] | 16 | 26 | 30 | [69 empty] | 0 | 0 | 4
2.2.4.54 | 776.25.14 | Alignment diagram |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 24 | 36 | 52 | [45 empty] | 4: 8; 8: 14; 12: 26 | [6 empty] | 4 | 6 | 12 | [15 empty] | 14 | 20 | 20
2.2.4.55 | 776.25.15 | Superelevation table |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 24 | 36 | 44 | [45 empty] | 4: 8; 8: 20; 12: 24 | [6 empty] | 2 | 2 | 6 | [15 empty] | 10 | 14 | 16
2.2.4.56 | 776.25.16 | Plan and profile sheets |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [45 empty] | 4: 16; 8: 24; 12: 32 | [6 empty] | 4 | 4 | 6 | [15 empty] | 20 | 32 | 44
2.2.4.57 | 776.25.17 | Plan and profile - mainline |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [45 empty] | 4: 16; 8: 24; 12: 32 | [6 empty] | 4 | 4 | 6 | [15 empty] | 20 | 32 | 44 | [69 empty] | 0 | 0 | 4
2.2.4.58 | 776.25.18 | Plan and profile - crossroads |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [45 empty] | 4: 16; 8: 24; 12: 32 | [6 empty] | 4 | 4 | 6 | [15 empty] | 20 | 32 | 44 | [69 empty] | 0 | 0 | 4
2.2.4.59 | 776.25.19 | Plan and profile - ramps | [15 empty] | X | X | X |  |  |  |  | sheet | 40 | 60 | 80 | [45 empty] | 4: 16; 8: 24; 12: 32 | [6 empty] | 4 | 4 | 6 | [15 empty] | 20 | 32 | 44 | [69 empty] | 0 | 0 | 4
2.2.4.60 | 776.25.20 | Cross sections |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | sheet | 2 | 4 | 6 | [45 empty] | 4: 1; 8: 1; 12: 2 | [6 empty] | 0 | 1 | 1 | [15 empty] | 1 | 2 | 3
2.2.4.61 | 776.26 | Specialty - Roundabout design | [15 empty] | X | X | X
2.2.5 | 786 | Develop Quantities and Estimates
2.2.5.1 | 786 | Develop Quantities and Estimates - Scoping task | FDM 19-5
2.2.5.2 | 786.1 | Calculate/estimate quantities | FDM 15-1-30, 19-5-5.7 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 68 | 114 | 152 | [45 empty] | 32 | 54 | 70 | 8 | 12 | 16 | [6 empty] | 2 | 4 | 8 | [12 empty] | 16 | 26 | 30 | 8 | 14 | 18 | 2 | 4 | 10
2.2.5.3 | 786.2 | Calculate Earthwork and Develop Summary Tables | FDM 11-5-10, 15-1-30 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 24 | 36 | 48 | [45 empty] | 4 | 6 | 8 | 8 | 12 | 16 | [6 empty] | 2 | 3 | 4 | [15 empty] | 8 | 12 | 16 | 2 | 3 | 4
2.2.5.4 | 786.3 | Prepare Estimate Documentation Report/Determine unit prices | FDM 19-5-5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 24 | 40 | 80 | 1 | 1 | 1 | [42 empty] | 4: 16; 8: 26; 12: 52 | [6 empty] | 4 | 8 | 16 | [15 empty] | 0 | 1 | 3 | 3 | 4 | 8
2.2.5.5 | 786.4 | Prepare non-delivery cost (Estimator/Trns.port PES estimate) | FDM 19-5-10 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 20 | [45 empty] | 4 | 6 | 10 | 1 | 2 | 3 | [6 empty] | 1 | 1 | 1 | [15 empty] | 2 | 3 | 6
2.2.6 | 856 | Develop PSE Documents
2.2.6.1 | 856 | Develop PSE Documents - Scoping task | FDM 19-10
2.2.6.2 | 856.1 | Develop special provisions |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 20 | 40 | 80 | 1 | 1 | 4 | [42 empty] | 4: 19; 8: 39; 12: 59 | [24 empty] | 0 | 0 | 20
2.2.6.3 | 856.2 | Develop construction time chart |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 20 | 40 | [45 empty] | 4: 7; 8: 19; 12: 10 | [6 empty] | 1 | 1 | 5 | [18 empty] | 0 | 0 | 25
2.2.6.4 | 856.3 | Develop certificate of right of way |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 3 | [45 empty] | 4: 1; 8: 2; 12: 2 | [27 empty] | 0 | 0 | 2 | [147 empty] | 0 | 0 | 1
2.2.6.5 | 856.4 | Develop Utility status report |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 3 | [45 empty] | 4: 1; 8: 2; 12: 2 | [27 empty] | 0 | 0 | 2
2.2.6.6 | 856.5 | Develop Certification of Railroad Coordination |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | bar: 4 to 12
2.2.6.7 | 856.6 | Develop Governors Bond - DT25 |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | [78 empty] | 0 | 0 | 1 | bar: 4 to 12
2.2.6.8 | 856.7 | Develop highway work proposal |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 2 | [78 empty] | 0 | 0 | 2 | bar: 4 to 12
2.2.6.9 | 856.8 | Develop plan letter |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 16 | 24 | [45 empty] | 4: 7; 8: 15; 12: 15 | [6 empty] | 1 | 1 | 1 | [18 empty] | 0 | 0 | 18
2.2.6.10 | 856.9 | Develop news release form |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 2 | 2 | [45 empty] | 4: 2; 8: 2; 12: 2
2.2.6.11 | 856.1 | Develop notes to construction engineer |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 4 | [45 empty] | 4: 1; 8: 2; 12: 2 | [27 empty] | 0 | 0 | 3
2.2.6.12 | 856.11 | Develop Region Specific PS&E Documents |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [45 empty] | 4: 2; 8: 4; 12: 4 | [27 empty] | 0 | 0 | 6
2.2.6.13 | 856.12 | AutoCAD Civil 3D Project Data Submittal |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 4 | 8 | 16 | [78 empty] | 4 | 8 | 16
2.2.6.14 | 856.13 | Project Archive |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [78 empty] | 2 | 4 | 8
2.2.6.15 | 856.14 | Contractor Data Packet |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 24 | 40 | [78 empty] | 8 | 24 | 40
2.2.6.16 | 856.15 | Create Standard Detail Spreadsheet |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | [78 empty] | 1 | 1 | 1
2.2.6.17 | 856.16 | Prepare e-plan submittal |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [78 empty] | 2 | 4 | 8
2.3 |  | Data, Survey, and Mapping
2.3.1 | 610 | Acquire Aerial Imagery
2.3.1.1 | 610 | Acquire Aerial Imagery - Scoping task
2.3.1.2 | 610.1 | Develop flight plans and target document | FDM 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.6 | 0.7 | 0.9 | [282 empty] | 0.6 | .7 | .9
2.3.1.3 | 610.2 | Capture aerial imagery | FDM 9-45-5.1, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.6 | 0.7 | 0.9 | [282 empty] | .6 | .7 | .9
2.3.1.4 | 610.3 | Image processing - film; develop; QA/QC | FDM 9-45-5, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.2 | 0.4 | 0.6 | [282 empty] | .2 | .4 | .6
2.3.1.5 | 610.4 | Image processing - digital; initial processing; QA/QC | FDM 9-45-5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 10 | [282 empty] | 4 | 8 | 10
2.3.2 | 668 | Scan Aerial Images
2.3.2.1 | 668 | Scan Aerial Images - Scoping task
2.3.2.2 | 668.1 | Convert film imagery to digital with high resolution scanners | FDM 9-45-5.1, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.12 | 0.18 | 0.24 | [282 empty] | .12 | .18 | .24
2.3.3 | 237 | Perform Analytical Triangulation
2.3.3.1 | 237 | Perform Analytical Triangulation - Scoping task
2.3.3.2 | 237.1 | Analytical Control | FDM 9-45-10, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 0.4 | 2 | 8 | [282 empty] | .4 | 2 | 8
2.3.3.3 | 237.2 | Softcopy Analytical Triangulation | FDM 9-45-10, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 3 | 6 | 10 | [282 empty] | 3 | 6 | 10
2.3.4 | 232 | Develop Digital Terrain Model (DTM)
2.3.4.1 | 232 | Develop Digital Terrain Model (DTM) - Scoping task
2.3.4.2 | 232.1 | Create digital terrain model for Civil3D (DTM) | FDM 9-45-10.1, 9-45-15
2.3.4.3 | 232.1.1 | No R/W | FDM 9-45-10.1, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 12 | 20 | 48 | [282 empty] | 12 | 20 | 48
2.3.4.4 | 232.1.2 | With R/W | FDM 9-45-10.1, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 24 | 40 | 96 | [282 empty] | 24 | 40 | 96
2.3.5 | 236 | Develop Planimetric Mapping
2.3.5.1 | 236 | Develop Planimetric Mapping - Scoping task
2.3.5.2 | 236.1 | Create base planimetric mapping | FDM 9-45-10.2, 9-45-10.3, 9-45-15
2.3.5.3 | 236.1.1 | No R/W | FDM 9-45-10.2, 9-45-10.3, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 6 | 10 | 24 | [282 empty] | 6 | 10 | 24
2.3.5.4 | 236.1.2 | With R/W | FDM 9-45-10.2, 9-45-10.3, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 12 | 20 | 48 | [282 empty] | 12 | 20 | 48
2.3.6 | 665 | Edit Mapping and Digital Terrain Model
2.3.6.1 | 665 | Edit Mapping and Digital Terrain Model - Scoping task
2.3.6.2 | 665.1 | Edit planimetric mapping | FDM 9-45-10, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 0.5 | 1 | 2 | [273 empty] | .5 | 1 | 2
2.3.6.3 | 665.2 | Edit digital terrain model (DTM) | FDM 9-45-10, 9-45-15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 1 | 2 | 4 | [273 empty] | 1 | 2 | 4
2.3.7 | 669 | Develop Digital Orthophotos
2.3.7.1 | 669 | Develop Digital Orthophotos - Scoping task
2.3.7.2 | 669.1 | Develop digital orthophotos | FDM 9-45-10.5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.3 | 0.4 | 0.5 | [282 empty] | .3 | .4 | .5
2.3.7.3 | 669.2 | Develop digital georeferenced imagery | FDM 9-45-5.3 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 0.4 | 0.5 | 0.6 | [282 empty] | .4 | .5 | .6
2.3.8 | 373 | Acquire Aerial LiDAR
2.3.8.1 | 373 | Acquire Aerial LiDAR - Scoping task
2.3.8.2 | 373.1 | Develop flight plans and target document | FDM 9-45-20.2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 16 | [273 empty] | .2 | .3 | .6 | [6 empty] | 3.8 | 7.7 | 15.4
2.3.8.3 | 373.2 | Collect aerial LiDAR data | FDM 9-45-20.1.1 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 1 | 1 | 1 | [282 empty] | 1 | 1 | 1
2.3.9 | 374 | Process Aerial LiDAR
2.3.9.1 | 374 | Process Aerial LiDAR - Scoping task
2.3.9.2 | 374.1 | Data preparation and registration; QA/QC | FDM 9-45-20.1.1 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 1 | 1.75 | 2.5 | [273 empty] | .1 | .1 | .1 | [6 empty] | .9 | 1.65 | 2.4
2.3.9.3 | 374.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | centerline mile | 5 | 8 | 10 | [273 empty] | .2 | .3 | .4 | [6 empty] | 4.8 | 7.7 | 9.6
2.3.10 | 375 | Acquire Static LIDAR
2.3.10.1 | 375 | Acquire Static LIDAR - Scoping task
2.3.10.2 | 375.1 | Develop scan positions and target document | FDM 9-45-20.2.1, 9-45-25 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 3 | 4 | 5 | [282 empty] | 3 | 4 | 5
2.3.10.3 | 375.2 | Collect scan data and images | FDM 9-45-20.1.3, 9-45-25 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 20 | 25 | 30 | [282 empty] | 20 | 25 | 30
2.3.11 | 376 | Process Static LIDAR
2.3.11.1 | 376 | Process Static LIDAR - Scoping task
2.3.11.2 | 376.1 | Data preparation and registration; QA/QC | FDM 9-45-20.2.1 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 10 | 12 | 15 | [282 empty] | 10 | 12 | 15
2.3.11.3 | 376.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 50 | 85 | 110 | [282 empty] | 50 | 85 | 110
2.3.12 | 377 | Acquire Mobile LiDAR
2.3.12.1 | 377 | Acquire Mobile LiDAR - Scoping task
2.3.12.2 | 377.1 | Develop drive paths and target document | FDM 9-45-20.2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24 | [273 empty] | 2 | 3 | 4 | [6 empty] | 6 | 13 | 20
2.3.12.3 | 377.2 | Collect scan data and images | FDM 9-45-20.1.2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | centerline mile | 1 | 2 | 3 | [273 empty] | .5 | .5 | .5 | [6 empty] | .5 | 1.5 | 2.5
2.3.13 | 378 | Process Mobile LiDAR
2.3.13.1 | 378 | Process Mobile LiDAR - Scoping task
2.3.13.2 | 378.1 | Data preparation and registration; QA/QC | FDM 9-45-20.1.2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | centerline mile | 3 | 4.5 | 6 | [273 empty] | .1 | .2 | .2 | [6 empty] | 2.9 | 4.3 | 5.8
2.3.13.3 | 378.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | centerline mile | 10 | 12 | 15 | [273 empty] | .4 | .5 | .6 | [6 empty] | 9.6 | 11.5 | 14.4
2.3.14 | 379 | Merge LiDAR Data
2.3.14.1 | 379 | Merge LiDAR Data - Scoping task
2.3.14.2 | 379.1 | Develop boundary between data types; delete unneeded data | None | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 1 | 3 | 4 | [282 empty] | 1 | 3 | 4
2.3.14.3 | 379.2 | Create deliverables; QA/QC | FDM 9-45-20.5 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | mile | 1 | 3 | 4 | [282 empty] | 1 | 3 | 4
2.3.15 | 382 | Setup Survey Project
2.3.15.1 | 382 | Setup Survey Project - Scoping task
2.3.15.2 | 382.1 | Fill out "Greenie" request form |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 1 | 5 | 10 | [282 empty] | 1 | 5 | 10
2.3.15.3 | 382.2 | For aerial photography flights |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 16 | [282 empty] | 8 | 12 | 16
2.3.15.4 | 382.3 | For aerial LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 16 | [282 empty] | 8 | 12 | 16
2.3.15.5 | 382.4 | For mobile LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24 | [282 empty] | 8 | 16 | 24
2.3.15.6 | 382.5 | For static LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 12 | [282 empty] | 4 | 8 | 12
2.3.16 | 381 | Place and Survey Targeting
2.3.16.1 | 381 | Place and Survey Targeting - Scoping task
2.3.16.2 | 381.1 | Targeting for aerial photography and aerial LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | flight line mile | 7 | 15 | 25 | [282 empty] | 0 | 1 | 5 | [6 empty] | 0 | 7 | 10 | 7 | 7 | 10
2.3.16.3 | 381.2 | Targeting for static LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | acre | 8 | 10 | 12 | [282 empty] | 0 | 2 | 4 | [9 empty] | 8 | 8 | 8
2.3.16.4 | 381.3 | Targeting for mobile LiDAR |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | centerline mile | 30 | 35 | 40 | [282 empty] | 2 | 5 | 8 | [6 empty] | 14 | 16 | 16 | 14 | 15 | 16
2.3.17 | 666 | Establish Project Control
2.3.17.1 | 666 | Establish Project Control - Scoping task
2.3.17.2 | 666.1 | Set horizontal and vertical control for GPS or other conventional methods | FDM 9-25-5
2.3.17.3 | 666.1.1 | Set project control | FDM 9-25-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | point | 0.25 | N/A | 0.5 | [291 empty] | .25 | .25 | .5
2.3.17.4 | 666.1.2 | Set project benchmarks | FDM 9-25-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | point | 0.25 | N/A | 0.5 | [291 empty] | .25 | .25 | .5
2.3.17.5 | 666.1.3 | Create control tie sheets | DT2262 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 1 | [288 empty] | 1 | 1 | 1
2.3.17.6 | 666.1.4 | Set project reference points |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | station | 0.5 | 0.5 | 0.5 | [291 empty] | .5 | .5 | .5
2.3.17.7 | 666.1.5 | GPS observation | FDM 9-45, FDM 9-20, | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | point | 0.25 | 0.5 | 1 | [294 empty] | .25 | .5 | 1
2.3.17.8 | 666.1.6 | Total station observations (closed traverse) | FDM 9-35 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 0.5X2 | 0.5X2 | 1X2 | [291 empty] | .5 | .5 | 1 | .5 | .5 | 1
2.3.17.9 | 666.1.7 | Perform leveling (closed traverse) | FDM 9-40 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 2X2 | 4X2 | 5X2 | [291 empty] | 2 | 4 | 5 | 2 | 4 | 5
2.3.17.10 | 666.2 | Replace Height Modernization geodetic survey control
2.3.17.11 | 666.2.1 | Perform geodetic survey control station reconnaissance | None | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 2 | 3 | 4 | [294 empty] | 2 | 3 | 4
2.3.17.12 | 666.2.2 | Install geodetic survey control station | FDM 9-25-10.1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 2 | 4 | 6 | [282 empty] | 1 | 2 | 3 | [6 empty] | 1 | 2 | 3
2.3.17.13 | 666.2.3 | Develop a geodetic survey control station description | “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 2 | 3 | [291 empty] | 1 | 2 | 3
2.3.17.14 | 666.2.4 | Perform Second Order, Class 1 geodetic leveling (double-run) | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993. 6.3.6.2 "Geodetic Leveling", NOAA Manual NOS NGS3, NOAA, National Geodetic Survey, August 1981; "Interim FGCS Specifications and Procedures to Incorporate Electronic Digital/Bar-Code Leveling Systems", FGCS (Ver. 4.0 7/15/94); "VFPROC--Vertical Control Field Data Processing System", NOAA, C&GS, National Geodetic Survey, Version 3.00, December 1992; "Input Formats and Specifications for the National Geodetic Survey Data Base", Volume II, Vertical Control Data, Federal Geodetic Data Committee, September 1994, Reprinted November 1998; “NGS PROPOSAL for An Addendum to Current FGCS Specifications and Procedures to Incorporate Electronic Digital/Bar-Code Leveling Systems”, National Geodetic Survey, February 2001; “Input Formats and Specifications of the National Geodetic Survey Data Base", Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | kilometer | 3 | 5 | 7 | [291 empty] | 2 | 4 | 6 | 1 | 1 | 1
2.3.17.15 | 666.2.5 | Perform static GPS observations to National Geodetic Survey (NGS) standards | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993; “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998; “Guidelines for Establishing GPS-Derived Orthometric Heights (Standards: 2cm and 5 cm),” Draft, Version 1.4, National Geodetic Survey, October 2005; “Guidelines for Establishing GPS-Derived Ellipsoid Heights (Standards: 2cm and 5 cm),” NOAA Technical Memorandum NOS NGS-58, National Geodetic Survey, November 1997. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | station | 10 | 20 | 30 | [282 empty] | 2 | 4 | 6 | [6 empty] | 6 | 12 | 18 | 2 | 4 | 6
2.3.17.16 | 666.2.6 | Perform data post-processing, analysis, adjustment for acceptance and inclusion into the National Spatial Reference System (NSRS) | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993; “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 15 | 20 | [273 empty] | 1.67 | 2.5 | 3.33 | [6 empty] | 5 | 7.5 | 10 | [9 empty] | 3.33 | 5 | 6.67
2.3.17.17 | 666.3 | Specialty - Wisconsin height modernization program
2.3.17.18 | 666.4 | Specialty - Geodetic services
2.3.18 | 723 | Conduct and Process Existing Field Survey
2.3.18.1 | 723 | Conduct and Process Existing Field Survey - Scoping task | FDM Chapter 9
2.3.18.2 | 723.1 | Review plans and as-builts | FDM 9 & 12 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 4 | 6 | [273 empty] | 0 | 2 | 4 | [18 empty] | 2 | 2 | 2
2.3.18.3 | 723.2 | Measure existing centerline | FDM 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 2 | 4 | 6 | [282 empty] | 0 | 1 | 1 | [6 empty] | 2 | 3 | 5
2.3.18.4 | 723.3 | Measure existing monumentation | FDM 9.25 | [14 empty] | X | X | X |  | X |  |  | mile | 4 | 5 | 6 | [282 empty] | 1 | 1 | 1 | [6 empty] | 3 | 4 | 5
2.3.18.5 | 723.4 | Existing surface and topographic survey | FDM 9.65 |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 10 | 16 | 20 | [282 empty] | 4 | 5 | 6 | [6 empty] | 6 | 10 | 15
2.3.18.6 | 723.5 | Structure field survey | FDM 9.60 | [17 empty] | X | X | X | X | 0.1 mile | 8 | 10 | 20 | [282 empty] | 4 | 5 | 10 | [6 empty] | 4 | 5 | 10
2.3.18.7 | 723.6 | Call diggers hotline | FDM Chapter 9 | [12 empty] | X | X | X | X | X | X | X | X | X | mile | 1 | 2 | 2 | [294 empty] | 1 | 2 | 2
2.3.18.8 | 723.7 | Dip manholes and water valves | FDM Chapter 9 | [12 empty] | X | X | X | X | [5 empty] | each | 1 | 2 | 2 | [282 empty] | 0 | 1 | 1 | [6 empty] | 1 | 1 | 1
2.3.18.9 | 723.8 | Stake marking limits | FDM Chapter 9 | [12 empty] | X | X | X |  |  |  | X | X | X | trip | 4 | 5 | 6 | [282 empty] | 4 | 5 | 6
2.3.18.10 | 723.9 | Photographs | FDM Chapter 9 | [12 empty] | X | X | X |  |  | X | X | X | X | project | 2 | 4 | 8 | [291 empty] | 2 | 4 | 8
2.3.18.11 | 723.1 | Meet with utility locator in field | FDM Chapter 9 | [14 empty] | X | [6 empty] | trip | 4 | 5 | 6 | [294 empty] | 4 | 5 | 6
2.3.18.12 | 723.11 | Review 1077 utility facility map | FDM Chapter 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 4 | 8 | [294 empty] | 2 | 4 | 8
2.3.18.13 | 723.12 | Field survey exisitng utilities | FDM Chapter 9 | [12 empty] | X | X | X | X | X | X | X | X | X | mile | 4 | 6 | 10 | [282 empty] | 2 | 3 | 5 | [6 empty] | 2 | 3 | 5
2.3.18.14 | 723.13 | Perform storm sewer structure evaluations (size-depth-invert) | FDM Chapter 9 | [12 empty] | X | X | X | X | X |  |  |  |  | each | 1 | 2 | 2 | [294 empty] | 1 | 2 | 2
2.3.18.15 | 723.14 | Process survey data and create existing surface | FDM Chapter 9 | [12 empty] | X | X | X | X | X | X | X | X | X | 0.1 mile | 2 | 3 | 4 | [294 empty] | 2 | 3 | 4
2.3.18.16 | 723.15 | Field notes |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 5 | 6 | [291 empty] | 2 | 5 | 6
2.3.18.17 | 723.16 | Measure/map exisitng drainage features | FDM Chapter 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | 0.1 mile | 1 | 2 | 3 | [282 empty] | 1 | 2 | 3
2.3.18.18 | 723.17 | Traffic control for survey | [22 empty] | day | 1 | 2 | 4 | [291 empty] | 1 | 2 | 4
2.3.18.19 | 723.18 | Create deliverables in Civil 3D | FDM Chapter 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 6 | 8 | 10 | [294 empty] | 6 | 8 | 10
2.3.18.20 | 723.19 | Reduce field notes | FDM Chapter 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 2 | 3 | 4 | [291 empty] | 2 | 3 | 4
2.3.18.21 | 723.2 | Level 1500 feet upstream and downstream from structure | FDM 9.60 | X | X | X |  |  |  | X | X | X | X | X | X | GPS | GPS |  |  | X | X | X | X | X | 0.1 mile | 2 | 6 | 8 | [282 empty] | 1 | 3 | 4 | [6 empty] | 1 | 3 | 4
2.3.18.22 | 723.21 | Measure structure clearances | FDM 9.60 | [16 empty] | X | X | X | X | X | structure | 4 | 6 | 10 | [282 empty] | 2 | 3 | 5 | [6 empty] | 2 | 3 | 5
2.3.18.23 | 723.22 | Measure water and high water elevations | FDM 9.60 | [16 empty] | X | X | X | X | X | project | 2 | 3 | 4 | [282 empty] | 1 | 2 | 2 | [6 empty] | 1 | 1 | 2
2.3.18.24 | 723.23 | Create stream cross sections | FDM 9.60 | [16 empty] | X | X | X | X | X | project | 4 | 6 | 8 | [282 empty] | 2 | 3 | 4 | [6 empty] | 2 | 3 | 4
2.3.18.25 | 723.24 | Railroad Profile Survey
2.3.19 | 726 | Survey Existing and Proposed Right-of-Way
2.3.19.1 | 726 | Survey Existing and Proposed Right-of-Way - Scoping task | [13 empty] | X | X | X | X | X | X | X | X | X
2.3.19.2 | 726.1 | Measure existing right of way and property monumentation | FDM 12-1-5 | [12 empty] | X | X | X | X | X | X | X | X | X | per person per 0.25 mile | 8 | 12 | 20 | [273 empty] | 1 | 1 | 2 | [6 empty] | 1 | 1 | 4 | [6 empty] | 3 | 5 | 7 | 3 | 5 | 7
2.3.19.3 | 726.2 | Measure evidence of occupation | FDM 12-1-5 | [12 empty] | X | X | X | X | X | X | X | X | X | per person per 0.25 mile | 3 | 9 | 16 | [273 empty] | 0 | 0 | 4 | [6 empty] | 1 | 1 | 4 | [6 empty] | 1 | 4 | 4 | 1 | 4 | 4
2.3.19.4 | 726.3 | Measure government corners and ties | FDM 12-1-5, FDM 9-5-1 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 1 | 3 | 8 | [273 empty] | 0 | 0 | 2 | [6 empty] | 0 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 0 | 1 | 2
2.3.19.5 | 726.4 | Re-establish missing government corners and ties | FDM 12-1-5, FDM 9-5-1, FDM 9-25, A-E 7.08 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 4 | 8 | 16 | [282 empty] | 2 | 2 | 6 | [6 empty] | 1 | 3 | 5 | 1 | 3 | 5
2.3.19.6 | 726.5 | Produce tie sheets for government corners | FDM 12-1-5, FDM 9-5-1, A-E 7.08 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 2 | 3 | 4 | [282 empty] | 1 | 2 | 2 | [6 empty] | 1: 1; 3: 1; 5: 2
2.3.19.7 | 726.6 | Research public records | FDM 12-1-5, A-E 7.03 | [12 empty] | X | X | X | X | X | X | X | X | X | mile | 2 | 4 | 6 | [273 empty] | 1 | 2 | 3 | [6 empty] | 1 | 2 | 3
2.3.19.8 | 726.7 | Review legal documents | FDM 12-1-5, A-E 7.03 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 0.5 | 1 | 2 | [273 empty] | 0 | 0 | 1 | [6 empty] | .5 | 1 | 1
2.3.19.9 | 726.8 | Review plans and as-builts | FDM 12-1-5, A-E 7.03 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 0.5 | 2 | 4 | [273 empty] | 0 | 0 | 2 | [6 empty] | 0 | 2 | 2 | bar: 1 to 5
2.3.19.10 | 726.9 | Review title work | FDM 12-1-10, Real Estate Program Manual | [12 empty] | X | X | X | X | X | X | X | X | X | each | 0.5 | 2 | 4 | [273 empty] | 0 | 1 | 3 | [6 empty] | .5 | 1 | 1
2.3.19.11 | 726.1 | Field locate section corners, block corners, iron pins | FDM 12-1-5, FDM 9-1, 9-5, 9-10 | [12 empty] | X | X | X | X | X | X | X | X | X | each | 0.25 | 0.5 | 3 | [273 empty] | 0 | 0 | 1 | [6 empty] | 0 | 0 | 1 | [6 empty] | 1: .25; 3: .5; 5: 1
2.3.19.12 | 726.11 | Survey property corners | FDM 12-1-5, FDM 9-1, 9-5, 9-10 | [12 empty] | X | X | X | X | X | X | X | X | X | corner | 0.25 | 0.5 | 2 | [273 empty] | 0 | 0 | .5 | [6 empty] | 0 | 0 | .5 | [6 empty] | .25 | .25 | .5 | 0 | .25 | .5
2.3.19.13 | 726.12 | Survey section corners | FDM 12-1-5, FDM 9-1, 9-5, 9-10 | [12 empty] | X | X | X | X | X | X | X | X | X | corner | 1 | 3 | 8 | [273 empty] | 0 | 0 | 2 | [6 empty] | 0 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 0 | 1 | 2
2.3.19.14 | 726.13 | Appraisal staking | FDM 9-75 | [12 empty] | X | X | X | X | X | X | X | X | X | point | 0.25 | 0.5 | 1 | [273 empty] | 0 | 0 | .25 | [6 empty] | 0 | 0 | .25 | [6 empty] | .25 | .25 | .25 | 0 | .25 | .25
2.3.20 | 897 | Place Monumentation
2.3.20.1 | 897 | Place Monumentation - Scoping task | [13 empty] | X | X | X | X | X | X | X | X | X
2.3.20.2 | 897.1 | Set right of way pins | FDM 9-5, FDM 9-25, A-E 7.07 | [12 empty] | X | X | X | X | X | X | X | X | X | point | 1.25 | 2 | 4 | [282 empty] | .5 | .5 | 1 | [6 empty] | .5 | 1 | 2 | .25 | .5 | 1
2.3.20.3 | 897.2 | Place type 1, 2,3, 4 monument | FDM 9-5, FDM 9-25, A-E 7.07 | [12 empty] | X | X | X | X | X | X | X | X | X | point | 1.25 | 2 | 6.5 | [282 empty] | .5 | .5 | 2 | [6 empty] | .5 | 1 | 2 | .25 | .5 | 2
2.3.20.4 | 897.3 | Recover monumentation | FDM 9-5, FDM 9-25, A-E 7.07 |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 0.25 | 1 | 4 | [282 empty] | 0 | 0 | 2 | [6 empty] | .25 | .5 | 1 | 0 | .5 | 1
2.3.21 | 745 | Develop Transportation Project Plat (TPP)
2.3.21.1 | 745 | Develop Transportation Project Plat (TPP) - Scoping task | FDM Chapter 12 and A-E 7 | [12 empty] | X | X | X | X | X |  | X | X | X
2.3.21.2 | 745.1 | Railroad right of way | FDM 12-15-1.6.2 | [12 empty] | X | X | X | X | X |  | X | X | X | project | 1 | 2 | 4 | [273 empty] | 0 | 1 | 2 | [6 empty] | 1 | 1 | 2
2.3.21.3 | 745.2 | Develop property exhibits | REPM (CH2 ?) | [12 empty] | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 3 | [282 empty] | .5 | 1 | 1 | [6 empty] | 1: .5; 3: 1; 5: 2
2.3.21.4 | 745.3 | Develop schedule of lands | FDM 12-10-1.2.21 | [12 empty] | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 3 | [282 empty] | .5 | .5 | .5 | [6 empty] | 1: .5; 3: 1.5; 5: 2.5
2.3.21.5 | 745.4 | Legal descriptions | FDM 12-10-20 | [12 empty] | X | X | X | X | X |  | X | X | X | parcel | 1 | 1 | 2 | [282 empty] | .5 | .5 | 1 | bar: 1 to 5
2.3.21.5.1 | 745.4.1 | Closure reports | FDM 12-10a1.6 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 1 | N/A | 2 | [282 empty] | .5 | .5 | 1 | bar: 1 to 5
2.3.21.6 | 745.5 | Record TPP | [13 empty] | X | X | X | X | X |  | X | X | X | sheet | 1 | 2 | 2 | [282 empty] | .5 | 1 | 1 | bar: 1 to 5
2.3.21.7 | 745.6 | Design information to TPP section | FDM 12-5 | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 1 | 1 | 1 | [282 empty] | 1 | 1 | 1
2.3.21.8 | 745.7 | Section corners | FDM 12-10-1.2.13 | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 1 | 4 | 8 | [282 empty] | .5 | 1 | 2 | [6 empty] | 1: .5; 3: 3; 5: 6
2.3.21.9 | 745.8 | Review title searches and updates | FDM 12-1-10 | [12 empty] | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 4 | [282 empty] | .5 | 1 | 3 | bar: 1 to 5
2.3.21.10 | 745.9 | Existing R/W lines, easements, alignments, and access control | FDM 12-1-10 & 12-1-5 | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 10 | 20 | 30 | [282 empty] | 4 | 8 | 10 | [6 empty] | 1: 6; 3: 12; 5: 20
2.3.21.11 | 745.1 | Field review-property owner walkthrough | REPM Chatper 2 | [12 empty] | X | X | X | X | X |  | X | X | X | parcel | 3 | 10 | 20 | [228 empty] | 3 | 10 | 20
2.3.21.12 | 745.11 | Preliminary TPP (Layout and Annotation) | FDM 12-10 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 2 | 4 | 6 | [282 empty] | .5 | 1 | 2 | [6 empty] | 1: .5; 3: 3; 5: 4
2.3.21.13 | 745.12 | Determine/label compensable utilities and utility easements | FDM 12-10-1.2.26 | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 10 | 15 | 20 | [282 empty] | 6 | 10 | 15 | [6 empty] | 1: 4; 3: 5; 5: 5
2.3.21.14 | 745.13 | Utility legal descriptions (may be included in legal descriptions and closure calculations) | Move to Utility Section??? Or 12-10-1.2.26 |  | X | X | X | X | X | X |  | X | X | X | X | X | X | X | X | X |  | X | X | X | PLSS qtr section | 2 | 4 | 10
2.3.21.15 | 745.14 | Proposed R/W lines, easements, alignments, parcels, etc. | FDM 12-5-1 | [12 empty] | X | X | X | X | X |  | X | X | X | each | 1 | 2 | 4 | [282 empty] | .5 | 1 | 2 | [6 empty] | 1: .5; 3: 1; 5: 2
2.3.21.16 | 745.15 | Final plat to technical services section | ?? WisDOT function | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 5 | 10 | 20
2.3.21.17 | 745.16 | Final TPP relocation order | FDM 12-10-1.2.4 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 1 | 2 | 2 | [282 empty] | .5 | 1 | 1 | bar: 1 to 5
2.3.21.18 | 746.17 | TPP drafting (Title sheet) | FDM 12-10-1.3 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 1 | 1 | 2 | [282 empty] | .5 | .5 | .5 | [6 empty] | 1: .5; 3: .5; 5: 1.5
2.3.21.19 | 747.18 | Sheet revisions/ amendments | FDM 12-10-15 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 0.5 | 1 | 2 | [273 empty] | .5 | .5 | .5 | [6 empty] | .5 | 1 | 2
2.3.21.20 | 745.19 | Traditional plats | FDM 12-15
2.3.21.21 | 745.19.1 | Existing R/W lines, easements, alignments, and access control | FDM 12-1-10 & 12-1-5 | [12 empty] | X | X | X | X | X |  | X | X | X | PLSS qtr section | 10 | 20 | 30 | [282 empty] | 4 | 8 | 10 | [6 empty] | 1: 6; 3: 12; 5: 20
2.3.21.22 | 745.19.2 | Proposed R/W lines, easements, alignments, parcels, etc. | FDM 12-5-1 | [12 empty] | X | X | X | X | X |  | X | X | X | each | 1 | 2 | 4 | [282 empty] | .5 | 1 | 2 | [6 empty] | 1: .5; 3: 1; 5: 2
2.3.21.23 | 745.19.3 | Title sheet | FDM 12-15-1.1 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 8 | 8 | 8 | [282 empty] | 4 | 4 | 4 | [6 empty] | 1: 4; 3: 4; 5: 4
2.3.21.24 | 745.19.4 | Overview sheet | FDM 12-15-1.3 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 8 | 12 | 16 | [282 empty] | 4 | 6 | 8 | [6 empty] | 1: 4; 3: 6; 5: 8
2.3.21.25 | 745.19.5 | Schedule of lands and interests | FDM 12-15-1.2 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 4 | 8 | 8 | [282 empty] | 2 | 3 | 4 | [6 empty] | 1: 2; 3: 3; 5: 4
2.3.21.26 | 745.19.6 | Detail sheets | FDM 12-15-1.4 | [12 empty] | X | X | X | X | X |  | X | X | X | sheet | 12 | 18 | 24 | [282 empty] | 6 | 9 | 12 | [6 empty] | 1: 6; 3: 9; 5: 12
2.3.21.27 | 745.19.7 | Legal descriptions | FDM 12-15-20 | [12 empty] | X | X | X | X | X |  | X | X | X | each | 0.5 | 1 | 2 | [282 empty] | .5 | 1 | 2
2.3.21.28 | 745.19.8 | Relocation order and revision | FDM 12-15-1, 12-15-15 | [12 empty] | X | X | X | X | X |  | X | X | X | each | 0.5 | 0.5 | 1 | [282 empty] | .5 | .5 | 1
2.4 |  | Environmental and Cultural Impact
2.4.1 | 762 | Analyze Socio-Economic and Physical Environment Impacts
2.4.1.1 | 762 | Analyze Socio-Economic and Physical Environment Impacts - Scoping task
2.4.1.2 | 762.1 | Conduct air quality analyses | 22
2.4.1.3 | 762.1.1 | Overview of conformity and disucssion of MSATs | 22 | [21 empty] | project | 16 | 36 | 48* | [81 empty] | 12 | 28 | 36 | [9 empty] | 4 | 8 | 12
2.4.1.4 | 762.1.2 | Review/compare carbon monoxide | 22 | [21 empty] | project | 40 | [83 empty] | 20 | 20 | 20 | 12 | 12 | 12 | [6 empty] | 8 | 8 | 8
2.4.1.5 | 762.1.3 | Run air quality model | 22 | [21 empty] | project | 96* | [83 empty] | 56 | 56 | 56 | 24 | 24 | 24 | [6 empty] | 16 | 16 | 16
2.4.1.6 | 762.2 | Conduct farmland studies | FDM 21-25-35; FDM 24-10-15; NRCS form AD-1006 or CPA-106 | [14 empty] | X | X | X |  | X | X |  | project |  | 16
2.4.1.7 | 762.2.1 | Conduct farmland studies with low to moderate impacts | FDM 21-25-30; FDM 24-10-15; Ag Impact Notice | [14 empty] | X | X | X |  | X | X |  | owner | 2 | 6 | 8 | [81 empty] | 1 | 4 | 6 | [9 empty] | 1 | 2 | 2
2.4.1.8 | 762.2.2 | Conduct farmland studies with high impacts | FDM 21-25-30; FDM 24-10-15; Ag Impact Notice |  |  |  | X | X | X | X |  | X | X |  | X |  |  | X | X | X |  | X | X |  | owner |  |  | 10 | [81 empty] | 0 | 0 | 6 | [9 empty] | 0 | 0 | 4
2.4.1.9 | 762.3 | Review economic factors (general, business, agriculture) | 25-5-10; 25-5-18; 25-5-20 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | buisness | 1 | 2 | 4 | [81 empty] | 1 | 2 | 3 | [9 empty] | 0 | 0 | 1
2.4.1.10 | 762.4 | Review community and residential issues | 25-5-5; 25-5-30; 25-10-5
2.4.1.11 | 762.4.1 | Evaluate right of way impacts | [15 empty] | X | X | X |  | X | X |  | owner | 1 | 2 | 4 | [81 empty] | 1 | 1 | 2 | [9 empty] | 0 | 1 | 2
2.4.1.12 | 762.4.2 | Evaluate relocation impacts | 25-5-30 | [14 empty] | X | X | X |  | X | X |  | relocation | 20 | 24 | 32 | [81 empty] | 16 | 18 | 24 | [9 empty] | 4 | 6 | 8
2.4.1.13 | 762.4.3 | Collect/obtain socio-economic data | 25-10-1 | [12 empty] | X | X | X | X | X |  | X | X | X | project | 8 | 20 | 40 | [81 empty] | 6 | 16 | 32 | [9 empty] | 2 | 4 | 8
2.4.1.14 | 762.4.4 | Collect/obtain population data | 25-10-5 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 4 | 6 | [81 empty] | 2 | 4 | 6
2.4.1.15 | 762.4.5 | Evaluate impacts to environmental justice and Title VI populations | 20-10-35; 20-5-35; 25-5-5 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | affected resident or business | 1 | 4 | 10 | [84 empty] | 1 | 3 | 8 | [6 empty] | 0 | 1 | 2
2.4.1.16 | 762.4.6 | Evaluate transportation, access, and alternate mode impacts | 25-5-2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 16 | [84 empty] | 2 | 6 | 12 | [6 empty] | 0 | 2 | 4
2.4.1.17 | 762.4.7 | Obtain land use plans | 25-5-15 | [14 empty] | X | X | X |  | X | X |  | project | 2 | 4 | 6 | [81 empty] | 1 | 3 | 4 | [9 empty] | 1 | 1 | 2
2.4.1.18 | 762.4.8 | Complete indirect and cumulative effects pre-screening worksheets | 25-5-17; Pre-Screening Worksheets | [15 empty] | X | X |  | X |  |  | project | 8 | 12 | 20 | [84 empty] | 6 | 10 | 16 | [6 empty] | 2 | 2 | 4
2.4.1.19 | 762.4.9 | Conduct indirect effects analysis | 25-5-17; Indirect and Cumulative Effect Analysis for Project-Induced Land Development: Technical Reference Guidance Document; WisDOT Guidance for Conducting an Indirect Effects Analysis | [15 empty] | X | X |  | X |  |  | project |  | 96 | 176 | [84 empty] | 0 | 72 | 120 | [6 empty] | 0 | 24 | 56
2.4.1.20 | 762.4.10 | Conduct cumulative effects analysis | 25-5-17; Indirect and Cumulative Effect Analysis for Project-Induced Land Development: Technical Reference Guidance Document; WisDOT Guidance for Conducting a Cumulative Effects Analysis | [15 empty] | X | X |  | X |  |  | project |  | 60 | 120 | [84 empty] | 0 | 48 | 96 | [6 empty] | 0 | 12 | 24
2.4.1.21 | 762.4.11 | Evaluate aesthetic impacts | 27-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project |  | 4 | 40 | [81 empty] | 0 | 4 | 32 | [9 empty] | 0 | 0 | 8
2.4.1.22 | 762.4.12 | Evaluate construction noise impacts | 23-40 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 4 | 12 | [81 empty] | 2 | 3 | 8 | [9 empty] | 0 | 1 | 4
2.4.1.23 | 762.5 | Perform noise analysis | 23
2.4.1.24 | 762.5.1 | Perform field review/measurement for sound quality impact | 23-20-5 | [14 empty] | X | X | X |  |  |  |  | sampling site | 8 | 6 | 4 | [81 empty] | 3 | 4 | 6 | [9 empty] | 2 | 2 | 2
2.4.1.25 | 762.5.2 | Set up existing conditions model | 23-20-10; 23-25-10 | [14 empty] | X | X | X |  |  |  |  | model | 8 | 16 | 24 | [81 empty] | 8 | 16 | 24
2.4.1.26 | 762.5.3 | Set up future no-build model | 23-20-10; 23-25-10 | [14 empty] | X | X | X |  |  |  |  | model | 4 | 8 | 16 | [81 empty] | 4 | 8 | 16
2.4.1.27 | 762.5.4 | Set up build model | 23-20-10; 23-25-10 | [14 empty] | X | X | X |  |  |  |  | model | 8 | 16 | 24 | [81 empty] | 8 | 14 | 20 | [9 empty] | 0 | 2 | 4
2.4.1.28 | 762.5.5 | Create sound quality report | 23-45 | [14 empty] | X | X | X |  |  |  |  | receptor | 3 | [83 empty] | 2 | 2 | 2 | [9 empty] | 1 | 1 | 1
2.4.1.29 | 762.5.6 | Identify impacted receptors (owners and occupants) | 23-30 | [14 empty] | X | X | X |  |  |  |  | receptor | 1 | [83 empty] | 1 | 1 | 1
2.4.1.30 | 762.5.7 | Perform noise wall analysis | 23-30-1; 23-30-2; 23-25-5; 23-36-6; 23-35-7, 23-25-10, 23-25-15; 23-35-20 | [14 empty] | X | X | X |  |  |  |  | project | 24 | 36 | 50 | [81 empty] | 16 | 24 | 32 | 6 | 8 | 12 | [6 empty] | 2 | 4 | 6
2.4.1.31 | 762.5.8 | Conduct Public Involvement Meeting for Noise Abatement Measures | 23-35-20 | [14 empty] | X | X | X |  |  |  |  | meeting | 52 | 72 | 96 | [81 empty] | 24 | 32 | 40 | 16 | 24 | 32 | [6 empty] | 12 | 16 | 24
2.4.1.32 | 762.5.9 | Prepare, mail and tabulate Noise Wall Voting Ballot | 23-35-20 | [14 empty] | X | X | X |  |  |  |  | ballot | 2 | 4 | [82 empty] | 24: 2; 32: 4; 40: 4
2.4.1.33 | 762.5.10 | Follow-up/request unreturned ballots | 23-35-20 | [14 empty] | X | X | X |  |  |  |  | ballot | 2 | [95 empty] | 1 | 1 | 1 | bar: 24 to 40
2.4.1.34 | 762.5.11 | Document Noise Analysis, Voting, and Barrier Selection Process | 23-35-20 | [14 empty] | X | X | X |  |  |  |  | project | 8 | 12 | 16 | [81 empty] | 24: 6; 32: 10; 40: 12 | [6 empty] | 2 | 2 | 4
2.4.1.35 | 762.5.12 | Coordinate Results with WisDOT | 23-35-20 | [14 empty] | X | X | X |  |  |  |  | project | 4 | [95 empty] | 4 | 4 | 4
2.4.2 | 763 | Analyze Archaeological and Historical Impact and Tribal Consultation
2.4.2.1 | 763 | Analyze Archaeological and Historical Impact and Tribal Consultation - Scoping task | FDM Ch 26
2.4.2.2 | 763.1 | Identify Consulting Parties/Notify | FDM 26-5-2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 16 | 24 | 4 | 9 | 14 | [45 empty] | 1 | 2 | 4 | [240 empty] | 3 | 5 | 6
2.4.2.3 | 763.2 | Does the project have the potential to affect historic properties (screening list) | FDM 26-5-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | X |  |  | X | project | 4 | X | 24 | [99 empty] | 1 | 1 | 4 | 2 | 2 | 18 | 1 | 1 | 2
2.4.2.4 | 763.3 | Determine Area of Potential Effect | FDM 26-5-3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 22 | [48 empty] | 2 | 4 | 10 | [48 empty] | 0 | 2 | 6 | 0 | 2 | 6
2.4.2.5 | 763.4 | Conduct archaeological and historical surveys (Identification Step) | FDM 26-5-4
2.4.2.6 | 763.4.1 | Conduct archaeological surveys | FDN 26-5-4 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | acre | 1.5 | 4 | 10 | [102 empty] | 1 | 3 | 8 | .25 | .5 | 1 | [183 empty] | .25 | .5 | 1
2.4.2.7 | 763.4.2 | Conduct historical surveys | FDM 26-5-4 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 25 | 50 | 110 | [102 empty] | 20 | 40 | 80 | 3 | 6 | 15 | [183 empty] | 2 | 4 | 15
2.4.2.8 | 763.5 | Determine if Eligible Properties are present (evaluation) | FDM 26-5-5
2.4.2.9 | 763.5.1 | DOE - archaeology | FDM 26-5-5 | [12 empty] | X | X | X | X | X | X | X | X | X | cubic meter excavated | 40 | 100 | 240 | [102 empty] | 30 | 78 | 200 | 5 | 12 | 25 | [183 empty] | 5 | 10 | 15
2.4.2.10 | 763.5.2 | DOE - history | FDM 26-5-5 | [12 empty] | X | X | X | X | X | X | X | X | X | potentially eligible property | 65 | 145 | 250 | [102 empty] | 50 | 120 | 200 | 10 | 15 | 30 | [183 empty] | 5 | 10 | 20
2.4.2.11 | 763.6 | Determine if there is an effect (if NRHP listed/eligible property present) | FDM 26-5-6 | [11 empty] | X | [9 empty] | eligible property | 6 | X | 40 | [48 empty] | 2 | 2 | 6 | [51 empty] | 4 | 4 | 34
2.4.2.12 | 763.7 | Complete/submit Section 106 Review Form | [13 empty] | X | X | X | X | X | X | X | X | X | project | 16 | X | 32 | [48 empty] | 6 | 6 | 10 | [48 empty] | 4 | 4 | 12 | 6 | 6 | 10
2.4.2.13 | 763.8 | Assess Effects (if NRHP listed or eligible properties are affected) | FDM 26-5-7
2.4.2.14 | 763.8.1 | Prepare Determination of No Adverse Effect (DNAE) or Conditional No Adverse Affect (CNAE) | FDM 26-5-7 | [12 empty] | X | X | X | X | X | X | X | X | X | project | 25 | 90 | 144 | [48 empty] | 2 | 8 | 12 | [48 empty] | 10 | 20 | 30 | 10 | 50 | 80 | 2 | 7 | 12 | [183 empty] | 1 | 5 | 10
2.4.2.15 | 763.8.2 | Resolution of Adverse Effects | FDM 26-5-8
2.4.2.16 | 763.8.2.1 | Prepare Finding of Adverse Affect (FAE aka DforC, now through e106) | FDM 26-5-8 | [12 empty] | X | X | X | X | X | X | X | X | X | project | 25 | 90 | 144 | [48 empty] | 2 | 8 | 12 | [48 empty] | 10 | 20 | 30 | 10 | 50 | 80 | 2 | 7 | 12 | [183 empty] | 1 | 5 | 10
2.4.2.17 | 763.8.2.2 | Develop and Evaluate Measures to Avoid, Minimize, or Mitigate Adverse Effects to Historic Properties. Prepare MOA. Obtain agreement on stipulations of MOA. Obtain signatures on MOA. | FDM 26-5-8 | [12 empty] | X | X | X | X | X | X | X | X | X | project | 50 | 120 | 300 | [48 empty] | 12 | 35 | 100 | [48 empty] | 6 | 20 | 60 | 30 | 60 | 120 | 2 | 5 | 20
2.4.2.18 | 763.9 | Implementation of commitments or stipulations | FDM 26-5-9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 60 | 600 | [48 empty] | 2 | 10 | 100 | [48 empty] | 4 | 20 | 100 | 4 | 25 | 350 | 0 | 5 | 50
2.4.2.19 | 763.1 | State Burial Site Law (Wisconsin 157.70) | FDM 26-25-1
2.4.2.20 | 763.10.1 | determine whether the boundary of the cemetery or other type of burial site extends into the project's APE | FDM 26-25-1.2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | burial site | 8 | 16 | 40 | [48 empty] | 1 | 2 | 6 | [51 empty] | 7 | 14 | 34
2.4.2.21 | 763.10.2 | petition for permission to work within the boundaries of the site | FDM 26-25-1.3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 4 | 4 | [48 empty] | 1 | 1 | 1 | [48 empty] | 3 | 3 | 3
2.4.2.22 | 763.11 | prepare Section 4(f) determination | FDM 26-35-5.1.3 | [14 empty] | X | X | X |  |  | X | X | 4(f) property with use | 10 | 40 | 120 | [48 empty] | 6 | 30 | 95 | [48 empty] | 4 | 10 | 25
2.4.3 | 765 | Analyze Hazardous Materials Site Impact
2.4.3.1 | 765 | Analyze Hazardous Materials Site Impact - Scoping task | FDM 21-35 (potentially exempt projects 21-35-1.5)
2.4.3.2 | 765.1 | Perform Phase 1 hazardous materials assessment | 21-35-5 | [14 empty] | x | x | x | x |  | x | x |  | 71 | 175 | 400
2.4.3.3 | 765.1.1 | Data Collection and Review | 21-35-5.3 (1) | [21 empty] | project | 16 | 70 | 150
2.4.3.4 | 765.1.2 | Field reconnaisance | 21-35-5.3 (2) | [11 empty] | X | [9 empty] | project | 10 | 30 | 50
2.4.3.5 | 765.1.3 | Data evaluation and review, prepare conclusions and recommendations; Prepare site summaries and draft/final hazardous materials report | 21-35-5.3 (3) | [21 empty] | project | 45 | 75 | 200
2.4.3.6 | 765.2 | Perform additonal hazardous materials assessment | [15 empty] | x | x | x | x |  | x | x
2.4.3.7 | 765.2.1 | Perform field investigation and phase 2 report | 21-35-10 | [21 empty] | site | 70 | 100 | 150
2.4.3.8 | 765.2.2 | Perform Phase 2.5 investigation, develop materials handling plan and special provisions | 21-35-12 | [14 empty] | x | x | x | x |  | x | x | project | 30 | 150 | 300
2.4.3.9 | 765.2.2.1 | Prepare phase 2.5 report | 21-35-12.5 | [21 empty] | 0
2.4.3.10 | 765.2.2.2 | Obtain DNR concurrence on materials handling plan | 21-35 attachment 12.1 | [21 empty] | 0
2.4.3.11 | 765.2.3 | Perform Phase 3 investigation, Determinefull nature and extent of contamination and prepare remediation plan | 21-35-15 | [14 empty] | x | x | x | x |  | x | x | site | 65 | 300 | 520 to 1000 or more
2.4.3.12 | 765.2.3.1 | Perform field investigation | 21-35-15.4 (3) | [21 empty] | 0
2.4.3.13 | 765.2.3.2 | Develop remediation plan | 21-35-15.5 | [21 empty] | 0
2.4.3.14 | 765.2.3.3 | Obtain DNR Concurrence on Remediation Plan | 21-35-15.8 | [21 empty] | 0
2.4.3.15 | 765.2.3.4 | Prepare Phase 3 report | [22 empty] | 0
2.4.3.16 | 765.2.4 | Perform Phase 4 Hazardous Materials Remediation and Materials Management | 21-35-20 | [14 empty] | x | x | x | x | x | x | x | site | 100 to 300 | 600 | 1000 or more
2.4.3.17 | 765.2.4.1 | Prepare phase 4 report, site closure package | 21-35-20.5 | [14 empty] | x | x | x | x |  | x | x | 0
2.4.3.18 | 765.3 | Conduct asbestos inspection | 21-35-45 | [14 empty] | x | x | x | x | x | x | x | structure | 15 | 35 | 100
2.4.3.19 | 765.4 | Conduct asbestos abatement | [18 empty] | x | x | x | x | structure | 50 | 150 | 200
2.4.3.20 | 765.4.1 | Prepare abatement plan
2.4.3.21 | 765.4.2 | Prepare notification of Demolition
2.4.3.22 | 765.4.3 | conduct abatement
2.4.3.23 | 765.4.4 | prepare and submit abatement report and disposal documentation
2.4.4 | 766 | Analyze Natural Environment Impact
2.4.4.1 | 766 | Analyze Natural Environment Impact - Scoping task
2.4.4.2 | 766.1 | Evaluate impact on wetlands | Wetlands - C1
2.4.4.3 | 766.1.1 | Determine presence and delineate exisiting wetlands | FDM 21-25-20 and 24-5-10,21-30-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 8 | 20 | 40 | [93 empty] | 2 | 5 | 10 |  |  |  | 5 | 13 | 25 | [189 empty] | 1 | 2 | 5
2.4.4.4 | 766.1.2 | Determine and Quantify wetland and waterway impacts | FDM 21-30-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 8 | 40 | [93 empty] | 0 | 3 | 15 |  |  |  | 0 | 4 | 20 | [189 empty] | 0 | 1 | 5
2.4.4.5 | 766.1.3 | Prepare wetland finding if needed | FDM 21-30-1; Factor Sheet C1 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 24 | 24 | [93 empty] | 0 | 12 | 12 |  |  |  | 0 | 12 | 12
2.4.4.6 | 766.1.4 | Develop 401/404 permit application | 21-30-1.1 and 21-30-1.2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 56 | 96 | [93 empty] | 0 | 20 | 30 |  |  |  | 0 | 30 | 50 | [189 empty] | 0 | 6 | 16
2.4.4.7 | 766.2 | Evaluate impacts to rivers, streams and floodplains | Rivers, Streams, and Floodplains - C2
2.4.4.8 | 766.2.1 | Inventory resources, document impacts and mitigation | FDM 24-5-5, Factor Sheet C2 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 16 | 24 | [93 empty] | 1 | 2 | 4 |  |  |  | 2 | 12 | 16 | [189 empty] | 1 | 2 | 4
2.4.4.9 | 766.2.2 | Obtain permits/approvals as applicable: USACE - Section 10 (with 404 permit), Section 408 USCG Section 9 | FDM 21-25-25 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 24 | 40 | [93 empty] | 0 | 8 | 16 |  |  |  | 0 | 14 | 20 | [189 empty] | 0 | 2 | 4
2.4.4.10 | 766.3 | Evaluate impacts to lakes and other open water | Lakes or other Open Water - C3
2.4.4.11 | 766.3.1 | Inventory resources, document impacts and mitigation | FDM 24-5-5, Factor Sheet C3 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [93 empty] | 1 | 2 | 4 |  |  |  | 2 | 4 | 16 | [189 empty] | 1 | 2 | 4
2.4.4.12 | 766.4 | Evaluate impacts to groundwater wells and springs | Groundwater, Wells and Springs - C4
2.4.4.13 | 766.4.1 | Inventory resources (locate wells and springs), document impacts and mitigation | FDM 24-5-5, Factor Sheet C4 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [93 empty] | 1 | 2 | 4 |  |  |  | 2 | 4 | 16 | [189 empty] | 1 | 2 | 4
2.4.4.14 | 766.5 | Evaluate impacts to upland habitat | Upland Wildlife and Habitat - C5
2.4.4.15 | 766.5.1 | Inventory resources (habitat and wildlife), document impacts | FDM 24-10 and 24-15, Factor Sheet C5 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [93 empty] | 1 | 2 | 4 |  |  |  | 2 | 4 | 16 | [189 empty] | 1 | 2 | 4
2.4.4.16 | 766.6 | Evaluate impact to coastal zones | Coastal Zones - C6
2.4.4.17 | 766.6.1 | Identify if project is in Coastal Zone, coordinate with Coastal Management Program, obtain coastal zone consistency determination | FDM 5-10-35.2; 20-30-1.4, Factor Sheet C6 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [93 empty] | .5 | 2 | 4 |  |  |  | 1 | 4 | 16 | [189 empty] | .5 | 2 | 4
2.4.4.18 | 766.7 | Evaluate impacts to Threatened and Endangered Species | Threatened and Endangered Species - C7
2.4.4.19 | 766.7.1 | Determine if any species are present in project area (IPaC/official species list for federally listed species, NHI review for state listed species) | FDM 20-25-1, Factor Sheet C7 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 6 | [95 empty] | 6 | 6 | 6 |  |  |  | 6 | 6 | 6
2.4.4.20 | 766.7.2 | Survey for species/habitat | FDM 20-25-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 50 | 100 | [99 empty] | 16 | 40 | 85 | [189 empty] | 4 | 10 | 15
2.4.4.21 | 766.7.3 | Evaluate impacts and make effect determinations for species/critical habitat | FDM 20-25-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | listed species | 1 | 5 | 20 | [93 empty] | .5 | 2 | 5 |  |  |  | .5 | 3 | 15
2.4.4.22 | 766.7.4 | Agency Consultation | FDM 20-25-1
2.4.4.23 | 766.7.4.1 | Federally Listed Species (Section 7 Consultation): United States Fish and Wildlife Service (USFWS) | FDM 20-25-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 6 | 150 | [93 empty] | 1 | 2 | 40 |  |  |  | 1 | 4 | 110
2.4.4.24 | 766.7.4.2 | State Listed Species: Wisconsin Department of Natural Resources (WDNR) | FDM 20-25-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 8 | 70 | [93 empty] | .5 | 3 | 20 |  |  |  | .5 | 5 | 50
2.4.4.25 | 766.7.5 | Relocations (mussels, rare plants, host plants, etc.) | FDM 20-25-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 24 | 50 | 150 | [99 empty] | 25 | 50 | 150
2.4.4.26 | 766.8 | Analyze Drainage and Stormwater Impacts | Stormwater - D5
2.4.4.27 | 766.8.1 | Determine and document project's effect on drainage/stormwater | FDM 10, Factor Sheet D5 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 16 | 32 | [93 empty] | 3 | 14 | 28 |  |  |  | 1 | 2 | 4
2.4.4.28 | 766.9 | Section 4(f) – This section covers parks/refuges only. Historical 4(f) is covered under 763.11 | Section 4(f) and 6(f) or Other Unique Areas - B8
2.4.4.29 | 766.9.1 | Determine if Section 4(f) properties are present | FDM 21-25-1, Factor Sheet B8 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 40 | [93 empty] | 2 | 3 | 6 |  |  |  | 10 | 15 | 26 | [189 empty] | 4 | 6 | 8
2.4.4.30 | 766.9.2 | Determine if there is a "use" of the 4(f) property | FDM 21-25-1, Factor Sheet B8 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 24 | 40 | [93 empty] | 8 | 9 | 12 |  |  |  | 8 | 10 | 20 | [189 empty] | 4 | 5 | 8
2.4.4.31 | 766.9.3 | Prepare Section 4(f) Evaluation | FDM 21-25-1, Factor Sheet B8 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | property | 40 | 60 | 160 | [93 empty] | 35 | 55 | 120 |  |  |  | 5 | 5 | 40
2.4.4.32 | 766.1 | Section 6(f) and other grant funded properties | Section 4(f) and 6(f) or Other Unique Areas - B8
2.4.4.33 | 766.10.1 | Identify if any properties have special funding associated with them | FDM 21-25-5, Factor Sheet B8 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 32 | [93 empty] | 4 | 6 | 8 |  |  |  | 8 | 12 | 16 | [192 empty] | 4 | 6 | 8
2.4.4.34 | 766.10.2 | Identify replacement property, if required; prepare Section 6(f) conversion request | FDM 21-25-5, Factor Sheet B8 guidance | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | property | 70 | 110 | 190 | [93 empty] | 10 | 20 | 40 |  |  |  | 40 | 50 | 70 | [126 empty] | 10 | 20 | 40 | [63 empty] | 10 | 20 | 40
2.4.4.35 | 766.11 | Specialty - Storm water management
2.4.4.36 | 766.12 | Specialty - Biological services
2.4.5 | 769 | Environmental Documentation and Agency Coordination
2.4.5.1 | 769 | Environmental Documentation and Agency Coordination - Scoping task
2.4.5.2 | 769.1 | Initial Agency and Tribal Coordination
2.4.5.3 | 769.1.1 | WDNR - General Coordination & Assessment | FDM 5-10-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter | 10 | 16 | 24 | [81 empty] | 16: 8; 24: 12; 32: 18 | [6 empty] | 2 | 4 | 4 | [51 empty] | 0 | 0 | 2
2.4.5.4 | 769.1.2 | USFWS | FDM 5-5-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter | 3 | 5 | 8 | [81 empty] | 1 | 2 | 3 | 1 | 2 | 3 | [6 empty] | 1 | 1 | 2
2.4.5.5 | 769.1.3 | Bureau of Indian Affairs - Native American Tribes | FDM 5-15-10 and Environmental Webpage | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter batch | 16 | 16 | 24 | [81 empty] | 6 | 6 | 10 | 6 | 6 | 10 | [6 empty] | 3 | 3 | 3 | [51 empty] | 1 | 1 | 1
2.4.5.6 | 769.1.4 | BOA | FDM 5-10-25 | [14 empty] | X | X | X |  | X |  |  | letter | 10 | 24 | 24 | [81 empty] | 4 | 9 | 9 | 4 | 9 | 9 | [6 empty] | 2 | 4 | 4 | [51 empty] | 0 | 2 | 2
2.4.5.7 | 769.1.5 | FAA |  |  |  |  | X | X | X | X |  | X |  |  | X |  |  | X | X | X |  | X |  |  | letter
2.4.5.8 | 769.1.6 | County Drainage Board | FDM 5-15-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter | 2 | 8 | 8 | [93 empty] | 2 | 8 | 8
2.4.5.9 | 769.1.7 | USACE | FDM 5-5-20 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter | 8 | 12 | 16 | [81 empty] | 3 | 5 | 5 | 3 | 5 | 5 | [6 empty] | 2 | 2 | 4 | [51 empty] | 0 | 0 | 2
2.4.5.10 | 769.1.8 | US EPA | 2015 Red Book | [14 empty] | X | X | X |  |  |  |  | letter | 16 | 16 | 16 | [81 empty] | 1: 8; 2: 8; 3: 8 | [6 empty] | 6 | 6 | 6 | [51 empty] | 2 | 2 | 2
2.4.5.11 | 769.1.9 | Local Agency Coordination | FDM 3-10-1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | per letter per agency | 6 | 8 | 10 | [81 empty] | 1: 4; 2: 6; 3: 8 | [6 empty] | 2 | 2 | 2
2.4.5.12 | 769.1.10 | Add'l Coord. ( NPS, NRCS, USGS) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | letter | 8 | 12 | 16 | [81 empty] | 1: 6; 2: 10; 3: 10 | [6 empty] | 2 | 2 | 4 | [51 empty] | 0 | 0 | 2
2.4.5.13 | 769.2 | Determine document type | FDM 21-5 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | 8 | 8 | 8 | [93 empty] | 6 | 6 | 6 | [51 empty] | 2 | 2 | 2
2.4.5.14 | 769.3 | Prepare draft project initiation letter, submit to REC | FDM 21-10-1 23 USC 139(e) | [12 empty] | X | X |  | X | X | X |  |  |  | letter | 10 | 10 | 10 | [81 empty] | 1: 5; 2: 5; 3: 5 | [6 empty] | 4 | 4 | 4 | [51 empty] | 1 | 1 | 1
2.4.5.15 | 769.4 | Categorical Exclusion Checklist |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | X | X | X | each | 54 | 54 | 54 | [81 empty] | 18 | 18 | 18 | 18 | 18 | 18 | [6 empty] | 14 | 14 | 14 | [51 empty] | 4 | 4 | 4
2.4.5.16 | 769.5 | Programmatic Categorical Exclusion |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | X | X | X | X | each | 60 | 60 | 60 | [81 empty] | 20 | 20 | 20 | 20 | 20 | 20 | [6 empty] | 16 | 16 | 16 | [51 empty] | 4 | 4 | 4
2.4.5.17 | 769.6 | Environmental Report
2.4.5.18 | 769.6.1 | Environmental Report Basic Sheets | [13 empty] | X | X | X | X | X |  | X | X | X | LS | 70 | 100 | 130 | [81 empty] | 25 | 40 | 50 | 25 | 40 | 50 | [6 empty] | 15 | 20 | 25 | [51 empty] | 5 | 5 | 10
2.4.5.19 | 769.6.2 | Environmental Report Factor Sheets | [13 empty] | X | X | X | X | X |  | X | X | X | each | 8 | 16 | 20 | [81 empty] | 1: 5; 2: 10; 3: 14 | [6 empty] | 2 | 5 | 5 | [51 empty] | 1 | 1 | 1
2.4.5.20 | 769.6.3 | Environmental Report Appendices | [13 empty] | x | x | X | X | X |  | X | X | X | LS | 12 | 18 | 24 | [81 empty] | 1: 10; 2: 16; 3: 20 | [6 empty] | 2 | 2 | 4
2.4.5.21 | 769.7 | Environmental Assessment
2.4.5.22 | 769.7.1 | Environmental Assessment Basic Sheets | [15 empty] | X | X | X |  |  |  |  | LS | 95 | 135 | 180 | [81 empty] | 30 | 50 | 75 | 35 | 50 | 75 | [6 empty] | 20 | 25 | 30 | [51 empty] | 10 | 10 | 10
2.4.5.23 | 769.7.2 | Environmental Assessment Factor Sheets |  |  |  |  | X | X | X | X |  |  |  |  | X |  |  | X | X | X |  |  |  |  | factor sheet | 8 | 16 | 20 | [81 empty] | 3 | 5 | 7 | 2 | 5 | 7 | [6 empty] | 2 | 5 | 5 | [51 empty] | 1 | 1 | 1
2.4.5.24 | 769.7.3 | Environmental Assessment Appendices | [15 empty] | X | X | X |  |  |  |  | LS | 12 | 18 | 24 | [81 empty] | 5 | 8 | 10 | 5 | 8 | 10 | [6 empty] | 2 | 2 | 4
2.4.5.25 | 769.7.4 | Environmental Assessment NOA, Dist, and Comment Period | [15 empty] | X | X | X |  |  |  |  | each | 32 | 46 | 58 | [81 empty] | 10 | 15 | 20 | 10 | 15 | 20 | [6 empty] | 10 | 12 | 14 | [51 empty] | 2 | 4 | 4
2.4.5.26 | 769.7.5 | Environmental Assessment Public Hearing | [15 empty] | X | X | X |  |  |  |  | each | 120 | 180 | 270 | [81 empty] | 35 | 60 | 100 | 35 | 60 | 100 | [6 empty] | 30 | 40 | 50 | [51 empty] | 20 | 20 | 20
2.4.5.27 | 769.7.6 | Environmental Assessment Addendum A | [15 empty] | X | X | X |  |  |  |  | each | 16 | 28 | 36 | [81 empty] | 10: 6; 15: 12; 20: 18 | [6 empty] | 8 | 14 | 14 | [51 empty] | 2 | 2 | 4
2.4.5.28 | 769.7.7 | FONSI | [15 empty] | X | X | X |  |  |  |  | each | 8 | 8 | 8 | [81 empty] | 10: 2; 15: 2; 20: 2 | [6 empty] | 4 | 4 | 4 | [51 empty] | 2 | 2 | 2
2.4.5.29 | 769.7.8 | Agency Meeting | [15 empty] | X | X | X |  |  |  |  | each | 45 | 65 | 100 | [81 empty] | 10 | 15 | 20 | 15 | 25 | 35 | [6 empty] | 15 | 20 | 35 | [51 empty] | 5 | 5 | 10
2.4.5.30 | 769.8 | Environmental Impact Statement
2.4.5.31 | 769.8.1 | Prepare draft notice of intent to prepare an EIS | [15 empty] | X | X | [5 empty] | each | 10 | 10 | 10 | [93 empty] | 6 | 6 | 6 | [51 empty] | 4 | 4 | 4
2.4.5.32 | 769.8.2 | Identify lead, participating, and cooperating agencies | FDM 21-10-5 | [14 empty] | X | X | [5 empty] | each | 12 | 12 | 18 | [93 empty] | 8 | 8 | 14 | [51 empty] | 4 | 4 | 4
2.4.5.33 | 769.8.3 | Prepare Draft Coordination plan | * none of these documents can be finalized without input. FDM 21-10-13 | [14 empty] | X | X | [5 empty] | each | 40 | 80 | 110 | [81 empty] | 10: 30; 15: 60; 20: 90 | [6 empty] | 8 | 16 | 16 | [51 empty] | 2 | 4 | 4
2.4.5.34 | 769.8.4 | Update Coordination plan | * none of these documents can be finalized without input. FDM 21-10-13 | [14 empty] | X | X | [5 empty] | each | 24 | 32 | 40 | [81 empty] | 12 | 18 | 24 | 6 | 8 | 10 | [6 empty] | 6 | 6 | 6
2.4.5.35 | 769.8.5 | Prepare Draft Impact Assessment Methodology(IAM) | [15 empty] | X | X | [5 empty] | each | 80 | 120 | 160 | [81 empty] | 10: 60; 15: 80; 20: 110 | [6 empty] | 15 | 30 | 40 | [51 empty] | 5 | 10 | 10
2.4.5.36 | 769.8.6 | Agency Meeting | FDM 21-10-15 | [14 empty] | X | X | [5 empty] | each | 65 | 100 | 140 | [81 empty] | 10 | 20 | 10 | 30 | 40 | 50 | [6 empty] | 20 | 30 | 40 | [51 empty] | 5 | 10 | 10
2.4.5.37 | 769.8.7 | Prepare DEIS
2.4.5.38 | 769.8.7.1 | Purpose and Need | [15 empty] | X | X | [5 empty] | each | 100 | 160 | 220 | [81 empty] | 30 | 50 | 70 | 40 | 60 | 70 | [6 empty] | 20 | 30 | 50 | [51 empty] | 10 | 20 | 30
2.4.5.39 | 769.8.7.2 | Alternatives | [15 empty] | X | X | [5 empty] | each | 240 | 360 | 480 | [81 empty] | 80 | 120 | 160 | 90 | 130 | 170 | [6 empty] | 50 | 80 | 110 | [51 empty] | 20 | 30 | 40
2.4.5.40 | 769.8.7.3 | Affected Environment | [15 empty] | X | X | [5 empty] | each | 200 | 300 | 400 | [81 empty] | 100 | 160 | 220 | 60 | 80 | 120 | [6 empty] | 20 | 40 | 40 | [51 empty] | 20 | 20 | 20
2.4.5.41 | 769.8.7.4 | Environmental Consequences | [15 empty] | X | X | [5 empty] | each | 500 | 750 | 1000 | [81 empty] | 200 | 300 | 335 | 160 | 240 | 335 | [6 empty] | 100 | 150 | 250 | [51 empty] | 40 | 60 | 80
2.4.5.42 | 769.8.7.5 | Cover Sheet, TOC, List of Preparers, Dist List, References, Acronyms, Index, Exhibit List | [15 empty] | X | X | [5 empty] | each | 150 | 175 | 200 | [81 empty] | 80 | 80 | 80 | 50 | 65 | 80 | [6 empty] | 10 | 20 | 30 | [51 empty] | 10 | 10 | 10
2.4.5.43 | 769.8.7.6 | DEIS Appendices | [15 empty] | X | X | [5 empty] | each | 60 | 90 | 120 | [81 empty] | 10: 30; 15: 45; 20: 55 | [6 empty] | 20 | 35 | 45 | [51 empty] | 10 | 10 | 10
2.4.5.44 | 769.8.7.7 | Executive Summary | [15 empty] | X | X | [5 empty] | LS | 100 | 100 | 100 | [81 empty] | 40 | 40 | 40 | 40 | 40 | 40 | [6 empty] | 15 | 15 | 15 | [51 empty] | 5 | 5 | 5
2.4.5.45 | 769.8.7.8 | Comment Review Meetings During DEIS Prep | [15 empty] | X | X | [5 empty] | LS | 40 | 75 | 110 | [81 empty] | 15 | 20 | 35 | 10 | 25 | 35 | [6 empty] | 10 | 20 | 25 | [51 empty] | 5 | 10 | 15
2.4.5.46 | 769.8.8 | DEIS Release and Comment Period
2.4.5.47 | 769.8.8.1 | Prepare and publish Notice of Availability |  |  |  |  | X |  | X | [5 empty] | X |  |  | X | X | [5 empty] | each | 28 | 28 | 28 | [81 empty] | 10: 20; 15: 20; 20: 20 | [6 empty] | 6 | 6 | 6 | [51 empty] | 2 | 2 | 2
2.4.5.48 | 769.8.8.2 | Print and Distribute DEIS to Agencies and Individuals | [15 empty] | X | X | [5 empty] | each | 100 | 140 | 180 | [81 empty] | 40 | 50 | 65 | 40 | 50 | 65 | [6 empty] | 18 | 38 | 48 | [51 empty] | 2 | 2 | 2
2.4.5.49 | 769.8.8.3 | Prepare Web-ready Document | [15 empty] | X | X | [5 empty] | each | 24 | 32 | 40 | [81 empty] | 10 | 14 | 17 | 10 | 14 | 17 | [6 empty] | 3 | 3 | 5 | [51 empty] | 1 | 1 | 1
2.4.5.50 | 769.8.8.4 | Conduct Hearing | [15 empty] | X | X | [5 empty] | each | 140 | 260 | 360 | [81 empty] | 40 | 70 | 85 | 40 | 70 | 85 | [6 empty] | 50 | 60 | 70 | [51 empty] | 5 | 5 | 5
2.4.5.51 | 769.8.8.5 | Collect and Categorize Comments | [15 empty] | X | X | [5 empty] | each | 16 | 32 | 48 | [81 empty] | 10 | 20 | 30 | 3 | 8 | 12 | [6 empty] | 3 | 4 | 6
2.4.5.52 | 769.8.8.6 | Prepare Hearing Certification for FHWA | [15 empty] | X | X | [5 empty] | each | 24 | 36 | 48 | [81 empty] | 10: 17; 15: 24; 20: 30 | [6 empty] | 5 | 10 | 16 | [51 empty] | 2 | 2 | 2
2.4.5.53 | 769.8.9 | Prepare FEIS and ROD
2.4.5.54 | 769.8.9.1 | Respond to comments and make EIS revisions | FDM 21-15-1.2.5 | [14 empty] | X | X | [5 empty] | each | 100 | 400 | 700 | [81 empty] | 30 | 200 | 300 | 20 | 110 | 260 | [6 empty] | 40 | 60 | 100 | [51 empty] | 10 | 30 | 40
2.4.5.55 | 769.8.9.2 | Document environmental commitments | http://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/environment/formsandtools.aspx | [14 empty] | X | X | [5 empty] | each | 40 | 60 | 80 | [81 empty] | 10: 20; 15: 40; 20: 60 | [6 empty] | 18 | 18 | 18 | [51 empty] | 2 | 2 | 2
2.4.5.56 | 769.8.9.3 | Prepare Record of Decision (ROD) | [15 empty] | X | X | [5 empty] | each | 100 | 160 | 200 | [81 empty] | 30 | 50 | 60 | 30 | 50 | 60 | [6 empty] | 36 | 54 | 72 | [51 empty] | 4 | 6 | 8
2.4.5.57 | 769.8.10 | FEIS Release and Comment Period
2.4.5.58 | 769.8.10.1 | Prepare and publish Notice of Availability | [15 empty] | X | X | [5 empty] | each | 24 | 24 | 24 | [81 empty] | 10: 16; 15: 16; 20: 16 | [6 empty] | 6 | 6 | 6 | [51 empty] | 2 | 2 | 2
2.4.5.59 | 769.8.10.2 | Print and Distribute FEIS to Agencies and Individuals | [15 empty] | X | X | [5 empty] | each | 80 | 120 | 180 | [81 empty] | 10: 60; 15: 95; 20: 150 | [6 empty] | 20 | 25 | 30
2.4.5.60 | 769.8.10.3 | Prepare Web-ready Document | [15 empty] | X | X | [5 empty] | each | 24 | 32 | 40 | [81 empty] | 10: 20; 15: 28; 20: 36 | [6 empty] | 4 | 4 | 4
2.4.5.61 | 769.8.10.4 | Collect and Categorize Comments | [15 empty] | X | X | [5 empty] | each | NA | NA | NA
2.4.5.62 | 769.8.10.5 | Prepare Statute of Limitations Notice | [15 empty] | X | X | [5 empty] | each | 8 | 8 | 8 | [93 empty] | 7 | 7 | 7 | [51 empty] | 1 | 1 | 1
2.4.5.63 | 769.9 | Prepare administrative record |  |  |  |  | X |  | X | [5 empty] | X |  |  | X | X | [5 empty] | 100 records | 12 | 20 | 36 | [81 empty] | 10: 11; 15: 19; 20: 34 | [6 empty] | 1 | 1 | 2
2.4.5.64 | 769.1 | Carry out environmental commitments | [15 empty] | X | X
2.4.5.65 | 769.11 | Prepare DRR or other Amended Environmental Documentation | [15 empty] | X | X | [5 empty] | each | 60 | 120 | 200 | [81 empty] | 10: 40; 15: 85; 20: 150 | [6 empty] | 16 | 30 | 44 | [51 empty] | 4 | 5 | 6
2.4.5.66 | 769.12 | Revise environmental document | [15 empty] | X | X | X
2.5 |  | Structures
2.5.1 | 647 | Develop Structure Survey Report
2.5.1.1 | 647 | Develop Structure Survey Report - Scoping task
2.5.1.2 | 647.1 | Conduct structures site review |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | structure | 4 | 6 | 8 | [234 empty] | .5 | .5 | 1 | 3 | 5 | 6 | [6 empty] | .5 | .5 | 1
2.5.1.3 | 647.2 | Prepare structure survey report |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | structure | 16 | 24 | 40 | [234 empty] | 1.5 | 2.5 | 4 | 13 | 19 | 32 | [6 empty] | 1.5 | 2.5 | 4
2.5.2 | 651 | Structure Fabrication - Review and Oversight (WisDOT only)
2.5.2.1 | 651 | Structure Fabrication - Review and Oversight (WisDOT only) - Scoping task
2.5.2.2 | 651.1 | Specialty - Shop inspection structural steel
2.5.3 | 653 | Structure - Liaison Activities (WisDOT only)
2.5.3.1 | 653 | Structure - Liaison Activities (WisDOT only) - Scoping task
2.5.4 | 656 | Design Structure
2.5.4.1 | 656 | Design Structure - Scoping task
2.5.4.2 | 656.1 | Preliminary design
2.5.4.3 | 656.1.1 | Box Culvert (cast in place concrete)
2.5.4.4 | 656.1.1.1 | Single Cell
2.5.4.5 | 656.1.1.1.1 | BOS | [22 empty] | structure | 14 | 19 | 24 | [234 empty] | 2.8 | 3.8 | 4.8 | 9.8 | 13.3 | 16.8 | [6 empty] | 1.4 | 1.9 | 2.4
2.5.4.6 | 656.1.1.1.2 | Consultant | [22 empty] | structure | 60 | 65 | 70 | [234 empty] | 12 | 13 | 14 | 42 | 45.5 | 49 | [6 empty] | 6 | 6.5 | 7
2.5.4.7 | 656.1.1.2 | Two Cell
2.5.4.8 | 656.1.1.2.1 | BOS | [22 empty] | structure | 18 | 23 | 26 | [234 empty] | 3.6 | 4.6 | 5.2 | 12.6 | 16.1 | 18.2 | [6 empty] | 1.8 | 2.3 | 2.6
2.5.4.9 | 656.1.1.2.2 | Consultant | [22 empty] | structure | 64 | 69 | 74 | [234 empty] | 12.8 | 13.8 | 14.8 | 44.8 | 48.3 | 51.8 | [6 empty] | 6.4 | 6.9 | 7.4
2.5.4.10 | 656.1.2 | Prestressed concrete slabs and boxes | [12 empty] | X | [9 empty] | structure | * | * | *
2.5.4.11 | 656.1.3 | Prestressed concrete girders
2.5.4.12 | 656.1.3.1 | Single span | [22 empty] | structure | 40 | 60 | 80 | [234 empty] | 8 | 12 | 16 | 28 | 42 | 56 | [6 empty] | 4 | 6 | 8
2.5.4.13 | 656.1.3.2 | Additional Span(s) | [22 empty] | span | 8 | 24 | 40 | [234 empty] | 1.6 | 4.8 | 8 | 5.6 | 16.8 | 28 | [6 empty] | 0.8 | 2.4 | 4
2.5.4.14 | 656.1.4 | Concrete slab
2.5.4.15 | 656.1.4.1 | Single span | [22 empty] | structure | 40 | 60 | 80 | [234 empty] | 8 | 12 | 16 | 28 | 42 | 56 | [6 empty] | 4 | 6 | 8
2.5.4.16 | 656.1.4.2 | Additional Span(s) | [22 empty] | span | 8 | 16 | 24 | [234 empty] | 1.6 | 3.2 | 4.8 | 5.6 | 11.2 | 16.8 | [6 empty] | 0.8 | 1.6 | 2.4
2.5.4.17 | 656.1.5 | Steel plate girders
2.5.4.18 | 656.1.5.1 | Single span | [22 empty] | structure | 64 | 84 | 104 | [234 empty] | 12.8 | 16.8 | 20.8 | 44.8 | 58.8 | 72.8 | [6 empty] | 6.4 | 8.4 | 10.4
2.5.4.19 | 656.1.5.2 | Additional Span(s) | [22 empty] | span | 8 | 28 | 48 | [234 empty] | 1.6 | 5.6 | 9.6 | 5.6 | 19.6 | 33.6 | [6 empty] | 0.8 | 2.8 | 4.8
2.5.4.20 | 656.1.6 | Retaining wall
2.5.4.21 | 656.1.6.1 | Cast in place concrete | [22 empty] | structure | 48 | 80 | 100 | [234 empty] | 9.6 | 16 | 20 | 33.6 | 56 | 70 | [6 empty] | 4.8 | 8 | 10
2.5.4.22 | 656.1.6.2 | Modular block (no MSE) | [22 empty] | structure | 40 | 52 | 64 | [234 empty] | 8 | 10.4 | 12.8 | 28 | 36.4 | 44.8 | [6 empty] | 4 | 5.2 | 6.4
2.5.4.23 | 656.1.6.3 | MSE | [22 empty] | structure | 40 | 64 | 80 | [234 empty] | 8 | 12.8 | 16 | 28 | 44.8 | 56 | [6 empty] | 4 | 6.4 | 8
2.5.4.24 | 656.1.6.4 | Wire face with tip-up precast panel | [22 empty] | structure | * | * | *
2.5.4.25 | 656.1.6.5 | Post and panel, Soldier pile | [22 empty] | structure | 48 | 72 | 88 | [234 empty] | 9.6 | 14.4 | 17.6 | 33.6 | 50.4 | 61.6 | [6 empty] | 4.8 | 7.2 | 8.8
2.5.4.26 | 656.1.6.6 | Sheet pile | [12 empty] | X | [9 empty] | structure | * | * | *
2.5.4.27 | 656.1.7 | Sign bridge | [22 empty] | structure | * | * | *
2.5.4.28 | 656.1.8 | Noise wall | [22 empty] | structure | * | * | *
2.5.4.29 | 656.1.9 | Rigid frame | [22 empty] | sheet | * | * | *
2.5.4.30 | 656.1.10 | Rehabilitation
2.5.4.31 | 656.1.10.1 | Box culvert single cell extension
2.5.4.32 | 656.1.10.1.1 | BOS | [22 empty] | structure | 14 | 19 | 24 | [234 empty] | 2.8 | 3.8 | 4.8 | 9.8 | 13.3 | 16.8 | [6 empty] | 1.4 | 1.9 | 2.4
2.5.4.33 | 656.1.10.1.2 | Consultant | [22 empty] | structure | 60 | 65 | 70 | [234 empty] | 12 | 13 | 14 | 42 | 45.5 | 49 | [6 empty] | 6 | 6.5 | 7
2.5.4.34 | 656.1.10.2 | Box culvert multi cell extension
2.5.4.35 | 656.1.10.2.1 | BOS | [22 empty] | structure | 18 | 23 | 26 | [234 empty] | 3.6 | 4.6 | 5.2 | 12.6 | 16.1 | 18.2 | [6 empty] | 1.8 | 2.3 | 2.6
2.5.4.36 | 656.1.10.2.2 | Consultant | [22 empty] | structure | 64 | 69 | 74 | [234 empty] | 12.8 | 13.8 | 14.8 | 44.8 | 48.3 | 51.8 | [6 empty] | 6.4 | 6.9 | 7.4
2.5.4.37 | 656.1.10.3 | Deck overlay | [22 empty] | structure | 16 | 24 | 32 | [234 empty] | 3.2 | 4.8 | 6.4 | 11.2 | 16.8 | 22.4 | [6 empty] | 1.6 | 2.4 | 3.2
2.5.4.38 | 656.1.10.4 | Deck replacement (w/o widening) | [22 empty] | structure | * | * | *
2.5.4.39 | 656.1.10.5 | Widening (w/deck replacement) | [22 empty] | structure | * | * | *
2.5.4.40 | 656.1.10.6 | Widening (w/ or w/o deck replacement) | [22 empty] | structure | * | * | *
2.5.4.41 | 656.1.10.7 | Superstructure replacement | [22 empty] | structure | * | * | *
2.5.4.42 | 656.1.11 | Structure alternative development | [22 empty] | structure alternative | 20 | 26 | 32 | [234 empty] | 4 | 5.2 | 6.4 | 14 | 18.2 | 22.4 | [6 empty] | 2 | 2.6 | 3.2
2.5.4.43 | 656.2 | Final design
2.5.4.44 | 656.2.1 | Box Culvert (cast in place concrete)
2.5.4.45 | 656.2.1.1 | Single Cell
2.5.4.46 | 656.2.1.1.1 | BOS | [22 empty] | structure | 42 | 57 | 72 | [234 empty] | 12.6 | 17.1 | 21.6 | 25.2 | 34.2 | 43.2 | [6 empty] | 4.2 | 5.7 | 7.2
2.5.4.47 | 656.2.1.1.2 | Consultant | [22 empty] | structure | 80 | 85 | 90 | [234 empty] | 24 | 25.5 | 27 | 48 | 51 | 54 | [6 empty] | 8 | 8.5 | 9
2.5.4.48 | 656.2.1.2 | Two Cell
2.5.4.49 | 656.2.1.2.1 | BOS | [22 empty] | structure | 56 | 68 | 80 | [234 empty] | 16.8 | 20.4 | 24 | 33.6 | 40.8 | 48 | [6 empty] | 5.6 | 6.8 | 8
2.5.4.50 | 656.2.1.2.2 | Consultant | [12 empty] | X | [9 empty] | structure | 88 | 93 | 98 | [234 empty] | 26.4 | 27.9 | 29.4 | 52.8 | 55.8 | 58.8 | [6 empty] | 8.8 | 9.3 | 9.8
2.5.4.51 | 656.2.2 | Prestressed concrete slabs and boxes | [22 empty] | structure | * | * | *
2.5.4.52 | 656.2.3 | Prestressed concrete girders
2.5.4.53 | 656.2.3.1 | Single span | [22 empty] | structure | 160 | 200 | 240 | [234 empty] | 48 | 60 | 72 | 96 | 120 | 144 | [6 empty] | 16 | 20 | 24
2.5.4.54 | 656.2.3.2 | Additional Span(s) | [22 empty] | span | 40 | 80 | 120 | [234 empty] | 12 | 24 | 36 | 24 | 48 | 72 | [6 empty] | 4 | 8 | 12
2.5.4.55 | 656.2.4 | Concrete slab
2.5.4.56 | 656.2.4.1 | Single span | [22 empty] | structure | 120 | 160 | 200 | [234 empty] | 36 | 48 | 60 | 72 | 96 | 120 | [6 empty] | 12 | 16 | 20
2.5.4.57 | 656.2.4.2 | Additional Span(s) | [22 empty] | span | 32 | 64 | 96 | [234 empty] | 9.6 | 19.2 | 28.8 | 19.2 | 38.4 | 57.6 | [6 empty] | 3.2 | 6.4 | 9.6
2.5.4.58 | 656.2.5 | Steel plate girders
2.5.4.59 | 656.2.5.1 | Single span | [22 empty] | structure | 224 | 272 | 320 | [234 empty] | 67.2 | 81.6 | 96 | 134.4 | 163.2 | 192 | [6 empty] | 22.4 | 27.2 | 32
2.5.4.60 | 656.2.5.2 | Additional Span(s) | [22 empty] | span | 48 | 120 | 160 | [234 empty] | 14.4 | 36 | 48 | 28.8 | 72 | 96 | [6 empty] | 4.8 | 12 | 16
2.5.4.61 | 656.2.6 | Retaining wall
2.5.4.62 | 656.2.6.1 | Cast in place concrete | [22 empty] | structure | 40 | 60 | 80 | [234 empty] | 12 | 18 | 24 | 24 | 36 | 48 | [6 empty] | 4 | 6 | 8
2.5.4.63 | 656.2.6.2 | Modular block (no MSE) | [22 empty] | structure | 16 | 20 | 24 | [234 empty] | 4.8 | 6 | 7.2 | 9.6 | 12 | 14.4 | [6 empty] | 1.6 | 2 | 2.4
2.5.4.64 | 656.2.6.3 | MSE | [22 empty] | structure | 16 | 24 | 32 | [234 empty] | 4.8 | 7.2 | 9.6 | 9.6 | 14.4 | 19.2 | [6 empty] | 1.6 | 2.4 | 3.2
2.5.4.65 | 656.2.6.4 | Wire face with tip-up precast panel | [22 empty] | structure | * | * | *
2.5.4.66 | 656.2.6.5 | Post and panel, Soldier pile | [12 empty] | X | [9 empty] | structure | 20 | 28 | 36 | [234 empty] | 6 | 8.4 | 10.8 | 12 | 16.8 | 21.6 | [6 empty] | 2 | 2.8 | 3.6
2.5.4.67 | 656.2.6.6 | Sheet pile | [22 empty] | structure | * | * | *
2.5.4.68 | 656.2.7 | Sign bridge | [22 empty] | structure | * | * | *
2.5.4.69 | 656.2.8 | Noise wall | [22 empty] | structure | * | * | *
2.5.4.70 | 656.2.9 | Rigid frame | [22 empty] | sheet | * | * | *
2.5.4.71 | 656.2.10 | Rehabilitation
2.5.4.72 | 656.2.10.1 | Box culvert single cell extension
2.5.4.73 | 656.2.10.1.1 | BOS | [22 empty] | structure | 42 | 57 | 72 | [234 empty] | 12.6 | 17.1 | 21.6 | 25.2 | 34.2 | 43.2 | [6 empty] | 4.2 | 5.7 | 7.2
2.5.4.74 | 656.2.10.1.2 | Consultant | [22 empty] | structure | 80 | 85 | 90 | [234 empty] | 24 | 25.5 | 27 | 48 | 51 | 54 | [6 empty] | 8 | 8.5 | 9
2.5.4.75 | 656.2.10.2 | Box culvert multi cell extension
2.5.4.76 | 565.2.10.2.1 | BOS | [22 empty] | structure | 56 | 68 | 80 | [234 empty] | 16.8 | 20.4 | 24 | 33.6 | 40.8 | 48 | [6 empty] | 5.6 | 6.8 | 8
2.5.4.77 | 565.2.10.2.2 | Consultant | [22 empty] | structure | 88 | 93 | 98 | [234 empty] | 26.4 | 27.9 | 29.4 | 52.8 | 55.8 | 58.8 | [6 empty] | 8.8 | 9.3 | 9.8
2.5.4.78 | 656.2.10.3 | Deck overlay | [22 empty] | structure | 48 | 64 | 96 | [234 empty] | 14.4 | 19.2 | 28.8 | 28.8 | 38.4 | 57.6 | [6 empty] | 4.8 | 6.4 | 9.6
2.5.4.79 | 656.2.10.4 | Deck replacement (w/o widening) | [22 empty] | structure | * | * | *
2.5.4.80 | 656.2.10.5 | Widening (w/deck replacement) | [22 empty] | structure | * | * | *
2.5.4.81 | 656.2.10.6 | Widening (w/ or w/o deck replacement) | [22 empty] | structure | * | * | *
2.5.4.82 | 656.2.10.7 | Superstructure replacement | [22 empty] | structure | * | * | *
2.5.4.83 | 656.2.11 | ESubmit | [22 empty] | structure | 4 | 4 | 4 | [234 empty] | 1.5 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5
2.5.5 | 657 | Draft Structure Plan
2.5.5.1 | 657 | Draft Structure Plan - Scoping task
2.5.5.2 | 657.1 | Box Culvert (cast in place concrete) | [22 empty] | sheet | 4 | 6 | 8
2.5.5.3 | 657.2 | Prestressed concrete slabs and boxes | [22 empty] | sheet | * | * | *
2.5.5.4 | 657.3 | Prestressed concrete girders | [22 empty] | sheet | 9 | 12 | 18
2.5.5.5 | 657.4 | Concrete slab | [22 empty] | sheet | 10 | 13 | 19
2.5.5.6 | 657.5 | Steel plate girders | [12 empty] | X | [9 empty] | sheet | 10 | 15 | 21
2.5.5.7 | 657.6 | Retaining wall
2.5.5.8 | 657.6.1 | Cast in place concrete | [22 empty] | sheet | 10 | 11 | 12
2.5.5.9 | 657.6.2 | Modular block (no MSE) | [22 empty] | sheet | 8 | 8 | 8
2.5.5.10 | 657.6.3 | MSE | [22 empty] | sheet | 8 | 8 | 8
2.5.5.11 | 657.6.4 | Wire face with tip-up precast panel | [22 empty] | sheet | 8 | 8 | 8
2.5.5.12 | 657.6.5 | Post and panel, Soldier pile | [22 empty] | sheet | 8 | 8 | 8
2.5.5.13 | 657.6.6 | Sheet pile | [22 empty] | sheet | 8 | 8 | 8
2.5.5.14 | 657.7 | Sign bridge | [22 empty] | sheet | * | * | *
2.5.5.15 | 657.8 | Noise wall | [22 empty] | sheet | * | * | *
2.5.5.16 | 658.9 | Rigid frame | [22 empty] | sheet | * | * | *
2.5.5.17 | 657.1 | Rehabilitation
2.5.5.18 | 657.10.1 | Box culvert extension | [22 empty] | sheet | 4 | 6 | 8
2.5.5.19 | 657.10.2 | Deck overlay | [22 empty] | structure | 20 | 60 | 100
2.5.5.20 | 657.10.3 | Deck replacement (w/o widening) | [22 empty] | sheet | * | * | *
2.5.5.21 | 657.10.4 | Widening (w/deck replacement) | [22 empty] | sheet | * | * | *
2.5.5.22 | 657.10.5 | Widening (w/ or w/o deck replacement) | [12 empty] | X | [9 empty] | sheet | * | * | *
2.5.5.23 | 657.10.6 | Superstructure replacement | [22 empty] | sheet | * | * | *
2.5.6 | 658 | Design Structure Hydrology and Hydraulics
2.5.6.1 | 658 | Design Structure Hydrology and Hydraulics - Scoping task
2.5.6.2 | 658.1 | Hydrology Computations & Documentation | [22 empty] | structure | 8 | 12 | 20
2.5.6.3 | 658.2 | Hydraulics Computations, Modeling & Report | [22 empty] | structure | 28 | 36 | 60
2.5.6.4 | 658.3 | Scour Computations & Evaluation | [22 empty] | structure | 2 | 4 | 8
2.5.6.5 | 658.4 | H&H for Temporary Structures | [22 empty] | structure | 6 | 6 | 6
2.5.7 | 659 | Review In-House Structure Plan (WisDOT only)
| 659 | Review In-House Structure Plan (WisDOT only) - Scoping task
2.5.8 | 779 | Review Consultant Structure Plan (WisDOT only)
2.5.8.1 | 779 | Review Consultant Structure Plan (WisDOT only) - Scoping task
2.5.8.2 | 779.1 | Specialty - Complex structural analysis
2.6 |  | Traffic Operations
2.6.1 | 313 | Analyze Traffic Data/ Forecast
2.6.1.1 | 313 | Analyze Traffic Data/ Forecast - Scoping task
2.6.1.2 | 313.1 | Review local land use and transportation plans | [13 empty] | X | X | X | X | X |  |  |  |  | plan | 1 | 4 | 8 | [189 empty] | 1 | 4 | 6 | 0 | 0 | 2
2.6.1.3 | 313.2 | Process crash data-analyze crash trends (per road segment) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | segment | 1 | 40 | 80 | [297 empty] | 1 | 30 | 60 | 0 | 10 | 20
2.6.1.4 | 313.3 | Process crash data-analyze crash trends (per intersections) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | intersection | 1 | 40 | 80 | [297 empty] | 1 | 30 | 60 | 0 | 10 | 20
2.6.1.5 | 313.4 | Certified traffic for preferred alternative | [22 empty] | forecast
2.6.1.6 | 313.5 | Transportation demand modeling ( Microscopic) | [13 empty] | X | X | X | X | [5 empty] | alternative | 4 | 40 | 160 | [297 empty] | 2 | 20 | 80 | 2 | 20 | 80
2.6.1.7 | 313.6 | Transportation demand modeling (Macroscopic) | [13 empty] | X | X | X | X | [5 empty] | alternative | 8 | 24 | 80 | [189 empty] | 4 | 12 | 40 | 4 | 12 | 40 | [102 empty] | 4 | 12 | 40 | 4 | 12 | 40
2.6.1.8 | 313.7 | Conduct road safety audit | [15 empty] | X | X | [5 empty] | project | 100 | 290 | 480 | [297 empty] | 40 | 135 | 230 | 40 | 135 | 230 | [6 empty] | 20 | 20 | 20
2.6.1.9 | 313.8 | Traffic projection and traffic forecast | [13 empty] | X | X | X | X | X |  |  |  |  | project | 1 | 6 | 12 | [189 empty] | 1 | 4 | 8 | 0 | 2 | 4
2.6.1.10 | 313.9 | Determine time of day peak characteristics (peak hour factors) |  |  |  | X | X |  | X | [5 empty] | X | X | X | X | X | [5 empty] | intersection | 2 | 2 | 2 | [189 empty] | 2 | 2 | 2 | [105 empty] | 2 | 2 | 2
2.6.1.11 | 313.1 | Determine directional composition of traffic flow (directional distribution) | [13 empty] | X | X | X | X | [5 empty] | alternative | 2 | 2 | 2 | [189 empty] | 2 | 2 | 2 |  |  | 4 | [102 empty] | 2 | 2 | 2
2.6.1.12 | 313.11 | Develop and document Intersection Control Evaluation (ICE) report | [13 empty] | X | X | X | X | X |  |  |  |  | intersection | 8 | 32 | 48 | [297 empty] | 6 | 20 | 32 | 2 | 8 | 8 | [6 empty] | 0 | 4 | 8
2.6.2 | 347 | Collect Traffic Field Data
2.6.2.1 | 347 | Collect Traffic Field Data - Scoping task
2.6.2.2 | 347.1 | Complete directional counts on roadways and ramps (ADT Counts) | FDM 3-10-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | setup | 3 | 4 | 8 | [297 empty] | 3 | 4 | 4 | [27 empty] | 0 | 0 | 4
2.6.2.3 | 347.2 | Complete vehicle classification counts | FDM 3-10-10 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | setup | 4 | 6 | 12 | [297 empty] | 4 | 6 | 6 | [27 empty] | 0 | 0 | 6
2.6.2.4 | 347.3 | Complete speed data collection | TGM 13-5-1, Wisconsin Statewide Speed Management Guidelines | [14 empty] | X | X | [5 empty] | setup | 4 | 6 | 12 | [297 empty] | 4 | 6 | 6 | [27 empty] | 0 | 0 | 6
2.6.2.5 | 347.4 | Turning movement counts at intersections
2.6.2.6 | 347.4.1 | Automated turning movement counts at intersections | TSDM Chapter 2, Section 2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 3 | 4 | 8 | [297 empty] | 3 | 4 | 4 | [24 empty] | 3 | 4 | 4 | 0 | 0 | 4
2.6.2.7 | 347.4.2 | Manual turning movement counts at intersections | TSDM Chapter 2, Section 2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 2 | 3 | 4 | [297 empty] | 2 | 3 | 3 | [24 empty] | 2 | 3 | 3 | 0 | 0 | 2
2.6.2.8 | 347.5 | Control and continuous counts |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 6 | 12 | [297 empty] | 2 | 4 | 8 | 0 | 2 | 4
2.6.2.9 | 347.6 | Complete field signal timing data study |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | timing plan per intersection | 2 | 3 | 4 | [297 empty] | 2 | 3 | 4 | [27 empty] | 2 | 3 | 4
2.6.2.10 | 347.7 | Complete traffic gap study | [15 empty] | X | X | [5 empty] | location | 2 | 3 | 4 | [297 empty] | 2 | 3 | 4 | [27 empty] | 2 | 3 | 4
2.6.2.11 | 347.8 | Complete traffic delay study | [15 empty] | X | X | [5 empty] | approach | 2 |  | 4 | [297 empty] | 2 | 2 | 4 | [27 empty] | 2 | 2 | 4
2.6.2.12 | 347.9 | Collect queue data | [15 empty] | X | X | [5 empty] | approach | 2 |  | 3 | [297 empty] | 2 | 2 | 3 | [27 empty] | 2 | 2 | 3
2.6.2.13 | 347.1 | Collect lane utilization data |  |  |  |  | X |  | X | [5 empty] | X |  |  | X | X | [5 empty] | location | 2 |  | 3 | [297 empty] | 2 | 2 | 3 | [27 empty] | 2 | 2 | 3
2.6.2.14 | 347.11 | Collect occupancy data | [15 empty] | X | X | [5 empty] | location | 2 |  | 3 | [297 empty] | 2 | 2 | 3 | [27 empty] | 2 | 2 | 3
2.6.2.15 | 347.12 | Complete travel time study | [15 empty] | X | X | X | [5 empty] | * | * | *
2.6.2.16 | 347.13 | Complete origin-destination study | FDM 3-10-10 | [14 empty] | X | X | X | [5 empty] | * | * | *
2.6.3 | 785 | Design Traffic Signal and Details
2.6.3.1 | 785 | Design Traffic Signal and Details - Scoping task
2.6.3.2 | 785.1 | Prepare, submit, review signal warrant | TSDM - Chapter 2 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 2 | 4 | 10 | [297 empty] | 1 | 3 | 8 | 1 | 1 | 2
2.6.3.3 | 785.2 | Traffic analysis
2.6.3.4 | 785.2.1 | Analyze and determine signal phasing | TSDM Chapter 7 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 2 | 4 | 6 | [300 empty] | 1 | 3 | 4 | [6 empty] | 1 | 1 | 2
2.6.3.5 | 785.2.2 | Analyze and determine intersection timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 2 | 3 | 5 | [300 empty] | 3 | 4 | 6 | [6 empty] | 1 | 1 | 2
2.6.3.6 | 785.2.3 | Analyze and determine coordination timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | timing plan per intersection | 6 | 8 | 10 | [147 empty] | 2 | 2 | 2 | [159 empty] | 4 | 6 | 8
2.6.3.7 | 785.3 | Traffic signal plan details
2.6.3.8 | 785.3.1 | Develop signal equipment layout | TSDM - Chapter 3/MUTCD | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 8 | 10 | 16 | [300 empty] | 3 | 4 | 5 | [6 empty] | 1 | 1 | 4 | [15 empty] | 3 | 5 | 7
2.6.3.9 | 785.3.2 | Develop cable routing | TSDM - Chapter 9 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 4 | 5 | 8 | [300 empty] | 2 | 3 | 4 | [6 empty] | 1 | 1 | 2 | [15 empty] | 1 | 1 | 2
2.6.3.10 | 785.3.3 | Develop sequence of operations | TSDM - 7.1.5 & 7.1.6 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 4 | 6 | 10 | [300 empty] | 2 | 4 | 6 | [6 empty] | 1 | 1 | 2 | [15 empty] | 1 | 1 | 2
2.6.3.11 | 785.4 | Develop quantities and estimate | FDM 19.5.1 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 16 | 24 | 32 | [297 empty] | 10 | 8 | 4 | 4 | 8 | 16 | [6 empty] | 0 | 4 | 6 | [15 empty] | 2 | 4 | 6
2.6.3.12 | 785.5 | Develop PSE special provisions | FDM 19.15 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 6 | 9 | 16 | [297 empty] | 4 | 4 | 4 | 4 | 8 | 12 | [6 empty] | 1 | 2 | 4
2.6.3.13 | 785.6 | Determine existing signal inventory and complete signal removal plan |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | intersection | 5 | 6 | 10 | [297 empty] | 4 | 5 | 7 | 1 | 1 | 2 | [6 empty] | 0 | 0 | 1
2.6.3.14 | 785.7 | Complete traffic signal communication design |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | signal system | 12 | 24 | 48 | [147 empty] | 0 | 0 | 5 | [150 empty] | 8 | 15 | 25 | [6 empty] | 2 | 5 | 10 | [15 empty] | 2 | 4 | 8
2.6.3.15 | 785.8 | Develop railroad preemption plans |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [5 empty] | signal | 5 | 10 | 20 | [300 empty] | 4 | 8 | 15 | [6 empty] | 2 | 2 | 5
2.6.3.16 | 785.9 | Temporary signals
2.6.3.17 | 785.9.1 | Develop signal equipment layout | TSDM - Chapter 3/MUTCD | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | signal | 4 | 8 | 12 | [300 empty] | 2 | 4 | 8 | [6 empty] | 1 | 1 | 2 | [15 empty] | 4 | 6 | 8
2.6.3.18 | 785.9.2 | Develop sequence of operations | TSDM - 7.1.5 & 7.1.6 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | signal | 3 | 5 | 8 | [300 empty] | 2 | 4 | 8 | [6 empty] | 1 | 1 | 2
2.6.3.19 | 785.9.3 | Analyze and determine intersection timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | intersection | 2 | 3 | 5 | [300 empty] | 3 | 4 | 6 | [6 empty] | 1 | 1 | 2
2.6.3.20 | 785.9.4 | Analyze and determine coordination timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | timing plan per intersection | 6 | 8 | 10 | [147 empty] | 2 | 2 | 2 | [159 empty] | 4 | 6 | 8
2.6.4 | 788 | Develop Traffic Control and Staging
2.6.4.1 | 788 | Develop Traffic Control and Staging - Scoping task
2.6.4.2 | 788.1 | Develop/Coordinate/Review Transportation Management Plan (Type 1, 2, 3, 4) for all statuses.
2.6.4.3 | 788.1.1 | Identify work restrictions (special events-holidays) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | occurance | 4 | 6 | 16
2.6.4.4 | 788.1.2 | Work hour restrictions-lane closure evaluation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 6 | 16
2.6.4.5 | 788.1.3 | Work zone capacity traffic analysis (LOS-delay-queue) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 12 | 40
2.6.4.6 | 788.1.4 | Detour route evaluations (vertical clearance-travel time-improvements needed; surface and shoulder condition-corridor; and intersection capacity) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 12 | 40
2.6.4.7 | 788.1.5 | Temporary pedestrian accomodations |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | intersection | 4 | 8 | 16
2.6.4.8 | 788.1.6 | OSOW accomodations (clear lane width determination) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | location | 8 | 24 | 48
2.6.4.9 | 788.1.6 | Alternate route evaluations (vertical clearance-travel time-improvements needed; surface and shoulder condition-corridor; and intersection capacity) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | route-mile | 16 | 40 | 80
2.6.4.10 | 788.1.8 | Temporary transit accomodations |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bus stop | 4 | 8 | 16
2.6.4.11 | 788.1.9 | Temporary ITS |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 0 | 4 | 16
2.6.4.12 | 788.2 | Develop incident management plan |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | plan | 16 | 24 | 40
2.6.4.13 | 788.3 | Detour plan and signing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | detour | 8 | 16 | 24
2.6.4.14 | 788.4 | Traffic control plan |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 40 | 60 | 120
2.6.4.15 | 788.5 | Traffic control staging plans |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 40 | 120
2.6.4.16 | 788.6 | Pedestrian/bike/snowmobile detour |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | per detour per direction | 8 | 8 | 12
2.6.5 | 819 | Design Signing and Pavement Marking
2.6.5.1 | 819 | Design Signing and Pavement Marking - Scoping task
2.6.5.2 | 819.1 | Prepare Type 1 and/or Type 2 guide sign alternatives | MUTCD (multiple chapters) & TGM Chapter 2 | [14 empty] | x | x | [5 empty] | interchange | 25 | 60 | 100
2.6.5.3 | 819.2 | Develop plan sign plans
2.6.5.4 | 819.2.1 | Inventory eixsting signs | FDM Chapters 11 & 15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 5 | 10 | 12
2.6.5.5 | 819.2.2 | Develop sign removal plans | FDM Chapters 11 & 15 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 3 | 6 | 8
2.6.5.6 | 819.2.3 | Develop permanent sign plans | TGM Chpater 2 and MUTCD Part 2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 22 | 44 | 60
2.6.5.7 | 819.2.4 | Develop signing plates (DOT task only) | Guide Sign Design Manual & MUTCD Part 2 | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24
2.6.5.8 | 819.3 | Develop pavement marking plan details | FDM Chapters 11 & 15, TGM Chapter 3, WisMUTCD (multiple parts) | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40
2.6.6 | 830 | Design Street Lighting
2.6.6.1 | 830 | Design Street Lighting - Scoping task
2.6.6.2 | 830.1 | Improvement Project Operational Improvement - Lighting Plan & Inspection |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 16 | 60 | 120
2.6.6.3 | 830.2 | Determine potential locations for lighting |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 16 | 80 | 150
2.6.6.4 | 830.3 | Complete Lighting Investigation Report |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | report | 12 | 40 | 80
2.6.6.5 | 830.4 | Complete lighting permit forms (preliminary and final) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | permit | 16 | 32 | 80
2.6.6.6 | 830.5 | Determine existing lighting inventory and complete lighting removal plan |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 16 | 40 | 120
2.6.6.7 | 830.6 | Complete street lighting layout and equiptment design |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 40 | 200 | 1000
2.6.6.8 | 830.7 | Complete street lighting electrical design |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 40 | 200 | 1000
2.6.6.9 | 830.8 | Temporary lighting |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 40 | 100 | 500
2.6.7 | 832 | Design ITS
2.6.7.1 | 832 | Design ITS - Scoping task
2.6.7.2 | 832.1 | Design Traffic/Vehicle Detection Components – Interchange |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | interchange | 60 | 80 | 100
2.6.7.3 | 832.2 | Design Traffic/Volume Detection Components – Mainline |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 60 | 80
2.6.7.4 | 832.3 | Design Traffic/Volume Detection Components – Bluetooth |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 20 | 30 | 40
2.6.7.5 | 832.4 | Design CCTV Camera Components |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 60 | 80
2.6.7.6 | 832.5 | Design Dynamic Message Sign – Roadside |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 60 | 80 | 100
2.6.7.7 | 832.6 | Design Dynamic Message Sign – Overhead |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 80 | 160 | 240
2.6.7.8 | 832.7 | Design Fiber Regeneration Hut |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 100 | 150 | 200
2.6.7.9 | 832.8 | Design Fiber Optic Communications |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 50 | 80
2.7 |  | Real Estate, Railroad and Utilities
2.7.1 | 247 | Manage Real Estate Relocation
2.7.1.1 | 247 | Manage Real Estate Relocation - Scoping task | REPM
2.7.1.2 | 247.1 | Conceptual Plan - Relocation (environmental document)
2.7.1.3 | 247.1.1 | Residential | [15 empty] | X | X | X |  | X | X | X | relocation | 4 | 8 | 16
2.7.1.4 | 247.1.2 | Non-Residential | [15 empty] | X | X | X |  | X | X | X | relocation | 12 | 24 | 28
2.7.1.5 | 247.2 | Relocation Plan (at acquisition stage)
2.7.1.6 | 247.2.1 | Residential | [15 empty] | X | X | X |  | X | X | X | relocation | 38 | 74 | 114
2.7.1.7 | 247.2.2 | Non-Residential | [15 empty] | X | X | X |  | X | X | X | relocation | 47 | 70 | 108
2.7.1.8 | 247.3 | Relocation Assistance to Displaced Person
2.7.1.9 | 247.3.1 | MOVE ONLY with No Displaced Persons | [22 empty] | relocation | 20-40
2.7.1.10 | 247.3.2 | Residential | [22 empty] | relocation | 86 | 147 | 289
2.7.1.11 | 247.3.3 | Non-Residential | [22 empty] | relocation | 92 | 156 | 429
2.7.1.12 | 247.4 | Demolition/razing contracts
2.7.2 | 254 | Develop Real Estate Appraisal
2.7.2.1 | 254 | Develop Real Estate Appraisal - Scoping task | REPM
2.7.2.2 | 254.1 | Prepare and review real estate appraisal | [22 empty] | parcel | 40 | 68 | 96
2.7.2.3 | 254.2 | Specialty - Real estate appraisal services right of way projects | [15 empty] | X | X | X |  | X | X | X | parcel | 40 | 68 | 96
2.7.2.4 | 254.3 | Specialty - Real estate appraisal review services | [15 empty] | X | X | X |  | X | X | X | parcel | 8 | 12 | 16
2.7.2.5 | 254.4 | Specialty - Eminent domain real estate services | [15 empty] | X | X | X |  | X | X | X | parcel | 40 | 68 | 96
2.7.3 | 253 | Nominal Parcel Acquisition (less than $10k)
2.7.3.1 | 253 | Nominal Parcel Acquisition (less than $10k) - Scoping task | REPM
2.7.3.2 | 253.1 | Purchase of nominal parcel acquisition with appraisal | [15 empty] | X | X | X |  | X | X | X | parcel | 24
2.7.3.3 | 253.2 | Purchase of nominal parcel acquisition without appraisal | [15 empty] | X | X | X |  | X | X | X | parcel | 16
2.7.4 | 256 | Parcel Acquisition (greater than $10k)
2.7.4.1 | 256 | Parcel Acquisition (greater than $10k) - Scoping task | REPM
2.7.4.2 | 256.1 | Purchase of parcel | [15 empty] | X | X | X |  | X | X | X | parcel | 24 | 28 | 32
2.7.5 | 265 | Litigate Real Estate
2.7.5.1 | 265 | Litigate Real Estate - Scoping task | REPM | [22 empty] | * | * | *
2.7.6 | 746 | Coordinate Utilities
2.7.6.1 | 746 | Coordinate Utilities - Scoping task | FDM 18-1
2.7.6.2 | 746.1 | Prepare and maintain TUMS or DT1079 form |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 16
2.7.6.3 | 746.2 | SMA Review |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 2 | 4
2.7.6.4 | 746.3 | Plan/attend/document utility meetings |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 35 | 60+
2.7.6.5 | 746.4 | Create Utility Coordination Task List and/or review utility coordination contract |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 2 | 3
2.7.6.6 | 746.5 | PMP |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 2 | 3
2.7.6.7 | 746.6 | 1077 Process |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 10 | 15
2.7.6.8 | 746.7 | Field survey and compare data to system maps |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 3 | 5
2.7.6.9 | 746.8 | Review base and preliminary right of way plats and establish utility projects in FIIPS |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 5 | 10 | 15
2.7.6.10 | 746.9 | DSR Review |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 2 | 3
2.7.6.11 | 746.1 | Identify potential utility conflicts |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 10 | 32+
2.7.6.12 | 746.11 | 1078 Project Plan Process |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 13 | 18
2.7.6.13 | 746.12 | 1078 Compensable Process |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 3 | 5 | 8+
2.7.6.14 | 746.13 | Plan changes |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | plan change | 9 | 17 | 40+
2.7.6.15 | 746.14 | Reviews of utility work plans |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 24 | 40+
2.7.6.16 | 746.15 | Create or review utility special provisions |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 6 | 15+
2.7.6.17 | 746.16 | Execute utility agreements |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | utility number | 1 | 3 | 5
2.7.6.18 | 746.17 | Work plan approval and start work notice process |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 5 | 7
2.7.6.19 | 746.18 | Permitting Process |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 5 | 10 | 20+
2.7.6.20 | 746.19 | PS&E Review |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 3 | 5
2.7.6.21 | 746.2 | Post PS&E activities |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 3 | 4
2.7.6.22 | 746.21 | Construction support |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 3 | 6
2.7.6.23 | 746.22 | Utility invoicing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | utility number | 0 | 2 | 3
2.7.7 | 847 | Coordinate Railroad
2.7.7.1 | 847 | Coordinate Railroad - Scoping task | FDM 17-10
2.7.7.2 | 847.1 | Complete railroad safety training or notification to enter railroad right of way |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | person | 0.5 | 0.75 | 1
2.7.7.3 | 847.2 | Railroad project submittal package
2.7.7.4 | 847.2.1 | For grade separated crossing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 15 | 15 | 15
2.7.7.5 | 847.2.2 | For at grade crossing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 15 | 40 | 62
2.7.7.6 | 847.3 | Complete OCR process
2.7.7.7 | 847.3.1 | For grade separated crossing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 8 | 104
2.7.7.8 | 847.3.2 | For at grade crossing |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 56 | 140
2.7.7.9 | 847.4 | Coordinate traffic signal peemption plans |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | project | 21 | 40 | 80
2.7.7.10 | 847.5 | Acquire railroad real estate |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 15 | 102
3 |  | Construction Management
3.1 |  | Post-PSE through Letting
3.1.1 | 790 | Manage Post-PSE Though Let
3.1.1.1 | 790 | Manage Post-PSE Though Let - Scoping Task
3.1.1.2 | 790.1 | Prepare addendum development form and addendum form |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | addendum | 12 | 20 | 32 | [21 empty] | 12 | 20 | 32
3.1.1.3 | 790.2 | Respond to contractor inquires prior to let |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 2 | [23 empty] | 2 | 2 | 2
3.1.1.4 | 790.3 | Respond to BPD requests (engineer's estimate justification, etc.) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 10 | 12 | [21 empty] | 8 | 10 | 12
3.1.1.5 | 790.4 | Pre-letting meeting
3.1.1.6 | 790.5 | Manage letting
3.2 |  | Post-Let Pre-Construction Project Management
3.2.1 | 791 | Manage Construction Start
3.2.1.1 | 791 | Manage Construction Start - Scoping Task
3.2.1.2.2 | 791.1 | Develop contruction outreach meetings |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | meeting | 8 | 8 | 8 | [21 empty] | 8 | 8 | 8
3.2.1.5 | 791.2 | Set up field office and materials testing arrangements (coordinate computer application set up) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 16 | 24 | 40 | [21 empty] | 16 | 24 | 40
3.2.1.7 | 791.3 | Set up of lane closure system (STOC coordination) |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 2 | 4 | 8 | [21 empty] | 2 | 4 | 8
3.3 |  | Construction Contract Administration
3.3.1 | 271 | Perform Construction Surveying | [23 empty] | 64 | 238 | 392
3.3.1.1 | 271 | Perform Construction Surveying - Scoping task
3.3.1.2 | 271.1 | Initial preparation/checking |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 30 | 40 | [291 empty] | 10 | 15 | 20 | 10 | 15 | 20
3.3.1.3 | 271.2 | Perform construction staking |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 15 | 80 | 140 | [291 empty] | 5 | 30 | 50 | 10 | 50 | 90
3.3.1.4 | 271.3 | Survey quantity measurements/computation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 25 | 100 | 160 | [291 empty] | 10 | 40 | 60 | 15 | 60 | 100
3.3.1.5 | 271.4 | Develop as built |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 0 | 20 | 40 | [291 empty] | 0 | 10 | 20 | 0 | 10 | 20
3.3.1.6 | 271.5 | Digital file storage for archive |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 8 | 12 | [291 empty] | 0: 8; 10: 10; 20: 12
3.3.2 | 826 | Complete Construction Finals | [23 empty] | 106 | 262 | 396
3.3.2.1 | 826 | Complete Construction Finals - Scoping task
3.3.2.2 | 826.1 | Check all entries and source documents |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 60 | 80 | [12 empty] | 20 | 60 | 80
3.3.2.3 | 826.2 | Explanation of Variation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 20 | 32 | [12 empty] | 10 | 20 | 32
3.3.2.4 | 826.3 | Close out items in FM |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 12 | 16 | [12 empty] | 6 | 12 | 16
3.3.2.5 | 826.4 | FIT entries |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 4 | 8 | [12 empty] | 4 | 4 | 8
3.3.2.6 | 826.5 | Prepare As-Built Plans |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 28 | 40 | [12 empty] | 8 | 28 | 40
3.3.2.7 | 826.6 | Settle Quantity Discrepancies |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 40 | [12 empty] | 16 | 24 | 40
3.3.2.8 | 826.7 | Complete Evaluations (DQI, Contractor Performance) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 24 | 40 | [12 empty] | 8 | 24 | 40
3.3.2.9 | 826.8 | CQI Walkthrough |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 16 | [12 empty] | 4 | 8 | 16
3.3.2.10 | 826.9 | Prepare/organize accounting finals for submittal |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 14 | 28 | [12 empty] | 6 | 14 | 28
3.3.2.11 | 826.1 | DT 1310 Certification of Materials used on Highway Projects |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 16 | [12 empty] | 4 | 8 | 16
3.3.2.12 | 826.11 | Update finals after Department review |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 60 | 80 | [12 empty] | 20 | 60 | 80
3.3.3 | 852 | Evaluate Construction Material
3.3.3.1 | 852 | Evaluate Construction Material - Scoping task |  | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x
3.3.3.2 | 852.1 | Evaluate Structure Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | structure | 12 | 24 | 40 | [9 empty] | 4 | 10 | 16 | .3 | .8 | .8 | [6 empty] | .2 | .2 | .2 | [6 empty] | 7.5 | 13 | 23
3.3.3.3 | 852.2 | Evaluate Concrete Pavement Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | paving days | 4 | 8 | 12 | [9 empty] | 1 | 2 | 4 | .8 | 1.5 | 2 | [6 empty] | .2 | .5 | 1 | [6 empty] | 2 | 4 | 5
3.3.3.4 | 852.3 | Evaluate Ancillary Concrete Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | placement days | 2 | 4 | 8 | [9 empty] | 1 | 1 | 1 | .5 | .5 | .5 | [15 empty] | .5 | 2.5 | 6.5
3.3.3.5 | 852.4 | Evaluate HMA Pavement Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | paving days | 4 | 8 | 12 | [9 empty] | 1 | 2 | 4 | .8 | 1.5 | 2 | [6 empty] | .2 | .5 | 1 | [6 empty] | 2 | 4 | 5
3.3.3.6 | 852.5 | Evaluate Aggregate/Base Course Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | placement days | 4 | 6 | 8 | [9 empty] | 1 | 1 | 1 | .8 | 1.5 | 2 | [6 empty] | .2 | .5 | .5 | [6 empty] | 2 | 3 | 5
3.3.3.7 | 852.6 | Evaluate Electrical/ITS Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 24 | 40 | 80 | [9 empty] | 10 | 30 | 60 | 1 | 2 | 4 | [15 empty] | 8 | 13 | 16
3.3.3.8 | 852.7 | Evaluate Pipe Culverts & Storm Sewer Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 16 | [9 empty] | 2 | 4 | 6 | 1 | 2 | 3 | [15 empty] | 5 | 6 | 7
3.3.3.9 | 852.8 | Evaluate MSE/Noise Walll Materials | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 60 | 140 | 260 | [9 empty] | 20 | 80 | 120 | .3 | .8 | .8 | [6 empty] | .2 | .2 | .2 | [6 empty] | 39.5 | 59 | 139
3.3.3.10 | 852.9 | Review Misc. Project Material Submittals | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 40 | 64 | 160 | [9 empty] | 16 | 31 | 100 | 1 | 2 | 6 | [6 empty] | 0 | 1 | 2 | [6 empty] | 23 | 30 | 52
3.3.3.11 | 852.1 | Material Finals | CMM/Specials/E-guide | X | X | X | X | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x | project | 120 | 180 | 300 | [9 empty] | 59 | 89 | 149 | .8 | .8 | .8 | [6 empty] | .2 | .2 | .2 | [6 empty] | 60 | 90 | 150
3.3.4 | 853 | Evaluate Work Operations
3.3.4.1 | 853 | Evaluate Work Operations - Scoping task
3.3.4.2 | 853.1 | Inspect work operations |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | per day per person | 8 | 10 | 12 | [12 empty] | 8 | 10 | 12
3.3.4.3 | 853.2 | General construction engineering |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | per day per person | 1 | 4 | 6 | [12 empty] | 1 | 4 | 6
3.3.4.4 | 853.3 | General field inspection |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | per day per person | 1 | 2 | 4 | [12 empty] | 1 | 2 | 4
3.3.4.5 | 853.4 | Respond to contractor RFI's |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 4 | 20 | 40 | [12 empty] | 4 | 20 | 40
3.3.4.6 | 853.5 | Prepare DIN's |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 5 | 10 | [12 empty] | 1 | 5 | 10
3.3.4.7 | 853.6 | Review contractor proposed CRI's |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 10 | 25 | 40 | [12 empty] | 10 | 25 | 40
3.3.5 | 881 | Manage Construction Contract Accounting
3.3.5.1 | 881 | Manage Construction Contract Accounting - Scoping task |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
3.3.5.2 | 881.1 | FM/FIT initial contract info entry |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | project ID | 8 | 8 | 10 | [12 empty] | 6 | 6 | 8 | [6 empty] | 2 | 2 | 2
3.3.5.3 | 881.2 | Quantity measurement/computation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [9 empty] | 4 | 8 | 10
3.3.5.4 | 881.3 | Ticket entry into pantry sheets |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 2 | 4 | 5 | [9 empty] | 1 | 3 | 4 | 1 | 1 | 1
3.3.5.5 | 881.4 | Quantity checking and entry into FM |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [9 empty] | 2 | 4 | 5 | 2 | 4 | 5
3.3.5.6 | 881.5 | FM/FIT steps to create estimate (diary consolidation) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [12 empty] | 4 | 8 | 10
3.3.5.7 | 881.6 | Print estimate/diaries to binder |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 2 | 2 | 2 | [12 empty] | 2 | 2 | 2
3.3.5.8 | 881.7 | Cost Tracking Updates |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 1 | 1 | 2 | [12 empty] | 1 | 1 | 2
3.3.5.9 | 881.8 | Research quantity discrepancies (plan vs. measured) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 1 | 4 | 5 | [12 empty] | 1 | 4 | 5
3.3.5.10 | 881.9 | Other project records (Erosion control reports, Traffic Control reports) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [9 empty] | 3 | 7 | 9 | 1 | 1 | 1
3.3.5.11 | 881.1 | Contract Modifications
3.3.5.12 | 881.10.1 | Engineer ROM |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [12 empty] | 1 | 1 | 2
3.3.5.13 | 881.10.2 | CM Negotiation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 4 | 8 | 15 | [12 empty] | 4 | 8 | 15
3.3.5.14 | 881.10.3 | WAF |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [12 empty] | 1 | 1 | 2
3.3.5.15 | 881.10.4 | AJR |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 3 | [12 empty] | 1 | 1 | 3
3.3.5.16 | 881.10.5 | Write/review/process CM |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 3 | [12 empty] | 1 | 1 | 3
3.3.5.17 | 881.10.6 | Filing of all CM source documentation |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [12 empty] | 1 | 1 | 2
3.3.5.18 | 881.10.7 | Claims |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 1 | [12 empty] | 1 | 1 | 1
3.3.6 | 885 | Enforce Labor Provisions
3.3.6.1 | 885 | Enforce Labor Provisions - Scoping task
3.3.6.2 | 885.1 | Sublet approval (DT 1925) | [15 empty] | X | X | X | X | X | X | X | project | 2 | 2-4 | 4 | [30 empty] | 2 | 3 | 4
3.3.6.3 | 885.2 | Precon preparation and attendance | [15 empty] | X | X | X | X | X | X | X | project | 2 | 2-4 | 4 | [30 empty] | 2 | 3 | 4
3.3.6.4 | 885.3 | Assist contractor with worker classification and reporting (CRCS) | [15 empty] | X | X | X | X | X | X | X | project | 2 | 4 | 6 | [30 empty] | 2 | 4 | 6
3.3.6.5 | 885.4 | Wage interviews | [15 empty] | X | X | X | X | X | X | X | project | 2 | 4 | 8 | [12 empty] | 1 | 2 | 4 | [15 empty] | 1 | 2 | 4
3.3.6.6 | 885.5 | Weekly payroll review | [15 empty] | X | X | X | X | X | X | X | week | 2 | 3 | 6 | [30 empty] | 2 | 3 | 6
3.3.6.7 | 885.6 | Payroll clear date process and payroll audits | [15 empty] | X | X | X | X | X | X | X | project | 4 | 8 | 16 | [30 empty] | 4 | 8 | 16
4 |  | Program Management
4.1 |  | Policy Development and Program Controls
4.1.1 | 855 | Program and Policy Development
4.1.1.1 | 855 | Program and Policy Development - Scoping task
4.1.1.2 | 855.1 | Develop transportation program and policy
4.1.1.3 | 855.2 | Manual development and updates (FDM, CMM, etc.)
4.1.1.4 | 855.3 | Standards and specification development and updates (Std Spec, STSP, Region SPV)
4.1.1.5 | 855.4 | Process reviews and process improvements
4.1.1.6 | 855.5 | Prepare STIP and TIP
4.1.2 | 863 | Program Controls
4.1.2.1 | 863 | Program Controls - Scoping task
4.1.2.2 | 863.1 | Performance measurement management
4.1.2.3 | 863.2 | Report development and updates
4.1.2.4 | 863.3 | Report processing and review (Production, Health, Scheduling, Finals, etc.)
4.1.2.5 | 863.4 | Update project tracking applications (ex FIIPS, FOS, PeopleSoft)
4.1.2.6 | 863.5 | Project audits (LAB)
4.1.2.7 | 863.6 | Document management
4.2 |  | Systems Planning
4.2.1 | 211 | Statewide System Plans
4.2.1.1 | 211 | Statewide System Plans - Scoping task
4.2.2 | 214 | Corridor Study (Major Highway)
4.2.2.1 | 214 | Corridor Study (Major Highway) - Scoping task
4.2.3 | 249 | Corridor Study (Other Highway)
4.2.3.1 | 249 | Corridor Study (Other Highway) - Scoping task
4.2.4 | 250 | 84.25 Access Control Project New/Update
4.2.4.1 | 250 | 84.25 Access Control Project New/Update - Scoping task
4.2.5 | 251 | 84.295 Statutory Expressway/Freeway
4.2.5.1 | 251 | 84.295 Statutory Expressway/Freeway - Scoping task
4.2.6 | 252 | Conceptual Land Division Review Activities
4.2.6.1 | 252 | Conceptual Land Division Review Activities - Scoping task
4.2.7 | 257 | Formal Land Division Review Activities
4.2.7.1 | 257 | Formal Land Division Review Activities - Scoping task
4.2.8 | 263 | Land Division TIA Review
4.2.8.1 | 263 | Land Division TIA Review - Scoping task
4.2.8.2 | 263.1 | Determine land divisions
4.2.9 | 269 | Functional Class Routine Activities
4.2.9.1 | 269 | Functional Class Routine Activities - Scoping task
4.2.10 | 280 | Census Review - (Urban Boundary Change)
4.2.10.1 | 280 | Census Review - (Urban Boundary Change) - Scoping task
4.2.11 | 281 | Jurisdictional Transfers on Non-State Roads
4.2.11.1 | 281 | Jurisdictional Transfers on Non-State Roads - Scoping task
4.2.12 | 282 | Jurisdictional Transfers per STH Change Statute 84.02(3)
4.2.12.1 | 282 | Jurisdictional Transfers per STH Change Statute 84.02(3) - Scoping task
4.2.13 | 283 | Jurisdictional not Associated with any Relocation Project 84.02(8)
4.2.13.1 | 283 | Jurisdictional not Associated with any Relocation Project 84.02(8) - Scoping task
4.2.14 | 284 | Comprehensive Plan Involvement
4.2.14.1 | 284 | Comprehensive Plan Involvement - Scoping task
4.2.15 | 285 | MPO and RPC Planning Liaison Activities
4.2.15.1 | 285 | MPO and RPC Planning Liaison Activities - Scoping task
4.2.16 | 286 | Miscellaneous Land Use Studies
4.2.16.1 | 286 | Miscellaneous Land Use Studies - Scoping task
4.2.17 | 287 | Corridor Planning (Non-statutory Access Management Plans)
4.2.17.1 | 287 | Corridor Planning (Non-statutory Access Management Plans) - Scoping task
4.2.18 | 288 | Non-Highway Special Studies
4.2.18.1 | 288 | Non-Highway Special Studies - Scoping task
4.2.19 | 289 | Public Transit Coordination and Outreach
4.2.19.1 | 289 | Public Transit Coordination and Outreach - Scoping task
4.2.20 | 296 | Park and Ride Lot and Commuter Center Management & Coordination
4.2.20.1 | 296 | Park and Ride Lot and Commuter Center Management & Coordination - Scoping task
4.2.21 | 297 | Bike and Pedestrian Coordination and Outreach
4.2.21.1 | 297 | Bike and Pedestrian Coordination and Outreach - Scoping task
4.2.22 | 299 | Coordination of Rail and Harbor Activities
4.2.22.1 | 299 | Coordination of Rail and Harbor Activities - Scoping task
4.2.23 | 300 | State Highway Program Development
4.2.23.1 | 300 | State Highway Program Development - Scoping task
4.2.24 | 314 | STN Activities
4.2.24.1 | 314 | STN Activities - Scoping task
4.2.25 | 340 | Program Level Scoping
4.2.25.1 | 340 | Program Level Scoping - Scoping task
4.2.26 | 348 | Local Program Management and Implementation
4.2.26.1 | 348 | Local Program Management and Implementation - Scoping task
4.2.27 | 349 | State Program Management and Implementation
4.2.27.1 | 349 | State Program Management and Implementation - Scoping task
4.2.28 | 687 | Rideshare Coordination and Outreach
4.2.28.1 | 687 | Rideshare Coordination and Outreach - Scoping task
4.3 |  | Systems Operations
4.3.1 | 227 | Roadside Facilities
4.3.1.1 | 227 | Roadside Facilities - Scoping task
4.3.2 | 228 | Bridge Maintenance
4.3.2.1 | 228 | Bridge Maintenance - Scoping task
4.3.3 | 231 | Accident Damage Administration
4.3.3.1 | 231 | Accident Damage Administration - Scoping task
4.3.4 | 275 | Inspect Structure
4.3.4.1 | 275 | Inspect Structure - Scoping task
4.3.4.2 | 275.1 | Specialty - Underwater dive bridge inspection
4.3.4.3 | 275.2 | Specialty - Bridge sign and signal inspection
4.3.4.4 | 275.3 | Specialty - Bridge deck survey structure inspection
4.3.4.5 | 275.4 | Specialty - Structure nondestructive evaluations and structure inspection
4.3.4.6 | 275.5 | Specialty - In plant QV inspection at prestress plants
4.3.4.7 | 275.6 | Specialty - Quality verification of precast concrete and metal drainage ...
4.3.5 | 322 | Inventory or Data Gathering
4.3.5.1 | 322 | Inventory or Data Gathering - Scoping task
4.3.6 | 332 | Outdoor Advertising
4.3.6.1 | 332 | Outdoor Advertising - Scoping task
4.3.7 | 333 | Adopt-A-Highway
4.3.7.1 | 333 | Adopt-A-Highway - Scoping task
4.3.8 | 334 | Utility Permits
4.3.8.1 | 334 | Utility Permits - Scoping task
4.3.9 | 335 | Driveway and Street Connection Permits
4.3.9.1 | 335 | Driveway and Street Connection Permits - Scoping task
4.3.10 | 338 | Work on Right-of-Way Permits
4.3.10.1 | 338 | Work on Right-of-Way Permits - Scoping task
4.3.11 | 520 | Crash Investigation
4.3.11.1 | 520 | Crash Investigation - Scoping task
4.3.12 | 648 | Automation, Policy, and Standards Development
4.3.12.1 | 648 | Automation, Policy, and Standards Development - Scoping task
4.3.13 | 649 | Bridge Management and Asset Management
4.3.13.1 | 649 | Bridge Management and Asset Management - Scoping task
4.3.14 | 650 | Bridge Load Rating
4.3.14.1 | 650 | Bridge Load Rating - Scoping task
4.3.15 | 652 | Bridge OSOW Permits Analysis and Review
4.3.15.1 | 652 | Bridge OSOW Permits Analysis and Review - Scoping task
4.3.16 | 684 | Sign & Miscellaneous Permits
4.3.16.1 | 684 | Sign & Miscellaneous Permits - Scoping task
4.3.17 | 685 | Diggers Hotline Administration
4.3.17.1 | 685 | Diggers Hotline Administration - Scoping task
4.3.18 | 686 | Ancillary Structure Inspection
4.3.18.1 | 686 | Ancillary Structure Inspection - Scoping task
4.3.18.2 | 686.1 | Specialty - Sign, signal and ancillary structure inspection
4.3.19 | 688 | Bridge Maintenance & Operations-Operational Bridges
4.3.19.1 | 688 | Bridge Maintenance & Operations-Operational Bridges - Scoping task
4.3.20 | 689 | Bridge Maintenance & Operations-Ferry
4.3.20.1 | 689 | Bridge Maintenance & Operations-Ferry - Scoping task
4.3.21 | 690 | Bridge Maintenance and Operations - Ancillary Structures
4.3.21.1 | 690 | Bridge Maintenance and Operations - Ancillary Structures - Scoping task
4.3.22 | 691 | Roadway Maintenance-Pavement & Shoulder
4.3.22.1 | 691 | Roadway Maintenance-Pavement & Shoulder - Scoping task
4.3.23 | 692 | Roadway Maintenance-Culverts
4.3.23.1 | 692 | Roadway Maintenance-Culverts - Scoping task
4.3.24 | 693 | County Budget Development & Oversight
4.3.24.1 | 693 | County Budget Development & Oversight - Scoping task
4.3.25 | 694 | Winter Maintenance Field Monitoring
4.3.25.1 | 694 | Winter Maintenance Field Monitoring - Scoping task
4.3.26 | 695 | Winter Chemical Oversight
4.3.26.1 | 695 | Winter Chemical Oversight - Scoping task
4.3.27 | 696 | Roadside Maintenance-Encroachments
4.3.27.1 | 696 | Roadside Maintenance-Encroachments - Scoping task
4.3.28 | 697 | Roadside Maintenance-Drainage & Slopes
4.3.28.1 | 697 | Roadside Maintenance-Drainage & Slopes - Scoping task
4.3.29 | 698 | Roadside Maintenance-Vegetation Management
4.3.29.1 | 698 | Roadside Maintenance-Vegetation Management - Scoping task
4.3.30 | 738 | Lighting Design (non-improvement work)
4.3.30.1 | 738 | Lighting Design (non-improvement work) - Scoping task
4.3.31 | 739 | Contacts & Response to Inquiries
4.3.31.1 | 739 | Contacts & Response to Inquiries - Scoping task
4.3.32 | 800 | COMPASS
4.3.32.1 | 800 | COMPASS - Scoping task
4.3.33 | 801 | Improvement Project Operational Involvement-Roadway Maintenance
4.3.33.1 | 801 | Improvement Project Operational Involvement-Roadway Maintenance - Scoping task
4.3.34 | 802 | Improvement Project Operational Involvement-Bridge Maintenance
4.3.34.1 | 802 | Improvement Project Operational Involvement-Bridge Maintenance - Scoping task
4.3.35 | 804 | Traffic Engineering Studies
4.3.35.1 | 804 | Traffic Engineering Studies - Scoping task
4.3.36 | 805 | Traffic Regulations & Declarations
4.3.36.1 | 805 | Traffic Regulations & Declarations - Scoping task
4.3.37 | 806 | Electrical Facility Locates
4.3.37.1 | 806 | Electrical Facility Locates - Scoping task
4.3.38 | 807 | Improvement Project Operational Involvement-Traffic General
4.3.38.1 | 807 | Improvement Project Operational Involvement-Traffic General - Scoping task
4.3.39 | 808 | Traffic Signal/Beacon-Design & Review (non-improvement work)
4.3.39.1 | 808 | Traffic Signal/Beacon-Design & Review (non-improvement work) - Scoping task
4.3.40 | 809 | Traffic Signal/Beacon Operational Review-Engineering
4.3.40.1 | 809 | Traffic Signal/Beacon Operational Review-Engineering - Scoping task
4.3.41 | 810 | Traffic Signal/Beacon Maintenance & Installation
4.3.41.1 | 810 | Traffic Signal/Beacon Maintenance & Installation - Scoping task
4.3.42 | 811 | Signal/Lighting Inventory Data Management
4.3.42.1 | 811 | Signal/Lighting Inventory Data Management - Scoping task
4.3.43 | 812 | Improvement Project Operational Involvement-Traffic Signal/Beacon
4.3.43.1 | 812 | Improvement Project Operational Involvement-Traffic Signal/Beacon - Scoping task
4.3.44 | 813 | Sign Program Management
4.3.44.1 | 813 | Sign Program Management - Scoping task
4.3.45 | 814 | Sign Plan Design (non-improvement work)
4.3.45.1 | 814 | Sign Plan Design (non-improvement work) - Scoping task
4.3.46 | 815 | Sign Inventory Data Management
4.3.46.1 | 815 | Sign Inventory Data Management - Scoping task
4.3.47 | 817 | Sign Installation Review & Oversight
4.3.47.1 | 817 | Sign Installation Review & Oversight - Scoping task
4.3.48 | 818 | Engineering Evaluation of Sign Needs/Requests
4.3.48.1 | 818 | Engineering Evaluation of Sign Needs/Requests - Scoping task
4.3.49 | 820 | Pavement Marking Program Management
4.3.49.1 | 820 | Pavement Marking Program Management - Scoping task
4.3.50 | 821 | Pavement Marking Plan Design (non-improvement work)
4.3.50.1 | 821 | Pavement Marking Plan Design (non-improvement work) - Scoping task
4.3.51 | 822 | Pavement Marking Inventory Data Management
4.3.51.1 | 822 | Pavement Marking Inventory Data Management - Scoping task
4.3.52 | 828 | Lighting Equipment Installation & Maintenance
4.3.52.1 | 828 | Lighting Equipment Installation & Maintenance - Scoping task
4.3.53 | 829 | Lighting Permits
4.3.53.1 | 829 | Lighting Permits - Scoping task
4.3.54 | 835 | ITS Activities
4.3.54.1 | 835 | ITS Activities - Scoping task
4.3.55 | 838 | Incident Response
4.3.55.1 | 838 | Incident Response - Scoping task
4.3.56 | 867 | Traffic Signal System Program Delivery (admin of "stand-alone" only)
4.3.56.1 | 867 | Traffic Signal System Program Delivery (admin of "stand-alone" only) - Scoping task
4.3.57 | 868 | Implements of Husbandry
4.3.57.1 | 868 | Implements of Husbandry - Scoping task
4.4 |  | Technical Services
4.4.1 | 239 | Materials Research
4.4.1.1 | 239 | Materials Research - Scoping task
4.4.1.2 | 239.1 | Specialty - WisDOT qualified labs inspection
4.4.2 | 259 | R/E Technical User Groups
4.4.2.1 | 868 | R/E Technical User Groups - Scoping task
4.4.3 | 260 | Property Management
4.4.3.1 | 868 | Property Management - Scoping task
4.4.4 | 262 | Surplus Land Sales
4.4.4.1 | 868 | Surplus Land Sales - Scoping task
4.4.5 | 991 | Tribal Meetings
4.4.5.1 | 868 | Tribal Meetings - Scoping task
4.4.6 | 992 | Tribal Relations
4.4.6.1 | 868 | Tribal Relations - Scoping task
4.4.7 | 990 | Office of Business Opportunity and Equity Compliance
4.4.7.1 | 990 | Office of Business Opportunity and Equity Compliance - Scoping task
4.4.7.2 | 990.1 | Specialty - Loan mobilization program
4.4.7.3 | 990.2 | Specialty - Outreach and marketing
4.4.7.4 | 990.3 | Specialty - Technical assistance
4.4.7.5 | 990.4 | Specialty - Legal assistance
5 |  | General
5.1 |  | General
5.1.1 | 101 | Work time
5.1.1.1 | 101 | Work time
5.1.2 | 104 | Supervision
5.1.2.1 | 104 | Supervision
5.1.3 | 121 | Training
5.1.3.1 | 121 | Training
5.1.4 | 122 | Meetings and conventions
5.1.4.1 | 122 | Meetings and conventions
5.1.5 | 123 | Travel time
5.1.5.1 | 123 | Travel time
5.1.6 | 129 | Approved Professional Development Time
5.1.6.1 | 129 | Approved Professional Development Time
5.1.7 | 132 | Vacation - In Lieu of Sick Leave
5.1.7.1 | 132 | Vacation - In Lieu of Sick Leave
5.1.8 | 133 | Legal Holiday - In Lieu of Sick Leave
5.1.8.1 | 133 | Legal Holiday - In Lieu of Sick Leave
5.1.9 | 134 | Personal Holiday - In Lieu of Sick Leave
5.1.9.1 | 134 | Personal Holiday - In Lieu of Sick Leave
5.1.10 | 135 | Vacation - FMLA
5.1.10.1 | 135 | Vacation - FMLA
5.1.11 | 136 | Legal Holiday - FMLA
5.1.11.1 | 136 | Legal Holiday - FMLA
5.1.12 | 137 | Personal Holiday - FMLA
5.1.12.1 | 137 | Personal Holiday - FMLA
5.1.13 | 138 | Sick - FMLA
5.1.13.1 | 138 | Sick - FMLA
5.1.14 | 139 | Termination/Sabbatical - FMLA
5.1.14.1 | 139 | Termination/Sabbatical - FMLA
5.1.15 | 140 | Absence without Pay - FMLA
5.1.15.1 | 140 | Absence without Pay - FMLA
5.1.16 | 141 | Comp Time Taken - FMLA
5.1.16.1 | 141 | Comp Time Taken - FMLA
5.1.17 | 150 | Vacation Without Pay (Crafts)
5.1.17.1 | 150 | Vacation Without Pay (Crafts)
5.1.18 | 151 | Vacation
5.1.18.1 | 151 | Vacation
5.1.19 | 153 | Legal Holiday
5.1.19.1 | 153 | Legal Holiday
5.1.20 | 154 | Jury Duty
5.1.20.1 | 154 | Jury Duty
5.1.21 | 155 | Military Leave - Annual Training
5.1.21.1 | 155 | Military Leave - Annual Training
5.1.22 | 157 | Personal Holiday
5.1.22.1 | 157 | Personal Holiday
5.1.23 | 161 | Sick - Employee Illness
5.1.23.1 | 161 | Sick - Employee Illness
5.1.24 | 163 | Sick - Family Illness
5.1.24.1 | 163 | Sick - Family Illness
5.1.25 | 165 | Sick - Death in Family
5.1.25.1 | 165 | Sick - Death in Family
5.1.26 | 167 | Exam and Interview Time
5.1.26.1 | 167 | Exam and Interview Time
5.1.27 | 169 | Termination/Sabbatical
5.1.27.1 | 169 | Termination/Sabbatical
5.1.28 | 174 | Sick - Employee/Family Medical Appt
5.1.28.1 | 174 | Sick - Employee/Family Medical Appt
5.1.29 | 181 | Compensatory Time Taken
5.1.29.1 | 181 | Compensatory Time Taken
5.1.30 | 151 | Vacation
5.1.30.1 | 151 | Vacation
5.1.31 | 153 | Legal Holiday
5.1.31.1 | 153 | Legal Holiday
5.1.32 | 154 | Jury Duty
5.1.32.1 | 154 | Jury Duty
5.1.33 | 155 | Military Leave - Annual Training
5.1.33.1 | 155 | Military Leave - Annual Training
5.1.34 | 157 | Personal Holiday
5.1.34.1 | 157 | Personal Holiday
5.1.35 | 163 | Sick - Family Illness
5.1.35.1 | 163 | Sick - Family Illness
5.1.36 | 165 | Sick - Death in Family
5.1.36.1 | 165 | Sick - Death in Family
5.1.37 | 167 | Exam and Interview Time
5.1.37.1 | 167 | Exam and Interview Time
5.1.38 | 169 | Termination/Sabbatical
5.1.38.1 | 169 | Termination/Sabbatical
5.1.39 | 174 | Sick - Employee/Family Medical Appt
5.1.39.1 | 174 | Sick - Employee/Family Medical Appt
5.1.40 | 181 | Compensatory Time Taken
5.1.40.1 | 181 | Compensatory Time Taken
Note on AA374: MitchPatoka: EX 2 person crew
Note on CO205: MitchPatoka: Landscape Architect
Note on KZ110: MitchPatoka: GIS Professional
Note on KZ112: MitchPatoka: GIS Professional
Note on KZ172: MitchPatoka: GIS Professional
Note on KZ239: MitchPatoka: GIS
Note on KZ246: MitchPatoka: GIS