## Sheet1
Wisconsin Department of Transportation
Statewide Utility Conflict Analysis Report For Period: 1/1/2022 through 12/31/2022
Statewide Report Sorted by Contract, Project, and Report Number
10/12/2023
Contract ID | Federal Project Number | Construction Project ID | Description | Region | County | Route | Project Engineer | Project Engineer Office | Region Utility Coordinator | Conflict Report No | Report Completion Date | Project Type | Improvement Concept | Highway Contractor or Sub Affected #1 | Utility Company #1 | Facility Type #1 | Utility Location #1 | Highway Contractor or Sub Affected #2 | Utility Company #2 | Facility Type #2 | Utility Location #2 | Highway Contractor or Sub Affected #3 | Utility Company #3 | Facility Type #3 | Utility Location #3 | Date Utility Issue Discovered | Date Utility Issue Resolved | Digger Hotline Request Locating Issue | Utility Conflict Affects Controlling Item of Work | Existing Utility Facilities Shown Incorrectly In Project Plan | Conflict w/ Project Plan Not Identified | Not In Compliance w/ Work Plan/Permit | Project Plan Change | Other | Other Reason | Highway Contractor or Sub Used Alternate Means and Methods | Designed Around Utility Facility | Protected Utility Facility | Relocated Utility Facility | Discontinued Use of Utility Facility | Other | Other Resolution | Utility Conflict Impact On Contractor Schedule or Operations | Other Reason | Estimated Hours Spent by WisDOT / LPA / Consultant on Utility Issue | Other Reason | Estimated Hours Highway Contractor or Sub Was Affected | Other Reason | Impact to Contract Time and Cost | Other Reason | Attachments | Additional Pertinent Detail
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 10 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 07/19/2022 | 07/25/2022 | No | No |  |  |  |  | Yes | Sinkhole discovered in cut subgrade which was eventually discovered to be following an AT&T duct package for an unknown distance. | [5 empty] | Yes | Brian Perz's 7/19/22 DWR: 8:32am Chuck sent a txt reporting that the sinkhole in the WB lanes of North Ave under the SB freeway bridge appears to keep going to the East. Hoffman began excavating the sinkhole and eventually came upon 7 orange plastic ducts. I reported this to Sean and Zembroski. 8:51am I discussed the sinkhole with Birschbach who will try to get a hold of Jay from AT&T because we believe the orange ducts belong to them. 9:30am I arrived at the sinkhole excavation to find approximately 50 LF excavated to the East. 7 orange ducts could barely be seen at the East end of the excavation as material continued to fall into the trench. It appeared an approximate 2' diameter hole continued to the East above the duct package. We discussed our options and agreed we need AT&T on-site to evaluate the situation. I spoke with Kevin Kaufman and we agreed Hoffman should stop work at the sinkhole and return to storm sewer installation. The excavator walked away around 10am. 12:44pm Dulka called to report that AT&T arrived at the sinkhole. I called Birschbach and headed out right away. Jay Bulanek and two other AT&T representatives were on-site. We discussed the situation and Jay announced AT&T will not take any responsibility for the sinkhole that follows their duct package. He confirmed that is an AT&T facility and consists of 7 orange ducts. He stated their facility is not in conflict with roadway construction. He reminded us that the Wauwatosa watermain to the West of this area was knowingly leaking for some time. One theory is that water found a sand seam in the location that we found the sinkhole and made its way down to their duct package and was following that bore shot. Jay explained that they inject bentonite in the bore shot as they pull ducting back through. The question still remains as to where all their bentonite has gone if the watermain leakage is to blame. Jay did not have an answer for that, nor has anyone found washed out material downstream to the East in any storm sewer or other facilities. 1:02pm I called Zembroski to report that AT&T is not taking responsibility for this and asked how he thinks we should move forward. He does not want to keep digging, he would like to pump flowable material into it until it won't accept any more material. He confirmed Sean is willing to direct this as force account since AT&T won't do anything. Kevin Kaufman is making calls to Elastizell to find out if they can fill this. I left the site to begin writing an emergency WAF while Drew waited there for an Elastizell representative to arrive. Drew reported back that Elastizell showed up and recommended a foamed concrete material with no sand. After speaking with Kevin Kaufman who confirmed with Elastizell, the material they recommended is a grade 2 LFCF which meets the requirements of the LFCF item in our contract. Brian Perz's 7/25/22 DWR: 10:31am Chuck reported that Elastizell began filling the sinkhole in the WB lanes of North Ave under the SB freeway bridge. 10:45am I stopped by the sinkhole backfilling operation. Elastizell had already pumped 15 CY's of LFCF into the hole and had to order a second truck. Schindelholz, Chuck, Birschbach, and Drew were at the operation as well. Approximately 20 CY's were needed to fill the sinkhole. | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | Other | It took 7 days to mobilize Elastizell to backfill the sinkhole. | Non-Excusable Non-Compensable Delay
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 11 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 03/16/2022 | 05/17/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | Other | This took 2 months to completely resolve. | Non-Excusable Non-Compensable Delay |  |  | 3/16/22 Greg Dulka of Michels sent an email summarizing the potholes that were dug the morning of 3/16/22 in the median of North Ave at the intersection of 114th Street. Conduits running from the 114th Street cul-de-sac north through North Ave EB were exposed at approximately 4’ below existing grade. At the location of the test pit, the conduit is approximately 7” above the bottom of select crushed material that will be installed during the reconstruction of North Ave. Furthermore, the elevation of the conduit is thought to be higher at the 114th Street cul-de-sac south of North Ave. He states the conduits will need to be lowered and requests a meeting. 3/18/22 DOT and V2G survey shot top of conduits in conflict. DOT/Kapur plotted shots and created exhibit depicting the conflicts. 3/18/22 Email from Jay Bulanek of AT&T acknowledges the conflicts and lays out a plan for lowering their facilities. 3/29/22 7:30am Field meeting with Greg Dulka, Mike Birschbach, Jay Bulanek, and a representative from IHC. Dulka sent a summary email to all parties involved explaining the lowering of the facilities. 3/31/22 10:30am Birschbach confirmed that AT&T's subcontractor is on North Ave exposing the ducts in conflict with proposed subgrade at 114th St. AT&T/IHC spent the next week and a half lowering and encasing their communication facilities, finishing on 4/8/22. Hoffman construction operations were able to continue in the area 4/11/22. 5/10/22 A conduit previously exposed on the North side of the 114th St cul-de-sac in the EB North Ave right turn was discovered to not be previously encased in concrete and is at subgrade. Brian Perz sent Greg Dulka and Kevin Kaufman an email confirming the Department does not have concern with AT&T orange conduit concrete encasement being slightly up into the proposed select crushed layer in North Ave. 5/17/22 IHC subsequently returned to lower and concrete encase the duct on the North side of the 114th St cul-de-sac in the EB North Ave right turn.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 12 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | We Energies | Gas/Petroleum | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 08/12/2022 | 08/18/2022 | No | Yes |  |  |  |  | Yes | WE Energies Gas is unable to locate their 12" gas line running East/West in the WB lanes of North Ave near the Eastern limits of the project due to an apparent faulty tracer wire. | [5 empty] | Yes | On the 3rd day of hydro excavating, apparently WE Gas discovered they could increase voltage to the tracer wire and use a higher frequency to locate the gas main. Hydro excavation ended and the gas main was never physically seen/located. | Contractor stopped work at current location and moved to another location |  | Other | 6 working days passed before reliable locate marks were provided. | Other | 6 working days passed before reliable locate marks were provided and storm sewer could continue. | Excusable - Non-Compensable Delay |  |  | 8/12/22 Michels informed the Department that WE Gas is unable to locate their 12-inch gas main running in the WB lanes of North Ave at the Eastern limits of the project (between Denny's Drive and the UPRR bridge). 8/15/22 - 8/17/22 WE Gas and hydro excavator X-pose trying to locate the 12-inch gas line. They attempted numerous locations and excavated to a depth of approximately 14'. Excessive ground water made excavation difficult. Wednesday they brought a PVC pipe to the site to hydro excavate inside of in hopes they could control the ground water better. By the end of the 3rd day, 8/17/22, they still were not able to find the gas main. It was reported that WE Gas figured out how to increase voltage to the tracer wire and locate the main at a higher frequency. Mike Birschbach reported the afternoon of 8/17/22 that they have given up trying to physically locate the line and are confident that their higher frequency locate is accurate. 8/18/22 Brian Perz's DWR: 12:25pm I spoke with Mike Berg who confirmed the gas main has never been exposed. The Utility locators are now saying they are 100% confident in their locate signal and will not be exposing the line. Apparently the locator says the line is 18' deep. Hoffman has moved forward with storm sewer installation.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 13 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 08/12/2022 | 08/23/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Other | It took AT&T 10 working days, including Saturdays, to lower the communication lines out of conflict with proposed subgrade. | Other | 10 working days including Saturdays | Excusable - Non-Compensable Delay |  |  | 8/12/22 The communication line listed in the Special Provisions as " beginning at a manhole at Station 120NO+10, 11’LT and running northerly to a pull box at Station 120NO+07, 60’LT where it turns and runs easterly to Station 121NO+03, 60’LT and then turns and runs northerly to beyond the project limits. This line will remain in place without adjustment." has been found to be in conflict with the proposed subgrade. There is also a vault in the Northern slope of North Ave that these lines run to that has been buried by Hoffman topsoil. 8/15/22 Brian Perz's DWR: 11:20am I returned to the East limits on North Ave where Jay Bulanek, an IHC representative, Mike Birschbach, and Mike Berg were discussing the AT&T line that crosses the WB lanes around 120NO+10. The group seems to believe the AT&T lines that run East from a manhole on the North side of North Ave behind proposed sidewalk are also too high. Jay is lining up IHC to lower the four conduits that cross the WB lanes of North Ave, along with the lines that turn and run East. Best case scenario is IHC's Digger's Hotline ticket clears by Thursday and work could being. I told Jay that the WB lanes are high priority because Hoffman is held up for finishing subgrade cuts and stoning. 8/17/22 DOT was informed by AT&T that lowering the lines may not begin until Monday the 22nd. The communication vault on the North side of North Ave has been uncovered and is heavily damaged. 8/22/22 8:16am Email from Jay Bulanek of AT&T to Mike Berg of Michels: "Our contractor IHC will be on site today to lower the conduits in the road and the cables along the berm. We do not anticipate this taking more than 2 days to complete the adjustments, as long as we can get a replacement structure for the damaged handhole. This adjustment might need to take place in stages where we lower and protect the cables and utilize the damaged vault for temporary and then return to replace the structure when the new one is available." Mike Birschbach confirmed AT&T lowered the lines in conflict on Monday 8/22 and Tuesday 8/23. Project subgrade cutting could commence Wednesday 8/24.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 14 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | We Energies | Gas/Petroleum | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 06/20/2022 | 07/01/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Other | 12 calendar days | Other | Contractor is claiming 6 working day delay. | Excusable - Non-Compensable Delay |  |  | Gas main and gas service conflicts were discovered on 6/20/22 East and West of 115th St on the North side of North Ave. Greg Dulka sent a summary email to WE Energies, DOT, and Contractors. Brian Perz's 6/21/22 DWR: 7:45am I walked over to the North side of 115th St and North Ave where WE Energies, Hoffman, and Greg Dulka were locating gas lines. It appears a gas line running East/West on the North side of North Ave may be above subgrade, along with numerous laterals to the homes on the North side of North Ave between 115th St and 114th St. I spoke with Dulka and we agreed we will let WE Energies perform their investigation and determine what actions they need to take. I called Mike Birschbach to inform him that WE Energies was on-site. 6/21/22 More gas conflicts were discovered farther East to 114th St. Greg Dulka sent an email informing all parties. Hoffman exposed gas conflicts at 8 locations, 103NO+12.46 47.784' LT, 103NO+56.66 47.978' LT, 105NO+17.53 42.390' LT, 105NO+76.43 44.664' LT, 106NO+34.92 12.143' LT, 106NO+87.46 59.754' LT, 108NO+01.63 50.388' LT, 108NO+50.18 50.587' LT, which range from the West side of 115th S to East of 114th St. 6/22/22 WE Energies on-site adjusting facilities. 7/1/22 WE Energies and KS Energy finished lowering gas in conflict with proposed subgrade and storm sewer. 7/5/22 KS Energy demobilized equipment.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 15 |  | 301 | RECONSTRUCTION, EXPANSION | UPI, LLC | We Energies | Gas/Petroleum | Underground | HOFFMAN CONSTRUCTION COMPANY |  |  |  | MICHELS CORPORATION |  |  |  | 07/01/2022 | 07/07/2022 | No | Yes |  |  |  |  | Yes | WE Energies Gas did not identify the need to relocate the gas facility around the proposed watermain construction in the SE quadrant of 116th St and North Ave. | [5 empty] | Yes | WE Energies Gas cut and capped the segment of gas main that was in conflict with the proposed watermain construction. | Contractor stopped work at current location and moved to another location |  | Other | Approximately 3 working days. | Other | Contractor is claiming 1 working day delay. | Excusable - Non-Compensable Delay |  |  | 7/1/22 Nick Deming of the City of Wauwatosa emailed the Department acknowledging a conflict between the proposed watermain and existing WE Energies Gas in the SE quadrant of 116th St and North Ave. Nick proposed rerouting the watermain. 7/5/22 Brian Perz emailed the City back saying the proposed reroute of the watemain will not work due to a conflict with proposed signal base SB10. Mike Berg of Michels emailed Nick Ernster of WE Gas notifying him of the gas conflict. Nick replied asking why the project was working in this quadrant because the plans they were given did not indicate any work there. 7/6/22 Phil Bielefeld provided the Construction team a timeline of permitting and when PS&E plans were issued to Utilities. His information confirmed WE Energies did not update their workplan when watermain at 116th St was added. 7/7/22 Drew Timmerman's DWR: WE Energies on site 0800 to cut the existing gas at the SE corner of 116th so that UPI can continue with the wet connection at that location. WE Energies will return once the watermain work has been completed to repair/reconnect the 2-inch gas. 7/8/22 UPI returned to install the watermain in the conflict area. 7/29/22 WE Gas/KS Energy reinstated the cut and capped gas line.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 16 |  | 301 | RECONSTRUCTION, EXPANSION | UPI, LLC | Wauwatosa Water Utility | Water | Underground | HOFFMAN CONSTRUCTION COMPANY |  |  |  | MICHELS CORPORATION |  |  |  | 07/06/2022 | 07/12/2022 | No | Yes |  | Yes | [5 empty] | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | Other | Took 6 working days to issue redesigned plan sheets | Other | Took 6 working days to issue redesigned plan sheets | Excusable - Non-Compensable Delay |  |  | 7/6/22 Contractor found the proposed watermain on the South side of North Ave at 117th St to be in conflict with the existing watermain. The City of Wauwatosa and Greaf redesigned the watermain to avoid this conflict. 7/12/22 The redesigned watermain plan sheets were issued to Michels at 4:15pm via WAF0115-GN0054. 7/14/22 Contractor returned to the area to install the redesigned watermain.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 17 |  | 301 | RECONSTRUCTION, EXPANSION | UPI, LLC | City of Wauwatosa | Sewer (Storm or Sanitary) | Underground | HOFFMAN CONSTRUCTION COMPANY |  |  |  | MICHELS CORPORATION |  |  |  | 06/21/2022 | 06/22/2022 | No | No |  |  |  |  | Yes | Project storm sewer installation in close proximity to existing clay sanitary pipe. Unknowingly damaged during storm sewer construction. | [5 empty] | Yes | Removed recently installed storm sewer pipe and repaired the crushed sanitary sewer. | Other | Contractor means and methods caused the issue. | 16 to 24 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | 8:10pm June 21, 2022 Bill Wehrley emailed Sean Race saying "Wauwatosa sewer crews were dispatched this evening for report of several inches of water in basement on North Ave between 114th and 115th. Sewer crews observed approximately 3-feet of surcharge at the upstream manhole at 115th street. They started jetting from the downstream manhole at 114th and pulled back mud and gravel. Jetter got stuck approximately 25-feet west of the manhole at 114th Street. We are thinking the san sewer collapsed here." "Crews are setting up a portable pump at 115th to divert san flow to the south into a different sanitary manhole." 6/22/22 The City of Wauwatosa, Michels, Hoffman, and the construction team are at 114th St and North Ave investigating the reported sanitary sewer backup. The City has a pump setup at 115th St and is bypass pumping the sanitary sewer in the EB lanes of North Ave to a sanitary manhole on 115th St South of North Ave. It appears the installation of watermain or storm sewer could have damaged the existing sanitary sewer. The City crew has been on site since last night bypass pumping. Chuck Payant's 6/22/22 DWR: 930AM Craig D with UPI arrived on site, he mentioned that they installed watermain approximately 2 feet below the old sanitary line at this location. 10AM Survey Mike with V2G showed up and laid out as-built location of watermain in relation to the area they thought the break was. 1100AM Locator showed up to mark utilities. 1130AM Crew showed up to begin work. 1 operator, Excavator Cat 308-E2CR and 1 foreman. Craig D on site. 1200PM 2 additional laborers and Honda Foreman ATV with trailer arrived 1230PM Exposed sanitary sewer at location 15’ west of manhole. Broke into pipe and you could see storm sewer bedding material and the jetting hose. Foreman shined flashlight down pipe and could see at least another 20’ 1PM P525 exposed and it was clear that the storm sewer excavation for pipe completely removed the sanitary sewer pipe and installed pipe and bedding material through the sanitary completely blocking flow of sanitary. Damage was done during Hoffman’s installation of the storm sewer crossing P525. Pipe bedding material visible approximately 10" below bottom of 12" concrete storm sewer pipe. Appears a 4' section of 8" sanitary clay pipe was scooped out during storm sewer installation. About 35-40 feet of jetting hose stuck, not 15 feet like Wauwatosa was saying. 26’ feet of existing 8” clay pipe removed and replaced to repair. 2PM Finished connections with ferncos and 8” PVC. 2 Ferncos (clay to plastic type), 26’ of 8” PVC SDR35. The property that reported the sanitary backup was 11411 W. North Ave.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 18 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 10/08/2022 |  | No | No |  |  |  |  | Yes | Kevin Kaufman of Hoffman explained to Brian Perz of DOT that Hoffman requested utility locates from USIC on Monday 10/3/22. However, Hoffman did not inform USIC that the weekend's excavation would extend across all SB lanes of Mayfair Rd. Therefore, fresh utility locate markings were not painted above the AT&T communication ducts on the left side of SB Mayfair Rd. | [7 empty] | Other | The Contractor encountered the AT&T ducts and continued work on storm sewer manhole N2211. The ducts were tied to temporary barrier wall to suspend them from interrupting the excavated area for storm sewer work. | [7 empty] | The AT&T communication ducts in the SB left lane of Mayfair Rd just North of the freeway bridge were encountered by Hoffman excavation for the very large storm sewer manhole N2211. Hoffman's emergency Digger's Hotline ticket #20224125766
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 5 |  | 301 | RECONSTRUCTION, EXPANSION | UPI, LLC | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/01/2022 | 04/01/2022 | Yes | No | [15 empty] | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | Digger's Hotline ticket numbers 2022110405 & 2022130481 Chuck Payant's 4/1/22 DWR: Utility Report: Around 215PM I noticed UPI crew had hit a gas main at the intersection of 116th Street and North Ave. We Energies and the Fire department were on site around 220PM. I called Brian Perz at 2:32PM to notify the project team that the contractor hit a gas main. The approximate location of the hit was 100NO+79, 82'LT. 3". The gas line that was hit was not marked out. The gas line that runs parallel to this line was marked out about 15' to the west. UPI crew stayed on site and excavated out around the gas repair area and set a trench box for We Energies to work in. Approximately 4:15PM the gas was repaired and turned back on. Email from Craig Dretzka of UPI: From: Craig Dretzka &lt;craig@upiconstruction.com&gt; Sent: Thursday, April 7, 2022 9:52 AM To: Chandler Niemann &lt;cniemann@hoffcons.com&gt; Subject: RE: 1060-33-84 North Ave Gas Utility Hit 4/1/2022 Chandler, The gas main was marked. It was however 8’ off the location marks provided. These are the tickets involved: 2022110405 2022130481
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 6 |  | 301 | RECONSTRUCTION, EXPANSION | HOFFMAN CONSTRUCTION COMPANY | AT&T Wisconsin | Communication Line | Underground | [8 empty] | 04/26/2022 | 05/04/2022 | No | No |  |  |  |  | Yes | AT&T duct package was relocated in 2021 in preparation for North Ave roadway construction. AT&T claims they followed their relocation permit, however it resulted in a conflict with proposed storm sewer inlet N518 in the NE quadrant of North Ave and 114th St. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Email from Greg Dulka of Michels the day the conflict was discovered: From: Greg Dulka &lt;gdulka@michels.us&gt; Sent: Tuesday, April 26, 2022 3:52 PM To: BULANEK, JAY C &lt;jb5175@att.com&gt;; Perz, Brian - DOT &lt;Brian.Perz@dot.wi.gov&gt;; Birschbach, Michael P - DOT &lt;Michael.Birschbach@dot.wi.gov&gt;; Drew J. Timmerman, PE, PS &lt;dtimmerman@kapurinc.com&gt;; Payant, Charles J - DOT &lt;Charles.Payant@dot.wi.gov&gt; Cc: kkaufman@hoffcons.com; Chandler Niemann &lt;cniemann@hoffcons.com&gt;; Tony Straseske &lt;TStrases@michels.us&gt;; Branko Djuric &lt;bdjuric@michels.us&gt;; Lucas Doxtater &lt;ldoxtater@michels.us&gt;; Michael Berg &lt;mberg@michels.us&gt;; WCook@HoffCons.com Subject: N518 and AT&T Conduits Conflict Good afternoon, As discussed, there are multiple AT&T conduits running in the north / south direction on 114th Street just north of North Ave WB at approximately 100 TS + 89.10, 15’ RT. These conduits are directly in conflict with N518, a storm sewer structure that Michels needs to install at this location to progress the project. The conduits were shot at elevation 751.5, and the base of N518 is to be installed at elevation 751. Below is a construction drawing showing the proposed N518 structure and the AT&T telephone line highlighted red for reference. Please advise on a direction forward. Brian Perz DWR from 4/27/22: 10:09am Dulka called and said that Jay Bulanek is on 114th St to look at the newly discovered AT&T duct conflict with proposed inlet N518. Birschbach was not in the area so I stopped out to discuss the conflict with Dulka, Jay, Jay's Sub, Kevin with Hoffman, Drew, and Chuck. AT&T will lower and move the duct package to the West of the proposed inlet. We discussed the importance of getting a new hotline and making sure the new water lateral running to the NE quadrant is exposed carefully. Brian Perz DWR from 5/4/22: 12:34pm Jay Bulanek from AT&T called and asked if we could meet him on 114th St because IHC has excavated the duct package in conflict with proposed storm sewer inlet N518 and they would like survey confirmation of the inlet location. Koel, Chuck, and I made our way out to 114th St. Koel shot flowline of the proposed inlet and Chuck and I measured the deck of inlet N518 which was on-site. We informed Jay and his subcontractor that they need to be a minimum of 45 inches away from Koel's flowline marking. IHC worked to move the duct package to the West of Koel's mark. Vertical elevation will be very close to the proposed storm sewer pipe so Chuck and I measured the pipe opening in the structure to confirm the pipe could be propped up with a brick to gain every inch of clearance possible. Chuck and I discussed the orientation of the deck for N518 and propping the pipe up with a brick with Schindelholz so that Hoffman maximizes all space available when the inlet structure is installed.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 7 |  | 301 | RECONSTRUCTION, EXPANSION | HOFFMAN CONSTRUCTION COMPANY | Verizon | Communication Line | Underground | [8 empty] | 05/23/2022 | 05/23/2022 | Yes | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | 5/25/22 10:30am Mike Birschbach informed me that on Monday 5/23/22 Greg Dulka from Michels called him to report a fiber optic line hit. Hoffman was excavating for the west abutment of the NB 41 exit ramp to Mayfair Rd, ramp MA, B-40-877, and hit a fiber line. It was discovered later that day that the fiber was dead and relocated as part of a previous utility conflict last year during the construction of the SB 41 bridge over Mayfair Rd, B-4-876. Mike confirmed the dead fiber belonged to Verizon and was not previously removed because it was frozen in the conduit this past winter. Mike also discovered that the utility locator was marking the old fiber line and not the recently relocated line. Hoffman excavation proceeded once the line was confirmed dead.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 8 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY |  |  |  | ARROW-CRETE CONSTRUCTION, LLC |  |  |  | 01/31/2022 | 08/11/2022 | No | No |  |  |  |  | Yes | AT&T manhole cover will be in conflict with proposed curb and gutter on WB North Ave at 114th St. | [5 empty] | Yes | The manhole casting in the WB direction of North Ave that is in conflict with proposed median curb and gutter near 114th St will be corbeled to the North 6 to 10 inches to avoid curb head. | Other | Will be adjusted later this construction season. | Other | Cannot resolve the issue until later this construction season. | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Brian Perz 2/1/22 DWR: 12:58pm I spoke with Jay Bulanek about the AT&T facilities in North Ave. The manhole casting in the WB direction of North Ave that is in conflict with proposed median curb and gutter near 114th St will be corbeled to the North 6 to 10 inches to avoid curb head. Jay understood it will fall in the pan of the curb and gutter. I explained that I would prefer not to modify the proposed curb design. He will work with Michels as pavement removals begin. AT&T will remove and plate the necessary castings and then adjust them to final grade in coordination with our team, Michels, and the curb & gutter operations. Brian Perz 8/11/22 DWR: 10:30am I walked North Ave to the freeway area. AT&T's adjustment crew is on site raising their manhole casting to the pan of curb in the WB median near 114th St. Birschbach was on site with them.
20201013001 | WISC 2020466,467, WISC 2019728 | 1060-33-84 | Zoo Ic, Ush 45; Swan Blvd To Burleigh Street | SE | Milwaukee | USH 045 | Jason.Zembroski | CGC, INC. | Michael.Birschbach | 9 |  | 301 | RECONSTRUCTION, EXPANSION | MICHELS CORPORATION | AT&T Wisconsin | Communication Line | Underground | HOFFMAN CONSTRUCTION COMPANY | [7 empty] | 07/26/2022 | 07/29/2022 | No | Yes |  |  | Yes |  |  |  |  | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | The evening of 7/26/22, communication ducts were found to be above subgrade in the median of North Ave, East of 116th St. 7/27/22 Michels sent the following email: Last night, Hoffman encountered a conflict with an AT&T conduit during their excavation on North Avenue at the intersection of 116th Street (approximately STA100NO+33, 12.7’ LT). These conduits extend east along North Avenue out of a utility manhole at the intersection. Throughout the day today, Hoffman encountered a second conflict extending north along 116th Street coming from the same manhole structure (see attached photo). Mike from V2G shot the conduits (see attached) and they are roughly 0.5ft to 0.6ft above subgrade. AT&T was contacted this morning and verified these lines are live and just installed on their relocation project. IHC arrived this afternoon to investigate. There is about 20ft of the “northbound” conduit that needs to be lowered and about 20-30ft of the “eastbound” conduit that needs to be lowered. Could you confirm that this is the route we want to go to resolve the conflict? AT&T is estimating 7-10 days to adjust these lines. This may delay our progress on North Avenue, and we will keep you apprised as the work progresses. 7/28/22 The Department requested any survey data that the Contractor collected. Hoffman provided survey data and the Department plotted it and compared it to proposed subgrade. The Department sent the following email to the Contractor: Based on the information provided, it appears the line that runs North from the median is not in conflict with proposed subgrade. The Department approves placing less than the proposed 16 inches of Select Crushed Material in the area of the initial shots provided (near the median curb/flange/nose) to avoid conflicts with the AT&T conduits. Hoffman replied with the following: Please confirm that DOT is changing the typical section of the roadway to avoid utility conflicts in this area. 7/29/22 The Department closed the issue with the following email: Please consider this email official confirmation that the Department approves modifying the typical section to avoid conflict with the AT&T duct that runs East/West along the WB median curb on North Ave, East of 116th St. An example marked up typical section was included with the email. Jay Bulanek from AT&T sent Brian Perz a text message confirming IHC did not install the lines in conflict per the approved work plan. Jay stated they were approximately 3'-7" shallow from the proposed conduit profile.
20201110018 | wisc 2020539 | 2440-09-70 | Washington Ave, City Of Racine; Roosevelt Ave To West Blvd | SE | Racine | STH 020 | Brian.Hans | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 1 |  | 303 | RECONSTRUCTION, PRESERVATION | STARK PAVEMENT CORPORATION | We Energies | Electricity | Overhead | EDGERTON CONTRACTORS, INC. | AT&T Local Network | Communication Line | Overhead | D K CONTRACTORS, INC | Charter Communications | Communication Line | Overhead | 03/03/2022 | 06/09/2022 | No | Yes | [5 empty] | In accordance with Special Provisions all WE Energies work was to be completed prior to construction. | [6 empty] | Contractor worked in other of project and around the conflict at reduced productivity until WE Energies pole and associated work was completed. Contract time was extended by 5 days to 12/10/2021. | Contractor stopped work at current location and moved to another location |  | Other | Between project leader and WisDOT utility coordinator, more than 24 hrs were spent dealing with this issue. Total combined time is closer to 40-50 hours. | Other | Conflict caused adjustments to contractors work to some extent for 3 months. Work was ongoing, while issue was being resolved. | Excusable - Non-Compensable Delay |  |  | WE Energies was delayed in replacing pole in the NW corner of West Blvd and STH 20. The delay was caused by the unexpected need to install a composite pole. WE Energies completed installation of the pole and moved their facilities to the new pole by 3/24/2021. It took the next 12 weeks for the underbuilds (ATT Local, Charter, Crown Castle, and Midwest Fiber Network) to complete their respective moves. ATT needed to move first, but was delayed by the need for a special drill bit needed for the composite pole. Most overheads were moved to new pole by the end of April, but some work lagged behind mostly pertaining to the removal of guy wires. WE energies had all old poles removed by 6/9/2021 Contractor was able to continue working during this time, but staging at West Blvd was adjusted to accommodate the utility work and keep project moving. Contract time was extended by 5 days for this conflict.
20201110027 | wisc 2020549 |  |  | NC |  | STH 022 | Dan.StPierre | POINT OF BEGINNING, INC. |  | 2 | 11/10/2022 | 305 |  | VINTON CONSTRUCTION COMPANY | CenturyLink | Communication Line | [9 empty] | 06/14/2022 | 06/14/2022 | No | Yes |  |  |  |  | Yes | Vinton was excavating and installing culvert at 404+87 and encountered the Wautoma Airport communications line that was supppoed to be relocated vertically deeper than it was. Vinton was able to work with Centurylink to dip back up station and down station to create slack and lay the line deeper to allow the culvert endwall to be installed. |  |  |  | Yes |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | Vinton was excavating and installing culvert at 404+87 and encountered the Wautoma Airport communications line that was supppoed to be relocated vertically deeper than it was. Vinton was able to work with Centurylink to dip back up station and down station to create slack and lay the line deeper to allow the culvert endwall to be installed.
20201110027 | wisc 2020549 |  |  | NC |  | STH 022 | Dan.StPierre | POINT OF BEGINNING, INC. |  | 2 | 11/10/2022 | 305 |  | VINTON CONSTRUCTION COMPANY | CenturyLink | Communication Line | [9 empty] | 06/09/2022 | 06/09/2022 | Yes | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  |  | Vinton was excavating for the temporary stream diversion at 404+87 and came across the abandoned line. I spoke with Steve Bishop (Centurylink) and he assured me that that the new line was bored deep under the existing culvert at 404+87 and will not be a conflict.
20201110027 | wisc 2020549 |  |  | NC |  | STH 022 | Dan.StPierre | POINT OF BEGINNING, INC. |  | 2 | 11/10/2022 | 305 |  | VINTON CONSTRUCTION COMPANY | CenturyLink | Communication Line | [9 empty] | 06/10/2022 | 06/10/2022 | Yes | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | 08 to 16 hours |  | Digger&apos;s Hotline |  |  | Vinton was excavating for the temporary stream diversion at 404+87 and hit the unmarked Centurylink fiber optic on east side of STH 22. The fiber was repaired in under 10 hours after it was determined where it was hit
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 14 | 03/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | CenturyLink | Communication Line | Underground | [8 empty] | 03/03/2022 | 03/10/2022 | Yes | No | [10 empty] | Yes |  |  |  |  | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  |  | CenturyLink Fiber was being marked in direct conflict with bridge piling. CenturyLink As built and easement stated they were in the Railroad right of way and not in conflict with the bridge construction. With the fiber being 20-40’ deep CenturyLink decided to place a new fiber since they could not properly locate the existing fiber. Even after replacement digger hotline continually marked the old line. Since the line is marked the contractor can not proceed properly with his work.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 16 | 03/14/2022 | 302 | RECONSTRUCTION, EXPANSION | LUNDA CONSTRUCTION COMPANY | Charter Communications | Communication Line | Underground | [8 empty] | 01/04/2022 | 01/14/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor delayed start of work |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter’s new duct wondered about 2.5’ north of required running line. This placed the duct in conflict with the piling for the bridge. Charter had to excavate duct 10’ deep and move duct.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 17 | 04/26/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/04/2022 | 04/07/2022 | No | No |  | Yes | [7 empty] | Yes |  |  | ATT had a copper crossing on 60th Avenue that was not shown on the work plan. DOT contractor has to work around copper line until line was relocated. | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 18 | 04/26/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/06/2022 | 04/08/2022 | No | No |  | Yes | [7 empty] | Yes |  |  | Charter had Pedestal and service line on 60th Ave. The line was not show on the work plan or Identified as a conflict. Line was in conflict with roadway cuts and back of curb. Line was moved and lowered in place. | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 19 | 04/26/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/04/2022 | 04/11/2022 | No | No |  | Yes | [6 empty] | Yes |  |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter had crossing on 60th Ave that was not shown on the work plans. The line was in the roadway cut. Contractor worked around line until it was lowered in place.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 20 | 06/28/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 05/18/2022 | 05/20/2022 | No | No |  | Yes |  |  |  |  | Yes | [6 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Spectrum line crossed 70th WB Entrance ramp, the Line was following the approved work plan. Back of Curb cut was reduced to maintain 18 inch clearance of line.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 21 | 06/28/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 06/02/2022 | 06/24/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT Duct in conflict with storm sewer from structure 2907 to 2923. ATT had to lower significant section of clay duct. Duct was not originally identified as a conflict.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 22 | 06/28/2022 | 302 | RECONSTRUCTION, EXPANSION | ZIGNEGO COMPANY, INC. | Windstream KDL, LLC | Communication Line | Underground | [8 empty] | 06/01/2022 | 06/02/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Windstream handlhole was located in sidewalk. Windstream needed to relocate in terrace between sidewalk and curb.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 23 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Electricity | Underground | [8 empty] | 04/08/2022 | 04/11/2022 | No | No |  | Yes | [5 empty] | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | 1.48 Difference between Subgrade cut that was moving parallel with 60th avenue. Existing line was not called out for relocation on WE Electric original plans.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 24 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 03/14/2022 | 03/17/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter Coax line was not identified on Charter Communications plans. Charter drilled in a new Coax service.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 25 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/07/2022 | 04/08/2022 | No | No |  | Yes |  |  |  |  | Yes |  | Yes |  |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Musson Bros. Clipped an ATT line crossing 73rd. ATT repair team fixed the damaged line. ATT protected the line before Zignego began laying down breaker run.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 26 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/08/2022 | 04/11/2022 | No | No |  |  | Yes |  |  |  | Yes | [6 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT Relocated line was .99 Below subgrade on the East side of 60th avenue. ATT did not relocate this line lower in place.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 27 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/08/2022 | 04/14/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT fiber was not shown in plans. The fiber was lowered in place crossing 60th avenue East to West.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 28 |  | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/08/2022 | 04/14/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Spectrum Plans were outside DOT jurisdiction. Plans were not provided to DOT in this area. Communication line was lowered in place.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 29 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/08/2022 | 04/11/2022 | No | No |  | Yes | [5 empty] | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | WE Gas test stand in conflict with B.O.C. cut with a .23 Difference. WISDOT team designed around the facility.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 30 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/19/2022 | 04/20/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT spliced their service into an old pole location. ATT Exposed the cable and moved it North to get outside of Cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 31 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | ZIGNEGO COMPANY, INC. | Charter Communications | Communication Line | Overhead & Underground | [8 empty] | 04/21/2022 | 04/22/2022 | No | No |  | Yes | [8 empty] | Yes |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter down guy was in the middle of a sidewalk slab. Down guy was not identified in Charter plans. Down guy/anchor was discontinued and cut.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 32 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/19/2022 | 04/21/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter Coax riser had a large loop at the bottom of the WE power pole. Spectrum exposed their coax and relocated it outside the B.O.C. Cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 33 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/19/2022 | 04/20/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT had a service drop that looped South into proposed roadway cuts. ATT exposed the service drop line and trenched it to the north getting outside of road cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 34 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 06/08/2022 | 06/15/2022 | No | No |  |  | Yes | [6 empty] | Yes | Yes |  |  | Other |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | ATT had 3 pedestals that needed to be relocated outside the B.O.C. Cuts before Musson Brothers completed Excavation common. 1 pedestal was discontinued. 2 pedestals were relocated outside of B.O.C.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 35 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 05/31/2022 | 06/20/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Other |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Charter has 3 pedestals that needed to be relocated outside of the B.O.C. cuts before Musson begins Excavation common. All 3 pedestals were relocated outside of the B.O.C. cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 36 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 06/20/2022 | 06/30/2022 | No | No |  | Yes | [6 empty] | Yes | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT did not show relocations in their work plan. ATT fiber ran East and West with Storm Sewer trunk line in the West bound Lanes. ATT relocated their facilities further South outside of the Storm Sewer Trunk lines.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 37 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Communication Line | Underground | [8 empty] | 05/12/2022 | 05/23/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | WE gas was 1' 1/2" into a storm sewer pipe. WE gas discontinued the existing line. WE gas relocated the facility out of the storm sewer pipe with a new bore operation.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 38 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/11/2022 | 04/15/2022 | No | No |  |  | Yes |  |  |  |  | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | WE gas did not relocate near the North match line of 60th avenue. WISDOT team designed around the facility and did not complete their full 2' B.O.C. Cut.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 39 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION |  | Charter Communications | Communication Line | Underground | [8 empty] | 04/04/2022 | 04/30/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor delayed start of work |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter service line crossed 60th avenue. Line was in conflict with road cuts. Charter Relocated the facilities by a new bore operation across 60th avenue.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 40 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Windstream KDL, LLC | Communication Line | Underground | [8 empty] | 05/04/2022 | 05/09/2022 | No | No | Yes | [8 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Windstream plans showed fiber outside the B.O.C. cuts. Line was in conflict with B.O.C. cuts. Facilities were relocated outside of Roadway cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 41 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/27/2022 | 05/03/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT fiber line was in conflict with subgrade cuts following the radius on 70th avenue and 75th St. ATT lowered the line in place to get out of conflict.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 42 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/27/2022 | 05/05/2022 | No | No | Yes | [8 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT Fiber was not shown on project plans. ATT lowered the line in place to get out of conflict with roadway cuts.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 43 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 04/27/2022 | 05/06/2022 | No | No |  |  | Yes | [7 empty] | Yes |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT manhole needed to be wrecked out prior to Storm sewer getting in structures in. ATT discontinued manhole and wrecked it out.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 44 | 07/14/2022 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/27/2022 | 05/09/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Charter riser was spliced in at the old pole location. Charter line was exposed and relocated North in the trench to move under proposed side walk and get outside of Roadway Cuts.
20210810010 | wisc 2021438 | 5808-00-73 | Reedsburg - Lyndon Station; Sauk County Line To Cth J | SW | Juneau | CTH HH | Jamie.Brandt | TEAM ENGINEERING, INC. | Richard.Olson | 1 | 08/24/2022 | 201 | RECOND (INTERSECTION/WIDEN/SHOULDER) | GERKE EXCAVATING INC | Frontier Communications | Communication Line | Underground | [8 empty] | 07/22/2022 | 08/24/2022 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Other | Time to resolve the conflict is not yet determined | Other | Delay time is not determined | Excusable - Compensable Delay |  | Yes | Telephone line that runs from station 14+00 to 19+00 LT is in conflict with the cross section earthwork . The line was located and potholed in several locations. The elevation was checked with GPS and the line in conflict. Gerke can not continue grading is this area until the line is moved. The special provisions state the the line is not in conflict.
20210810011 | wisc 2021439, 440 | 5845-01-76 | Stoughton - Madison; Sth 138 To Silverado Dr/Hoel Ave | SW | Dane | USH 051 | Dylan.Douglas | JT ENGINEERING, INC. | Richard.Olson | 1 |  |  | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | AT&T | Communication Line | [9 empty] | 04/13/2022 | 05/02/2022 | No | Yes |  | Yes | [13 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | Communication hand hole discovered in conflict with grading operations and the location is within the proposed concrete pavement. The hand hole is quazite and should not be loaded with traffic. AT&T has been notified of the conflict on site and is working to relocate the entire facility to be outside of the roadway.
20210810011 | wisc 2021439, 440 | 5845-01-76 | Stoughton - Madison; Sth 138 To Silverado Dr/Hoel Ave | SW | Dane | USH 051 | Dylan.Douglas | JT ENGINEERING, INC. | Richard.Olson | 1 |  |  | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | AT&T | Communication Line | [9 empty] | 04/21/2022 | 05/15/2022 | No | Yes |  | Yes | [13 empty] | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | Multiple utility lines in conflict with proposed storm sewer. Storm sewer work is required during nighttime operations with limited closures.
20210810011 | wisc 2021439, 440 | 5845-01-76 | Stoughton - Madison; Sth 138 To Silverado Dr/Hoel Ave | SW | Dane | USH 051 | Dylan.Douglas | JT ENGINEERING, INC. | Richard.Olson | 1 |  |  | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | AT&T | Communication Line | [9 empty] | 04/13/2022 |  | Yes | No | Yes | [14 empty] | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | It was determined that the locator did not have the appropriate maps or means to mark a utility facility along the south side of US 51 near Hoel Ave. The facility is called out for relocation (lowering) in the contract special provisions, but is not actually shown anywhere in the plans. The located stated that he has never located that line in the field. AT&T confirmed the line exists and needs to be lowered. They are working on a means to locate the facility.
20210810011 | wisc 2021439, 440 | 5845-01-78 | Stoughton - Madison; Roby Road Intersection | SW | Dane | USH 051 | Dylan.Douglas | JT ENGINEERING, INC. | Richard.Olson | 1 |  |  | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) | JAMES PETERSON SONS, INC. | AT&T | Communication Line |  |  | TDS Metrocom LLC | Communication Line |  |  | Charter Communications | Communication Line |  | 06/17/2022 |  | No | Yes |  |  | Yes |  |  |  |  | Yes |  | Yes |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | Several conflicts with the subject utilites and grading/storm sewer operations. Utilities were relocated as part of the Trans 220 process, but were relocated incorrectly.
20210810018 | n/a | 1170-20-61 | Minocqua - Manitowish; Trout River Culvert Replacement | NC | Vilas | USH 051 | Jason.Hribar | MSA PROFESSIONAL SERVICES, INC. | David.Rogers | 1 |  |  | NEW BRIDGE | SHEET PILING SERVICES LLC | CenturyLink | Communication Line | [9 empty] | 04/28/2022 | 04/29/2022 | No | Yes | Yes | Yes |  |  |  |  | Yes |  |  |  |  | Yes | Contractor changed cofferdam sheeting driven depth over utility upon direction of utility representative based on assumed utility depth (off locating instrument). | Contractor productivity rate was affected |  | 04 to 08 hours |  | 01 to 04 hours |  | Other |  |  | 04/28/2022: Utility issue: 8:00 am looking at structure layout, a phone line not shown on the plans was determined to conflict with upstream wing construction (on both north and south sides, wings #1 & #4), based on USIC locates. This utility is owned by Century Link (now call Lumen). The south wing on the upstream side will cover this utility by 1-foot, but the north wing will not cover this utility. This issue is made worse by the cofferdam sheeting required to be installed beyond both wings. This utility was located between the existing USGS gauge station and the proposed structure. 8:15 am look at this issue with SPS superintendent Kevin Weber, and he agreed this is a problem, as unable to pothole this utility due to its proximity to the river and the anticipated groundwater. 8:30 am called Ben Baker with Century Link, and they said they would send a guy out to the site to determine what is going on with utility. 8:40 am WisDOT Project Manager Nick Voss notified, and we discussed that SPS does not want to take liability should this phone line be wrecked with their sheeting installation. 10:30 am received a call from Jeremy Sisko from Century Link requesting a plan and proposal for this project (as they feel that they did not receive this plan for review). 10:40 am emailed Jeremy (and CC’d Nick Voss) plan, proposal, and DT2236 (showing that they received and reviewed this plan). 2:00 pm Century Link technician Rich Gregorich onsite to try to relocate the makings (Century Link utility in conflict). It should be noted that there are (7) Century Link lines marked on the northeast quadrant, but the plan only shows (5). 3:05 pm Rich was finally able to locate this utility and it was determined to be a LIVE 144 fiber, ranging between 126 and 110 inches deep as measure at the top of bank at the river. Stations and outs off the “500” alignment were recorded (with Musson GPS) for the marks placed by Rich and were as follows: near SE bridge corner 559+80 41.7’RT & near NE bridge corner 560+18 40.8’ RT. Rich then contacted his boss (Jeremy Sisko) and the resolve to this issue was pushed to Ben Baker. At 4:30 pm reached out to Ben Baker and discuss the issue onsite. Based on these conversation, Ben Baker plans to be onsite ~10:00 am tomorrow (04/29) to try to replicate his locaters results and determine a “safe” driving depth for the contractor. It should be noted that Century Link located this utility in question ~18-inches west of the USIC marks, making the issue a little worse. Both Nick Voss and Kevin Weber kept informed of the progress resolving this issue. This utility does not appear to conflict the proposed wing pile at this time. SPS superintendent Kevin weber feels that they will be able to pull up their proposed 20-foot sheeting to avoid this number somewhat, but needs to know what allowable depth Century Link feels is acceptable. 04/29/2022: Utility issue: 10:15 am Ben Baker onsite from Century Link to determine issue with cofferdam sheeting and their fiber optic. After review of the depth, requested contractor wait till Monday when they can have a crew on stand-by should replacement be necessary. SPS superintendent Kevin Weber said this was not a preferred option. After a half an hour conversation with Ben Baker’s boss, they lined up a crew for standby and allowed the contractor to drive sheeting to a depth of 7-feet over their fiber. Ben Baker onsite all day ~2:30 pm when remainder of sheets were complete over their utility. No issues with cutting their utility during sheet installation, therefor this issue is over with ZERO down time from the contractor. Contractor slowed operation to give time to resolve issue but is NOT requesting compensation.
20210914004 | wisc 2021472 | 5436-00-71 | Sth 33 - Ih90; Cth O To Wolter Road | SW | La Crosse | CTH M | Matt.Palkowski | WISDOT | Richard.Olson | 1 |  | 201 | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) | GERKE EXCAVATING INC | Charter Communications | Communication Line | [9 empty] | 04/06/2022 | 04/06/2021 | No | Yes | Yes |  |  | Yes |  |  |  | Yes | [5 empty] | Other | There wasn't any impact on schedule or operations. | Less than 01 hour |  | Less than 01 hour |  | Other | Gerke didn't get paid to install a temporary pipe since it was eliminated. Contract time was not affected. |  | Charter relocated their communication line in the way of temporary pipe at inlet A3.1. It was decided in the field to eliminate the temporary pipe and create a ditch that would drain from about STA 416+50 to STA 414+00. The ditch will be constructed to plan from STA 414+00 to the West. Charter used a 60% plan to relocate this utility and the temporary pipe location changed in the LET plan. However, Charter would have still struggled if they had used the LET plan because the LET plan did not include the temporary widening cross sections.
20210914004 | wisc 2021472 | 5436-00-71 | Sth 33 - Ih90; Cth O To Wolter Road | SW | La Crosse | CTH M | Matt.Palkowski | WISDOT | Richard.Olson | 2 |  | 201 | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) | GERKE EXCAVATING INC | Charter Communications | Communication Line | [9 empty] | 04/11/2022 | 04/11/2022 | No | Yes | Yes | [7 empty] | Yes |  |  |  |  | Other | No impact on schedule or operations. | Less than 01 hour |  | Less than 01 hour |  | Other | Contract time was not affected. Gerke was paid for an additional cover plate. |  | Charter Communications relocated a utility vault in the temporary widening shoulder. Gerke used a cover plate to protect the vault and proceeded to build the temporary roadway. Charter used a 60% plan to relocate their utilities, it seemed like they didn't account for the temporary widening that was provided in the 60% plan. The temporary widening was missing in the LET plan.
20210914004 | wisc 2021472 | 5436-00-71 | Sth 33 - Ih90; Cth O To Wolter Road | SW | La Crosse | CTH M | Matt.Palkowski | WISDOT | Richard.Olson | 3 |  | 201 | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) |  | CenturyLink Communications, LLC | Communication Line | [9 empty] | 04/05/2022 | 04/06/2022 | Yes | Yes | [13 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 04 to 08 hours |  | Digger&apos;s Hotline |  |  | Diggers Hotline provided confusion by locating a bunch of utilities that were not in the plan prior to 4/5. Gerke started working on inlet A3.1 and was confused why so many lines were marked. While excavating for inlet A3.1, Gerke found more utility lines that were not marked and accidently hit one of the lines. Gerke contacted Lumen, a crew come to look at the hit utility and confirmed that the facility was live. Lumen fixed the utility and left. Gerke began hand shoveling for fear of finding more unmarked utility. Gerke also called for a new utility locate with Diggers. On 4/6, the area around inlet A3.1 went from around 8 utilities marked to only having 2 utilities marked. The line that Lumen repaired on 4/5 was not marked. A Lumen rep arrived on 4/6 and cut the line the Lumen crew repaired on 4/5 and said, "The line is dead and that is why Diggers didn't locate the line." It appeared that Diggers located many dead lines prior to the excavation on 4/5 and forgot to mark the live lines. Lumen's live lines were relocated outside of our work area.
20210914004 | wisc 2021472 | 5436-00-71 | Sth 33 - Ih90; Cth O To Wolter Road | SW | La Crosse | CTH M | Matt.Palkowski | WISDOT | Richard.Olson | 4 |  | 201 | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) |  | Midwest Natural Gas, Inc. | Gas/Petroleum | [9 empty] | 05/02/2022 | 07/28/2022 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | Less than 01 hour |  | Other | Time was added to the contract so Gerke was not charged liquidated damages. Gerke stayed busy by working on other parts of the project with a small crew. |  | Gerke and the Department started talking about the potential for gas lines to be in the way of construction throughout the CTH M corridor. Midwest Natural Gas (MNG) was contacted and they wanted someone with a GPS to walk with their workers to provide excavation cut information above their utilities. La Crosse County would not provide assistance. The Project Leader for the Department made time on 5/10 to walk with MNG workers. It was confirmed on the walk that several gas service lines to houses were in the common excavation, along with the main gas line through the Wolter Road intersection. On 6/20, it was discovered that the main gas line on CTH O was in conflict with common excavation for Stages 3 and 4. Gerke had to quit working on CTH O and start working on CTH M until the gas line was moved. Gerke had to adjust their schedule on 6/28 because the gas line hadn't been moved yet. On 07/05, MNG lowered the gas line. On 07/07, Gerke resumed work on CTH O for Stage 3. MNG knows they will have to come back and lower the line for Stage 4. On 07/15, Gerke removed asphalt on CTH O for Stage 4 and resumed working on CTH M until gas line is lowered. On 07/27, MNG finished lowering the gas line. On 07/28, Gerke resumed work on CTH O for Stage 4. Note, MNG could not lower gas line until Gerke stripped the asphalt for Stages 3 and 4. The gas line needed to be lowered from STA 218+30 to about STA 211+00. The existing gas line was not in conflict from about STA 211+00 to the project limit at STA 206+00.
20210914004 | wisc 2021472 | 5436-00-71 | Sth 33 - Ih90; Cth O To Wolter Road | SW | La Crosse | CTH M | Matt.Palkowski | WISDOT | Richard.Olson | 5 |  | 201 | RECOND (IMP CURVE/GRADE/SIGHT/INTERSECT) | GERKE EXCAVATING INC | Xcel Energy | Electricity | [9 empty] | 05/25/2022 | 08/17/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | Gerke continued to work around the poles, poles were replaced by the time Gerke finished placing topsoil. | 04 to 08 hours |  | Less than 01 hour |  | Other | Contract time was not impacted. |  | On 05/25 it was discovered that more poles were potentially in the way of grading than what are listed in the Specials. A list of poles that are in conflict was sent to Xcel in an email on 05/26. The list was created by the Department using a GPS. On 07/07, Xcel met with Michels to discuss adjusting all of the poles. It was determined on 07/07 that the poles will be replaced starting the week of 07/19 because that is the soonest Michels can get the materials. Gerke will continue grading slopes on CTH M, but will wait to topsoil the slopes until all of the poles are moved. Michels was still moving poles through the week of 08/08. It was unclear when Michels completed moving the telephone poles because there wasn't any confirmation from them, but it was most likely sometime during the early part of week of 08/15. All of the telephone poles were moved by the time Gerke started placing topsoil on 08/29.
20210914010 | wisc 2021479 | 2260-08-70 | Durand Ave, City Of Racine; Kearney Ave To East Of Memorial Dr | SE | Racine | STH 011 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 1 | 04/22/2022 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/21/2022 | 04/22/2022 | No | Yes | Yes |  |  |  | Yes | The new facilities were not reflected in the plan. The new permitted location was in conflict due to the depth and size of the trench required to install new storm sewer |  | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | After utility locates were done for a storm sewer run from manhole 4 to manhole 12, it was noticed that the gas main would conflict with the storm sewer construction. The gas main was permitted and relocated after the storm sewer plan was designed, so these changes were not show in the plan. The gas main runs along Durand Ave and forms a T in the Hamilton Ave/Durand Ave intersection. This T is located within the trench area needed for the construction of the new storm sewer. The gas main also crosses with the storm sewer just W of the T along Durand Ave and just NE of the T along Durand Ave. Due to the depth of the cut needed for the new storm sewer a trench box is required to safely construct this storm sewer. Since the storm sewer is running on an angle in this area, the storm sewer trench would cross the Hamilton Ave main and the Durand Ave main within about 25 feet, making it very difficult and dangerous to work with a trench box under the main in this location. After analyzing this in the field, we have decided to redirect the water in the storm sewer run between STR 12 and STR 12A and make that run 24", so it was flowing from STR 12 to STR 12A. We would then change catch basin 12A to a 5-FT manhole, then we would install a new 24" storm sewer run from catch basin 12A to manhole 4.
20210914010 | wisc 2021479 | 2260-08-70 | Durand Ave, City Of Racine; Kearney Ave To East Of Memorial Dr | SE | Racine | STH 011 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 2 | 05/04/2022 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | City of Racine | Water |  |  |  | Sewer (Storm or Sanitary) | [5 empty] | 04/27/2022 | 04/27/2022 | No | Yes | [7 empty] | Yes | [5 empty] | Other | There was no impact on schedule or operations | Less than 01 hour |  | Less than 01 hour |  | Other | There was no delay to contract or construction time |  | The water lateral and sanitary lateral running from 1707 Durand Ave to the main in the middle of the road was in direct conflict with Catch Basins 12A and 12E, as well as the storm sewer run between them. Catch Basins 12A and 12E had to be moved 7-FT to the west to avoid this conflict
20210914010 | wisc 2021479 | 2260-08-70 | Durand Ave, City Of Racine; Kearney Ave To East Of Memorial Dr | SE | Racine | STH 011 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 3 | 05/10/2022 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | City of Racine | Water | [9 empty] | 05/10/2022 | 05/10/2022 | No | Yes |  | Yes | [5 empty] | Yes | [5 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Other | No extra time will be awarded due to this conflict but there will be additional cost for a new manhole |  | The water main running along Phillips Ave and across Durand Ave is in direct conflict with our new storm sewer trunk line. A new manhole was added in front of the main to direct the storm sewer around it.
20210914010 | wisc 2021479 | 2260-08-70 | Durand Ave, City Of Racine; Kearney Ave To East Of Memorial Dr | SE | Racine | STH 011 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 4 | 06/30/2022 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | Spectrum | Communication Line | [9 empty] | 06/18/2022 | 06/30/2022 | No | No |  |  | Yes |  |  | The utility in conflict was not placed at the depth that was called out for in the plan |  |  |  | Yes |  |  | Spectrum dropped there fiber so it is 6 feet below our base | Other | The contractor worked around the utility until the facility is relocated | Less than 01 hour |  | Less than 01 hour |  | Other | No delay since the contractor could temporarily work around the area in conflict
20210914010 | wisc 2021479 | 2260-08-70 | Durand Ave, City Of Racine; Kearney Ave To East Of Memorial Dr | SE | Racine | STH 011 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 5 | 06/24/2022 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | We Energies | Gas/Petroleum | [9 empty] | 06/24/2022 | 06/24/2022 | No | No |  |  | Yes |  |  | The gas facilities were higher than the permit called for at structure 23B and 23C in the NE corner of the Memorial Drive/Durand Ave intersection. |  | Yes |  |  |  |  | The sump of the catch basin was removed in order to place the catch basins over the gas main. The catch basins could not be moved since the conflict was longitudinal. | Other | There was no impact on schedule or operations since a solution was provided quickly | Less than 01 hour |  | Less than 01 hour |  | Other | There was no impact on schedule since a solution was provided quickly
20210914011 | wisc 2021480 | 3240-11-70 | Sheridan Rd, Vil Pleasant Prairie; Sth 165 Intersection | SE | Kenosha | STH 032 | James.Hammerle | TOKI & ASSOCIATES-MILW | Michael.Birschbach | 1 |  | OTHER | RESURF(OVLAY< 2.5 IN W/FULLDEPTH PATCHG) | INTERSTATE TREE LAND CLEARING CO & ITL | We Energies | Electricity | Overhead | [8 empty] | 06/02/2022 | 06/06/2022 | No | Yes |  | Yes |  |  | Yes | Tree Branches entangled in utility power lines. | [5 empty] | Yes | Asphlundh, utilities subcontractor, removed branches entanglement from power lines. | Other | Subcontractor stopped worked and demobilized project until utility company can resolve issue. | Less than 01 hour |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | Subcontractor demobilized until utility company could remove branches from power lines which was on 6/6/2022. Subcontractor came out and removed all of the smaller trees on 6/13/2022. Waiting on INTERSTATE TREE LAND CLEARING CO & ITL to fix their machine to remove the two larger trees at 10106 Sheridan Road.
20210914011 | wisc 2021480 | 3240-11-70 | Sheridan Rd, Vil Pleasant Prairie; Sth 165 Intersection | SE | Kenosha | STH 032 | James.Hammerle | TOKI & ASSOCIATES-MILW | Michael.Birschbach | 3 |  |  | RESURF(OVLAY< 2.5 IN W/FULLDEPTH PATCHG) |  | We Energies | Electricity | [9 empty] | 06/27/2022 |  | No | No |  | Yes |  |  |  | Overhead power lines are in conflict with the final height of monotube pole at SB13 location as shown on the plans. Relocation closer to curb line and 17' south of original location still causes a WE Energies 10ft clearance problem. | [5 empty] | Yes | Reverse mounting SB13 with SB12 at the new locations for SB12 and SB13 with removal and relocation of the telemetry equipment form the SE Utility pole to the SW utility pole will resolve the issue. The 40' monotube may have to be replaced with a 45' arm. | Other | May delay signal base setup if monotube arm issue is not resolved | [7 empty] | ee
20210914011 | wisc 2021480 | 3240-11-70 | Sheridan Rd, Vil Pleasant Prairie; Sth 165 Intersection | SE | Kenosha | STH 032 | James.Hammerle | TOKI & ASSOCIATES-MILW | Michael.Birschbach | 4 |  | OTHER | RESURF(OVLAY< 2.5 IN W/FULLDEPTH PATCHG) | PRO ELECTRIC, INC. | We Energies | Electricity | Overhead | [8 empty] | 08/01/2022 |  | No | Yes |  | Yes | [9 empty] | Yes | The two north single phase conductors across Sheridan Road were removed from the power poles since they are not being used by the utility. The south single phase conductor is to remain and continue to provide power east on 104th Street. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Other | After the two power lines are removed the contractor will be installing the vibration dampener on SB6 monotube arm. | Excusable - Non-Compensable Delay |  |  | Existing power lines going across Sheridan Road (STH 32) are in conflict with the vibration dampener on the monotube arm of SB6.
20210914014 | N/A | 1590-12-72 | Monico - Laona; Ush 45 North To Forest County Line | NC | Oneida | USH 008 | Ryan.Erkkila | COLEMAN ENGINEERING COMPANY-IRNMTN | David.Rogers | 1 | 07/21/2022 | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | WISCONSIN INTERSTATE CONTRACTING LLC | Frontier Communications of WI LLC | Communication Line | Underground | [8 empty] | 06/20/2022 | 07/21/2022 | No | No |  |  |  |  | Yes | While installing siltfence an existing fiber line was discovered laying above ground within their work area. | [5 empty] | Yes | After multiple attempts to get an answer from Frontier and little to no response or communication from them of any concern it was assume this line must be abandoned. | Other | Work was not stopped given the line appeared to be damaged by work that took place on this contract. The line was located on top of the ground within the area of siltfence install and I'm told was not hit by this subcontractor. | Other | No redesign was necessary | Other | Other than the time lost by construction staff trying to get in contact with Frontier staff, no time has been lost to construction. | Other | No impact to contact time. The work in this area has been completed aside from addressing the communication line that's still laying on top of the grass. |  | Northeast Asphalt and Musson Brothers had digger’s hotline tickets called in for this area, and the communications lines were not marked by the clear date of those tickets. NEA’s locate ticket number is 20222319866. Wisconsin Interstate arrived on site on 6/20 to install silt fence. Their foreman indicated that they found a communications line laying unburied on the slope in the grass. They went around the line with their silt fence installation. Musson showed up on 6/20 to prepare for the culvert installation, and also found the line, which after closer inspection was found to be damaged, with some of the conductors exposed and broken. Musson’s foreman indicated that many of the copper wires have corrosion or patina visible which indicated the partial break was likely pre-existing for an extended period of time prior to construction activities for this project. Musson contacted the locator to find out if the line was active. NEA's PM, Conner Jensch was told by Musson that the locator arrived on site and hooked his tracer to the broken wires at the pipe location, and painted the line back in either direction approx. 30 feet from the pipe. Musson called the locator back to return to the site the following day to attempt to help confirm whether the line is active or inactive. The locator returned on 6/21, and I spoke with him afterward by phone. He indicated that the line is connected in the pedestals and appears to be a live line. Following that conversation, Conner reached out to Frontier on 6/21. The telephone number listed in the plans for them is an inactive phone line. Conner found another number online but got routed to their call screening system, at which time the automated call back system indicated that the next available call back time slot would be on 6/24 at 11:30 am. So Conner called back in to their call center to wait on hold to speak to a representative. When Conner was finally able to reach someone, he filed a report with Frontier to let them know that their line is exposed, and that it was encountered during construction, with a potential conflict for installation of the culvert and related work, and they explained that the next available review date for their service technician to address the issue was July 12th. Frontier’s report reference number is 2348933. There are numerous other communications lines beyond the end of the culvert pipe, (marked by locators now) with other companies indicated on the flags. It’s still unclear whether the line is still active, or if the line and pedestals have been abandoned and replaced. The locator did not seem 100% certain, other than to say it is connected in some pedestals. To my knowledge, no one has notified the construction staff, or called to indicate an outage in the area, and no one has shown up from the Utility to review the situation.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 1 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | GENESIS EXCAVATORS, INC. | Village of Brown Deer | Water | Underground | [8 empty] | 04/08/2022 | 04/12/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay |  |  | City water utility was contacted on Friday afternoon and decision to offset watermain was made. Contract was issued Monday for utility work and crews completed relocation on Tuesday. Storm sewer lost 2+ days.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 10 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Spectrum | Communication Line | Underground | [8 empty] | 08/30/2022 | 06/23/2023 | No | No |  | Yes | [5 empty] | Yes | [5 empty] | Other | identified before conflict with work operations | Less than 01 hour |  | Less than 01 hour |  |  |  |  | Handhole located at approx 487+50 LT falls in plan detailed bus pad location at NE corner of STH 100/ Deerbrook Trail. Bus pad will be moved slightly east so that handhole will fall in grass; however, handhole will require height adjustment after sidewalks are placed to match terrace grading. Height adjustment anticipated to occur in 2023
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 11 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Windstream KDL, LLC | Communication Line | Underground | [8 empty] | 08/30/2022 | 10/13/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  |  |  | Less than 01 hour |  |  |  |  | Windstream line crossing found to be too high (in subgrade) during Stage 3 - anticipated to be high in Stage 5 as well. (8/30/22) Facility determined to be too high during Stage 5 excavation are needed to be lowered.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 12 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Village of Brown Deer | Sewer (Storm or Sanitary) | Underground | [8 empty] | 09/06/2022 | 10/31/2022 | No | No | Yes | [10 empty] | Yes | Facility was connect to new storm sewer system - added extra work to contract | Other | No impact to operations - added extra work to contract | Less than 01 hour |  | 01 to 04 hours |  |  |  |  | Unidentified drainage structure outfall from W. River Lane (STA 118+00 LT) was found. Plan grading would bury this outfall so project made connection to new system at Structure 241.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 13 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Spectrum | Communication Line | Underground | [8 empty] | 10/04/2022 | 03/13/2023 | No | No |  |  |  | Yes | [5 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  |  |  |  | Pedestal in conflict with sidewalk at STA 482+58 70 LT. Plan revision 5/11/22 realigned sidewalk. Facility to be relocated in conjunction with sidewalk work (anticipated in 2023) Permit (40U-364-22) issued 11/28/22 for work to be completed by Jan 26,2023 site visit 3/13/23 - pedestal appears to be moved just into terrace along inside edge of sidewalk
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 14 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | AT&T | Communication Line | Underground | [8 empty] | 10/04/2022 | 11/30/2022 | No | No |  |  |  | Yes | [5 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  |  |  |  | Handhole in conflict with sidewalk at STA 482+40 70 LT. Plan revision 5/11/22 realigned sidewalk. Facility to be relocated or height adjusted in conjunction with sidewalk work (anticipated in 2023) - Crew moved to terrace 11/30/22
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 16 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Windstream KDL, LLC | Communication Line | Underground | [8 empty] | 11/01/2022 | 11/08/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  |  |  |  | Facility at Deerwood Dr /STH 100 matchpoint was too high (into subgrade excavation). Facility was lowered below subgrade.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 2 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | ZIGNEGO COMPANY, INC. | Windstream KDL, LLC | Communication Line | Underground | [8 empty] | 04/19/2022 | 04/29/2022 | No | Yes |  |  | Yes | [10 empty] | Contractor stopped work at current location and moved to another location | [8 empty] | Windstream notified 4/19/22 that crossing at STA 484+35 Rt was at or into subgrade by 0.2 ft and would need to be adjusted. per Lori Ketter (Windstream) - 4/26/22 TM Becker should be on site today (4/26) to lower facility - clear by 4/29/22
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 4 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | OUTDOOR LIGHTING CONST CO INC | Village of Brown Deer | Water | Underground | ZIGNEGO COMPANY, INC. | We Energies | Other | Underground |  |  | Communication Line | Underground | 04/20/2022 | 05/26/2022 | No | No | Yes | Yes | [10 empty] | Investigating moving of base 3-4 feet west (unknown communication cable in the way) to avoid gas line & watermain | Other | Water utility unable to complete watermain offset due to WE Electric line proximity. Delay impacts concrete work (curb & gutter) and signal underground bases & conduit | 01 to 04 hours | [6 empty] | 4/20/22 - Vill Brown Deer water utility on site to offset watermain around future Signal Base16 NE corner of STH 57/Schroeder- while exposing other utilities they discovered WE gas directly above watermain (not as indicated on plan) and WE electric to the east (offset direction). WE electric shut down operations until line could be researched/de-energized. Unknown the impact of doing this. Project staff contacted and discover that WE gas is in conflict with SB 16 (even if water is offset).
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 5 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | ZIGNEGO COMPANY, INC. | AT&T | Communication Line | Underground | [8 empty] | 04/20/2022 | 05/24/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | Identified prior to grading operations in vicinity | Less than 01 hour | [6 empty] | 4/20/22 - AT&T pedestal identified in future ditch cut area (STA 494+00 94' RT) per cross section approx. 1' cut at existing pedestal - pedestal in future flow line
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 7 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | GENESIS EXCAVATORS, INC. | We Energies | Gas/Petroleum | Underground | ZIGNEGO COMPANY, INC. | [7 empty] | 05/12/2022 | 05/25/2022 | No | Yes |  |  | Yes |  | Yes | WE permitted work plan was not revised after designer issued plan change, which was received and acknowledged by utility. Gas main at STA 194+50 fall in bottom half of 24" RCSSP between structures 673B & 649B |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 04 to 08 hours
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 8 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Spectrum | Communication Line | Overhead | [8 empty] | 08/01/2022 | 08/29/2022 | No | No |  | Yes |  | Yes | [5 empty] | Yes |  |  |  | Other |  | 01 to 04 hours |  | Less than 01 hour |  |  |  |  | OH wire at SW corner of Donges Bay Rd & STH 57 was too low for planned signal base/pole. Signal pole style (vertical) was revised to trombone arm due to adjacent building partially blocking view of signal head. Spectrum line needed to be raised to avoid pole. Conflict would have been less (point obstruction) with original pole verses the trombone arm.
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 9 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | AT&T | Communication Line | Underground | [8 empty] | 08/26/2022 | 10/26/2022 | No | No | Yes | [12 empty] | Other | Conflict identified before work began. |  |  | Less than 01 hour |  |  |  |  | Conflict with underground facilities and Traffic Signal base SB7 at SW corner of Schroeder Dr & STH 57. AT&T facilities not shown in signal plan sheets.
20210914024 | wisc 2021441, 442 | 2565-07-70 | Green Bay Rd, Village Brown Deer; Teutonia Ave Intersection | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 15 |  | 303 | RECONSTRUCTION, PRESERVATION |  | Milwaukee Metropolitan Sewerage District | Sewer (Storm or Sanitary) | Underground | [8 empty] | 11/01/2022 | 06/05/2023 | No | No |  | Yes |  | Yes | [6 empty] | Yes |  | MMSD verified MH was abandoned and had Veolia seal lid. Contractor reshaped ditch flowline to be +/- 6" lower than lid and moved slightly to the west. | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  |  |  |  | MMSD MH at STA 98+25 LT was to be located in the new planned ditchline. Project grading will move ditchline and will require MH to be raised to finish grade. Work is outside of roadway/sidewalk and can be completed after rough grading is complete (late season 2022 or early season 2023)
20210914024 | wisc 2021441, 442 | 2565-07-70 | Green Bay Rd, Village Brown Deer; Teutonia Ave Intersection | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 3 |  | 303 | RECONSTRUCTION, PRESERVATION | ZIGNEGO COMPANY, INC. | Milwaukee Metropolitan Sewerage District | Sewer (Storm or Sanitary) | [9 empty] | 04/14/2022 | 05/03/2022 | No | No |  | Yes | [8 empty] | Yes |  |  | Other | Identified before grading operations in area | 01 to 04 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | MMSD cabinet identified to be within grading limits and future facilities (STA 102SB+50 RT) 4/20/22 - Mikki Klappa-Sullivan (MMSD) report cabinet was removed and de-energized 4/26/22 - field visit indicated cabinet removed but meter pedestal still energized
20210914024 | wisc 2021441, 442 | 2565-07-70 | Green Bay Rd, Village Brown Deer; Teutonia Ave Intersection | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 6 |  | 303 | RECONSTRUCTION, PRESERVATION |  | Charter Communications | Other | [9 empty] | 04/14/2022 | 08/02/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | Identified prior to grading operations in vicinity | Less than 01 hour | [6 empty] | Down guy anchor in future curb & gutter - need to relocate gut wire STA 102SB+50 RT
20211109003 | wisc 2022002, 003 |  |  | SW |  | STH 016 | Brandon.Patterson | WISDOT |  | 1 | 06/15/2022 | 303 |  |  | Alliant Energy | Electricity | [9 empty] | 03/30/2022 | 06/15/2022 | No | No |  | Yes | [11 empty] | Other | No Delay | Less than 01 hour |  | Less than 01 hour |  | Excusable - Compensable Delay
20211214023 | wisc 2022083 | 7570-05-64 | La Crosse - Sparta; .27 Mi E Of La Crosse R To Big Ck | SW | La Crosse | STH 016 | Maxwell.Sebesta | KNIGHT PARTNERS, LLC | Richard.Olson | 1 | 08/26/2022 | 303 | PAVT REPLACEMENT | SMITH RESTORATIONS INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 05/25/2022 | 06/27/2022 | No | Yes |  |  |  |  | Yes | No conflicts anticipated per Special Provision's note. Plan shows caution diagram in the area. Digger's Hotline was not notified early enough to verify location of gas line. After hand digging in the area, the line was too close to proposed guardrail posts and required moving. |  |  |  | Yes |  |  |  | Contractor stopped work and demobilized from project |  | 01 to 04 hours |  | Other | 33 days passed between checking on the issue with the utility owner to the relocation of the utility. | Excusable - Non-Compensable Delay |  |  | 5/25: Digger's had been called and was marked out by today. Subcontractor, Smith Restorations, met with WE Energies on site to talk about the potential conflict. 5/31: Smith met with WE Energies on site to hand dig and verify the location of the actual gas line. This is when it was noted the line needed to be moved. Various communication occurred between PE and WE Energies to check in and try and get the work completed as soon as possible. 6/27: WE Energies' subcontractor able to get on site and relocate the gas line.
20211214024 | wisc 2022106 | 1229-04-74 | I-43 North South Freeway; W County Line Rd Interchange | SE | Ozaukee | IH 043 | Brad.Bacilek | ALFRED BENESCH & COMPANY | Michael.Birschbach | 1 |  | 302 | RECONSTRUCTION, EXPANSION | HOFFMAN CONSTRUCTION COMPANY |  | Communication Line | Underground | [8 empty] | 04/07/2022 | 04/08/2022 | No | No |  | Yes | [8 empty] | Yes |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | The existing WisDOT FTMS line provided signals to the I-43/Mequon Rd CCTV Camera pole. As part of the I-43 project, this line is being upgraded/relocated along the whole corridor of I-43 inside the reconstruction footprint. After giving notice to the traffic team and STOC, TAPCO arrived on site and cut the line with an anticipation of installing a wireless modem for connectivity in the near future.
20211214024 | wisc 2022106 | 1229-04-74 | I-43 North South Freeway; W County Line Rd Interchange | SE | Ozaukee | IH 043 | Brad.Bacilek | ALFRED BENESCH & COMPANY | Michael.Birschbach | 2 |  | 302 | RECONSTRUCTION, EXPANSION |  | We Energies | Electricity | Underground | [8 empty] | 04/26/2022 |  | No | No |  | Yes | [5 empty] | Yes | [14 empty] | Storm sewer lateral for inlet 473B-S2 was in conflict with an existing 3 phase We Energies electric line on Donges Bay Rd just east of Port Washington Rd. The design changes were to re-align the new storm sewer pipe into an existing structure rather than the planned location.
20220111012 | wisc 2022115 | 5245-02-76 | Sth 11 - Mineral Point; Minerva Street To Water Street | SW | Lafayette | STH 023 | Barry.Larson | HNTB | Richard.Olson | 1 | 02/03/2023 | 303 | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | IVERSON CONSTRUCTION, A DIV. OF MATHY CO | Alliant Energy | Electricity | Underground | ARBOR GREEN, INC. |  |  |  | MCGUIRE INC |  |  |  | 09/15/2022 | 09/15/2022 | No | Yes | Yes | Yes | [7 empty] | Yes |  |  | Alliant repaired damaged electric line and relocated out of conflict. | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | Thursday 9/15 @ 7:00AM - Arbor Green pounded steel guardrail post through Alliant's 750 MCM underground electric line at STA 720 RT, completely severing the power line. Alliant crew mobilized immediately, installed new power cable relocated further east out of conflict, spliced and made electric line operational by mid-afternoon ~2pm. After they hit the line, Arbor Green's crew continued installing posts to the south toward Merry Christmas Lane (less than 2 hrs downtime). Per Alliant's crew: This line runs parallel along the east side of the highway and is a main feed from Alliant's sub-station near Mineral Point. Properties were out of power from Mineral Point to Hollandale. It was recently installed in 2020 or 2021. This line was not displayed in plan or noted in special provisions, likely because it was so new. Thankfully nobody was injured. Understanding of the situation: 1) Arbor Green called in locates, 2) Vannguard located on Tue 9/13 in the morning, 3) McGuire placed shoulder gravel Tue 9/14 in the afternoon covering up the locates, 4) Arbor Green was unaware of the markings being covered and didn't see any locates, so they commenced with pounding posts Thursday morning.
20220111012 | wisc 2022115 | 5245-02-76 | Sth 11 - Mineral Point; Minerva Street To Water Street | SW | Lafayette | STH 023 | Barry.Larson | HNTB | Richard.Olson | 2 | 02/03/2023 | 303 | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | IVERSON CONSTRUCTION, A DIV. OF MATHY CO | Alliant Energy | Communication Line | Underground | ARBOR GREEN, INC. | [7 empty] | 09/13/2022 | 10/05/2022 | No | Yes | Yes | Yes |  |  |  | fiber optic line was installed in 2021, and since it was so new it was not even displayed in plan; project team didn't realize it existed until contractor called in locates for guardrail installation; this fiber line provides communication for Alliant's sub stations |  |  |  | Yes |  |  | Alliant bored new conduit out of conflict, transferred fiber optic cable over to new conduit, spliced fiber, then abandoned old conduit in place | Contractor delayed start of work |  | 08 to 16 hours |  | Other | 3 weeks to resolve issue | Excusable - Non-Compensable Delay |  |  | Location: STA 705+00 to 708+00 RT across from Greysville Rd Conflict: in conflict with proposed guardrail post installation Time extension of 7 days granted via CCO #5 due to this utility conflict issue
20220111012 | wisc 2022115 | 5245-02-76 | Sth 11 - Mineral Point; Minerva Street To Water Street | SW | Lafayette | STH 023 | Barry.Larson | HNTB | Richard.Olson | 3 | 02/03/2023 | 303 | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | IVERSON CONSTRUCTION, A DIV. OF MATHY CO | Frontier Communications | Communication Line | Underground | ARBOR GREEN, INC. | [7 empty] | 09/20/2022 | 10/05/2022 | No | Yes | Yes | Yes |  |  |  | Frontier's telephone line was displayed in the plan to be along the right of way line when in fact it was actually located up along the shoulder in conflict with proposed guardrail layout. It is believed that the existing telephone line was damaged recently and Frontier's crew bored new telephone line further up the slope to repair it, and that is why location differed from what was shown in plan. |  |  |  | Yes |  |  | Frontier bored new telephone line in further down the slope away from guardrail and abandoned old line in place | Contractor delayed start of work |  | 04 to 08 hours | 2 weeks to resolve | Other | 2 weeks to resolve | Excusable - Non-Compensable Delay |  |  | Location: STA 589+00 to 593+00 LT Conflict: telephone line in conflict with proposed guardrail posts Time extension of 7 days granted via CCO #5 due to this utility conflict issue
20220111019 | wisc 2022120, 121 | 4198-07-71 | T Holland, Risseeuw Road; Hand Creek Bridge | NE | Sheboygan | LOC STR | Zach.Pilichowski | HNTB | Becky.Reese | 1 | 04/21/2022 | 201 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | We Energies | Electricity | Overhead | [8 empty] | 04/06/2022 |  | No | No |  |  | Yes | [6 empty] | Yes |  | Yes | The overhead line will be relocated to temporary arms. | Other | Contract work has not yet begun. Work is scheduled to start April 25th. If the issue is not resolved by that date then work may be delayed. | 01 to 04 hours |  | Other | Work has not yet been affected. If the issue is not resolved by April 25th then work may be affected. | Other | This is a local program project and is not Trans 220. |  | Greg Boerner (WE energies engineering technician) on April 6th stated that the overhead line on the south side of Risseeuw Rd was not going to be relocated onto temporary arms as it would not result in a significant increase in the lateral distance to the work zone. Tim. D. (Pheifer PM) on April 6th asked We energies to relocate the line as is stated in the special provisions. We energies responded that the relocation was not part of their workplan and that the workplan stated only that they would try to relocate onto temporary arms. Tim D reached out to the project staff an April 7th for assistance to resolve the issue. Tim V. (WisDOT PM) emailed Emily Stewart (Sheboygan Co.) with help in resolving the issue as this is a local program project. We energies stated that they would see what they could do. Zach P (Project Engineer) followed up with We energies on April 12th and Greg B. stated that crews were scheduled for the week of April 15th but that weather delays may push the work into early the week of April 22nd. The line was moved onto temporary arms on April 21st.
20220111019 | wisc 2022120, 121 |  |  | NE |  | LOC STR | Zach.Pilichowski | HNTB |  | 2 | 06/15/2022 | 201 |  | PHEIFER BROTHERS CONSTRUCTION CO., INC. | Frontier Communications | Communication Line | Underground | VINTON CONSTRUCTION COMPANY | [7 empty] | 06/02/2022 | 06/15/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Other | contractor work was not affected as the utility relocated the same day structure work began. | Less than 01 hour |  | Less than 01 hour |  | Other | Contract time was not affected. |  | Frontier has not responded to multiple attempts to confirm that the underground line has been relocated. Zach Pilichowski (Project Engineer) sent emails on 4/20/22, 5/14/22 and 6/2/22. Tim Doell (Pheifer PM) sent an email on 6/2/22 and Emily Stewart (Sheboygan County) sent emails on 6/6/22 and 6/7/22. As of 6/8/22 Frontier has not responded with an update if the work has been completed or when it will be completed. There is no evidence in the field that the work is complete. Bridge work is scheduled to begin on June 15th and the utility is in direct conflict with the proposed piling. 6/14/22 Frontier located the facility and it is not in conflict with the proposed bridge but a pedestal is in conflict with the proposed grading. Frontier stated that the pedestal will be relocated. June 15th United Electric is on-site to relocate the pedestal.
20220111029 | n/a | 6580-10-71 | Clintonville - Howard; Herman Creek Crossing B-58-0019 | NC | Shawano | STH 156 | Bryan.Lampshire | GRAEF (MILW) | David.Rogers | 1 | 07/05/2022 | 303 | BRIDGE REPLACEMENT, PRESERVATION | LUNDA CONSTRUCTION COMPANY | WPS Resources Corporation | Gas/Petroleum | [9 empty] | 06/29/2022 | 07/05/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | Other | Gas Line Hit at 2:29 PM 6/27/2022, Gas Line EL. 818.31 at Hit, Gas Line is in the slab, Top of Slab EL. 818.96, WPS on site 6/28/2022 to access work to lower or relocate line out of conflict with Box Culvert | Other | Gas Line Hit at 2:29 PM 6/27/2022, Gas Line EL. 818.31 at Hit, Gas Line is in the slab, Top of Slab EL. 818.96, WPS on site 6/28/2022 to access work to lower or relocate line out of conflict with Box Culvert, WPS will be on site 7/5/2022 to lower gas line to be not in conflict with work. | Excusable - Non-Compensable Delay |  |  | WPS Gas Main was hit by Lunda Construction on 6/29/2022 at 2:29 PM on the north side of STH 156, approximately Sta 114+30.7, 31.5' LT. WPS crews were on site at 3:30 PM to shut off the gas main and make repairs to the line. Line back in service at 6:19 PM. While line was out of service Lunda Construction and Bryan Lampshire, GRAEF, took elevation shots on the gas main. The line was at elevation 818.17 where it was hit and at the approximate edge of slab for the box culvert floor elevation is 818.31. Plan top of slab elevation is 818.96 on the north side of STH 156, bottom of slab would be 818.04 and bottom of breaker run 817.04. This puts the gas main in conflict with the concrete slab and breaker run. Additional shots were taken with Trimble R10 GPS Rover on 6/30/2022. Sta 114+34.8, 31.4' LT EL. 818.54 Sta 114+30.7, 31.5' LT EL. 818.43 Sta 114+20, 32.1' LT EL. 817.99 Sta 114+10, 32.6' LT EL. 817.55 Sta 114+00, 32.9' LT EL. 817.20 WPS plans to lower the line on 7/5/2022 to remove it from conflicting with box culvert construction.
20220111029 | n/a | 6580-10-71 | Clintonville - Howard; Herman Creek Crossing B-58-0019 | NC | Shawano | STH 156 | Bryan.Lampshire | GRAEF (MILW) | David.Rogers | 2 | 07/06/2022 | 303 | BRIDGE REPLACEMENT, PRESERVATION |  | CenturyLink | Communication Line | Underground | [8 empty] | 06/30/2022 | 07/06/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | 16 to 24 hours | Centurylink representative on | Other | Centurylink Representative onsite said they installed a new line and they could install a new pedestal and hook up the new line, then abandon the line that was in conflict and hit. | Excusable - Non-Compensable Delay |  |  | Lunda Construction hit a Centurylink line north of STH 156 at Sta 114+37.3, 56.7' LT, EL. 819.14. They were looking for the line to verify it was not in conflict with the box culvert construction. Per the special provisions Centurylink stated the line was lower then construction and no conflicts anticipated. At the current elevation the line would be above the top of concrete elevation of 818.96 for the box culvert floor. The line is in conflict with construction of the box culvert inlet apron. Centurylink had installed a new line in the fall of 2021 but did not hook up the new line. The new line was not hooked up it was not located by diggers hotline. Lunda Construction may have driven sheet piling through the new line for the temporary diversion channel. If the new line is not damaged Centurylink plans to install a new pedestal, hook up the new line and abandon the line that was hit during excavation.
20220111034 | wisc 2022131 | 9140-12-61 | Antigo - Langlade; Sth 64 Culvert Replacements | NC | Langlade | STH 064 | Joel.Weber | CORRE INC. | David.Rogers | 1 |  | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | JANKE GENERAL CONTRACTORS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 06/10/2022 | 06/21/2022 | No | No | Yes | Yes | [11 empty] | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  | Other | contractor worked around it. |  | Utility was hit on Friday afternoon. Locates were not the best but I also thought the contractor should have called for a refresh prior to starting grading. Diggers was called after hit, but those that showed up couldn't tell if it was live or dead(one locater thought there were 2 lines one dead). Frontier called by contractor and they were told it wasn't their problem it was the locators. Locaters said the same. On Tuesday the following week Frontier shows up around 10:30 and said it is live and asks when it was hit.
20220111034 | wisc 2022131 | 9140-12-61 | Antigo - Langlade; Sth 64 Culvert Replacements | NC | Langlade | STH 064 | Joel.Weber | CORRE INC. | David.Rogers | 2 |  | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | JANKE GENERAL CONTRACTORS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 08/31/2022 | 08/31/2022 | No | Yes |  |  |  |  | Yes | There were 4 utility lines, only 2 had locates, though of the 2 the third line was 4' below the upper line. | [5 empty] | Yes | Utility temporary relocated line and will re-install after we are done with construction. | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline
20220111034 | wisc 2022131 | 9140-12-61 | Antigo - Langlade; Sth 64 Culvert Replacements | NC | Langlade | STH 064 | Joel.Weber | CORRE INC. | David.Rogers | 3 |  | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | JANKE GENERAL CONTRACTORS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 09/08/2022 |  | No | Yes | [22 empty] | Contractor started to work on placing end wall for pipe. Locator on site. It was found that fiber is within the flowline of the pipe. This pipe has a one foot bury to it.
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 1 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION |  | We Energies | Electricity | Underground | [8 empty] | 05/05/2022 | 05/09/2022 | No | No | Yes | [8 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | STA 110+75, WE came on site on May 9th and lowered the Electric in the way of storm sewer mainline
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 10 |  | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | City of Waukesha | Communication Line | Underground | [8 empty] | 09/10/2022 | 09/23/2022 | No | No |  | Yes |  |  | Yes | City Fiber wasn't buried deep enough |  |  | Yes | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | City fiber was in the subgrade at STA 705+25LT, Duct was repaired and lowered when it was fixed
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 2 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION |  | We Energies | Electricity | Underground | [8 empty] | 05/05/2022 | 05/09/2022 | No | No | Yes | [8 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | 111+75, WE Energies came out on 5/9 and lifted the electric over the storm pipe
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 3 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION |  | We Energies | Gas/Petroleum | Underground | [8 empty] | 05/11/2022 | 05/11/2022 | No | No |  |  | Yes |  |  |  | Yes | [6 empty] | Contractor productivity rate was affected |  | Less than 01 hour |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | STA 111+25, CB was cut out to raise pipe and get over the gas crossing
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 4 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION |  | AT&T | Communication Line | Underground | [8 empty] | 05/17/2022 | 05/25/2022 | No | Yes | Yes | [7 empty] | Yes | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | ATT had Larkman Construction come out and lower the ducts and then they protected the wires with slurry at STA 602+40LT
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 5 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | We Energies | Electricity | Underground | [8 empty] | 06/28/2022 | 06/28/2022 | Yes | Yes | [15 empty] | 01 to 04 hours |  | 04 to 08 hours |  | Digger&apos;s Hotline |  |  | We Energies Electric wasn't marked at Sta 105+00 LT and contractor pulled up on Electric Line while digging for watermain causing adjacent apartment complex to be without power.
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 6 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | Windstream Holdings, Inc. | Communication Line | Underground | [8 empty] | 07/06/2022 | 07/07/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | Windstream plans have a note of a minimum of 84" of cover in road crossings, this conflict had 4.5 feet of cover
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 7 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | Windstream Holdings, Inc. | Communication Line | Underground | [8 empty] | 07/06/2022 | 07/14/2022 | No | No |  |  |  |  | Yes | Utility bored through new storm sewer |  |  |  | Yes |  |  |  | Other | Work was not impacted, storm sewer was previously installed and was found during televising | Less than 01 hour |  | Other | 12 days from discovery to concrete patch opening strength | Non-Excusable Non-Compensable Delay |  |  | Utility plan called for 84" of cover in roadway crossings, this utility was 4' down, Ken Becker came out and removed fiber from pipe, and sealed the pipe back up, fiber was placed over top of the storm sewer
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 8 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 07/19/2022 | 07/20/2022 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | ATT Fiber Duct was in the way of storm sewer, Larkman came out the next day, broke the duct and lifted the fibers over the new pipe
20220208015 | wisc 2022167 | 2718-04-71 | W St Paul Avenue; Mountain Ave To Madison St | SE | Waukesha | LOC STR | Trigg.Knerr | DAAR ENGINEERING, INC | Michael.Birschbach | 9 | 07/21/2022 | 201 | RECONSTRUCTION, PRESERVATION | MUSSON BROS., INC. | We Energies | Electricity | Underground | [8 empty] | 06/14/2022 | 06/27/2022 | No | Yes |  |  | Yes |  | Yes | We Electric facility was bored through the existing 48" sanitary sewer |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | Other | Contractor was not able to work in this part of the intersection for 2 weeks | Excusable - Non-Compensable Delay |  |  | STA 304+60RT Wisconsin Ave. had to be closed in order for the facility to be relocated and sanitary pipe repaired
20220208016 | wisc 2022201 | 2720-09-70 | Lilly Road; Bridge Over Menomonee River | SE | Waukesha | LOC STR | Brian.Gresky | R.A. SMITH NATIONAL, INC. | Michael.Birschbach | 1 | 10/14/2022 | 201 | BRIDGE REPLACEMENT, PRESERVATION | ZENITH TECH., INC. - WAUKESHA | We Energies | Gas/Petroleum | Underground | SIRRAH CONSTRUCTION & CO. LLC | [7 empty] | 09/21/2022 | 09/27/2022 | No | Yes |  |  |  |  | Yes | The gas main was lowered by WE Energies earlier in the year however the location where it was lowered was not where it needed to be lowered. The offset needed to be west by 6 more feet. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | Other | Contractor was able to work on other areas but eventually stopped work and had to wait 3 days until they could finish the storm sewer. | Excusable - Compensable Delay
20220208017 | wisc 2022168 | 2722-07-71 | Moorland Road; I-94 To W Bluemound Road | SE | Waukesha | CTH O | Jeff.Norem | PATRICK ENGINEERING INC. | Michael.Birschbach | 1 |  | 201 | PAVT REPLACEMENT | ZIGNEGO COMPANY, INC. | AT&T | Communication Line | Underground | OUTDOOR LIGHTING CONST CO INC | [7 empty] | 06/20/2022 |  | No | No | [5 empty] | It was listed in the project's special provisions that the AT&T line would be relocated in order to install the concrete base for SB3 which is a monotube base (on the SW corner of the Brookfield Square North Entrance.
20220208026 | wisc 2022176, 178 | 4580-10-71 | Menasha-Hilbert; Ush 10-Village Of Sherwood | NE | Calumet | STH 114 | Josh.Frewerd | MCMAHON | Jordan.Maternoski | 1 | 11/03/2022 |  | RESURF (OVERLAY >= 4 IN) |  | TDS Telecom | Communication Line | Underground | [8 empty] | 07/22/2022 | 08/03/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | TDS relocated their facilities prior to construction; however, they only moved them slightly and they were still in conflict with the proposed ditch. Needed to relocate them again.
20220208035 | wisc 2022183 | 6355-00-74 | Cth H - Cth F; Edgewood Avenue To Cth F | NC | Adams | CTH Z | Ryan.Horst | STRAND ASSOCIATES, INC. | Michael.Caban | 1 | 02/21/2023 | 201 | RECONSTRUCTION, PRESERVATION | MEISE CONSTRUCTION INC | Frontier Communications | Communication Line | [9 empty] | 05/31/2022 | 08/15/2022 | No | Yes | Yes | Yes | Yes |  |  |  | Yes |  | Yes | Yes |  |  |  | Contractor delayed start of work |  | Other | Frontier has not completed planned relocations due to delay in material. Unknown schedule when relocations will begin | Other | Contractor is not comfortable to begin project without a known schedule when communications will be cleared. | Excusable - Compensable Delay |  |  | Frontier facilities were to be relocated prior the project starting in March. As of the precon on May 25, Frontier was not able to provide a timeline for its relocations. The contractor indicated it wanted to maintain its scheduled start date to allow the project to be completed in October. The contractor plans to start on a portion of the project where Frontier does not have facilities to relocate in order to get work started at its scheduled date.
20220208035 | wisc 2022183 | 6355-00-74 | Cth H - Cth F; Edgewood Avenue To Cth F | NC | Adams | CTH Z | Ryan.Horst | STRAND ASSOCIATES, INC. | Michael.Caban | 1 | 02/21/2023 | 201 | RECONSTRUCTION, PRESERVATION | MEISE CONSTRUCTION INC | Frontier Communications | Communication Line | [9 empty] | 06/15/2022 | 06/23/2022 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours | Frontier has not completed planned relocations due to delay in material. Unknown schedule when relocations will begin | 01 to 04 hours | Contractor is not comfortable to begin project without a known schedule when communications will be cleared. | Excusable - Compensable Delay |  |  | Frontier's contractor on site working on other relocations was able to mobilize to the unanticipated conflict area and temporarily relocate the line in conflict. Contract had to hand dig existing utility line and lay outside of the excavation limits.
20220208035 | wisc 2022183 | 6355-00-74 | Cth H - Cth F; Edgewood Avenue To Cth F | NC | Adams | CTH Z | Ryan.Horst | STRAND ASSOCIATES, INC. | Michael.Caban | 2 | 02/21/2023 | 201 | RECONSTRUCTION, PRESERVATION | MEISE CONSTRUCTION INC | Frontier Communications | Communication Line | [9 empty] | 06/20/2022 | 08/15/2022 | No | Yes | Yes | Yes |  |  |  |  | Yes |  |  | Yes | Yes |  |  | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | Other | Contractor operations affected for several weeks as contractor moved around project following areas where relocations were being completed. | Excusable - Compensable Delay |  |  | Frontier did not have its facilities located during the design of the project and was unaware of additional conflicts beyond what was planned in its proposed relocations. Contractor had to alter its work schedule and plan to work around utilities while utility crews worked to relocate facilities during construction. Contractor was able to maintain project schedule by working with private utility contractors, but much uncertainty and inefficiency impacted the project for several months while unanticipated relocations were taking place.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 1 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. |  | Communication Line | Underground | [8 empty] | 04/28/2022 |  | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  |  |  | 16 to 24 hours |  |  |  |  | Alliant Energy Communication line installed February 2022, appears to be installed at depth below existing ground and not proposed ground. Prime Contractor (JPS) potholed and found the facility to be above the proposed ditch, or less than 1-foot depth below proposed ditch. There is a stretch from approximately 390+00 to 396+00 LT that Alliant Communications is in conflict with proposed ditch. Alliant Communications and K&S were contacted 4/28/22. K&S was onsite Friday 4/29/22 to start relocation, drop line in place approx 3-feet.
20220308005 | wisc 2022228 | 4060-05-72 | Horicon - Kewaskum; Sth 67/175/Tw Intersection | SW | Dodge | STH 028 | Jordan.Hopp | GREMMER & ASSOCIATES, INC. | Richard.Olson | 1 |  | 303 | RECONSTRUCTION, PRESERVATION | MICHELS ROAD & STONE, INC. | We Energies | Electricity | Underground | [8 empty] | 05/09/2022 | 05/11/2022 | No | No | Yes | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  | Yes | We Energies has an underground electric line running from the pole at Sta. 107+70 'EB' LT to the west feeding the pedestal at Sta. 105+40 'EB' LT. This electric line does not appear in the project plans, but it was located and marked prior to grading work beginning. During grading on 5/9/22, the underground electric line was hit at Sta. 107+60 'EB' LT. We Energies repaired the facility and put in a work order to lower the line between the pole and pedestal. The depth of the facility is in conflict with the grading work, which is a cut section in this area.
20220308011 | wisc 2022235 | 7117-00-71 | Village Of Oakdale, Cth Pp; Ih 90/94 To Us 12/16 | SW | Monroe | CTH PP | Joseph.Stange | WisDOT | Richard.Olson | 1 |  | 201 | RECONSTRUCTION, PRESERVATION | ST. JOSEPH CONSTRUCTION CO.,INC. | Adams-Columbia Electric Cooperative | Communication Line | Underground | [8 empty] | 05/25/2022 | 05/27/2022 | No | No |  | Yes |  |  | Yes | No coordination with Dairyland Power Cooperative was performed during design, so the conflict was not listed in the specials nor was the facility shown in the plans. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Contractor's ditch excavation operations exposed a fiber optic line along the RT side of CTH PP, at approximate sta. 18+50. Presumed to be CenturyLink due to utilities listed in specials but unable to confirm. Coordination was eventually made through Harold Aaland at DPC to relocate the line 2-3' lower and move a handhole & post to the back side of the proposed sidewalk. Relocation was performed promptly without issues and did not affect the contractor's ability to perform work in other areas or impact the contract time. Dairyland Power Cooperative never received 1077's/1078's as part of the design process on this project, so the facility was not shown in the plans and the owner was unknown.
20220308011 | wisc 2022235 | 7117-00-71 | Village Of Oakdale, Cth Pp; Ih 90/94 To Us 12/16 | SW | Monroe | CTH PP | Joseph.Stange | WisDOT | Richard.Olson | 2 |  | 201 | RECONSTRUCTION, PRESERVATION | ST. JOSEPH CONSTRUCTION CO.,INC. | Charter Communications | Communication Line | Underground | [8 empty] | 06/27/2022 | 06/28/2022 | No | No | Yes |  |  |  | Yes | No coordination with Charter Communications was performed during design, so the conflict was listed in the plan and specials as belonging to CenturyLink. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Handhole and post on SW corner of W. Cougar Drive were found to still be in the way of new curb and gutter. Needed to be moved back 5-6'. Facilities belonged to Charter but were labelled in the plan/specials as CenturyLink, which is why the relocate was not completed with CenturyLink's other commitments. Once Charter was contacted, the relocation was performed promptly without issues and did not affect the contractor's ability to perform work in other areas or impact the contract time. Either Charter was not contacted with 1077's/1078's during the design process or failed to properly identify their facilities during the design utility coordination.
20220308013 | wisc 2022236 | 1032-10-75 | North South Freeway, Cth Ml-Sth 50; East Frontage Road | SE | Kenosha | OFF SYS | Ryan.Cournoyer | GRAEF, ANHALT, SCHLOEMER ASSOC. - MILW | Michael.Birschbach | 1 |  |  | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | PAYNE AND DOLAN, INC | We Energies | Gas/Petroleum | [9 empty] | 04/12/2022 | 04/21/2022 | No | No |  | Yes | [9 empty] | Yes | KS Construction was able to alter staging to complete area in conflict while only temporary signal installation was being done. KS worked from the south to the north instead of north to south to be clear of | Contractor delayed start of work |  | 04 to 08 hours |  | 08 to 16 hours |  | Other | No major construction items were impacted by the utility work. |  | WE Energies was given a permit to perform the gas installation during the same timeline as the East Frontage Road project (1032-10-75). The utility work needed to close a lane during Stage 1 of the frontage road project which planned to have bi-directional traffic in the same lanes.
20220308013 | wisc 2022236 | 1032-10-75 | North South Freeway, Cth Ml-Sth 50; East Frontage Road | SE | Kenosha | OFF SYS | Ryan.Cournoyer | GRAEF, ANHALT, SCHLOEMER ASSOC. - MILW | Michael.Birschbach | 2 |  |  | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | MP SYSTEMS, INC. | Midwest Fiber Networks LLC | Communication Line | Underground | [8 empty] | 06/06/2022 | 07/14/2022 | Yes | No | [15 empty] | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | MP Systems struck conduit that was incorrectly marked out on the site in the SE corner of the intersection at STH 165. Paint markings were 3' off from existing conduit. MP Systems Safety personnel were on site shortly after to document the site. See DWR on 6/6/2022 for more details. After multiple attempts by the contractor to contact MWFN with no success, we have determined that no local vendors lost communications and that everything has been repaired back to existing conditions.
20220308026 | wisc 2022250, 251 | 6560-08-71 | Kaukauna-Seymour; Cth Jj Intersection | NE | Outagamie | STH 055 | Brian.Heiden | WisDOT | Jordan.Maternoski | 1 | 09/14/2022 | 303 | MISCELLANEOUS | VINTON CONSTRUCTION COMPANY | We Energies | Gas/Petroleum | [9 empty] | 05/23/2022 | 06/03/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  | Other | No impact to contract time or cost. |  | 5-23-2022 Josh B (Vinton) called me about a gas main conflict along the north leg of the roundabout. I went out onsite and checked on the scope of the conflict. Vinton is cutting the ditch in along the west side of the north leg at the County JJ and WIS 55 intersection and they have discovered a conflict with a gas main on the west side of WIS 55. The depth of conflict varies but our surface model indicates cuts deeper than what the locate depth is reading to the gas main. Vinton and project staff agreed that from STA 5108+00 LT to STA 5110+50 LT, the gas main should be lowered at least 7 feet so crews don't have to worry about working around it. I called and emailed Eddie Hedlund (We Energies) right after returning from the meeting with Vinton and told him what the situation was as mentioned above. He said he will check into it and call me back. 5-24-2022 A little bit later Devin S (We Energies) called me back and asked how soon we needed the main lowered. I told him asap and he said he will get the locates started and that they will be out there next week May 31st at the latest to lower the main. 5-26-2022 Devon S (We Energies) called me back and said the will be in on Tuesday (5/31) to lower the gas main in conflict along the west side of the north leg as mentioned in yesterday's diary. 5-31-2022 Devon S (We Energies) called me at about 9:30 am and he was onsite with Michels Utilities discussing the gas main conflict along the north leg. I went out to site and discussed with him where the conflict is and he had some questions about grading limits, etc. Bryan Schaller and I used the gps to determine the cuts needed at locations where the gas main was going to be proposed so we could make sure they get it low enough. We Energies was going back and forth about where to put the gas main and how deep to go. Our estimate of 7 ft lower was pretty good as they had 8 ft in mind. I spoke with Devon S about the possibility of cutting and gapping the main in the conflict area so Vinton could get in and continue work. He checked with their engineers and they settled on cutting and gapping the conflict section. There is also the issue that the Vanderloop service needs to be adjusted as it falls within the conflict area. The service to Vanderloop Developments will be moved to the south so it is out of the cut and gap section and work can be done separate from Vinton and the service then won't have to be out until Friday. Discussion about where to put the gas main went on until about noon and then it was finally settled and Michels started work. 6-3-2022 Michels is finishing up with the gas main relocates today as well along the north leg of the roundabout that were discussed earlier this week. Vinton got in earlier this week and graded what they needed to in that area so they didn't experience any major delays.
20220308030 | N/A | 6270-00-63 | Waupaca - Northland; Depot Street To S Jct Sth 161 | NC | Waupaca | STH 049 | Tyler.Rutzen | EMCS, INC (MILW) | David.Rogers | 1 | 07/27/2022 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | NORTHEAST ASPHALT, INC | TDS Telecom | Communication Line |  | VANZILE CONTRACTORS LLC | [7 empty] | 07/25/2022 | 07/27/2022 | No | No | Yes | [5 empty] | Yes | Yes | [5 empty] | Contractor delayed start of work |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | TDS Telecom Fiber Optic cable was supposed to be relocated between removal of guardrail and installation of guardrail. After guardrail was removed on Monday 7/25/22 the contractor AJ Construction (Sub for TDS) was not able to locate fiber where it was marked. They decided they would pothole where new posts were in conflict during installation of new guardrail on 7/27/22. On 7/27/22 they line was remarked and showed the Fiber Optic in a different location, they began potholing and could not find cable so they reached out to USIC again and had them come re-mark. The fiber was re-marked in different location then plan and was informed TDS put in new lines so they may not match with plan. At this point TDS did not want any work done until the fiber was located. The fiber was finally located around 2-3pm approx. 5-feet deep where USIC had newest marks. The guardrail crew was able to begin work (approx. 6 hr delay). During installation the contractor had to hand dig around 8-12 posts to ensure they did not drive posts in over the top of cable. No relocations were required.
20220308030 | N/A | 6270-00-63 | Waupaca - Northland; Depot Street To S Jct Sth 161 | NC | Waupaca | STH 049 | Tyler.Rutzen | EMCS, INC (MILW) | David.Rogers | 2 |  | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | NORTHEAST ASPHALT, INC | Alliant Energy | Gas/Petroleum | [9 empty] | 08/10/2022 | 08/10/2022 | No | Yes |  |  |  |  | Yes | Gas service line was buried 1-inch below the milled surface. |  |  |  |  | Yes |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  | Yes | At 2pm contractor noticed gas line was leaking while compacting asphalt and had blown a hole in pavement. Emergency services took over after notification. Alliant repaired the line with a temporary line by 4pm. Will bore new line under roadway next week.
20220308031 | wisc 2021446 | 6320-00-73 | Plainfield - Wisconsin Rapids; Sth 13 To Church Avenue | NC | Wood | STH 073 | Elle.Miller | WisDOT | Michael.Caban | 1 |  | 303 | RESURF (OVERLAY < 2.5 IN) | AMERICAN ASPHALT OF WISCONSIN | Solarus | Communication Line | Underground | SMITH RESTORATIONS INC. |  |  |  | CHIPPEWA CONCRETE SERVICES, INC. |  |  |  | 09/30/2022 | 10/19/2022 | No | Yes | Yes | [5 empty] | Yes |  | Yes |  |  |  |  | Contractor stopped work and demobilized from project |  | Other | 19 days | Other | Issue identified on 9/30/22, crash cushion installed on 11/8/22 | Other | Additional days given to contractor in a Contract Modification | Yes
20220308035 | n/a | 9261-07-62 | Crandon - Three Lakes; Crandon To Argonne Culverts | NC | Forest | STH 032 | Zachary.Walczak | EMCS, INC (MILW) | David.Rogers | 1 |  | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | MUSSON BROS., INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 07/19/2022 | 07/19/2022 | Yes | No | [15 empty] | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  |  | At around 9 am a representative from Frontier Communication arrived on site at the Middle Branch Peshtigo River and informed Musson of an outage notice that they received. While excavating in the area of the new outfall endwall this morning, Musson had contacted a copper cable and broken it. The line was unmarked. The Frontier representative informed Musson that there were in fact 5 lines in the area that should have been marked but only the two recent borings that MasTec had completed before the project began had been marked. The other lines in the area were shallow and unmarked and hadn't been cut over to the new fiber and copper cable lines in the borings as the special provisions stated they would be. Later in the afternoon Larry with MasTec arrived on site and confirmed what we had been told earlier. Now that the line is broken the plan is to cut the existing lines over to the lines in the new borings.
20220308051 | wisc 2022069 | 5163-07-77 | Genoa - Lacrosse; Sunnyside Dr To Garner Place | SW | La Crosse | STH 035 | Timothy.Reichgelt | SHORT ELLIOTT HENDRICKSON INC. | Richard.Olson | 1 | 09/28/2023 | 303 | RECONSTRUCTION, PRESERVATION | CHIPPEWA CONCRETE SERVICES, INC. | CenturyLink | Communication Line | Underground | GERKE EXCAVATING INC | Xcel Energy | Gas/Petroleum | Underground |  | Mediacom LLC | Communication Line | Underground | 04/15/2022 | 05/19/2022 | No | Yes | Yes | Yes | [5 empty] | Yes |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Other | 80 to 120 hours | Other | 80 to 120 hours | Excusable - Compensable Delay |  |  | Dairyland Power also had a communications line that was in conflict. The contract initially decided to wait until the utilities were out of the way, and proceed with plan staging. After waiting 2-3 weeks, the contractor decided to abandon the plan staging and devised alternative staging, in order to be able to begin work.
20220412026 | wisc 2022306 | 6999-11-78 | C Wisconsin Rapids, W Jackson St; W Riverview Exp To Jackson St Brdge | NC | Wood | LOC STR | Dave.Katzner | MSA PROFESSIONAL SERVICES, INC. | Michael.Caban | 1 | 09/15/2022 | 303 | RECONSTRUCTION, PRESERVATION | MCCABE CONSTRUCTION, INC. | Charter Communications | Communication Line | Underground | [8 empty] | 09/13/2022 | 09/15/2022 | No | Yes | Yes | Yes |  |  |  | existing line was 3" into gravel of new roadway or approximately 16" deep. | [7 empty] | Contractor productivity rate was affected | [5 empty] | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility issue Existing fiber optic line was 3" in to gravel and needs to be lowered. location is crossing West Jackson St east of 6th Ave. The total depth was 16". The contractor hit with end loader while back filling storm sewer trench. Engineer called Jason Okeef of charter to inform him the line was hit and it was found to be 3" into gravel so will need to be lowered. He will try and send crew to look at cable tomorrow (7/14)
20220412026 | wisc 2022306 | 6999-11-78 | C Wisconsin Rapids, W Jackson St; W Riverview Exp To Jackson St Brdge | NC | Wood | LOC STR | Dave.Katzner | MSA PROFESSIONAL SERVICES, INC. | David.Rogers | 1 |  | 303 | RECONSTRUCTION, PRESERVATION | MCCABE CONSTRUCTION, INC. | Charter Communications | Communication Line | [9 empty] | 06/09/2022 | 07/12/2022 | No | Yes | Yes | Yes |  |  |  | existing line was directly under concrete pavement at 8" deep. | [7 empty] | Contractor productivity rate was affected |  | Less than 01 hour |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility issue Existing fiber optic line was directly under the concrete pavement at 2nd Ave / West Jackson Street intersection. The total depth was 8". Contractor called Charter and utility arrived on site at 12:45 PM. looked at site, asked some questions. What utility will do for permanent and temporary fixes is yet to be determined. on 6/10 Scott Olson from Charter called. He will meet me on site Monday to discuss conflict, and resolution.
20220412026 | wisc 2022306 |  |  | NC |  | LOC STR | Dave.Katzner | MSA PROFESSIONAL SERVICES, INC. |  | 2 | 07/13/2022 | 303 |  | MCCABE CONSTRUCTION, INC. | Solarus | Communication Line | Underground | [8 empty] | 07/12/2022 | 07/13/2022 | No | No | Yes | Yes |  |  |  | Fiber duct pack leaving vault was shallower than utility anticipated. |  |  |  | Yes |  |  |  | Contractor productivity rate was affected |  | Less than 01 hour |  | 01 to 04 hours |  |  |  |  | Fiber duct pack form 28+70 -29+25 was shallow and would be into gravel. it was discovered during grading. The utility was very responsive and worked with the contractor to lower their facilities.
20220412039 | wisc 2022354 | 1590-12-74 | Rhinelander - Monico; Cth P To Ush 45 North | NC | Oneida | USH 008 | Nathan.Anderegg | EXP U.S. SERVICES, INC. | David.Rogers | 1 |  | 302 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | MUSSON BROS., INC. | Frontier Communications | Communication Line | Underground | GORDON J. GRUBE CONSTR. CO., INC. | [7 empty] | 08/30/2022 | 08/30/2022 | Yes | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  |  | The original Diggers number was 20223216651, dated 8-3-22. On 8-29-22 Mitch with Musson called in a relocate and that number is 20223600839. Grube also had a diggers number for the same area, which is 20223418996.
20220412042 | wisc 2022025 | 7110-00-70 | Mondovi - Eau Claire; Ush 10 To Sth 85 | NW | Eau Claire | STH 037 | John.Mueller | KL ENGINEERING, INC | Jeorgia.Dahl | 1 | 05/02/2023 | 303 | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | CHIPPEWA CONCRETE SERVICES, INC. | Xcel Energy | Electricity | Overhead | [8 empty] | 07/26/2022 | 07/30/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | No impacts the conflict was identified by the department staff and corrected before the contractor was scheduled to work. | 01 to 04 hours |  | Other | None. | Non-Excusable Non-Compensable Delay |  |  | The existing power pole located in the NW quadrant of STH 37 and Oak Street at station 312+15, LT. The said pole was found to be in the proposed curb and gutter improvement at this location. The pole was relocated behind the proposed curb & gutter to complete the construction.
20220510010 | n/a | 1320-22-70 | Elkhorn - Burlington; Indian Run Cr 0.7 Mi E Claussen Rd | SE | Walworth | STH 011 | Matthew.Smith | WisDOT | Michael.Birschbach | 1 | 08/30/2022 |  | MISCELLANEOUS | MUSSON BROS., INC. |  | Communication Line |  | GRANITE CONSTRUCTION COMPANY | [7 empty] | 08/11/2022 | 08/30/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work until utility delay was resolved |  | Other | 19 days | Other | 19 days | Excusable - Non-Compensable Delay
20220510019 | wisc 2022394 |  |  | SE |  | CTH D | Isaac.Chavez | LAKESIDE ENGINEERS, LLC |  | 1 | 12/05/2022 | 201 |  |  | TDS Telecom | Communication Line | Underground | [8 empty] | 08/16/2022 | 08/16/2022 | Yes | No | [8 empty] | Yes |  |  |  |  | Contractor delayed start of work |  | 01 to 04 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | Wooden signpost was intended to be placed, due to utility was moved and hand dug to avoid any more issues. Station location at 62+25. signpost moved 2 feet left.
20220510024 | wisc 2022399 | 6240-22-71 | Appleton - Black Creek; Cth Jj - Cth B | NE | Outagamie | STH 047 | Matt.Geurts | EXP U.S. SERVICES, INC. | Jordan.Maternoski | 1 | 07/18/2022 | 303 | RESURF (OVERLAY >= 4 IN) | RELYCO, INC. |  | Gas/Petroleum | [9 empty] | 07/11/2022 | 07/18/2022 | No | Yes | Yes |  | Yes | [6 empty] | Yes | Yes |  |  | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  |  |  | Excusable - Compensable Delay |  |  | Unresolved utility issue the gas line at stat 381+55 Rt appears to be in conflict with the proposed box culvert structure C-44-133. The gas line elevation appears to be to high.
20220510027 | wisc 2022406 | 6610-04-70 | Rudolph - Knowlton; Sth 34 & Cth Db/Old 51 Intersection | NC | Marathon | STH 034 | Matthew.Spindler | REI ENGINEERING INC. | David.Rogers | 1 | 09/06/2022 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING INC. | Wisconsin Public Service Corporation | Electricity | Underground | [8 empty] | 08/24/2022 | 09/06/2022 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Other | On 8/24/22, the utility contractor informed the contractor the conflict will be resolved on 8/31/22 due to scheduling personnel/equipment. | Non-Excusable Non-Compensable Delay |  |  | The special provisions for the project stated to install new underground cable at Sta. 506+14B at a depth of 7 feet below original grade. It appears that the new installation was buried to a depth of 3.5 feet.
20220510027 | wisc 2022406 | 6610-04-70 | Rudolph - Knowlton; Sth 34 & Cth Db/Old 51 Intersection | NC | Marathon | STH 034 | Matthew.Spindler | REI ENGINEERING INC. | David.Rogers | 2 | 10/26/2022 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING INC. | WPS Resources Corporation | Electricity | Overhead | [8 empty] | 10/19/2022 | 10/26/2022 | No | No |  | Yes |  |  |  | Special provisions stated to extend guy wire 20'. This resulted in the guy wire being in the foreslope of the road. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Other | On 10/19/22, utility company and contractor discussed availability to install a new pole across the road as a new guy wire/pole. This work will be performed in a safe manner in the next stage of work when the area will be closed and away from traffic. The contractor will work around the guy wire in the foreslope until that time. | Non-Excusable Non-Compensable Delay |  |  | The guy wire in question is for pole 2607 21W19 at Sta. 510+13B. The guy wire extended to the east towards the new roadway.
20220510027 | wisc 2022406 | 6610-04-70 | Rudolph - Knowlton; Sth 34 & Cth Db/Old 51 Intersection | NC | Marathon | STH 034 | Matthew.Spindler | REI ENGINEERING INC. | David.Rogers | 3 | 10/26/2022 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING INC. | Wisconsin Public Service Corporation | Gas/Petroleum | Underground | [8 empty] | 10/19/2022 | 10/26/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | Other | Contractor performed work in other areas of the site. | Non-Excusable Non-Compensable Delay |  |  | A new driveway culvert pipe is to be installed at Sta. 510+85B, LT. The gas main is across the driveway and angles across the proposed pipe location. The top of the pipe is near the bottom of the culvert pipe once the new ditch is shaped for the alignment. A WPS representative was on site on 10/19/22 and stated that the gas main will be lowered to allow for for cover between the culvert pipe and the gas main.
20220510027 | wisc 2022406 | 6610-04-70 | Rudolph - Knowlton; Sth 34 & Cth Db/Old 51 Intersection | NC | Marathon | STH 034 | Matthew.Spindler | REI ENGINEERING INC. | David.Rogers | 4 | 10/24/2022 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING INC. | TDS Telecommunications Corp. (TDS) | Communication Line | Underground | [8 empty] | 10/19/2022 | 10/24/2022 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Other | Contractor performed work in other areas of the site. | Non-Excusable Non-Compensable Delay |  |  | The newly installed communications line was installed along the west side of Old Hwy 51 on the west side of the road between Sta. 511+10 - 512+90B, LT. The pedestals were installed at the locations of the new bottom of the ditch which has an approximate cut of about 3 feet. The pedestals were located near Sta. 511+15B, LT and Sta. 512+15B, LT. A representative was on site on 10/19/22 and plan to relocate the pedestals closer to the edge of R/W to have he pedestals in the backslope of the ditch.
20220510028 | wisc 2022407 | 6987-00-73 | Cth M - Waupaca County Line; Cth E To Cth Ae | NC | Waushara | CTH E | Paul.Eserhut | ONEIDA ENGINEERING SOLUTIONS, LLC (OES) | Michael.Caban | 1 | 05/03/2023 | 201 | PAVT REPLACEMENT | MICHELS ROAD & STONE, INC. | AT&T | Communication Line | Underground | [8 empty] | 10/10/2022 | 10/10/2022 | Yes | No | [15 empty] | 01 to 04 hours |  | Less than 01 hour |  | Digger&apos;s Hotline |  | Yes | The telephone line to the residence at N6799 CTH E was buried about 1' deep in the gravel shoulder 1' to 2' from the edge of pavement along the west side of CTH E from STA 354+50 to STA 359+00, LT. The telephone line was located approximately 22' from the location shown in the plan. On 10/10/22 the contractor tore out the telephone line while excavating to reconstruct the road in this section. AT&T arrived shortly after the telephone line was torn out and installed a temporary above-ground telephone line to bypass the damaged line, finishing the same day. Thone's Utility Construction Cable Plowing LLC installed a permanent buried telephone line on 10/19/22 once again along the west side of CTH E (further down the shoulder slope) after the roadway earthwork was complete. The contractor reported that their Digger's Hotline ticket number was 20224014083.
20220614006 | wisc 2022422 | 1310-04-70 | 75th St, Village Of Paddock Lake; 256th Ave To 236th Ave | SE | Kenosha | STH 050 | Ryan.Cournoyer | GRAEF (MILW) | Michael.Birschbach | 1 |  | 303 | RECONSTRUCTION, PRESERVATION | SHEET PILING SERVICES LLC | Village of Paddock Lake | Sewer (Storm or Sanitary) | Underground | A.W. OAKES & SON, INC. | [7 empty] | 10/11/2022 | 10/12/2022 | No | No | Yes | [5 empty] | Yes |  | Yes | Yes |  |  |  | Contractor productivity rate was affected |  | 16 to 24 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  | Yes | Location: STA 1029+50 LT, West side of R-30-70, wall A. Contractor (AW Oakes) connected 4" PVC to existing cast iron sanitary lateral for a permanent fix
20220614017 | wisc 2022400, 401 | 1580-30-75 | Prentice - Bradley; Little Somo River Bridge B-35-157 | NC | Oneida | USH 008 | Tom.Marschke | REI ENGINEERING INC. | Michael.Caban | 1 |  | 303 | BRIDGE REPLACEMENT, PRESERVATION | SHEET PILING SERVICES LLC | Frontier Communications of WI LLC | Communication Line | Underground | MUSSON BROS., INC. | [7 empty] | 10/11/2022 |  | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Other | The conflict does not affect this year's work and should be resolved before spring start up | Other | Utility believes they can complete the work mid-November this year | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | FO utility has been relocated except the splices have not been completed and the FO still runs in conflict with the temp. road. This does not affect this year's work and it should be resolved well before we start back up in the spring. 05/03/23 Inspected the project site for construction start up on 05/05/23. Observed the utility a noticed the splices have not been completed. Notified the responsible parties and was told the splice would be completed by 5/5/23. 5/8/23 utility is still not complete, Musson has mobilized in their equipment is on standby until the utility is moved.
20220712001 | wisc 2022450, 451 | 3080-01-40 | Madison - Cambridge; Cth Ab Overpass | SW | Dane | USH 012 | Jason.Lauters | CORRE INC. | Richard.Olson | 1 |  | OTHER | MISCELLANEOUS | R.G. HUSTON COMPANY, INC. | Alliant Energy | Gas/Petroleum |  |  | Frontier Communications of WI LLC | Communication Line | [5 empty] | 09/23/2022 | 02/13/2023 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue Other project IDs associated are 3080-01-75/76 -- Report No. 01 pertains to utility conflict associated with accelerated Ramp C grading work -- Alliant Energy Gas: Work Plan Comments: - Anticipated Start Date: Spring 2022 - Summer starts on June 22nd. 15 working days. Work completed by July 15th 2022 (assuming 2 rain days) - New R/W acquired for following properties needed before work could start -- Copart cleared on 12/23/2021 -- Dane County Waste and Renewables cleared on 5/18/2022 - No other conflicts or requirements listed, including no mention of clearing and grubbing SPV article comments: - Both projects 75/76 state that utility adjustments will occur prior to the project. WisDOT Utility Permit (if applicable) 2022-2033 - Amended completion date of 11/07/2022 due to crew and material delays. Impacts: - Started relocation work on week of 10/3/2022 - Excavation of Ramp C delayed - Delay Days = working days from 11/07/22 to 11/30/22 - inclement weather days (based on WisDOT Permit) - Contractor able to work on other accelerated locations, no delay costs to date (not controlling item) - Relocation work completed and confirmed on 12/5/2022 ---------------------------------------------------------------------------------------------------------------------- Frontier Communications: Work Plan Comments: - Work plan and DT1541 approved on 6/16/2022 - Anticipated Start Date: 04/11/2022 - 90 working days per 3080-01-76 work plan, 75 work plan has 60 days. - New R/W acquired for following properties needed before work could start -- Copart cleared on 12/23/2021 -- Dane County Waste and Renewables cleared on 5/18/2022 -- C&L Investments to on 05/19/2022 - Scheduling of cuts, fills or grading. No mention of clearing and grubbing. SPV article comments: - Both projects 75/76 state -- work to start June of 2022 and take approximately 90 working days -- work will occur prior to and during the project - Based on start date of 6/30/2022 and 90 working days (including 17 weather days per SS) Work complete on 12/2/2022 WisDOT Utility Permit (if applicable) 2022-2031 - The USH 12 anticipated start of construction date is 09/01/2022 and utility relocation work and Work Plans approved for prior to construction shall be completed before that date. Impacts: - Started relocation work on week of 10/3/2022 - Waiting for Alliant's work to be completed in Ramp C starting 9/23/22 - Fairway Electric pulls off the project on 11/3/2022 - Frontier indicates United Electric will be the new subcontractor on 11/15/2022, onsite continuing work for Frontier Communications on 11/28/2022 - Excavation of Ramp C, Millpond Road Storm Sewer and final grading on Maahic Way station 449+50 delayed - 12/8/2023 - Existing facilities throughout entire project are still live, not transferred to new lines. - 1/31/2023 - Confirmed existing facilities throughout entire project are still live, not transferred to new lines. - 2/15/2023 - All relocations complete 2/13/2023, all conflicts are resolved.
20220712001 | wisc 2022450, 451 | 3080-01-40 | Madison - Cambridge; Cth Ab Overpass | SW | Dane | USH 012 | Jason.Lauters | CORRE INC. | Richard.Olson | 2 |  | OTHER | MISCELLANEOUS | R.G. HUSTON COMPANY, INC. | Alliant Energy | Electricity | Underground | [8 empty] | 09/27/2022 | 12/05/2022 | No | No |  |  | Yes | [10 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Other project IDs associated are 3080-01-75/76 -- Report No. 02 utility conflict regarding accelerated grading work associated with Ramp B and Pond D -- Work Plan Comments: - Anticipated Start Date: Spring 2022 - Summer starts on June 22nd. 15 working days. Work completed by July 15th 2022 (assuming 2 rain days) - New R/W acquired for following properties needed before work could start -- Copart cleared on 12/23/2021 -- Dane County Waste and Renewables cleared on 5/18/2022 -- C&L Investments to DOT ownership on 05/19/2022 - No other conflicts or requirements listed, including no mention of clearing and grubbing SPV article comments: - Both projects 75/76 state that utility adjustments will occur prior to the project. WisDOT Utility Permit 2022-2033 - Amended completion date of 11/07/2022 due to crew and material delays. Impacts: - Started relocation work week of 10/3/2022 - Excavation of Ramp B pond and back slope delayed starting on 9/27/2022 - Potential Delay Days = working days from 11/07/22 to 12/5/2022 - inclement weather days (based on WisDOT Permit) - Contractor able to work on other accelerated locations - New electric service installed on 11/14/2022, Ramp grading no longer delayed - Relocated power line active, confirmed on 12/5/2022. Delay ends.
20220712001 | wisc 2022450, 451 | 3080-01-40 | Madison - Cambridge; Cth Ab Overpass | SW | Dane | USH 012 | Jason.Lauters | CORRE INC. | Richard.Olson | 3 |  | OTHER | MISCELLANEOUS | R.G. HUSTON COMPANY, INC. | Madison Gas And Electric Company | Gas/Petroleum | Underground | [8 empty] | 12/01/2022 | 12/12/2022 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue Other project IDs associated are 3080-01-75/76 -- Report No. 03 pertains to utility conflict associated with accelerated storm sewer work between Millpond Road and County AB -- Work Plan Comments: - Anticipated Start Date (West Phase): July 2022 - Anticipated Start Date (East Phase): Dependent on Clearing and Grubbing and Fence Removal - 20 working days for each phase. East Phase completed by August 31st 2022 - New R/W acquired for following properties needed before work could start -- City of Madison Parks cleared on 2/10/2022 -- City of Madison Streets cleared on 1/25/2022 -- C&L Investments to DOT ownership on 05/19/2022 SPV article comments: - State that west segment work will occur prior to the project, east segment will be completed during construction after clearing and grubbing activities. WisDOT Utility Permit 2022-2039 - The USH 12 anticipated start of construction date is 09/01/2022 and utility relocation work and Work Plans approved for prior to construction shall be completed before that date. Impacts: - City of Madison permit issued on 8/12/2022 - WisDOT Utility Permit issued on 7/6/2022 - Started relocation work (West Phase) week 8/31/2022 - West segment completed week of 9/26/2022 -, MG&E indicated would work with RGH to install gas line after embankment is installed for new Millpond Road. MG&E was supposed to start work in early November. At end of day 11/30/2022, accelerated storm sewer trunk line on Millpond Road is in conflict with existing gas line. Delays on accelerated work starts on 12/1/2022. MG&E starting to relocate/terminate existing gas main on 12/5/2022. - 12/12/2022 - MG&E relocated 1,000 feet of the gas main that was in conflict. RGH no able to install storm sewer working from the west to east.
Total Number of Contracts with Utility Conflict Reports: 44
Total Number of Contracts Excluding PBM, LFA, LCS, Test, and Utility Contracts: 803
-