## Introduction
APPENDIX D - SRM MATRIX and WORKBOOK
The tabs in this workbook relate to section 2.3 – Risk Mitigation, in WisDOT's ASP template. The workbook contains the following:
SRM-SA Terms
Guide to terms used in SRM and SA processes.
Safety Risk Management (SRM) Risk Register
Sample risk register, used to associate identified hazards (and existing mitigations) that are being tracked to their associated risk level, as determined by your agency. Includes columns for planned implentation dates for proposed mitigations, department(s) responsible for mitigation implementation, and contact person(s).
Safety Assurance (SA) Tracker
Sample hazard tracker, used to track identified hazards and mitigations as determined by your agency. Includes columns for safety performance targets impacted, department(s) responsible for mitigation implementation, and the means by which a hazard/mitigation is being monitored.
Severity Matrix
Sample matrix for rating severity; includes criteria for each rating.
Likelihood Matrix
Sample matrix for rating likelihood/freqeuency; includes practical examples for each rating.
Risk Assessment Matrix
Sample combined severity/likelihood matrix, used by your agency to assess each identified hazard for its risk to your transit system.
With respect to prioritization of safety risk mitigations, the template and appendices do not provide a process or criteria for determining the level of safety risk associated with each hazard - that is for each transit agency to assess and develop. The included matrices can help formalize the process.
For additional guidance in this area, consider reviewing FTA's Sample Safety Risk Assessment Matrices for Bus Agencies:
https://www.transit.dot.gov/regulations-and-guidance/safety/public-transportation-agency-safety-program/sample-safety-risk
It provides a structured approach for addressing the requirements to “establish methods or processes to assess the safety risks associated with identified safety hazards” (§ 673.25(c)).

## SRM-SA Terms
SAFETY RISK MANAGEMENT / SAFETY ASSURANCE - GUIDE TO TERMS
ELEMENT | DESCRIPTION | EXAMPLE
Hazard | Any real or potential condition that can cause injury, illness, or death; damage to or loss of the facilites, equipment, rolling stock, or infrastructure of a public transportation system; or damage to the environment. | The hazard in FTA's participant guide scenario is the out of calibration wheel balancer.
Type of Hazard | Classification used to help organize identified hazards to support an agency's data management and hazard prioritization activities. The three (3) main types of hazards include: Organizational (shortcomings in the organizational processes), Technical (the condition of the equipment, facilities, and infrastructure), and Environmental (the natural environment). | FTA's example hazard in the scenario is a technical hazard, as it pertains to an agency's equipment, rolling stock, infrastrucure, and facilities.
Identification date | The date the hazard was identified though agency means. This information can be used for evaluating the effectiveness of safety risk management activities by providing a starting point to see how long the agency takes to analyze and mitigate the hazard.
Identification source | How the hazard was identified. This information can provide insight into the effectiveness of the safety data sources available to the agency and can help identify items for improvement. | In FTA's scenario, the hazard was identified by a safety specialist upon reviewing the Safety Event Investigation Report.
Date of analysis | The date the hazard was analyzed. This information can be used for evaluating the efficiency of the analysis process and determine if certain hazards are more challenging to analyze than others.
Worst credible potential consequence(s) | The effect of a hazard involving injury, illness, or death; damage to or loss of the facilities, equipment, rolling stock, or infrastructure of a public transportation system; or damage to the environment. | The worst credible potential consequence for the hazard in FTA's scenario is a collision resulting in death, permanent injury, or destruction of property, with damage (losses over $1,000,000).
Existing mitigations (hard or soft) | The controls already exisiting within the agency to mitigate the potential consequence(s) of the hazard. | Pre-Trip Inspection: Bus operators are required to check tires for excessive wear as part of their pre-trip inspection.
Routine Bus Maintenance and Inspections: Tires are inspected and replaced as part of the agency's regular maintenance and inspection program.
Wheel Balancer Calibration: SOP governs the calibration of the wheel balancer.
Severity of consequences | Quantified effect of the potential consequence(s) of the hazard in the delivery of transit services and/or supporting activities, taking into account existing mitigations. | In FTA's scenario, the severity was identified by looking at historical data from the agency.
Likelihood of consequences | Quantified probability that the potential consequence(s) of the hazard materialize, taking into account existing mitigations. Calendar days, weeks, months, years, or decades are often used as time periods to support assessments of likelihood in safety risk assessment.
Safety risk index | Tolerability of the potential consequence(s) of the hazard, taking into account existing mitigations. It is the primary parameter for deciding priorities in the allocation of resources. | Combining the likelihood and severity of the potential consequence results in a risk rating.
Further Mitigation action | Additional controls that the agency needs to incorporate to mitigate the potential consequence(s) of the hazard if the safety risk exceeds tolerability criteria.
Revised safety risk index | Safety risk index that meets the tolerability criteria, following incorporation of additional controls to mitigate the potential consequence(s) of the hazard.
Revised safety risk index date | The date the revised safety index was determined. This information can be used to evaluate the efficiency of the analysis process and determine if certain hazards are more challenging to analyze than others.
Department responsbile for mitigation | Agency department (or other subdivision) taksed with the implementation of the additional controls to mitigate the potential consequence(s) of the hazard.
Estimated implementation date | The date the mitigation(s) are expected to be implemented. This information is used to track the completion of mitigations and identfiy any potential resources or other concerns.
Contact person | Primary point of contact within the department responsible for mitigation with other departments involved in safety risk management.
Consequence | Effect of the hazard in the delivery of tranist services and/or supporting activities, carried over from safety risk management section.
Safety performance indicator (SPI) | Parameter selected to monitor and measure the effectiveness of the additional controls incorporated to mitigate the potential consequence(s) of the hazard.
Safety performance indicator (SPI) value | Quantification of the parameter selected to monitor and measure the effectiveness of the additional controls incorporated to mitigate the potential consequence(s) of the hazard.
Safety performance target | Projected improvement over the SPI value resulting from the additional controls incorporated to mitigate the potential consequence(s) of the hazard.
Timeframe | Information for evaluating the effectiveness of safety performance monitoring and measurement activities.
Monitoring means | Resources and activities to monitor and measure the effectiveness of the additional controls incorporated to mitigate the potential consequence(s) of the hazard.
Department responsbile for monitoring mitigation effectiveness | Agency function primarily tasked with monitoring and measuring the effectiveness of the additional controls incorporated to mitigate the potential consequence(s) of the hazard.

## SRM - Risk Register
SAFETY RISK MANAGEMENT - SAMPLE RISK REGISTER for PUBLIC TRANSPORTATION AGENCY SAFETY PLAN (PTASP)
| HAZARD |  | IDENTIFICATION |  | Date of Analysis | Worst Credible Potential Consequence(s) | Existing Mitigations | CONSEQUENCES |  | Safety Risk Index | Further Mitigation Action | REVISED SAFETY RISK INDEX |  | Department Responsible for Mitigation | Estimated Implementation Date | Contact Person
ID | Hazard | Type | Date | Source |  |  |  | Severity | Likelihood |  |  | Revised Index | Date
| Out of calibration wheel balancer | Technical (equipment) |  | Safety Event Investigation Report |  | Collision resulting in death, permanent injury, or destruction of property (losses over $1,000,000) | Pre-trip inspection; routine inspection and maintenance; wheel balancer inspection and calibration | 1-Catastrophic | C-Occasional | 1C-High; Unacceptable - action required; must be mitigated or eliminated | Develop and implement a maintenance equipment calibration audit program; revise tire inspection procedure | 1E-Low; Acceptable - acceptable with management review

## SA - Tracker
SAFETY ASSURANCE - SAMPLE TRACKER for PUBLIC TRANSPORATION AGENCY SAFETY PLAN (PTASP)
HAZARD |  |  | Consequence | SAFETY PERFORMANCE |  |  | Timeframe | Mitigations | Monitoring Means | Department Responsible for Monitoring Mitigation Effectiveness
ID | Hazard | Type |  | Indicator | Value | Target
| Out of calibration wheel balancer | Technical (equipment) | Collision resulting in death, permanent injury, or destruction of property (losses over $1,000,000) | Tire failure rate | Annual rate of tire failures (in VRM) | 1 tire failue in 10,800,00 VRMs per year | 90 days | Develop and implement a maintenance equipment calibration audit program | Record review, workplace observation
[7 empty] | 180 days | Revise tire inspection guidelines to include condemning limits for patch wear | Document review, workplace observation, inspections

## Severity Matrix
Sample Safety Risk Assessment Matrix
Severity Categories
Description | Severity Category | Criteria
Catastrophic | 1 | Could result in one or more of the following:
Death
Multiple serious injuries requiring hospitalization
Irreversible environmental impact
Monetary loss equal to or exceeding $1,000,000
Critical | 2 | Could result in one or more of the following:
Serious injury requiring hospitalization
Reversible significant environmental impact
Monetary loss equal to or exceeding $250,000 but less than $1,000,000
Marginal | 3 | Could result in one or more of the following:
Injury requiring medical treatment beyond first aid that may result in one (1) or more lost work day(s)
Reversibe moderate environmental impact
Monetary loss equal to or exceeding $10,000 but less than $250,000
Negligible | 4 | Could result in one or more of the following:
Injury requiring first aid
Minimal environmental impact
Monetary loss less than $10,000

## Likelihood Matrix
Sample Safety Risk Assessment Matrix
Likelihood Levels
Description | Level | Individual item | System or Vehicle Fleet
Frequent | A | Likely to occur often in the life of an item. | Continuously experienced. Potential consequence may be experienced more than once in 40,000 vehicle revenue miles (VRM).
Probable | B | Will occur several times in the life of an item. | Will occur frequently. Potential consequence may be experienced once per 40,000 to 480,000 VRM.
Occasional | C | Likely to occur sometime in the life of an item. | Will occur several times. Potential consequence may be experienced once per 480,000 to 4,800,000 VRM.
Remote | D | Unlikely, but possible to occur in the life of an item. | Unlikely but can reasonably be expected to occur. Potential consequence may be experienced once per 4,800,000 to 14,400,000 VRM.
Improbable | E | So unlikely, it can be assumed occurrences may not be experienced in the life of an item. | Unlikely to occur, but possible. Potential consequence may be experienced less than once per 14,400,000 VRM.

## Risk Assessment Matrix
Sample Safety Risk Assessment Matrix
Risk Assessment Matrix
Severity | Catastrophic | Critical | Marginal | Negligible
Likelihood | 1 | 2 | 3 | 4
Frequent - A | HIGH - 1A | HIGH - 2A | HIGH - 3A | MEDIUM - 4A
Probable - B | HIGH - 1B | HIGH - 2B | MEDIUM - 3B | MEDIUM - 4B
Occasional - C | HIGH - 1C | MEDIUM - 2C | MEDIUM - 3C | LOW - 4C
Remote - D | MEDIUM - 1D | MEDIUM - 2D | LOW - 3D | LOW - 4D
Improbable - E | LOW - 1E | LOW - 2E | LOW - 3E | LOW - 4E