Non-Traditional Transportation Project Development

Timeline

| ##### WisDOT Project ID Number |  | ##### Date Checklist Completed |
| --- | --- | --- |
| ##### Project Title | Hwy No/Letter | ##### County |
| ##### Project Limits |  | ##### Sponsor |
| ##### Project Description |  | ##### Preparer/Title |

Enter Date Completed

___/____/_____Project initialization: Average 3 months from time State/Municipal Agreement is

sent to Sponsor and the design ID is authorized.

Check when completed

☐ State/Municipal Agreement sent to Sponsor

☐ Sponsor approval by governing body (Common council, county Board, etc.)

☐ WisDOT processing and execution of State/Municipal Agreement

*After receiving an approved State/Municipal Agreement, design is authorized to incur costs (although

you still need to follow design protocol below) *

____/____/____Design contract executed—WisDOT reimbursable (2-party or three-party):

Varies: 3-9 months - Dependent on familiarity with WisDOT contracting, scope of 		         project, need for negotiation, timing of Sponsor internal approvals and type of contract

For 3-party contract (Sponsor, Design Consultant, WisDOT)

☐ Creation of RFP

☐ Solicitation via QBS

☐ Consultant approval by WisDOT

☐ Scoping of the contract

☐ Creation, negotiation and review of 3-party

☐ Execution by Design Consultant & Sponsor

☐ WisDOT processing & execution

For 2–party contract (Sponsor & WisDOT)

☐ Scoping of the contract

☐ Creation and review of contract

☐ Execution by Sponsor

☐ WisDOT processing & execution

*After receiving Notice to Proceed, you can start design*

____/____/____Design:  Varies: 6 months to 3 years - Dependent on familiarity of designer with 			process, if design amendments are needed, & complexity of project.

Items that add to complexity include the following:

☐ Railroad

☐ Structures

☐ Real Estate

☐ Utility coordination

☐ DNR/ACOE permitting

☐ Multiple phases of construction

☐ Section 106 challenges (historic or archeological)

* Once authorized, you can submit Request to Advertise – Local Let Project*

____/____/_____Request to Advertise Approval/ Construction funds authorization: 2-3 months

Includes WisDOT and FHWA review, approval, processing and authorization

*After receiving an approved Request to Advertise – Local Let Project, advertise the project*

____/____/____   Request to Award – Local Let Project Approval/ Construction contract can be

executed: 1-1.5 months

☐ Advertisement of project

☐ Opening of bids

☐ Submittal & Approval of Request to Award – Local Let Project

*After receiving an approved Request to Award – Local Let Project, execute your construction contract*

____/____/____Construction: 3 months to 2 years - Varies based on complexity, construction oversight, 		enforcement of project schedule, phasing, and time of year when project began

☐ Pre-construction meeting

☐ Construction

☐ Processing of contract modifications (if applicable)

☐ Final walk-through/punch listing

____/____/____Reimbursement Requests (RR) & Project Completion: 3 months to 2 years – Varies

based on when RRs began & submitted, along with project completion cert.

☐ Submission of RRs and applicable back-up

☐ Field reviews based on the RRs & any necessary fixes in the field

☐ Approval of Reimbursement Requests & receipt of reimbursements

☐ Submission and approval of Project Completion Certificate

*When completed, project is closed. Note that this is applicable for all IDs (design, real estate, construction, etc.).

From project inception to project close-out:  2 years to potentially 8 years, 4.5 months