## Sheet1
Bi-Monthly Schedule Work Sheet
Sunset Date:
Commencement Date:
Sponsor/LPA:
Project ID:
Project Name/Description:
Project Limits/County
Submitted By/Date:
| Original Schedule |  | Current Schedule |  | Actual Schedule |  | Percent
Project Milestones | Submit | Approve | Submit | Approve | Submit | Approve | Complete
Start of Design
Operation Planning Meeting (OPM)
Request for History/Archeology Screening
Tribal Historic Preservation Letters
(Traffic Memo/LOS Report Approved)
Soils Report
Intersection Control Evaluation Report
Pavement Design Report (PDR)
Public Information Meeting (PIM)
(Preliminary Structure Plan - TSL)
Section 106
Phase 1 HMA Approved
Environmental Document
Right of Way Plat
Stormwater Report
Design Study Reort (DSR)
Real Estate Acquisition
(Railroad Package)
Final Structure Plan
Utility Status Checklist
R/W (Cert 1)
Draft Plans Specials Estimate 90% Plan
Final PSE (eSubmit)
LET
1. Important milestones, events, and/or accomplishments that were made this month:
2. Milestones, events, meetings, etc. to be held/completed in the next two (2) months:
3. Items/tasks that were scheduled to be completed this month but were not (list and explain):
4. Items that are needed from others in the next two (2) months:
5. Issues to be aware of or needing to be resolved:
- Fill in the schedule and approval dates for the tasks/milestones applicable for your project.
- Submit form to Region LPPM every two months | [6 empty] | 2019-02-26