RIGHT-OF-WAY (R/W) AND REAL ESTATE (R/E) CHECKLIST

| WisDOT Project ID Number |  | Date of Form Prepared |
| --- | --- | --- |
| Project Title | Hwy No/Letter | County |
| Project Limits |  | Sponsor |
| Project Description |  | Preparer/Title |

NOTE:  All Real Estate acquisition must be completed before PS&E. The project cannot be advertised until the local program real estate project manager (LPREPM) has reviewed and approved ROW documentation. Consult your LPREPM for any real estate questions.

- Preliminary

If persons or businesses are to be displaced, complete an acquisition stage relocation plan.  Use of a relocation consultant is recommended. Completed plan to be submitted to WisDOT BTS-RE for review and approval.

Submit parcel cost estimate (R/W Parcel Cost Estimate Form) to WisDOT for use in R/E funding authorization.  Do not incur costs until you have authorization.  Any R/E costs incurred prior to authorization will NOT be reimbursed.  R/E funding authorization is not the same as a signed State/Municipal Agreement.

Read The Rights of the Landowner Under Wisconsin Eminent Domain Law (Eminent Domain Brochure), available at the Department of Administration website https://doa.wi.gov/Pages/AboutDOA/RelocationAssistance.aspx

Complete title search.

Determine which parcels will need a partial release of mortgage.

Draft and approve R/W Plat and Relocation Order and file with County Clerk within 20 days.  Submit copies to LPREPM.

Draft Descriptions/Deeds.

Notify utilities.

Identify and remove/permit encroachments.

Complete the Acquisition Capability Statement (ACS) form. It is found on the Local Program Real Estate Forms webpage. Contact your LPREPM for assistance.

- Local Program real estate consultants (acquisition and relocation agents, appraisers, and review appraisers) must be listed on the approved list of consultants found on the Local Program Real Estate website.

- Individual LPA Staff performing right of way acquisition functions must meet certain criteria and be approved by WisDOT prior to working on project acquisition (See Section 2.2.1 LPA Staff in Local Program Real Estate Manual for details).

Use of WisDOT contracts are required.

Use of WisDOT’s Real Estate Automated Data Systems (READS) is required (WisDOT LPA forms are required and are stored here). Contact your LPREPM for more information.

Coordinate a real estate Start-Up Meeting with your LPREPM. Information about the Start-Up Meeting is found in section 3.5 Start-Up Meeting of the Local Program Real Estate Manual.

- Notify Owners

Prepare a parcel folder for each parcel acquisition.

Send introduction letter with the brochure: The Rights of the Landowner Under Wisconsin Eminent Domain Law to each property owner.

Send notification of the possible need for a partial release of mortgage.

- Appraisal

Contract with appraiser. Contract must be approved by your LPREPM when Fed/State funds in R/E.

Furnish appraiser with:

| - R/W Plat | - Appraisal requirement | - Construction Plan, Profiles and Cross Sections |
| --- | --- | --- |
| - Legal Description | - Title information for each parcel | - List of property owners names, addresses and phone numbers |

- Waiver of Appraisal Procedure:  The Agency may attempt to negotiate without formal appraisal those parcels valued at $25,000 or less.  If Fed/State funds in R/E, your LPREPM must approve nominal offering prices and any subsequent increases.  The following steps must still be followed:

Prepare sales study.

Tabulate on Waiver of Appraisal form a conclusion of damages (based on the sales study) for each parcel.

Fill out the Nominal Payment Parcel - Waiver of Appraisal Recommendation and Approval (RE1897-READS) form for each nominal parcel.  WisDOT must approve if Fed/State funds in R/E.

Advise owner of his/her rights as outlined in Eminent Domain Brochure.

Owner willingly signs the Nominal Payment Parcel - Waiver of Appraisal Recommendation and Approval (RE1897-READS) form, the deed easement and other necessary documents.  Note: No one can condemn a nominal parcel without first going through the appraisal process.

- Appraisal Review.  If Fed/State funds are used in the real estate, WisDOT must review appraisals and approve offering prices.  Submit completed Offering Price Report and Submittal (RE1894-READS) form along with the appraisal.

Review/approval of all appraisals is completed by qualified appraisal reviewer.  Nominal payment parcels have been approved.  Values concluded are uniform, consistent and complete throughout project, have been approved prior to the initiation of negotiations.

- Negotiation

Review Title Search for parties of interest and any encumbrances against the property (i.e., tax liens, judgments, etc.).  These must be satisfied or cleared before payment to the owner, including any possible partial release of mortgage.

Contact owner(s) and provide to them:

| - A copy of the appraisal or Waiver | - Copy of Deed and/or Easement and legal description. |
| --- | --- |
| - Offering Price Letter - Appraisal if over $25,000 or Waiver not signed | - Eminent Domain Brochure (if not given before negotiations) - Owner Appraisal Guidelines, if necessary |
| - Closing Statement - W-9 if appropriate - Statement to Construction Engineer | - A copy of the plat and the Schedule of Interests form to all affected property owners - Tax Proration, if appropriate |

Negotiation Diary Complete (Thorough documentation of all meetings and conversations during acquisition process is required.)

Wait for owners to secure their own appraisal, if appropriate, explained in Eminent Domain Brochure-they have 60 days from receipt of Agency appraisal.  Owners should be given the Owner Appraisal Guidelines at initial negotiation call.

Arrange for reimbursement of the owner's appraisal fee if their appraisal met the requirements outlined in the Owner Appraisal Guidelines.

Obtain any necessary Partial Releases of Mortgage.

Obtain a Purchase Agreement from owner if any special conditions or commitments are agreed to.  Any commitments are to be reviewed and approved by the consulting Engineer and Agency.  If Fed/State funds in R/E, WisDOT must approve any changes in offering prices. If the acquisition changes, start entire process over.

If the original approved offer is revised during negotiations, notify owner in writing.

- Closing

List commitments (if any) to owner.

Secure executed deed or easement.

Make payment to the owner.

Record documents with the Register of Deeds including TLEs.

Complete Diary Documentation and sign.

- Condemnation Procedures:  In accordance with State Statute 32.05 when an agreement cannot be reached and condemnation is necessary coordinate closely with your LPREPM. It is strongly suggested, the Agency’s attorney review all condemnation documents prior to service.

Serve a Jurisdictional Offer (J.O.) to all parties of interest.  But NOT before the end of the owner's 60-day period to obtain his/her own appraisal.

File Notice of Lis Pendens with attached copy of J.O. in the office of the Register of Deeds within 14 days of the service of the J.O.

If the owner(s) rejects or ignores the J.O. within the 20 days provided by Statute, then prepare, approve and serve Award of Damage along with payment.

Attempts to negotiate will continue through the J.O. period.

Record the award with Register of Deeds after payment made to owner or to Clerk of Court.

Do not amend an award of damages or continue to negotiate after the award is recorded.

- Certification

Forward the Certification of Local Public Agency (LPA) Right of Way Acquisition (form LPA3028) along with the WisDOT Certificate of Right of Way (form RE1899) to your LPREPM.

- Reimbursement:  If Fed/State funds used in R/E, send completed reimbursement request with all documentation to WisDOT Region LPA Coordinator as soon as practical.  NOTE:   In order to receive reimbursement for property owner appraiser fees, a form “Criteria for FHWA Reimbursement of LPA Property Owner Appraisal Fees” is required as part of the reimbursement package.

- If your project involves the relocation of a residence or business, contact your LPREPM.

- If you have any questions concerning the real estate process, refer to the Local Program Real Estate Manual  or contact your LPREPM.