## Schedule
Task | Scheduled Dates |  | Actual | Additional Days | Comments
Real Estate Project Start Date | 2022-10-01 | 26 months before PS&E |  | 0 |  | modules in learn center
Conceptual Stage Reocation Plan | 2022-10-01 |  |  | 0
Real Estate/Utility Coordination |  |  |  | 0
Encumbrance Cost Estimate/PCA Completed | 2022-10-08 | 30 days before prelim plat |  | 0
Preliminary Plat submitted to RE | 2022-11-07 | 21 days before scoping completion |  | 0
Appraisal & Acquisition Scoping Completed | 2022-11-28 | 21 days before contract started |  | 0
Contracts started | 2022-12-19 | 56 days before contract complete |  | 0
Setup Project in READS | 2023-01-30 | 7 days before DSR Approval |  | 0
DSR Approved | 2023-02-06 | 14 days before plat recording |  | 0
Consultant (acq, relo, appraisal) Contracts Completed / Internal staff assigned | 2023-02-13 | 21 days before start up meeting |  | 0
Plat Recorded | 2023-02-20 | 14 days before start up meeting |  | 0
Start Up Meeting | 2023-03-06 | 42 days before sales study submitted |  | 0
Sales Study Submitted for review | 2023-04-17 | 40 days before Sales study Approval |  | 0
Acquisition Stage Relocation Plan | 2023-05-21 | 90 days after plat recorded |  | 0
Staking | 2023-05-20 | 21 days before NPPR submitted |  | 0
Sales Study Approved | 2023-05-27 | 14 days before NPPR submitted |  | 0
NPPR submitted for review | 2023-06-10 | 21 days before NPPR approved |  | 0
NPPR Approved | 2023-07-01 | 21 days before nominal offers out |  | 0
Nominal offers out | 2023-07-22 | 30 days before flipping |  | 0
Flip remaining nominals | 2023-08-21 | 45 days before appraisal submission |  | 0
Appraisal submitted for review | 2023-10-05 | 60 days before apraisal approval |  | 0
Contract Amendment |  |  |  |  | enter additional days as needed
Appraisal approved | 2023-12-04 | 14 days before offer date |  | 0
Offer/relocation packet to owner | 2023-12-18 | 90 days before JO date |  | 0
Owner's appraisal due (if applicable) | 2024-02-16 | 60 days after appraisal delivered |  | 0
Finalize agreed negotiations | 2024-03-03 | 14 days before JO date |  | 0
Last date to JO | 2024-03-17 | 45 days before Target date |  | 0
Order Checks | 2024-03-23 | 21 days before paying owner |  | 0
JO expiration date | 2024-04-06 | 20 days after JO |  | 0
Owner Paid | 2024-04-13 | 7 days before recording |  | 0
Signed Conveyance Recorded | 2024-04-20 | 7 days after Owner paid |  | 0
Award recorded | 2024-04-20 | 14 days after JO Expiration |  | 0
Relocations vacated | 2024-06-04 | must be vacated before razing contract awarded |  | 0
Razing (begin contract docs, contact BPD, Advertise, bid opening, Contract award, Demo) | 2024-06-04 | begin 6 months before PS&E |  | 0
Target Acquisition Date/Utility date | 2024-05-01 | 7 mths before PS&E |  | 0
Documents submitted for Review (LPA) | 2024-11-03 | 28 days before PS&E |  | 0
Relocation Assistance & Advisory Services |  | relocation assistance and advisory services are on going through the acquisition process and until up to 2 years after vacate date.
PS&E | 2024-12-01 |  | 2024-12-01 | 0
Ad
Let date
# days | 780
#months | 26
Formulas:
Scheduled Dates = [Scheduled Dates, row above]
Scheduled Dates = [Scheduled Dates, row below]-30
Additional Days = IF([Actual]="",0,DAYS([Actual],[Scheduled Dates]))
Actual = SUM([Scheduled Dates],E2:E37)
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (factors include: complex parcels, relocations, appraisals, 15+ parcels)
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: compared to Preferred Schedule

## Project Wide Estimates
Project Wide Estimates |  |  |  |  | Blue means data can be entered |  |  | Orange means these cells are autofilled
| PROJECT I.D. | 123-45-6789
| NAME OF ROAD | Smith Street to County Line | [5 empty] | DATE | 2020-07-01
| HIGHWAY NO. | STH 123
| COUNTY | Acme | [5 empty] | PREPARED by | JPA
|  |  | R/E | PROJ |  |  |  |  | RELOC | SITE | TOTAL | TOTAL | Type descriptions and units can be modified for project needs
|  | NO. of | MANG'T | ADMIN | REVIEW | NOMINAL | APPRAISAL | NEGO | ASS'T | CLEARANCE | WITH STAFF | WITHOUT
| TYPE OF PARCEL | PARCELS | 104 | 241 | 255 | 253 | 254 | 256 | 247 | 260 | APPRAISALS | APPRAISAL
| WAIVER OF APPRAISAL | 1 | 0.1 | 0.9 | 0.25 | 1 | 0 | 1 | 0 | 0 | 3.25 | 3.25
| NOMINAL | 1 | 0.1 | 0.9 | 0.5 | 1 | 1 | 1 | 0 | 0 | 4.5 | 3.5
| INTERMEDIATE | 1 | 0.1 | 0.9 | 1 | 0 | 4 | 2 | 0 | 0 | 8 | 4 | Type of Land | price/unit | unit | Comments
| INTERMEDIATE IMPROVED | 1 | 0.5 | 1 | 1 | 0 | 4 | 2.5 | 0.2 | 0.2 | 9.4 | 5.4 | Agricultural 1 | 0.25 | sf | Irrigated
| MAJOR | 1 | 0.5 | 2 | 1.5 | 0 | 7 | 3.5 | 0 | 0 | 14.5 | 7.5 | Agricultural 2 | 0.1 | sf | non-irrigated
| MAJOR IMPROVED | 1 | 0.5 | 2 | 1.5 | 0 | 7 | 4 | 4.5 | 2.5 | 22 | 15 | Residential 1 | 0.57 | sf | under 2 ac
| COMPLEX | 1 | 0.5 | 2 | 2 | 0 | 10 | 4.5 | 0 | 0 | 19 | 9 | Residential 2 | 0.34 | sf | over 2 ac
| COMPLEX IMPROVED | 1 | 1 | 2 | 2 | 0 | 10 | 4.5 | 5 | 2.5 | 27 | 17 | Commercial 1 | 1.15 | sf | under 1 ac
| TOTAL PARCELS | 8 | 3.2 | 10.8 | 9.5 | 1 | 43 | 22 | 9.7 | 5.2 | 104.4 |  | Commercial 2 | 0.92 | sf | over 1 ac
|  | do not change these numbers | [6 empty] | 9.7 | WORKDAYS | 104.4 |  | Industrial 1 | 1.03 | sf | in industrial park
| SIGNS PARCELS | 1 | [6 empty] | 1 |  | 105.4 |  | Industrial 2 | 0.69 | sf | rural industrial
[9 empty] | 10.7 |  |  |  | Other 1 | 1.72 | sf | waterfront
| TOTAL PARCELS & SIGNS | 9 | [10 empty] | Other |  | ac
[8 empty] | Total Parcels & Sign Mandays | Workdays |  | 105.4
* 254 If two staff appraiser double figure.
| ** 246 If relocatees 8.0 days "have been" added. | [8 empty] | Add Ons | 0
*** 260 Add days for rental or sale if Major project requiring significant time
[8 empty] | TOTAL PROJECT WORKDAYS |  |  | 105.4
|  | 105.4 | DAYS X | 338.56 | = | 35684.224
|  |  | ( SAY ) | 35700

## Property Comparables
Address/Location | Conveyance # / MLS # | Town/Village | Zoning | Property Type | Sale Date | Tax ID | Acres | Sq ft | Price | Price/acre | Price/Sq Ft | Property Characteristics | Comments
7500 Smith St | WD 456 | T Maple Grove | Ag 1 | Ag | 2022-01-08 | 12-4567-235 | 40 | 15742400 | 200000 | 5000 | 0.012705 | open ag, level | non-irrigated, arm's length
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!
[10 empty] | #DIV/0! | #DIV/0!

## Individual Parcel Estimate
PROJECT I.D. | 123-45-6789
NAME OF ROAD | Smith Street to County Line |  |  |  | DATE | 44013
HIGHWAY NO. | STH 123
COUNTY | Acme |  |  |  | PREPARED by | JPA
Blue means data can be entered |  | Orange means these cells are autofilled
Individual Parcel Estimate |  |  |  |  | Delivery - Agency only | [19 empty] | Non-Delivery Estimate
[5 empty] | Appraisal |  | Negotiation |  | Relocation |  | Property Management |  | Site Clearance $ | Extra Expenses Incl. Title updates $ | Admin Cost $ | Total Parcel Size | Fee Size Needed | Fee Value $ |  | Property Type |  |  | TLE Size Needed | TLE Value $ | Fee Acquisition $ |  | TLE Acquisition $ | Improvements & Non-Fee (severance, cost to cure, etc) $ |  | Comments | Relocation $ | Prorated RE Taxes $ | Owners Appraisal $ | Signs / Billboards $ | Hazmat $ | Contingency $ | Orginal Estimate $ | Original Offer $ | Closed Acquistion $ | Litigation $ (if Majors Project) | Difference in Estimate and Actual $ | Comments
Par# (Tax ID#) | Owner Name | Parcel Type | Bike/Pedestrian (Wis Stats 32.015) | Relocation | who | cost | who | cost | who | cost | who | cost | [6 empty] | Zoning |  | PLE Size Needed | PLE Value $ |  |  |  | PLE Acquisition $ |  |  | Cost Breakdown
Wrightstown parcels | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE |  |  | FALSE |  |  | FALSE | [5 empty] | FALSE | FALSE | 0 | FALSE | [8 empty] | 0 | 0 |  |  |  | 0
Totals: | [5 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual:
|  | Parcel Types (see REPM 2.1.3): | [5 empty] | Who | Yes | [9 empty] | Zoning | Property Type
|  | WAIVER OF APPRAISAL |  |  |  | W
ONLY add rows to the end of the list |  | NOMINAL |  |  |  | N |  | In-house | No | [9 empty] | Residential | Agricultural 1
|  | INTERMEDIATE |  |  |  | I |  | Workshare | [10 empty] | Multi-Family | Agricultural 2
|  | INTERMEDIATE IMPROVED |  |  |  | II |  | Consultant | [10 empty] | Commercial | Residential 1
|  | MAJOR |  |  |  | M | [12 empty] | Industrial | Residential 2
|  | MAJOR IMPROVED |  |  |  | MI | [12 empty] | Agricultural | Commercial 1
|  | COMPLEX |  |  |  | C | [12 empty] | Recreational | Commercial 2
|  | COMPLEX IMPROVED |  |  |  | CI | [13 empty] | Industrial 1
Industrial 2
Other 1
|  | Bike/Ped Type | [17 empty] | Other 2
Bike/Ped
Roadway
Both
Other
Note on N7: demo costs if handled through real estate (consult property management)
Note on O7: partial release fees, recording fees, etc.
Note on R7: From TPP. Do NOT include unit
Note on U7: Category property falls under for $/unit purposes
Note on X7: From TPP. Do NOT include unit
Note on AC7: site improvements, buildings, severance, cost to cure, HE or anything unique
Note on AE7: describe impacts
Note on AF7: $ to relocatees (Consult Relocation agent)
Note on AG7: Estimated $ DOT will be responsible for (acquisition to year end)
Note on AI7: on-premise or off-premise. (consult Central office for off-premise)
Note on AJ7: Cost to remediate i.e, aspbestos inspections, lead paint dipsosal, etc.
Note on AM7: Manually enter DOT original offer $
Note on AN7: Total acquitision cost (including prorated taxes, relocation costs, hazmat, owenr's appraisal, etc after closing (used )for tracking purposes)
Note on AO7: Total Litigation costs (including settlement amount, attorney fees paid, etc after litigation is completed) (used for tracking purposes)
Note on AQ7: explain reason for divergence between estimate and actual
Note on A8: TPP # (County Tax Id#)
Note on B8: From title work or county records
Note on C8: See REPM Definitions
Note on D8: Is the parcel for the sole use of bike/ped, only project or both?
Note on E8: includes displacements and personal property moves
Note on V8: From TPP. Do NOT include unit
Note on W8: not auto calculated. Varies on each PLE. Must manually enter
Note on AD8: show $ for each impact in previous column

## Delivery Hours
Delivery Hours |  |  |  | Blue means data can be entered |  |  | Orange means these cells are autofilled
| PROJECT I.D. | 123-45-6789
| NAME OF ROAD | Smith Street to County Line |  |  |  | DATE | 44013
| HIGHWAY NO. | STH 123
| COUNTY | Acme |  |  |  | PREPARED by | JPA
Do Not Change This Table. It is autofilled.
|  |  | R/E | PROJ |  |  |  |  | RELOC | SITE | TOTAL | TOTAL
|  | NO. of | MANG'T | ADMIN | REVIEW | NOMINAL | APPRAISAL | NEGO | ASS'T | CLEARANCE | WITH STAFF | WITHOUT
| TYPE OF PARCEL | PARCELS | 104 | 241 | 255 | 253 | 254 | 256 | 247 | 260 | APPRAISALS | APPRAISAL
| WAIVER OF APPRAISAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NOMINAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INTERMEDIATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INTERMEDIATE IMPROVED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAJOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAJOR IMPROVED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMPLEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMPLEX IMPROVED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL PARCELS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | WORKDAYS | 0
| SIGNS PARCELS | 0 | [6 empty] | 0 |  | 0
0
| TOTAL PARCELS & SIGNS | 0
[8 empty] | Total Parcels & Sign Mandays | Workdays |  | 0
* 254 If two staff appraiser double figure.
| ** 246 If relocatees 8.0 days "have been" added. | [8 empty] | Add Ons | 0 | Can add or subtract workdays for project needs
*** 260 Add days for rental or sale if Major project requiring significant time
[8 empty] | TOTAL PROJECT WORKDAYS |  |  | 0
|  | 0 | DAYS X | 338.56 | = | 0
|  |  | ( SAY ) | 0

## Conclusion
PROJECT I.D. | 123-45-6789 |  | DATE | 44013
NAME OF ROAD | Smith Street to County Line
HIGHWAY NO. | STH 123 |  | PREPARED by | JPA
COUNTY | Acme
Delivery | [7 empty] | This Autofills. Do NOT Change
| Appraisal | Negotiation | Relocation | Property Management | Administrative | Site Clearance | Extra Expenses
I/E | 0 | 0 | 0 | 0 | 0
C/E | 0 | 0 | 0 | 0 |  | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total I/E | 0
Total C/E | 0
Total Delivery | 0
Non-Delivery | Fee | TLE Acquisition | Non-Fee |  |  |  |  | Owners | 20% of fee/non-fee
| Acquisition |  | Acquisition | Relocation | RE Taxes | Signs | Hazmat | Appraisals | Contingency
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Parcels closed past time to appeal removed from litigation.
Total Non-Delivery | 0
PROJECT ESTIMATE | 0
Appraisal Status
No Offers
Pending DOT Offers | 0
Closed | 0
Total | 0
Project Budget (FIIPS)

## Parcel Scoping Checklist
PROJECT I.D. | 123-45-6789 |  |  |  |  | Date Completed:
NAME OF ROAD | Smith Street to County Line |  |  |  |  | Person Completing Form:
HIGHWAY NO. | STH 123
COUNTY | Acme
Green means data can be entered |  |  |  |  | Yellow means these cells are autofilled
Parcel Scoping Checklist |  |  |  |  | Agent/Leadworker to verify that Autofilled cells are accurate before sending to negotiator/appraiser. Appraiser to verify information as part of appraisal process | [18 empty] | POTENTIAL SEVERANCE DAMAGE
Parcel # (Tax ID #): | Owner Name: | Parcel Type: | Bike/Ped (Wis Stats 32.105) | Priority Parcel: | Existing Use: | Zoning: | Owner Concerns: | Total Parcel Size: | Fee Size: | TLE Size: | PLE Size: | HE Size: | Existing ROW Size: | Appraisal: | Appraisal Type: | Encroachments (Describe): | Improvements Impacted: | Site Improvements: | Building Improvements (house, garage, shed, etc.): | Signs: | On or Off-Premise Signs (Describe): | Potential Separate Entity (Y/N): | Potential Alternate Offer (Y/N): | Proximity (Y/N): | Grade Change (Y/N): | Circuity (Y/N): | Access (Y/N): | Loss of Parking (Y/N): | Other Severance (Describe): | Need for Third Party Estimates (Y/N): | Partial Releases (Y/N): | Easemnts / Other Parties of Interest | Relocation Y/N | Comments
Wrightstown parcels | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  |  | N |  |  | N |  |  | N | [12 empty] | 0 | 0
ONLY add rows to the end of the list
Appraisal Types
Short Form
Standard Abbreviated
|  | Parcel Type |  | Priority Marker | Existing Use | [9 empty] | Before & After
|  | N - nominal |  | High | Agricultural
|  | I - Intermediate |  | Medium | Commercial
|  | II - Intermediate Improved |  | Low | Industrial
|  | M - Major |  |  | Multi-Family
|  | MI - Major Improved |  |  | Recreational
|  | C - Complex |  |  | Residential
|  | CI - Complex Improved |  |  | Special Use
Note on A8: TPP # (County Tax Id#)
Note on B8: From title work or county records
Note on F8: Category property falls under for $/unit purposes
Note on G8: From county or municipality map. Should be available in cost estimate file
Note on I8: From county records or title work. Should be available in cost estimate file
Note on M8: From TPP
Note on Q8: From Encroachment Report or staking
Note on S8: Impacted Screening, flower beds, shrubs, trees, etc.
Note on T8: Any other impacted items
Note on W8: Is the acquistion large enough, have access and dimensions to be a separate buildable site?
Note on Y8: Is the right of way getting significantly closer to the building improvements?
Note on Z8: Is the grade of the road or acquisition area changing significantly?
Note on AA8: internal or external
Note on AB8: acquiring access or changing access that may casue damage (compensable)
Note on AD8: conforming to non-conforming, conventional to holding tank, change of highest and best use, etc
Note on AG8: utility easements, life estate, ingress/egress easement, etc.
Note on AI8: autofilled, but may require changes or additions