## Blank Form
Bridge No.: |  |  |  | Inspection Start Date: |  | 2008-06-10
Bridge Name: |  |  |  | Inspection End Date: |  | 12
Feature On: |  |  |  | Inspection Hours:
Feature Under: |  |  |  | NSTM Inspector:
County: |  |  |  | Inspector No:
Location: |  |  |  | Team Members:
Girder | Span | Location | Feature Inspected | Detail Description | Remarks
General Note:

## Sample
Bridge No.: |  | B-62-755 |  | Inspection Start Date: | 2025-09-23 | 2008-06-10
Bridge Name: |  | Smith Creek Truss |  | Inspection End Date: | 2025-09-24 | 12
Feature On: |  | STH 56 |  | Inspection Hours: | 8
Feature Under: |  | Smith Creek |  | NSTM Inspector: | J. Smith
County: |  | Vernon |  | Inspector No: | 99999
Location: |  | 1.5 MI E JCT STH 82 |  | Team Members: | R. Jones
Girder | Span | Location | Feature Inspected | Detail Description | Remarks
General Note: |  | Web welds to the bottom flanges have many scattered areas of minor undercuts and surface defects scattered throughout. Girders have scattered web fill bolts are not torqued..
1 | 1 | bottom flange (tension zone) | welded cover plate | Welded cover plate on bottom flange with transverse terminaton weld, fatigue detail. | Random areas of active corrosion along edges of bottom flange and along longitudinal welds of cover plate. Transverse termination welds have light speckle rust. No visual cracks found. Photo taken to show typical conditon.
1 | 1 | Field Splices at FS 9-2 | Bolted Connection | Bolted Splice Plate Connections | Bottom flange interior has 2 bolts not torqued due to clearance issues. See photo #19.
1 | 1 | Web Tension Zone | Welded Connection | Transverse diaphragm to web welds, stiffener end welds and tension butt welds.
1 | 1 | Bot. Flange Tension Zone | Welded Connection | Longitudinal and transverse tension butt welds.
1 | 1 | Top Flange Tension Zone | Welded Connection | Longitudinal and transverse tension butt welds.
1 | 1 | Field Splices at FS 10-1 | Bolted Connection | Bolted Splice Plate Connections
1 | 2 | Field Splices at FS 10-2 | Bolted Connection | Bolted Splice Plate Connections
1 | 2 | Web Tension Zone | Welded Connection | Transverse diaphragm to web welds, stiffener end welds and tension butt welds.
1 | 2 | Bot. Flange Tension Zone | Welded Connection | Longitudinal and transverse tension butt welds.