## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20161213 | 20161213001 | 1 | Structure B-13-726 | On page 205/sheet 10 of structure B-13-726, it references a beveled anchor plate, see â€œbearing detailsâ€ sheet; however, I can not find any plate details. Is this a typo or are the plate details missing? | This note was an error on Sheet 10. The note that currently states â€œBeveled Anchor Plate, See â€œBearing Detailsâ€ Sht.â€ and the bold/hatched area that the note points to should not be there. No anchor plates are necessary. | Scott Lawry | 1 | 2016-12-05 16:09 | 2016-12-05 16:09
20161213 | 20161213001 | 1 | B-13-726 | The #4 stirrups are listed with a 4â€ leg. Traditionally, the leg has always been 4 1/2". Please confirm the length of the leg. The #3 epoxy hairpin bar should also be 5-5/8" not 5/8". Please confirm the correct length. Also, just a note the end of the girder depicted on the right-side is not correctly drawn as it is not symmetrical to the left-side. | The #4 stirrup bars should be 4 ½â€, not 4â€. The #3 epoxy hairpin bar should be 5-5/8â€, not 5/8â€. The observation that the girder is not drawn symmetrically is correct, but the correct symmetrical reinforcing is called out. | Scott Lawry | 2 | 2016-12-05 16:40 | 2016-12-07 12:21
20161213 | 20161213002 | 2 | Earthwork Data for ID 1071-06-82 | Please provide Computer Earthwork Data (station to station listings) for Project ID 1071-06-82. | A copy of the earthwork data can be found on the SW regions preliminary plans, specifications, and project information page at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx a direct link the file is below. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1071-06-82/ | Scott Lawry | 1 | 2016-11-10 11:05 | 2016-11-17 16:47
20161213 | 20161213002 | 2 | Plantings | What size pot are the perennials and grasses supposed to be? | All the perennials (forbs and grasses) are to be #1 size (1 gal). | Mike Coleman | 2 | 2016-11-11 07:59 | 2016-11-14 10:30
20161213 | 20161213002 | 2 | Entry Sign | Detail in the plans calls for 1/4" thick, perforated Cor-Ten steel. SPV's call for 1/2" thick steel. Which thickness is required? | 1/4" is the required thickness of the steel sign material | Scott Lawry | 3 | 2016-11-11 12:34 | 2016-11-14 10:32
20161213 | 20161213002 | 2 | Entry Sign Steel | On the previously answered question, the thickness shows a question mark in the answer. Also, for the perforations on the steel, what size are they, what is the spacing, and are they staggered? Thanks | The answer on the previous question, had a formatting issue and that answer has been corrected. A copy of the design file image is available from Shop Floors by contacting Trygve Wastvedt at (844) 258-5710: --ImageWal-2-1-2 --SN: IW-024595-278603 --www.shopfloorapp.com/ | Scott Lawry | 4 | 2016-11-17 05:16 | 2016-11-17 17:41
20161213 | 20161213002 | 2 | Gravity Wall | Are there any plans or elevations for the modular block gravity wall? | The top of wall elevations are listed on page 114 of the plan. | Scott Lawry | 5 | 2016-11-17 13:53 | 2016-11-17 15:26
20161213 | 20161213002 | 2 | Utility Questions | Bid Form Line Number 1380: What is the material for the 6â€ under drain pipe? Also, does the material need to be wrapped? If so, what is the material specification? Bid Form Line Number 4450: Are the relocated hydrants being moved to a different location in the project or are they being delivered to the city? Bid Form Line Number 4460/4520: Is the hydrant at stationing 151WG+70 going to be cut in with a tee or a wet tap connection? Bid Form Line Number 4500: Does the Ductile Iron pipe need Nitrile gaskets or is it just the fittings? Bid Form Line Number 4570: What is the existing water service size and material? What is the existing sanitary sewer service size and material? | Bid Form Line Number 1380 â€“ The materials for pipe and wrapping materials can be found in the standard special provisions for this item (Section 612 Underdrains). Note: this item is for Structure B-32-67 and not utilities. Bid Form Line Number 4450 â€“ The hydrants are to be moved to a different location. Each relocated hydrant has a length of hydrant lead associated with it. The new location is expected to be between the back-of-curb and the sidewalk. Bid Form Line Number 4460/4520 â€“ There is a hydrant at 155WG+70. If this is one being referred to, the existing hydrant needs to be removed and a new hydrant and control valve installed. The new hydrant lead should be connected to the hydrant lead. Bid Form Line Number 4500 â€“ Nitrile gaskets will be needed on both water main and fittings that are installed in contaminated soils. Bid Form Line Number 4570 â€“ The water services are ¾ inch copper. Existing Sanitary Sewer â€“ For Item SPV.0090.72. The City of La Crosse assumes the size of the pipes to be 6 inch. Material is not known. | Scott Lawry | 6 | 2016-11-23 10:10 | 2016-11-30 11:37
20161213 | 20161213002 | 2 | Miscellaneous Quantities - Earthwork Summary | Will the department issue a revised earthwork summary that shows earthwork broken down by stages? | The department updated an earthwork summary spreadsheet 10710682_ewl.xlsx via question #1 for this proposal that can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1071-06-82/ and will not be developing additional spreadsheets to split it out by stage. | Scott Lawry | 7 | 2016-11-28 15:02 | 2016-12-02 14:44
20161213 | 20161213002 | 2 | NE Quad | The NE Quad 67,089 CY of available cut material. There are two temporary ramps within this area that are constructed prior to the NE Quad material becoming available. The Temp. Ramp GY is a net short of 4,821 CY in Stage 1A/B and the Temp. Ramp GZ is a net excess of 9,627 CY in Stage 2A. Has the available cut in the NE Quad taken account of this previous staged temp ramp work? | The available cut in the NE Quad listed in the plan has taken into account the temporary ramp construction as part of the earthwork summary. | Scott Lawry | 8 | 2016-11-29 08:00 | 2016-12-02 14:46
20161213 | 20161213002 | 2 | Plaza Seat Stone and Lawn Seat Stone | Are there other allowed products besides those listed in Articles 61 & 62. There is a 6â€ tolerance on the height and length but 1â€ tolerance on the width for the seat stones can this be explained? | An addendum will be developed to show another product that would qualify as an approved equal for Items 61 and 62. The tolerance for the width of the rocks is smaller for the Seat Stones as the intent of the Seat Stone design is to fit into the same width as the colored concrete bands shown on the plans. | Scott Lawry | 9 | 2016-11-30 12:12 | 2016-11-30 12:20
20161213 | 20161213002 | 2 | CAD files | Will the department be making CAD files for this project available pre-bid? | The department will not be able to put the metadata package together prior to the letting. If there is a specific CAD file that is needed, the department may be able to meet that request and post on the departments HCCI site. | Scott Lawry | 10 | 2016-12-01 09:51 | 2016-12-02 16:32
20161213 | 20161213002 | 2 | Plaza Seat Bench | The tolerance for width is 1". In order to meet this tolerance, the process of drilling and hand splitting will be required to meet the width tolerance. This would only appear on one side of the bench. Is this appearance acceptable to the owner/architect. Thank you, Bob Altmann Rivard Stone 318 Highway 35 and 64 Houlton, WI 54082 612.860.8680 | The plan details require the face of each side of the width to be sawed edge per plan details on page 421. Drilling and hand splitting would not be acceptable. | Scott Lawry | 11 | 2016-12-01 09:56 | 2016-12-06 11:31
20161213 | 20161213002 | 2 | Earth Work Data refer to questions #7 and #1-Quantities by Stage. | Question #7 refers that the answer was provided in question #1. This is not an acceptable answer. The link provided in question #1 is labeled as "preliminary and not for bidding purposes". And, those plan sheets (provided in the link) are not part of the bid package. Therefore the plan set used for bidding is NOT complete. | The department updated an earthwork summary spreadsheet 10710682_ewl.xlsx via question #1 for this proposal that can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1071-06-82/ and will not be developing additional spreadsheets to split it out by stage. The preliminary plans that were previously posted at the above link were provided to industry as a courteously prior the advertisement and have been removed this morning. The correct plan and provisions for proposal #2 can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2016/12December_13/ | Scott Lawry | 12 | 2016-12-02 16:20 | 2016-12-05 11:29
20161213 | 20161213002 | 2 | Seed Mix Design | For SPV.0085.1-3, what are the mix designs for the 3 different seed types listed? | The seeding mixes were based on Prairie Moon Nursery Mixes. Links to each mix are listed below: Native Prairie SPV.0085.01: https://www.prairiemoon.com/seed-mixes/shortgrass-prairie-for-mesic-soils.html Pollinator Mix SPV.0085.02: https://www.prairiemoon.com/seed-mixes/pollinator-palooza-seed-mix.html No Mow Fescue SPV.0085.03: https://www.prairiemoon.com/lawn-alternatives-eco-grass.html | Scott Lawry | 13 | 2016-12-06 15:01 | 2016-12-09 14:34
20161213 | 20161213002 | 2 | Plaza Seat Stones | The Special Provision calls for the Plaza Seat Stones and Lawn Seat Stones to have a width of 24â€. The plan details call this width to be 1â€™6â€ on page 421. Which is correct? | The plan details are correct. The width needs to be 1â€™6â€ for all Plaza Seat Stones and Lawn Seat Stones. | Scott Lawry | 14 | 2016-12-09 09:07 | 2016-12-09 09:08
20161213 | 20161213002 | 2 | Shade Structure Details | Please provide more information on what was used to prepare the Shade Structure drawings/specials. What were the fabric specs based on? | Manufacturer: Shade Systems 1-800-609-6066 Fabric: CoolNetTM polyethylene knitted shade fabric with reinforced corners. Complies with NFPA 701, ASTM-E84, and CAFM-13115. (This is from the manufacturer website) | Scott Lawry | 15 | 2016-12-09 09:09 | 2016-12-09 09:10
20161213 | 20161213002 | 2 | Decorative Bollards | Please provide more information on the types decorative bollards that are to be installed as part of this project. | The Decorative Bollards shall meet the requirements as show in the attached detail sheet. This is based on landscape forms design for FGP Path Light. See link for product information: http://www.landscapeforms.com/en-US/product/Pages/FGP-Path-Light.aspx | Scott Lawry | 16 | 2016-12-09 14:45 | 2016-12-09 14:45
20161213 | 20161213002 | 2 | Decorative Lighting items | There are two decorative lighting special provision items. Do they need to be the same manufacturer and style? | Yes, the intent is to match the lighting unit styles for Decorative Lighting Unit 20-Foot, Item SPV.0060.26 and Decorative Street Light Assembly, Item SPV.0060.97. | Scott Lawry | 17 | 2016-12-09 14:46 | 2016-12-09 14:47
20161213 | 20161213002 | 2 | Item #4390 | Please verify Expedite Bid is showing the wrong quantity for line item 4390. I believe this quantity should be 1 per addendum 1 not 2 as currently shown. Thanks. | Industry will need to bid on this item as they are interpreting the plans, provisions and item totals. | Scott Lawry | 18 | 2016-12-10 13:40 | 2016-12-12 14:31
20161213 | 20161213003 | 3 | Const. Staking - Structure Layout | There is currently not a item listed for Const. Staking - Structure Layout. Will this be added by addendum? | An addendum will be issued to add the bid item Construction Staking Structure Layout B-32-0232, Item 650.6500.01. | Scott Lawry | 1 | 2016-11-17 11:32 | 2016-11-17 17:17
20161213 | 20161213004 | 4 | Storm Sewer Selection Criteria | Some of the materials list for storm sewer that was specâ€™d at Class IV would be eligible for this based on fill height for Class III which would allow for Thermoplastic pipe. (See Spec 608) Why was this specâ€™d that way and would thermoplastic be allowable in this case? The only segments of pipe in the class IV range appear to be 18-18b and 12-13. FDM 13-1-1 paragraph 17.5 â€œThe objective of specifying new materials is to take advantage of advances in materials technology. When new materials are approved for use as alternatives to traditional materials, the competitive bidding process is enhanced. Allowing contractors to bid on the basis of total installed cost for several materials should result in the lowest total cost for the storm sewer system. Therefore, it is desirable to allow all materials that meet engineering requirements for the project.â€ | The reasoning behind choosing class IV was due to the depth of coverage. A number of the pipes (more than just the two runs listed), the pipe runs within a foot of the bottom of the select crush. This was determined by comparing the datum surface which was created, to the storm sewer network in civil 3d, not just off rim and invert elevations or looking at the existing surface line in the storm sewer details. The rim elevation takes into account the concrete pavement depth and base aggregate depth. Even by just looking at the rim elevation compared to the invert, there are a number of other pipes which are right at the bottom of the bottom of the select crush. Due to a majority of the pipes being within a foot of the select crush at some point, we used class IV pipe. | Scott Lawry | 1 | 2016-12-05 15:22 | 2016-12-06 11:15
20161213 | 20161213004 | 4 | CAD Files | Does the department have any CAD files available pre-bid? For example and Grading Datum Surface and an Existing Surface. | The surface files can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213004/ | Scott Lawry | 2 | 2016-12-06 12:33 | 2016-12-07 16:16
20161213 | 20161213004 | 4 | Storm Sewer Bedding | Can on site materials be used for storm sewer bedding or is there a specified bedding material needed other than onsite? | Section 608.3.2 (2) of the standard spec for 2017 states: â€œExcavate trench to at least 6 inches below the elevation established for the bottom of the pipe. Backfill to this depth with foundation backfill. After laying the pipe, place and mechanically compact foundation backfill before laying the pipe. After laying the pipe, place and mechanically compact foundation backfill to an elevation of 12 inches above the pipe to provide full and continuous support.â€ The Foundation Backfill material is defined in 608.2.2.2. | Scott Lawry | 3 | 2016-12-12 08:33 | 2016-12-12 10:25
20161213 | 20161213005 | 5 | Working Hours | With no lane closures allowed during peak hours on this project, will night work be allowed on this be allowed to maximize the working days? | Yes, night work will be allowed. | Scott Lawry | 1 | 2016-12-02 08:18 | 2016-12-02 14:40
20161213 | 20161213007 | 7 | Concrete Approach Slab | On page 1 of the structure plans, there are concrete pavement approach slabs slated for the new structure, yet there is not a bid item. Will a concrete approach slab bid item be added by addenda? | The concrete approach slab and associated plan revisions will be added by Addendum. | Mike Coleman | 1 | 2016-11-10 14:07 | 2016-11-17 10:42
20161213 | 20161213010 | 10 | HMA Base Patching | In the special provision on Page 6 under the Base Patching Paragraph the last sentences states "Base patching HMA will not be measured separately but will be paid for as HMA Pavement 4 MT 58-28." On page 1 of the schedule of items, there is item #0070 Base Patching Asphaltic for 420 ton. This is also list separately on the miscellaneous quantities within the plan set. Can you please clarify if the HMA Base Patching and HMA base patching material will get paid under item #70 Base Patching Asphaltic or if it will get paid under item #0140 HMA Pavement 4 MT 58-28 S. | This issue will be corrected via addendum. | Scott Lawry | 1 | 2016-12-06 15:05 | 2016-12-07 16:20
20161213 | 20161213015 | 15 | Opening to traffic of B-64-07 - Night Work | The repair of the Bridge B-64-07 requires E mix concrete in the deck patches, which needs a 3 day wet cure according to spec. This does not allow for opening to traffic by morning. What do we do? Also the lane rental fee is XXX in the proposal and I do not see an addendum. | Regarding the lane rental fees, the lane rental fee will be $1,250/15-minutes. The department will proceed with the adjustment to the spec removing the 3-day wet cure but adding the strength requirement of min. 3000psi compressive strength before reopening the lane to traffic. This will maintain the requirement to reopen the lane to traffic by morning. both of these will be part of an addendum late today or over the weekend. | Scott Lawry | 1 | 2016-12-08 11:05 | 2016-12-09 15:10
20161213 | 20161213016 | 16 | 0690 Polymer overlay | The line item 0690 Polymer overlay quantity states 5067 SY. When adding the individual structures together the combined quantity is 5040 SY. Which calculation is correct? | 5040 SY is the correct quantity. An addendum will be developed to correct. | Scott Lawry | 1 | 2016-11-28 11:04 | 2016-12-02 08:57
20161213 | 20161213016 | 16 | Topsoil/Salvage Topsoil | What is the intent/difference in using topsoil and salvage topsoil in respective areas? | Salvage topsoil is intended for areas at the SWEF, Park & Ride, and Crossovers. Due to minimal grading depths to get to proposed slopes along mainline IH 41 (median and outside shoulders), waste is intended to be hauled away and new topsoil for restoration would be trucked in. In addition, per Addendum #1, the department will allow topsoil to be used as a substitute for needed borrow material in areas noted specifically in the Addendum. This substitution does not change any payment method for the respective Borrow or Topsoil items. | Scott Lawry | 2 | 2016-12-06 16:28 | 2016-12-06 16:29
20161213 | 20161213016 | 16 | Temporary Barrier | What is the correct quantity for temp barrier wall labeled in the MQs as Sta 1368-19 â€“ 1368+44, what stage is the permanent barrier wall in this area to be built in, and confirm the permanent wall type? | The plan label is incorrect as the station range for temp barrier wall is intended to be 1368+19 â€“ 1384+09. The quantity is accurate in the MQs. This section of temp barrier wall is protecting work for the installation on permanent Type 56A barrier wall. With the protection of this work zone, department is allowing this work to take at contractors choice (not a specific stage). No addendum will be posted for this. | Scott Lawry | 3 | 2016-12-08 13:41 | 2016-12-08 13:42
20161213 | 20161213016 | 16 | French Road Grades | Can the department provide grades on French Road adjacent to the Type 56A permanent wall at Sta 1368+44 â€“ 1383+70? | See construction detail on sheet 31. The department will not be providing additional grades as the Type 56A wall will tie into existing French Road shoulder. | Scott Lawry | 4 | 2016-12-08 13:43 | 2016-12-08 13:43
20161213 | 20161213017 | 17 | Storm Sewer | There are 5 each 2 x 2 Inlets listed in the bid quantities for project 1210-12-71. There is no information in the misc qtys about these. Plan sheets 192 - 194 show them as proposed inlets and give an elevation. Does not say if this is Rim or invert? What are we supposed to be building at these locations? | An addenda will be issued to address missing information in miscellaneous quantities, the inlets on project 1210-12-71 are either adjusting or reconstruct inlets, the elevations provided are rim elevations. There will be items changed in addenda and existing elevations will be provided. | Scott Lawry | 1 | 2016-11-23 09:09 | 2016-11-30 11:26
20161213 | 20161213017 | 17 | Item 509.901.S - Removing Asphaltic Concrete Deck Overlay | With having both the bid item for Removing Asphaltic Concrete Deck Overlay and the Cleaning Deck items (509.0500), should it be considered that the Removing Asphaltic Concrete Deck Overlay is only for the Removal of the asphalt overlay and that the Cleaning of Decks item will be used on all structures? | Removing Asphaltic Concrete Deck Overlay and Cleaning Decks items will both be used on the structures that have Asphaltic Concrete overlays. The contractor means and methods to accomplish the work specified under these items is up to the contractor. | Scott Lawry | 2 | 2016-12-02 13:45 | 2016-12-05 08:43
20161213 | 20161213017 | 17 | Concrete Joint and Crack Cleaning | In special for Concrete Joint and Crack Cleaning will the 465 spec with 19 mm or 12.5 mm mix be allowed to be used instead of 315 spec which has a 1â€ nominal size aggregate? | Yes the Section 465 specifications with a 19 mm or 12.5 mm mix will be allowable for use in Concrete Joint and Crack Cleaning. | Scott Lawry | 3 | 2016-12-07 16:06 | 2016-12-07 16:07
20161213 | 20161213018 | 18 | B-36-231 Piling Designation | Bid item #990 indicates that 10.75"x.219" CIP piling would be used for structure B-36-231. Per the structure plans all piling in this structure is to be 10.75"x.250". Please clarify quantities and pile types. | The item #990 was incorrectly added, the piling should all be 10.75â€x.25â€ CIP Piling, so bid item # 990 should go to 0 and item # 1000 should be increased to 7250 LF. This will be addressed in a forthcoming addendum. | Scott Lawry | 1 | 2016-11-29 09:28 | 2016-12-02 15:11
20161213 | 20161213018 | 18 | Temporary Barrier Wall | Can additional details be provided on the locations and intent for the temporary precast barrier other than what is shown in the Misc. quantities table. It is difficult to determine which stage(s) the block will be required in, whether or not it will be sitting on a paved shoulder, whether or not a connection to the existing bridges is required, etc. | Temp Barrier that is in Northbound lanes is to be installed in Stage 1 and remain up until the end of Stage 2, only the temp barrier at South crossover will need to be installed in Stage 3 and remain for Stage 4 (the stationing is incorrect in plans it should read SB 1199+35 SB â€“ 1203+35 SB) Also in regards to connection to bridges and placement location, the construction details on pages 16-17 lays out the placement of temp barrier at bridge structures and these will have to follow standard details for connection to structures. The intent of the concrete barrier is to provide protection of structure when bi-directional traffic is placed on Northbound roadway, where there is no guardrail currently present. New guardrails and proper grading will be done in Southbound lanes during stage 2 at the structures, so no temporary guardrail will be needed at these structures. | Scott Lawry | 2 | 2016-12-01 11:49 | 2016-12-02 14:51
20161213 | 20161213018 | 18 | Item 509.901.S - Removing Asphaltic Concrete Deck Overlay | With having both the bid item for Removing Asphaltic Concrete Deck Overlay and the Cleaning Decks items (509.0500), should it be considered that the Removing Asphaltic Concrete Deck Overlay is only for the removal of the asphalt overlay and that the Cleaning of Decks item will be used on all Structures? | Removing Asphaltic Concrete Deck Overlay and Cleaning Decks items will both be used on the structures that have Asphaltic Concrete overlays. The contractor means and methods to accomplish the work specified under these items is up to the contractor. | Scott Lawry | 3 | 2016-12-02 13:49 | 2016-12-05 08:42
20161213 | 20161213018 | 18 | Structures | On structure B-36-231, the quantity for Concrete Masonry Bridges on Piers 1 & 2 appears to be wrong, is this the case? | The quantity of Concrete Masonry Bridges is incorrect, an amendment will be issued for this change either late today or Monday. | Scott Lawry | 4 | 2016-12-09 14:37 | 2016-12-09 14:37
20161213 | 20161213019 | 19 | Storm Sewer and Culverts | According to the WisDOT FDM, the following COMPETITIVE bid item changes would be appropriate: - 608.3612 Storm Sewer Pipe Class III-B in lieu of 608.0312 - 608.3615 Storm Sewer Pipe Class III-B in lieu of 608.0315 - 608.3618 Storm Sewer Pipe Class III-B in lieu of 608.0318 - 608.3621 Storm Sewer Pipe Class III-B in lieu of 608.0321 - 608.3624 Storm Sewer Pipe Class III-B in lieu of 608.0324 - 608.3630 Storm Sewer Pipe Class III-B in lieu of 608.0330 - 608.3636 Storm Sewer Pipe Class III-B in lieu of 608.0336 These bid item changes are appropriate being that the installations are as follows: - With an agency responsible for maintaining the storm sewer that approves the use of the alternate material (Two Rivers) (FDM 17.4.1) - Within approved diameter range (12â€-36â€) (FDM 17.4.2) - Not located underneath lane of traffic with design AADT above 7000 (FDM 17.4.3) - Within approved fill heights (2â€™-15â€™) (FDM 17.3 Table 17.1) For further information see FDM 13-1-1 paragraph 17.5 | The design team has reviewed the question to allow the use of the items asked for, the department is not going to change the items in the proposal. The reasons includes maintaining authority preference, timing and consistency between new and existing storm systems. | Scott Lawry | 1 | 2016-12-05 13:44 | 2016-12-07 12:37
20161213 | 20161213019 | 19 | Electrical, Curb & Gutter and dowel bars | #1 For the Rectangular Rapid Flashing Beacon specified for this project, will the Carmanah SC315 be acceptable option to use for this project? #2 Is curb and gutter to be sealed and paid for under the item Concrete Joint Sealing SPV.0180.02? #3 Will items of drilled dowel bars, sawing concrete and concrete removal be added to the contract for the areas of colored crosswalk? | #1 We have reviewed the information for the Carmanah SC315, this product will be an acceptable option for this project. #2 All longitudinal, transverse and construction joints (In pavement & curb and gutter) shall be sealed and will be paid based on the SY of Concrete Pavement 8-inch #3 No items will be added to the contract, means and methods of the work up to the contractor. | Scott Lawry | 2 | 2016-12-07 16:29 | 2016-12-07 16:34
20161213 | 20161213019 | 19 | Bid item #1660 SPV.0035 backfill sanitary and water utility | According to the specials we only get paid for this item if we import backfill material from a place other than the Cityâ€™s owned pile? If we use the Cityâ€™s material it does NOT fall under this pay item, correct? | The intent of the item Backfill Sanitary and Water Utility, Item SPV.0035.01, is to pay for backfill from a source, either the material owned by the City of Two Rivers (Mirro Dr) or from another Contractor source from somewhere else meeting the requirement for backfill. The contractor could use a combination of both also, but price would remain the same as in bid proposal. | Scott Lawry | 3 | 2016-12-12 12:17 | 2016-12-12 12:18
20161213 | 20161213020 | 20 | Estimated Quantity | Line No. 0610 Item No. 624.0100 Water lists an Estimated Quantity of 400 MGAL. This undistributed quantity seems rather large for the amount of Base Aggregate Dense being utilized within this project. Please review this quantity and advise. Thank you. | The 624.0100 Water item was intended to be reduced when the 631.0300 Sod Water item was added for watering seeded areas as outlined in the special provisions. The quantity will be revised via addendum prior to the letting. | Scott Lawry | 1 | 2016-11-17 15:53 | 2016-11-18 13:49
20161213 | 20161213020 | 20 | Prosecution and Progress | It is anticipated that the Notice to Proceed will be issued by August 3, 2017. Implement the detour no later than September 5, 2017. Can the detour be implemented on August 3, 2017-the date of the Notice to Proceed? | Yes the detour can be implemented as long as USH 10 work begins at that same time. As shown in the Prosecution and Progress and Traffic articles, USH 10 will be constructed under detour. If the contractor opts to use any single lane closures before the USH 10 detour is implemented, the restrictions are provided in the Traffic article. | Scott Lawry | 2 | 2016-11-18 08:09 | 2016-11-18 13:46
20161213 | 20161213020 | 20 | Adjusting Manholes and Inlets | Special provisions include statements about rubber rings, plan Sheet 21 has a note associated with one particular location as noting the use of Rubber Rings. Is this special provision relative to only this one location OR ALL Structures either built, reconstructed or adjusted on this project? | Rubber adjusting rings must be used on the one inlet shown on Sheet 21 as called out in the special note. The contractor can use rubber or concrete rings in accordance with this provision and Standard Spec on the remaining structure adjustments or placements. | Mike Coleman | 3 | 2016-11-23 10:09 | 2016-11-23 12:18
20161213 | 20161213021 | 21 | Temporary Barrier Bid Items | Would you be able to provide clarification on payment for Temporary Barrier Left in Place (SPV.0090.209)? Is the payment for delivered and installed included in items 603.8000 and 603.8125? Also, under the item of maintain and remove barrier (SPV 0090.208), the plan indicates 27,610 lf as removed in stage 1. Is the assumption correct that this barrier is completely removed from the project in stage 1, or is it intended to be used as Left in Place barrier as shown in stage 1. If that is the case, how is the delivery and installation of the Left in Place barrier paid? All in all, we are having a difficult time understanding how only 6896 lf is delivered to the project and 12,760 lf is left on the project but 49,524 lf is to be removed from the project??? | 1. The payment was for delivered and installed but by updating the quantities per the note below means this item is likely no longer needed and will be addressed with an addendum. 2. Maintain and remove barrier is concrete barrier temporary precast that was placed in the location shown in the plans under a previous contract. The intent is to maintain the barrier in its current location until it is no longer needed on the project. All maintain and remove barrier is required for the duration of Stage A on IH-41, as well as Stage 1 on USH 10. Much of the maintain and move barrier will remain in place for the duration of stage 2A on USH 10 as well. If the barrier is to be moved to a new location in a subsequent stage, the move will be paid for under installation. 3. Concrete barrier temporary precast quantities will be updated to correct this discrepancy in an upcoming addendum. | Scott Lawry | 1 | 2016-11-16 14:10 | 2016-11-18 12:54
20161213 | 20161213021 | 21 | Removing rumble strips | It appears that rumble strips northbound have been removed on previous projects; could you please verify bid item quantity? | It has been confirmed the northbound rumble strips were removed under a previous project. The quantity for the northbound strips will be removed under an Addendum. | Scott Lawry | 2 | 2016-11-23 11:26 | 2016-11-29 18:01
20161213 | 20161213021 | 21 | Need Cross sections for Noise Barrier walls | Please provide cross sections for the applicable noise barrier walls. Thank you | Sections in the area of wall N-70-100 will be provided as part of Addendum #2. Sections in the area of wall N-70-101 from the plans for project ID 1517-75-75 and can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2015/07July_14/20150714019plan.pdf pages 943-947. This wall is to be attached to previously constructed retaining wall R-70-120 which can be seen in the sections. Sections in the area of wall N-70-110 are in the plans pages 933 â€“ 938. | Scott Lawry | 3 | 2016-11-28 13:05 | 2016-12-08 13:09
20161213 | 20161213021 | 21 | Structures | 1. Plan sheet 745 refers to plan sheet for retaining wall R-70-120 for the noise barrier 101 connection details. I could not find in plan set. Can you please send? 2. The specification calls for design to AASHTO LRFD Bridge Design Specification and SM windload of 37.5psf however plan sheet 745 calls for Sound Barrier Design Guide with interims (this has been replaced by the AASHTO LRFD Bridge Design Specification) and a windload of 42psf. Can you confirm which windload is correct and if it is acceptable to design to the latest AAASHTO LRFD Bridge Design Specification with 2016 updates? | The structure plans for R-70-120 can be found in the plan set that was let in July 2015, the file is located at ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2015/07July_14/20150714019plan.pdf | Scott Lawry | 4 | 2016-11-29 17:44 | 2016-11-29 18:19
20161213 | 20161213021 | 21 | Noisewall Construction | The current staging plans do not account for construction of the N-70-100 Noisewall. Will EB 10/441 traffic be closed for a long enough duration to allow access for construction of this wall? There also is a utility conflict with the proposed location of the N-70-100 wall and the recently installed lighting and TIS lines from previous contracts. Will these utilities be moved in order to allow construction of teh noisewall? Can a typical section be provided showing the location of the noisewall relative to the existing utilites and permanent barrier wall? | We account for it in the specials in stage 1 but it could be installed during any stage. If it is not built in stage 2b, it will need to be built from the fill side. If it is built during stage 2, there will be 90 days. The noise wall alignment will be revised to accommodate the ITS and lighting conduit via post-let revision with minor shifts to the noise wall alignment. No change will be required to the ITS & lighting conduit east of ITS & lighting conduit. Conduit will need to be relocated in the area west of Tayco St in order to accommodate construction of the noise barrier. This work is not in the current plans and will either be addressed under a separate contract or as a contract modification. This will be included in the post let revision and conduit location is not expected to be an issue with construction of the noise barrier. | Scott Lawry | 5 | 2016-12-02 14:22 | 2016-12-06 16:08
20161213 | 20161213021 | 21 | Excess Common Excavation | Does DOT have any locations (waste sites) within the interchange that will be available to accept excess common excavation from the 1517-07-80 project? | We have allowed contractors to waste material in the interchange previously and there are currently areas we would allow waste to be placed but bidders should consider that there are other contractors currently working in the interchange that the 1517-07-80 contractor would need to coordinate with. | Scott Lawry | 6 | 2016-12-06 16:14 | 2016-12-06 16:15
20161213 | 20161213021 | 21 | ITEM 2820 Maintain & Remove Temporary Barrier | Item 2820 Maintain and remove concrete barrier temporary precast left in place, indicates a quantity for removal of approximately 50,000 LF. it appears that there is approximately only 25,000 LF of barrier on the current project site. Will the current contract be adding an additional 25,000 lf to get up to the plan quantity of 50,000 lf being removed under this proposal? Can the Department verify the actual amount of barrier to be removed? | This question is very similar to question 1 for this proposal. Please see the answer provided and the upcoming addendum. | Scott Lawry | 7 | 2016-12-08 10:21 | 2016-12-08 14:15
20161213 | 20161213022 | 22 | Item 511.2300 Temporary Shoring Left in Place | The stationing in the Miscellaneous Quantities on sheet 89 seems to somewhat coincide with the shoring shown on sheets 38 and 39. One indicates a 504 linear foot wall while sheets 38 and 39 indicate a 235 linear foot wall. which one is correct? Once that is understood, it would seem the quantity of 228 SF would potentially need to be adjusted. Also, how does the shoring shown on sheet 17 figure into the quantities? | 1) The begin stationing for item 511.2300 shown on sheet 86 of the Miscellaneous Quantities is incorrect. The correct station should coincide with what is stated on sheets 38 and 39 in the plans. Temporary Shoring Left in Place is from STA 227WB+79 to 230WB+13. So the shoring is 228 feet in length. 2) The quantity shown of 228 SF is also incorrect in the plans. The standard bid item 511.2300 is measured in Square Feet and is the area of exposed face in the plane of the shoring from ground line in front of the shoring to a maximum of one foot above the retained grade. The exposed face area is 1,368 SF. An addendum will be done to address this change in quantity. 3) Per the detail on sheet 17, the temporary shoring at existing storm sewer is incidental to the above temporary shoring bid item. The existing storm sewer is within the station limits of the temporary shoring quantity listed above. Sheet 64 of the plans shows the location of the existing storm sewer. | Scott Lawry | 1 | 2016-11-21 15:29 | 2016-11-30 11:14
20161213 | 20161213022 | 22 | Excavation and Waste material | Are there any fill areas available in the 441/41 project corridor that could accept the excess excavation from this project? Can you clarify the detail for the temporary barrier wall backfill from sta. 227WB LT+80 to STA. 230WB+14 LT as to where the excavation volume is covered. Thank you. | Waste can be placed at CTH OO and STH 441. The Contractor is responsible for access construction, site prep, erosion control and complete site restoration following placement of fill. In regards to the temporary barrier wall backfill from sta. 227WB LT+80 to STA. 230WB+14 LT--The excavation is included in the roadway construction quantities. | Scott Lawry | 2 | 2016-11-30 11:45 | 2016-11-30 11:46
20161213 | 20161213022 | 22 | Typical Section Note regarding Base Aggregate Base | What is the intent of the statement â€˜12â€ Base Aggregate Dense 3/4 inch Or 1 1/4 inch Measured As 3/4 inchâ€™? How will this item be paid under 3/4" or 1 1/4"? | The material will be paid for as 3/4 inch and the quantities will be adjusted in an addendum. | Scott Lawry | 3 | 2016-11-30 12:24 | 2016-11-30 12:25
20161213 | 20161213022 | 22 | Temporary Shoring | Use of Temporary Shoring appears to conflict between typical sections and cross sections. | The typical sections are correct. The cross sections are inaccurate showing a 1:1 backslope from the proposed gravel base. Construction will require a 1:2.5 cut from the bottom of the break run. A finished cross section will be a 2â€™ flat ditch from the edge of asphalt to a 1:2.5â€™ finished backslope. This will require a maximum of 5â€™ of exposed shoring. Traffic will be maintained with the final configuration for approximately 1 year. | Scott Lawry | 4 | 2016-12-09 14:41 | 2016-12-09 14:41
20161213 | 20161213023 | 23 | Asphaltic Surface Question | Seeing that the asphaltic surface will be holding 10 / 441 traffic, will it be allowed to be placed in one lift? It will be provide a better quality product with less maintenance potential. The other project that has asphaltic surface being used in the same manner (#22) details 5" one lift. | The Asphaltic Surface can be placed in one lift for Project 1517-75-88 | Mike Coleman | 1 | 2016-11-15 15:57 | 2016-11-16 10:26
20161213 | 20161213023 | 23 | Excavation | Are there any fill areas available in the 441/41 project corridor that could accept the excess excavation from this project? | Waste can be placed at CTH OO and STH 441. The Contractor is responsible for access construction, site prep, erosion control and complete site restoration following placement of fill. | Scott Lawry | 2 | 2016-11-30 11:47 | 2016-11-30 11:47
20161213 | 20161213023 | 23 | Phragmites and loostrife | There are areas in the median of 441/10 that are identified to contain the above mentioned items. It states in the typical that they are to stay onsite and be paid as salvaged topsoil. There is no salvaged topsoil item. How will this be handled? | Only one median area, approximately Sta 352+50 to Sta 353+25, contains purple loosestrife which may or may not be impacted by the project. Any material containing the loosestrife shall be graded in the same location. | Scott Lawry | 3 | 2016-12-08 13:53 | 2016-12-08 15:54
20161213 | 20161213023 | 23 | 611.3225 Inlets 2x2.5-ft | Just wondering where to find these in the plan besides the misc. quantities? | TI 1 â€“ Page 29 TI 2-5 â€“ Page 30 | Scott Lawry | 4 | 2016-12-12 09:45 | 2016-12-12 11:06
20161213 | 20161213024 | 24 | Recycled Concrete Pavement | With the changes in the 2017 Specs, will recycled concrete pavement be allowed as base and/or breaker run? | According to the 2017 Specs, recycled material as base is not allowed below virgin base. It is also not allowed at all under open graded base course. Recycled concrete can be used as Breaker Run since it is considered a subgrade improvement and not part of the pavement structure. On this contract, recycled material could also be used for the 3/4" base under the sidewalks. | Scott Lawry | 1 | 2016-12-01 09:44 | 2016-12-01 09:44
20161213 | 20161213024 | 24 | Pavement Gaps / Access | On page 5 of 47 "Intersection Closure" states to provide 14' wide lane across 4 of the intersections "Pedestrian Access" states 5 intersections require crosswalk access across 8th St. The Plan calls out for 3 intersections to be gapped. Please clarify if there is a time line to allow for the other closures or if there should be more gaps included. | There should be a quantity for a pavement gap at Cedar Street. This will be added via addendum. We will not require the crosswalk at Spruce Street to be maintained at all times and this will also be updated in the spec language via addendum. | Scott Lawry | 2 | 2016-12-06 09:42 | 2016-12-07 12:11
20161213 | 20161213025 | 25 | Railroad Insurance and Coordination | Can the Department provide the published rate for railroad flagging for this project? What poriton of the expenses are covered by the Department when flagging is required by the railraod? Will railroad flagging be required for the structure construction at B-5-35,B-5-408/409 even though they are not within railroad right of way? | The subject project has STSP 107-026 which does not list flagging rates. It would be more appropriate to ask the railroad this question. However, the rates anticipated shown below. Note, the contractor needs to inform the RR that it is a WisDOT project otherwise the standard rates are much higher. --The following rates, reimbursement provisions, and excluded conditions will be used to determine the contractorâ€™s cost of flagging: $1,000 daily rate (including wages, labor surcharges, meals, lodging, vehicle and mileage expenses) for a minimum eight-hour flagging day at the job site; $1,200 daily rate (including wages, labor surcharges, meals, lodging, vehicle and mileage expenses) for a minimum eight-hour flagging day at the job site on Saturdays, Sundays or holidays; $150 per hour overtime rate for all time worked before or after the eight hour flagging day. Flagging costs are incidental to the contract. Flagging will be required if a crane (or other equipment or materials) could fall and land within 25â€™ of the railroad tracks. This question is best confirmed with the railroad. Additional note on the subject of railroads. The CN Railroad is now requiring that all contractors working on railroad right-of-way have Contractor Orientation. The Department is writing new specification language to inform contractors of this requirement, but it is not completed yet. However, it will still be required by CN. For more information, contact CN Railroad. | Scott Lawry | 1 | 2016-11-29 10:10 | 2016-12-06 11:35
20161213 | 20161213025 | 25 | In Stream Disturbance | With the in stream disturbance restriction of March 1 to June 15, it doesn't appear there is enough time to complete construciton of B-5-35 with coincides with the completion of stage 4 and still be able to complete the project. Will a variance be given for the in stream disturbance for B-5-35 construction? | There will not be a variance given for the in stream disturbance for B-5-35 construction. WisDOTâ€™s schedule shows the work completed after June 15. Note, the box culvert B-5-35 is within the closure area for both Stages 4 and 5. | Scott Lawry | 2 | 2016-11-29 10:29 | 2016-12-05 11:31
20161213 | 20161213025 | 25 | Lambeau Field Events | The special provisions indicate that WIS 32 needs to be open to traffic in all lanes for Lambeau Field Events with an expected attendance of 30,000 or more, which also has liquidated damages associated. Who determines the expected attendance criteria? Does this requirement apply to the structure reconstruction at B-5-408/409? If an event is added after the bid date, does this restriction still apply/who pays for the additional measures required to fully open the roadway? | The attendance criteria is based on large scale events (Packer home games, Family Night, college games, concerts). The interim completion date to complete B-5-408/409 overrides the Lambeau Field Events requirement. Once the bridges are completed and open to traffic on or prior to the August 4, 2017 date, the Lambeau Field Events requirement will apply. The restriction would still apply if events are added after the bid date and the contractor would be responsible for additional measures required to fully open the roadway. After the August 4th date, we anticipate the only applicable events to be Packer home games and Family Night, but if a concert, college football game, etc gets added, the 30,000+ requirement still captures these late added events. | Scott Lawry | 3 | 2016-11-29 10:36 | 2016-12-06 16:04
20161213 | 20161213025 | 25 | Earthwork | Q1--Should the earthwork for the railroad crossing be included in a separate division from the grading in the bridge approach area? If the railroad work doesnâ€™t line up with the bridge completion, the material would have to be stockpiled on site for use near the bridge as assumed in the earthwork summary table. Q2--The cross sections for the work at the bridge approaches show an area of cut at the shoulders on some of the sections, but this is not reflected in the earthwork summary table. Should there be a quantity for common excavation for these areas? Q3--Are there cross sections and grading/restoration quantities for the Barrier System grading, shaping, and finishing for the median barrier from station 110+02 NB to 113+18 NB STH 32? | A1--It is likely that the railroad work will be completed prior to the logical time for grading near the bridge. The railroad earthwork will be separated into its own division via addendum. A2--Yes, there is some shoulder replacement anticipated near the bridge approaches. The cross sections are correct. Quantities for common excavation will be added for these areas via addendum. A3--At this location the barrier will only be removed and replaced. The existing median is relatively flat and there is no need for any grading. There may be some restoration needed depending on impact of removal and installing operations and condition of the median at the time of construction (wet or dry), but this should be minimal. | Scott Lawry | 4 | 2016-12-01 09:48 | 2016-12-01 09:49
20161213 | 20161213025 | 25 | Asphalt Paving | 1. In the specials there is note stating that temporary asphalt will need to be placed at locations where there is greater than a 2â€ drop off. I just want to verify that this will not be required if the milling and paving takes place during the anticipated stages as it states the road is closed? Other than stage 1 where it looks like a business will need access, will the road be able to be closed tight or will local traffic be allowed? 2. The typical for the 8â€™ shoulder calls for 3â€ milling but 4â€ HMA to be placed. How will the extra 1â€ of material be removed. I am assuming the designer anticipated the shoulders to be milled at the same depth as the mainline and just take the extra 1â€ of stone with the asphalt but I would just like to verify that. 3. The reheating longitudinal joint QTY seems to be including centerline and the joint between the 8â€™ shoulders and mainline for both lifts. Was this a mistake or is the intent to heat the joint between the shoulder and mainline as well? | 1. The road will be able to be closed tight without local traffic in the stages described in the Special Provisions. Local traffic to business requiring access may be needed as you recognize in Stage 1. If areas are closed to traffic, the 2â€ drop off note will not apply. Only if the contractor proposes and has an approved alternate staging plan to complete work under traffic will the 2â€ drop off need to be addressed. 2. Removing the 1â€ of stone with the asphalt will be acceptable. 3. The expectation is to reheat that shoulder/mainline joint. | Scott Lawry | 5 | 2016-12-05 16:15 | 2016-12-05 16:16
20161213 | 20161213025 | 25 | Asphaltic Paving | Q1: The Asphaltic Surface Milling item is shown as pay plan quantity in the Miscellaneous Quantities table, but the item is not labeled that way in the proposal. Which is correct? Q2: What is the intent for the undistributed 200 ton of Asphaltic Surface Patching? Q3: Looking for more clarification on the joint reheating item. There are constructability issues with mounting the joint heater on an 8â€™ paver when paving the shoulder. Is reheating the shoulder joint needed? | A1: The intent is for this item to be pay plan quantity. The item is shown correctly in the miscellaneous quantities table, but was not correctly entered into Transport as a pay plan quantity item. The status of the item in the proposal will be updated via addendum. A2: The intent of the patching is to repair any areas of the underlying asphalt in poor condition that are found after the milling operation. A3: There was some miscommunication between the design team and technical services on if this item was needed for the shoulder joint. The shoulder joint will not need to be heated. The quantity will be adjusted to remove the shoulder joint length via addendum. | Scott Lawry | 6 | 2016-12-07 16:10 | 2016-12-07 16:10
20161213 | 20161213025 | 25 | Railroad Protective Insurance Policy & Flagging Clarification. | On typical WIDOT projects where the CN tracks may be fouled by a crane boom the department not only includes flagging in the proposal but also requires a railroad protective insurance policy. Will a railroad protective insurance policy be required for this project? When an addendum is issued for the railroad protective policy will the typical language for railroad flagging reimbursement be included in it? | Yes, a railroad protective insurance policy will be required. The railroad insurance and coordination language is included in the special provisions. It does not include the language for railroad flagging reimbursement. Note, question #1 provided a response that flagging costs are incidental to the contract. | Scott Lawry | 7 | 2016-12-08 14:12 | 2016-12-08 16:37
20161213 | 20161213026 | 26 | Sanitary Sewer | Does WisDOT or McMahon has CCTV inspection videos available for the sanitary sewer sections to be lined and also the sections called out for lateral connection sealing. A call in to McMahon on Wednesday, but have not heard anything back yet. | The City of Sheboygan provided videos for of most of the sanitary sections you are looking for. You can download the them from the following site. The files can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213026/ The information also includes a PDF file of a map that shows the sections and manhole numbers. The manhole numbers on the PDF are different than what are shown in our plans, but match the video names. So, you should be able to reference the sections you are looking for on the PDF and match it to the video. The files should cover all the sanitary sections you were looking for except the sections to be lined from 6+15 to 7+82 STH 42 and from 12+21 to 12+31 25th Street (per miscellaneous quantities). additional files have been uploaded today. CAUMET DR 9-26-11-SA-35-51-SA-35-52-2928 N25TH ST0.mpg CAUMET DR 9-26-11-SA-37-6-SA-37-5-2610 CALUMET DR1.mpg Addendum #2 is also being developed to include language to article 54 to explain that these videos are available by contacting the region. | Scott Lawry | 1 | 2016-12-07 16:23 | 2016-12-07 16:53
20161213 | 20161213026 | 26 | Soils Report | is there any soils reports for this project? | A copy of the report is available at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213026/ | Scott Lawry | 2 | 2016-12-12 13:24 | 2016-12-12 13:25
20161213 | 20161213027 | 27 | Earthwork Summary | Does the earthwork detail include the CUT / FILL for the newly proposed passing lanes? I donâ€™t believe it does only because the preliminary plan earthwork summary versus the new earthwork summary did not change a whole lot. Will there be an addendum to clarify earthwork? | The earthwork detail does include the passing lanes. An upcoming addendum is to include the detail sheets as requested, modify some of the notes on the earthwork summary and to correct a computer error in calculating the total common excavation. A copy of the earthwork spreadsheet report can be found on the NE regions preliminary plans, specifications, and project information page at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx a direct link the file is below. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/6110-05-70/ | Mike Coleman | 1 | 2016-11-14 08:32 | 2016-11-14 08:35
20161213 | 20161213027 | 27 | Soils Report | Is there a soils report available for this project? | A copy of the soils report can be found on the NE regions preliminary plans, specifications, and project information page at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx a direct link the file is below. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/6110-05-70/ | Scott Lawry | 2 | 2016-11-17 11:02 | 2016-11-17 16:52
20161213 | 20161213027 | 27 | Cross Sections | The cross sections in the plan do clearly show the EBS limits. Can the be modified to include the ebs and made available to all contractors? | The typical sections and the listing in the miscellaneous quantities under â€œBreaker Runâ€ are deemed to be sufficient for EBS work. | Scott Lawry | 3 | 2016-11-29 15:05 | 2016-12-05 16:25
20161213 | 20161213027 | 27 | Geotextile Fabric, Type SR | The special provisions do not have a section to list the required physical properties of the Type SR. Will the Department be issuing a Special Provision section to clarify the requirements of the Type SR? | The department believes you are referring to Geogrid Type SR, Item 645.0220. This is a new item and industry should refer to the 2017 specifications that are effective with the December letting to determine the physical properties necessary. | Scott Lawry | 4 | 2016-12-01 11:02 | 2016-12-02 15:40
20161213 | 20161213027 | 27 | DTM | Would the Department provide the DTM? | The department will not release CAD files for this project prior the contract execution. The department may provide select surface models if necessary to the successful low bidder after contract execution. | Scott Lawry | 5 | 2016-12-01 12:15 | 2016-12-08 14:48
20161213 | 20161213027 | 27 | Conversion Factors | What conversion factors did the Department use for the 1 1/4" Base and the Breaker Run items? | For 1 1/4" base: CU YD x 2.0 For Breaker run: CU YD x 1.75 | Scott Lawry | 6 | 2016-12-01 15:13 | 2016-12-02 14:47
20161213 | 20161213027 | 27 | Addendum #4 | The addendum adds column #10 - Waste showing 56,627 Cy. The mass ordinate shows 28,992. The difference between the mass ordinate and waste of 56,627 cy equals 27,635. If I add back in 12,000 for borrow the difference is reduced to 15,365. Can you explain where the additional waste of 15,365 is coming from? | The waste number is actually 15,635 CU YD. It consists of EBS plus all of the negative numbers in the mass ordinate column added as positive numbers. Our standard earthwork calculation sheet does not carry negative mass ordinate amounts into the waste column. | Scott Lawry | 7 | 2016-12-12 09:18 | 2016-12-12 12:09
20161213 | 20161213028 | 28 | Line # 0090 Removing Masonry | This item refers to removing part of the existing retaining wall by McDonalds. In the structure plan there is a note that say "Removal of Existing Modular block wall and tying the new wall into the existing modular block wall is included in the bid item "Removing Masonry". Can you clarify what the meaning of tying the new wall into the existing modular block wall, | To allow for proper interlock from existing to proposed modular blocks, the intent of the plan is to remove the existing modular blocks (including top cap block) to the nearest block/joint at the station/offset directed in the structure plan. A vertical sawcut would not be allowed as this would not allow for the interlock between old/new. | Scott Lawry | 1 | 2016-12-06 11:20 | 2016-12-06 16:17
20161213 | 20161213028 | 28 | Common Excavation | In the miscellaneous quantities table for excavation listed on sheet no. 188 could you please explain what type of material is the salvaged /unusable pavement material? Item No. 204.0100 pays for the existing concrete pavement removal. | See typical section sheets 4 â€“ 5. Concrete pavement of varying depths exist currently. The earthwork table is accurate to illustrate the anticipated pavement removed is considered unusable as a fill material as mentioned in Note 4 on sheet 188. Having the designation of unusable material does not discount having its removal being paid under the 204.0100 item. | Scott Lawry | 2 | 2016-12-08 08:43 | 2016-12-08 14:10
20161213 | 20161213029 | 29 | Asphalt paving | Does the temporary lane shifts require asphalt? The lane shift detail shows none. In contrast, the lane shift table in the miscellaneous quantities shows that temporary asphalt is be included. Please clarify what is intended. | The temporary lane shifts do not require asphalt. The quantities identified in the Miscellaneous Quantities sheets for the lane shifts are in error, the proposal quantities are correct. | Scott Lawry | 1 | 2016-12-07 17:41 | 2016-12-08 14:44
20161213 | 20161213033 | 33 | Traffic Control on I-39/USH51 for parapet repairs | Traffic control on I-39 does not appear to be addressed in the plan. The location of the repairs on the parapet walls on B-49-24 would indicate that lane closures will be required on I-39 to safely complete the removal of the deteriorated concrete. | The design intent for the repairs of B-49-24 was to complete repairs that could be constructed from USH 10 without closures to IH 39. (Note that during design, other repair needs were identified that would require longer duration closures on IH 39. Through coordination with the region, it is the intended that these repairs requiring IH 39 closure would be completed with a future IH 39 project to minimize the travel disruption to that facility. In this case, the concrete surface repairs are located on the inside face and the top of the parapets, accessible from USH 10. However, due to the saw cut location on top of the parapet and the proximity of the jackhammering activities to live travel lanes, there may be the potential for small concrete fragments to be generated and become airborne during these operations. To address this, an addendum will be issued to incorporate the item â€œDebris Containment B-49-24â€ into the project. | Scott Lawry | 1 | 2016-12-05 11:27 | 2016-12-05 16:33
20161213 | 20161213034 | 34 | Structure B-49-181 Piling | We understand this project requires the piling to be driven through Pile sleeves after the MSE walls are installed. Is there any reason why the piling cannot be driven prior to the MSE walls being installed then placing the pile sleeves as the fill is brought up thereby avoiding the concerns of the pile hammer energy and vibrations caused by pile driving? | The piling must be driven through the sleeves, after the fill is placed and MSE walls are constructed. The reason for this is that the existing soils are anticipated to settle approximately 4â€ under the weight of the new roadway embankment. If the piling were installed prior to placement of the embankment, this settlement would create a substantial downdrag load on the piles. This downdrag load was initially considered in the design process, but resulted in a foundation design that wasnâ€™t feasible. The pile sleeves allow the embankment to be constructed, and all settlement to occur, before the piling are driven, eliminating the downdrag load. An addendum will be issued to provide further clarification. | Scott Lawry | 1 | 2016-11-15 12:57 | 2016-11-17 15:55
20161213 | 20161213034 | 34 | CAD FIles | Will the department release CAD files for this project pre-bid? | The department will not release CAD files for this project prior the contract execution. The department may provide select surface models if necessary to the successful low bidder after contract execution. | Scott Lawry | 2 | 2016-11-28 16:41 | 2016-12-07 11:50
20161213 | 20161213034 | 34 | Storm Sewers and Culverts | According to the WisDOT FDM, the following COMPETITIVE bid item changes would be appropriate: - 608.3612 Storm Sewer Pipe Class III-B in lieu of 608.0312 - 608.3615 Storm Sewer Pipe Class III-B in lieu of 608.0315 - 608.3618 Storm Sewer Pipe Class III-B in lieu of 608.0318 - 608.3621 Storm Sewer Pipe Class III-B in lieu of 608.0321 - 608.3624 Storm Sewer Pipe Class III-B in lieu of 608.0324 - 608.3630 Storm Sewer Pipe Class III-B in lieu of 608.0330 These respective bid item changes are appropriate being that the proposed installations are as follows: - Not located underneath lane of traffic with design AADT above 7000 (FDM 17.4.3) o With 12â€ lateral exception (FDM 17.4.3 Exception) - Approved with local municipality (Stevens Point) - Within approved diameter range (12â€-36â€) (FDM 17.4.2) - Within approved fill heights (2â€™-15â€™) (FDM 17.3 Table 17.1) For further information on these design changes and competition, please see FDM paragraph 17.5 under section 13-1-1. | The department will not allow substitution of the RCCP storm sewer. The storm sewer is located under the traffic lane and the AADT is greater than 7000. Where the AADT is less than 7000 on the side roads, the cover from top of pipe to bottom of subgrade is less than 2 feet. In addition, these side roads lead into an industrial park with heavy truck traffic. | Scott Lawry | 3 | 2016-12-05 13:49 | 2016-12-07 12:18
20161213 | 20161213034 | 34 | Line # 690 | Are the diameters of the existing manholes available for bidding purposes that are called out in the bid item reconstructing manholes? | Here are the sizes: Sta 15+15 15' Rt Size not available Sta 15+34 2' Rt 48" diameter Sta 41+63 8' Lt 33" diameter Sta 15+85 41' Lt 33" diameter Sta 16+53 47' Rt 48" diameter Sta 30+19 14' Lt 48" diameter Sta 30+70 35' Rt 48" diameter | Scott Lawry | 4 | 2016-12-06 14:58 | 2016-12-08 13:39
20161213 | 20161213034 | 34 | Soils Report | Is a soils report available for this project? | The soils report can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213034/ | Scott Lawry | 5 | 2016-12-07 15:32 | 2016-12-07 16:25
20161213 | 20161213034 | 34 | Structure B-49-181 Piling | If the piling is to be driven after the MSE Wall is installed, who is responsible for any damage (settlement, cracking, etc) that may occur to the installed MSE Wall? We have never installed an MSE Wall prior to installing the piling, as the pile sleeves have always been used after piling was installed to prevent the down-drag mentioned.If a pile location encounters an obstruction during installation, what is the next step? Typically if this happens, a new pile location near the obstructed location is tried. This will not be possible after the MSE Wall has already been installed. Isn't there an increased risk to secondary settlement of the MSE Wall installing the piling after constructed? How is the contractor to install the MSE Wall to the horizontal and vertical tolerances required if it is anticipated that 4"-5" of settlement will occur after installation at the highest portions of the wall. Would pile supporting of the leveling pad be needed to prevent this? |  |  | 6 | 2016-12-09 17:30
20161213 | 20161213035 | 35 | Select Borrow | Why is Select Borrow specified on this project? With a majority of the embankment in slope fills and this being a local low-volume traffic roadway, wouldn't Borrow Excavation be a more appropriate item? | The Pavement Design Report noted the use of select materials, and the geotech report indicated predominantly silt (~14') in the approach fills. | Scott Lawry | 1 | 2016-12-08 23:17 | 2016-12-09 15:14
20161213 | 20161213036 | 36 | Miscellaneous Quantities for Concrete Repairs Special and Concrete Replacements special. | Can stationing of each area, the size of each area, and the lane of each area be provided as is typically provided by WisDOT? | Pages 55 and 56 of the plan detail a location, lane, and approximate size of all the concrete repair and replacement that was anticipated by the design team. Final locations will be marked by the field engineer as is typical/required for concrete patching projects. No further information is available. | Mike Coleman | 1 | 2016-11-13 18:40 | 2016-11-14 10:27
20161213 | 20161213036 | 36 | Temporary Precast Concrete Barrier | Should Temporary Precast Concrete Barrier be added to the project at the locations of the structure wing repairs. Would seem necessary to protect both the traveling public and the construction works. | Yes, it will be added by addenda. | Scott Lawry | 2 | 2016-11-15 09:17 | 2016-11-17 15:23
20161213 | 20161213036 | 36 | Rumble Strip Question | Is the quantity really 705,528 LF? Please confirm the quantity. | Total quantity for rumble strips is correct. However, an addenda will be required to split out concrete rumble strips from asphalt rumble strips. | Scott Lawry | 4 | 2016-12-06 12:11 | 2016-12-08 12:47
20161213 | 20161213036 | 36 | Removal and replacing the ramp edgelines | does the DOT want the lines that are in the removal items of the misc. quantities on the ramps of EB and WB stationing for page 53 of the plans replaced after they are removed? there are no quantities in the Misc quantities to replace, and there is a removal item on the ramps, or is it included in the quantities above the ramp items? If that is the case, there is not enough quantities for the skips for EB and WB lane lines. There are 50 Miles of skip lines that are contrast Wet Reflective Epoxy that was installed 2 years ago, will the DOT be replacing these skips with contrast? Tape? Epoxy? Anything, or will they stay as is?Tried calling. | Markings along the ramps will need to be replaced after they are removed. Quantities are included in the overall station limits listed above the ramp items in the miscellaneous quantity sheets. Quantities were double checked by the design team and are consistent with information provided by Regional Pavement Marking personnel. The plan details replacing all existing markings within the project limits with epoxy per discussions with the Regional Pavement Marking section. | Scott Lawry | 5 | 2016-12-06 15:59 | 2016-12-07 12:24
20161213 | 20161213036 | 36 | Water Item | There does not appear to be a water item, is water incidental to the project for shouldering? | Standard specification 624.5(3) If the contract does not contain the bid item Water, then furnishing and applying water is incidental to other items of work. | Scott Lawry | 6 | 2016-12-12 13:35 | 2016-12-12 13:47
20161213 | 20161213039 | 39 | Overhead Sign Supports | What size footings are needed for each of the sign structures? | 36â€ Diameter base support. | Scott Lawry | 1 | 2016-11-22 13:51 | 2016-11-29 16:30
20161213 | 20161213040 | 40 | Storm Sewer Selection Standards | According to the WisDOT FDM, the following COMPETITIVE bid item changes would be appropriate: - 608.3615 Storm Sewer Pipe Class III-B in lieu of 608.0315 - 608.3618 Storm Sewer Pipe Class III-B in lieu of 608.0318 - 608.3624 Storm Sewer Pipe Class III-B in lieu of 608.0324 - 608.3630 Storm Sewer Pipe Class III-B in lieu of 608.0330 These respective bid item changes are appropriate being that the proposed installations are as follows: -[With an] agency responsible for maintaining the storm sewer [that] approves the use of the alternate material (City of Loyal) (FDM 17.4.1) - Within approved diameter range (12â€-36â€) (FDM 17.4.2) - Not located underneath lane of traffic with design AADT above 7000 (FDM 17.4.3) - Within approved fill heights (2â€™-15â€™) (FDM 17.3 Table 17.1) For further information on these design changes and competition, please see paragraph 17.5 under section 13-1-1 of the Wisconsin Department of Transportation Facilities Development Manual. | The City of Loyal will be the maintaining authority of this pipe per the project agreement with them. The designer sent an email to the Mayor requesting their approval per FDM 13-1-17.4. The City Engineer discussed with the Clerk and Mayor and do not want to change the bid request to all for alternative materials to be considered. | Scott Lawry | 1 | 2016-11-28 10:55 | 2016-12-01 17:32
20161213 | 20161213040 | 40 | Removing Pavement | In the Misc. Quantities table for the removing pavement it seems from station 240+00-265+30 and 366+00-381+00 includes the area of asphalt pavement overlay in the quantity. While the stations from 362+13-366+00 and 381+00-389+75 is only the area of the concrete pavement and does not include the width of the asphalt pavement. Can you clarify or adjust the quantities accordingly to reflect what you will measure to and pay for? | Based on our review, the quantity amount will be revised and included in Addendum 1. | Scott Lawry | 2 | 2016-12-02 10:43 | 2016-12-05 16:52
20161213 | 20161213040 | 40 | Soil Boring | Please provide any geotech data / soil boring data utilized for the design of the project. | The soil borings collected for the project can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213040/. These borings were completed to aid in the environmental documentation for the project design and intended solely for that purposeâ€¦.contaminated soil. Any other use of them is entirely at the contractorâ€™s risk. | Scott Lawry | 3 | 2016-12-02 13:30 | 2016-12-05 16:28
20161213 | 20161213040 | 40 | retaining walls | The drawings on sheet 24 to 26 of the plan set provide the design for a modular block gravity retaining wall. The proposal includes the special provisions for a â€œWall Concrete Panel Mechanically Stabilized Earth LRFD/QMP Pilot, Item SPV.0165.01â€ The pay item is also based on SPV.0165, Special 01, Wall Concrete Panel MSE LRFD/QMP Pilot Please confirm what is required for this project - modular block gravity retaining wall OR Wall Concrete Panel Mechanically Stabilized Earth? | Modular block is proposed. The department has replaced the wall special and modified the plans. This will be included in Addendum 1. | Scott Lawry | 4 | 2016-12-06 10:46 | 2016-12-06 17:19
20161213 | 20161213041 | 41 | Milled Surface | Page 3 of 43 in Special Provisions. ...all milled surface must be repaved prior to the close of construction on Fridays... This essentially eliminates milling after Wednesday of the week in order to allow time for paving. Not sure the reason for this? Really puts the contractor in a situation where you cannot fully maximize the work week and prohibits working on Saturday. | Addendum #2 will address this concern and is currently be processed. | Scott Lawry | 1 | 2016-12-01 10:49 | 2016-12-02 09:00
20161213 | 20161213041 | 41 | Lane Closure Length | Page 4 of 43 in special provisions. ...maximum lane closure length will be one mile.... Almost anytime asphalt paving is happening the 1 mile lane closure length is limiting the operation. Compaction is related to temperature. To decrease lane closure length we would have to reduce production. Reduced production increases costs...... | Lane closure length restriction will remain. Contractor shall work with the Project Leader in the field to suggest reducing lane closure length while under direct supervision of traffic impacts. | Scott Lawry | 2 | 2016-12-01 10:51 | 2016-12-02 09:08
20161213 | 20161213042 | 42 | Storm Sewer Items | According to the WisDOT FDM, the following COMPETITIVE bid item changes would be appropriate: - 608.3630 Storm Sewer Pipe Class III-B in lieu of 608.0330 - 608.3636 Storm Sewer Pipe Class III-B in lieu of 608.0336 These respective bid item changes are appropriate being that the proposed installations are as follows: - With agency responsible for maintaining the storm sewer that approves the use of the alternate material (City of Bayfield County) (FDM 17.4.1) - Within approved diameter range (12â€-36â€) (FDM 17.4.2) - Not located underneath lane of traffic with design AADT above 7000 (FDM 17.4.3) - Within approved fill heights (2â€™-15â€™) (FDM 17.3 Table 17.1) For further information see paragraph 17.5 under section 13-1-1 of the FDM. | WisDOT is the agency responsible for maintenance of this storm sewer. Concrete storm sewer with all joints tied was specified due to concerns with joint separation. The department will not be revising the plan at this time. The successful contractor may propose a change to the plan as a Cost Reduction Incentive under 104.10 of the Standard Specifications after contract execution. | Scott Lawry | 1 | 2016-12-05 16:12 | 2016-12-07 15:45
20161213 | 20161213042 | 42 | Excavation | There is no bid item for Common Excavation listed. How is the excavation for the culvert pipe transition cuts being paid? | All excavation shown in the details, including transition excavation, is included in the price of the culvert under 520.5(3), which states that ALL excavation is included in this item. We have two other items associated with replacements, pipe removal and backfill granular, that are paid for under the separate items. | Scott Lawry | 2 | 2016-12-07 17:46 | 2016-12-08 14:40
20161213 | 20161213043 | 43 | Temporary Precast Concrete Barrier requirement | Should Temporary Precast Concrete Barrier be added to the project at the locations of joint repairs. Would seem necessary to protect both the traveling public and the construction works. | We have no joint repair work on mainline. We have some new concrete pavement in the areas of the new concrete approach slabs. We are reducing traffic to 25 mph throughout the project limits. There is joint repair called out on the structure plans. If the concern is the joint repair on the bridges, during stage 1 the NB bridge will be closed and traffic will utilize the crossovers. During stage 2, the SB bridge will be closed and traffic will utilize the crossovers. No traffic will be near the structure joint repairs. | Mike Coleman | 1 | 2016-11-15 09:19 | 2016-11-16 10:40
20161213 | 20161213043 | 43 | Pavement Marking Quantities? | Looking at the pavement marking quantities. They look understated. There are two Polymer overlays on bridge decks that are 1,114' and 1,185' long. With both edge lines and skips, that total would be close to 5,175'. Total bid item quantity for 4" epoxy is only 4,585'. The stationing in the misc. quantities seems understated too. From Station 168+62.62 to 200+87.04 there is only 1,850' of white edge line and 1,850' of yellow edge line. That total should be around 3,225' each. Can you check these quantities? | There is an in the item 646.0106 Epoxy 4-Inch. An addendum will be issued to address this. | Scott Lawry | 2 | 2016-11-17 16:08 | 2016-11-21 11:02
20161213 | 20161213043 | 43 | Bridge Painting | Section 27 Structure Painting General C.1 Indicates "Place final field coat of paint on the exterior of the exterior beams as a continuous operation"...however, General note 9 on sheets 183 and 200 state "Clean and paint existing steel girders at the abutments 6' from the girder end"..... The quantities in 28.A.1 indicates the intent is just the beams ends. Please confirm this. | The painting limits are detailed in the General Notes, clean and paint the existing steel girders at the abutments 6â€™ from the girder ends along with the diaphragms, stiffeners and exposed hardware contained in that 6'. | Scott Lawry | 3 | 2016-11-23 11:25 | 2016-11-30 10:58
20161213 | 20161213043 | 43 | Bridge | Reference Special Provision 45 (page 62) and â€œNote to Contractorâ€ on plan sheets 183 and 200. The contractor is to â€œProvide superstructure restraints to prevent bridge superstructure from longitudinal and lateral movement.â€ What are the longitudinal/downgrade loads the contractor will be required to restrain during the bridge jacking and abutment removal. Based on the damage to the existing north abutment it appears this load may be substantial. | The horizontal (longitudinal/downgrade) load expected at the North abutment would be 130 kips per girder for B-9-146 and 95 kips per girder for B-9-147. These loads are the horizontal component of the service vertical dead load. This does not include live loads or other construction loads. | Scott Lawry | 4 | 2016-11-30 11:01 | 2016-12-01 16:15
20161213 | 20161213043 | 43 | Electric Utility Question | Do you know what type of conduits are in the parapet (SB) and sidewalk (NB)? These are housing the City of Chippewa electric lines and may be problematic since we have to raise the bridge to replace the bearings. The work would be much easier if we could kill the lines for a couple of days to complete the removal and bridge jacking and then repair the lines and replace the conduit. Also, do you know what kind of voltage these lines are carrying? | The City of Chippewa Falls would allow the contractor to de-energize the lines for a couple of days to complete the required work. There is a breaker box, to shut off the power, located near Court Street and on STH 124 NB on-ramp coming from Park Avenue. The voltage is 240/120. The conduit in the boulevard is pvc. It is unknown what type of conduit is located in the parapet and sidewalk. | Scott Lawry | 5 | 2016-12-07 16:13 | 2016-12-07 16:14
20161213 | 20161213043 | 43 | Asphalt Paving | The spec calls for Night Paving on turn lane and intersections. Can you define the night time hours? Is there a reason that traffic cannot run on milled surface as on other jobs? This will create a large amount of joints on this job. On sheet 6 shows a cross section showing paving in stations 200+05 to 200+87 but on sheet 53 the bridge slaps show a note â€œconcrete pavement 10-Inchâ€ Please confirm that we will be paving on the North side of the large bridge approach. | A1--Nighttime hours are 10pm-6am. A2--There are concerns of running on the milled surface therefore it is limited to having to place the leveling layer first. Requirement was project specific and we feel it is necessary. A3--No HMA paving from 200+05 to 200+87. Finished typical is incorrect. Concrete Approach Slabs and Concrete Pavement 10-Inch will be placed in this location | Scott Lawry | 6 | 2016-12-08 12:42 | 2016-12-08 12:43
20161213 | 20161213044 | 44 | Soil Boring Data | Please provide any soil boring information available for the project. | A copy of the soils report can be found on the NW regions preliminary plans, specifications, and project information page at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx a direct link the file is below. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213044/ | Scott Lawry | 1 | 2016-11-15 15:59 | 2016-11-17 17:13
20161213 | 20161213044 | 44 | DOT Schedule | Please provide a copy of the project schedule developed during the proposal preparation. | This has been posted on the NW page http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx The schedule is not a contractual document, the actual means, methods and workforce necessary to complete the work in accordance with the contract will be up to the contractor. | Scott Lawry | 2 | 2016-11-15 16:02 | 2016-11-17 17:05
20161213 | 20161213044 | 44 | Preformed Plastic Crosswalk | Does the DOT want the 6,080' of 24" Preformed Plastic Crosswalk grooved in, or surface applied? Typically all tape is grooved in to avoid being torn up by plows. | Preformed Plastic Crosswalk should be grooved in. | Scott Lawry | 3 | 2016-11-29 09:55 | 2016-12-05 17:23
20161213 | 20161213044 | 44 | CAD Files | Will the Department be releasing CAD files Pre-Bid? | The department will provide surface models if necessary to the successful low bidder after contract execution. Other file requests need to be more specific as to what is needed. | Scott Lawry | 4 | 2016-11-30 12:27 | 2016-12-05 17:23
20161213 | 20161213044 | 44 | Earthwork | Q1--Watermain and lateral install staging. Unclear how the staging plan for the watermain install and laterals correlates with the overall staging plan for the project. I did request the stage lines be added to the cross sections below. Q2--Specials #29 & #38 discuss not allowing the use of recycled concrete (from the project or from an outside source). Is this correct? is there something wrong with the concrete that we need to be made aware of? Q3--Earthwork summary table note #1 states Common Excavation is the sum of the cut less pulverized material item Number 205.0100. Does this column and note pertain to this project? I do not want to be missing something. Q4--can the staging lines be added to the cross sections? | Q1--The US 2, Belknap Street stage plan layout is a general roadway reconstruction plan. It was not the intent to completely design the contractorâ€™s construction process. The water main and lateral install staging was to show that they need to complete those items of work within the stages shown, in relation to where we are working on the general roadway reconstruction plan. Staging lines are shown for the main line staging on the detail pages 431-437 and the water main staging details can be found on pages 141-143. Q2--Yes it is correct, no use of recycled concrete. No, nothing is technical wrong with the concrete but recycled concrete contains excess fines that could block filtration fabric and the underdrain system. This roadway has a history of poor subgrade drainage and with the freeze thaw cycle causes premature distress in the concrete. Q3--That pulverized note is a standard note in table, there is zero quantity in that column as there is no pulverizing. A revised earthwork table will include another couple thousand yards for parking lot removals, and will be revised to add the unusable concrete volumes via addendum. Q4--Staging lines are shown for the main line staging on the detail pages 431-437 and the water main staging details can be found on pages 141-143. | Scott Lawry | 5 | 2016-12-01 10:05 | 2016-12-05 17:28
20161213 | 20161213044 | 44 | Directional Drilling | 1. I do not see at what station the directional drilling of the 12â€ HDPE main begins. Thereâ€™s an end at 147+80 at an MJ adaptor. 2. At station 140+65 it indicates a hydrant service to be drilled across. This is not possible given there is no place to set up the drill rig and drill from the surface and get down to grade at the main. Also the presence on the north side of a building prohibits the laying out of the pipe prior to pullback. Additionally the depth of the existing water main and sanitary sewer are not provided. There is no way to formalize a drill plan without knowing the depths of the existing utilities. 3. The plan sheets state that all water services to the north are to be installed by directional drilling and in looking at the plans I would have guessed that only the services on Sheets 145 and 146 are to be drilled in. Please clarify/confirm that all services to the north are to be drilled in. Regardless of that, in order to get down to depth at the main there needs to be 50-70â€™ from the front of the drill rig to the point where the service is at depth. The drill rig itself is approximately 20 feet long. While there is room on some of the services to set the drill rig up on the south side of US 2 and drill to the north access will be needed from the property owners in order to place the equipment on their property. Also there will be surface restoration that will be required at these locations as well. For those services that have buildings on both sides of US 2 there is no way to install the water service using standard methods of directional drilling. The only option is to use a pit launch rig. This would require an excavated pit having the dimensions of at least 14â€™ long by 6â€™ wide for which the rig would be placed into and drill out to the north. The use of a pit launch rig is much more time consuming than using a standard drill rig. No matter what method is used the depth of the existing water and sanitary sewer is needed to be known to see whether it is possible to avoid them and still be able to get to the north side of the street without being too deep. 4. On Sheet 147 Station 151+60 it states that the service penetrates through vault. What type of vault is it? Drilling fluid will enter the vault and therefor access into the vault will be needed to remove the drilling fluids. Will this be possible? | Q1--Directional drilling is intended to start at the 12â€ X 12â€ cross at the intersection of Tower Avenue at station 141+24.00. Q2--The hydrant at station 140+65 is intended to be open cut, as opposed to the directional drill called out in the bid plan, and installed concurrently with the 12â€ HDPE in the intersection of Tower Avenue. See Utility Closure window found in the Traffic Special Provision under â€œSpecial Requirementsâ€. Q3--The intention of the plan is to have all services to the north are to be drilled in. If the contractor chooses to utilize a different method and is approved by the engineer in the field, any additional costs will be incidental. All special provisions would still be applicable, see Utility Closure window found in the Traffic Special Provision under â€œSpecial Requirementsâ€. The plan contains the Transportation Project Plat (TPP) pages 633-648 which contains the available Temporary Limited Easements (TLE) agreed upon with the property owners and WisDOT. Any additional work on property outside of TLE would need department approval for locations and any and all environmental review. Any additional property agreed upon with private land owners and the contractor would need paper work to substantiate the agreement. The intention of the plan is to utilize shorter length drill equipment, it is understood that smaller equipment is available. The unit of measure for boring pits is â€œeachâ€ and excavation and restoration is included within this item. It shall be up to the contractor to determine the actual pit sizes. Generally, the water main, (from the 1880s-1890s) is expected to be 6â€™ to 8â€™ in depth. It shall be the responsibility of the Contractor to verify depths as needed to proceed with drilling operations. Sewer depths are in the compressed file: Combined-SSS-Depths.zip. Water services in directionally drilled water main areas are generally anticipated to be exposed per detail shown on sheet 140. Please note that verification of existing utility depths is considered incidental. Q4--Vault to be abandoned, details on pages 38 and 39 for vaults to be abandoned, and special provisions 117 and 118. Since this will be abandoned/removed/stabilized access to the vault is possible and necessary. See files: ElksVault-DNAE.pdf and Vault-FoundationSurvey.pdf that are post at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161213044/ | Scott Lawry | 6 | 2016-12-01 17:36 | 2016-12-05 17:32
20161213 | 20161213044 | 44 | RRFB system | The RRFB system specs that are published appear to be proprietary towards Tapcoâ€™s product, will the department accept the Carmanah SC315 RRFB. | The specifications will remain as currently shown the in special provisions. It is a standard item in the City of Superior. | Scott Lawry | 7 | 2016-12-05 10:10 | 2016-12-05 10:13
20161213 | 20161213044 | 44 | Storm Sewer Alternate Materials | According to the WisDOT FDM, the following COMPETITIVE bid item changes would be appropriate: - 608.3618 Storm Sewer Pipe Class III-B in lieu of 608.0318 - 608.3624 Storm Sewer Pipe Class III-B in lieu of 608.0324 - 608.3630 Storm Sewer Pipe Class III-B in lieu of 608.0330 - 608.3636 Storm Sewer Pipe Class III-B in lieu of 608.0336 These respective bid item changes are appropriate being that the proposed installations are as follows: - With an agency responsible for maintaining the storm sewer that approves the use of the alternate material (City of Superior) (FDM 17.4.1) - Within approved diameter range (12â€-36â€) (FDM 17.4.2) - Not located underneath lane of traffic with design AADT above 7000 (FDM 17.4.3) - Within approved fill heights (2â€™-15â€™) (FDM 17.3 Table 17.1) For further information, please see paragraph 17.5 under section FDM 13-1-1. Furthermore, is there a reason large portions are spec'd Class IV despite that those pipes fall within the fill height range for Class III? | The special provisions and plans have been revised in Addendum 2 to allow substitution of the pipe materials defined within 608.3612, 608.3618, 608.3624, 608.3630 and 608.3636 for reinforced concrete pipe as listed in the miscellaneous quantity sheets. The following criteria were utilized in the determination of the eligible pipe runs: The entire pipe length from structure to structure must be located outside of street surfaces consisting of concrete pavement. A minimum of 2 feet of cover must exist along the entire length of pipe as measured from top of pipe to sub grade. When this substitution is selected by the Contractor, the Materials and Construction shall be in conformance with sections 608. All bedding/backfill materials to 6-inches above the top of pipe shall be select borrow which shall be incidental to the pipe items. In addition, rigid connections between the pipe and structures will not be allowed and therefore, the Contractor shall submit shop drawings to the Department for their review and approval which shows the proposed flexible watertight connection method and details between structures and pipe. Deflection testing shall be completed for 100 percent of the installed pipe after backfill to subgrade level is complete. | Scott Lawry | 8 | 2016-12-05 14:49 | 2016-12-08 13:12
20161213 | 20161213044 | 44 | Contaminated Soil | 1.) There are 2 pay items for handling of contaminated material. SPV.0195.002 & SPV.0195.003. How is it determined which pay item is to be utilized? 2.) SPV.0195.002 has the backfilling and compacting of the excavation incidental to the item. What backfill material is to be utilized for the work? 3.) SPV.0195.003 Excavation, Hauling and Disposal of Contaminated Soil. What material it to be utilized to replace this material and how will it be paid? | A1--In SPV.0195.002 Section A.2 of the special provisions these select sites are the only locations that will be utilized by this bid item. Excavation below subgrade or beyond limits would be directed by the Environmental Consultant in the field. See answers for questions 2 and 3 below. Any other contaminated soil excavation will be paid for under item SPV.0195.003. A2--This item is utilized for excavation, segregations, hauling, offsite disposal, backfill and compaction of contaminated soil and fill material for select sites listed in the special provision. The intent of the contract would be to backfill (and well compact) below subgrade with clean, native material. Excavation below subgrade or beyond limits would be directed by the Environmental Consultant in the field. A3--SPV.0195.003 Excavation, Hauling and Disposal of Contaminated Soil - This item is utilized for excavation, segregation, hauling, offsite disposal of contaminated soil and fill material that is required to construct the highway project and only the material required to construct the project. No over excavation is included with this item. The material to be utilized to replace the contaminated soil will depend upon which part of the roadway is being reconstructed. This material will be paid as per the plan depending upon which part of the roadway is being reconstructed. | Scott Lawry | 9 | 2016-12-05 17:17 | 2016-12-08 13:14
20161213 | 20161213044 | 44 | Lane Rental Fee Assessment | There are approx. 40 EA water services being directional drilled beneath live traffic on Belknap. There will undoubtedly be potential conflicts with the existing utilities, including the existing watermain. Will the traffic control staging be changed to allow depth investigation of the existing utilities at the HDD locations or will we be at risk for a potential $20,000/HR assessment if a utility is hit and traffic is detoured to perform the repair? | The intention of the plan staging is to keep one lane of US 2 in each direction open for the duration of the project, with the exclusion of the utility closure windows listed in the special requirements section of the Traffic special. Lane Rental Fee Assessment will not be applied as long as US 2 traffic remains open. The departmentâ€™s intention is to remain with the existing staging. The contractor is allowed to make slight adjustments to the staging with the approval of the Engineer in the field to check depths of existing utilities. One way contractor or others can get some idea of the water main and service depths on the existing is to go out and measure down all the main valves and service stops. Contractor should plan for the use of the utility closure windows listed in the Special requirements section of the Traffic special. In an event beyond the control of the contractor, the department would need to evaluate whether there was justifiable need for a longer or alternate closure window. | Scott Lawry | 10 | 2016-12-05 17:56 | 2016-12-08 16:54
20161213 | 20161213044 | 44 | Construction Staking | 1. Construction Staking Curb and Gutter includes quantities for curb and gutter abutting concrete pavement. According to Section 650.4 of the Standard Specifications, this is not measured for payment. This appears to result in about an 18,000 LF quantity overrun. 2. Construction Staking Supplemental Control for projects 8680-00-72 & 8998-00-24 is missing from the proposal. 3. Construction Staking Slope Stakes is missing from the proposal. Will these items be corrected and added with an addenda? | 1. This was an intentional portion of the plan. Due to the flat terrain of the area and the difficult drainage issues, the department added the staking to ensure the positive drainage of the curb in ALL curb flow lines and ADA compliant slopes at pedestrian crossings. 2. The supplemental control item will be paid for under the 8680-00-71 for all projects within the construction zone. 3. Addenda will add item | Scott Lawry | 11 | 2016-12-07 11:52 | 2016-12-08 16:53
20161213 | 20161213044 | 44 | C100 AWWA Weight Fittings | Will the DIP fittings be required to be AWWA C110 Weight as specified in the special provisions? | Please have it noted that AWWA C153 Weight is acceptable. | Scott Lawry | 12 | 2016-12-08 10:16 | 2016-12-08 14:42
20161213 | 20161213044 | 44 | Fittings weights - Full Body or C153 | Will the DIP fittings be required to be AWWA C110 Weight as specified in the special provisions? Or will C150 - C153 weight fittings be allowed? | Please have it noted that AWWA C153 Weight is acceptable. | Scott Lawry | 13 | 2016-12-08 13:52 | 2016-12-08 14:42
20161213 | 20161213044 | 44 | Preformed Crosswalk Bid Item | With your answer to the previously submitted question about the preformed crosswalk being grooved in, will you be issuing an addendum to correct the proposal bid item to grooved in? Without the correct bid item called out, it will still be a surface applied situation and a contract change order would be in order to make it grooved in. Thank you. | The error will be corrected via addendum. | Scott Lawry | 15 | 2016-12-08 14:27 | 2016-12-08 14:38
20161213 | 20161213044 | 44 | Recycled Concrete | The response to the use of recycled concrete does not make sense. Whether recycled concrete or virgin aggregates are used, isn't the fines content determined by the gradation requirements? For 1 1/4" Base Course the fines content is going to be 2%-12% (P200), whether it is recycled concrete or virgin stone (could be 2%-10% P200 if >= 50% crushed gravel). Furthermore, every detail I see has a 12" layer of Select Borrow directly above the underdrain trench that is of concern. The fines content of the Select Borrow can be up to 15% P200. So the fines that are of concern must migrate through a 12" layer of material that is potentially finer, to plug an underdrain trench? And the material you are specifying must be virgin will still be 2%-12% fines(P200), just like recycled concrete would be? | There has been some issues and appearance of more than 15% fines in recycled concrete on the grade. It is correct that the select borrow will provide some filtration of these fines. However, these fines are also more likely to become cemented together and render the top of the select borrow and/or DF fabric non-functional if they get there. The NW Region has also had problems with cracked concrete pavement in the City of Superior using recycled concrete as breaker run backfill for EBS under a full pavement structure. Therefore, due to the historic problems of premature pavement distress, the NW Region is unwilling to take the risk of using of recycled concrete. | Scott Lawry | 16 | 2016-12-08 23:12 | 2016-12-09 14:35
20161213 | 20161213044 | 44 | Ornamental Fence | The Special provisions state that the Ornamental Fence, shall be galvanized and painted black. The Plan Detail for the Ornamental Fence states that the Ornamental Fence, shall be galvanized and black powder coated. Which method was intended ? | The intent is as stated on the Plan details - The Ornamental Fence shall be galvanized and black powder coated. | Scott Lawry | 17 | 2016-12-09 16:05 | 2016-12-09 16:05
20161213 | 20161213044 | 44 | Recycled Concrete | The previous response to the use of recycled concrete is still confusing. The typical details given for USH 2 shows that the CABC 1 1/4" ends at the edge of the outside lane and does not cover the area above the underdrain trench, therefore it does not seem like it could affect the fabric of the underdrain trench in the future? It actually looks like the CABC 1 1/4" is used to seal the top of the Select Borrow layer to force water through the upper layer of Open Graded Base to the outsides, which makes sense as you would not want water to saturate into the subgrade (Select Borrow) directly beneath the pavements. If the intent is to make this layer (CABC 1 1/4") permeable, why is it even being installed? | The pipe underdrain system is to provide an exit path to the storm sewer for any water that gets into the subgrade. The water can get to the subgrade from many places (including sidewalk, curb and gutter, utility trenches, etc.) not just through the pavement. WisDOT at this time does not want to take the risk of any adverse effects from the degradation of any remaining cement paste from the recycled concrete pavement. | Scott Lawry | 18 | 2016-12-10 10:51 | 2016-12-12 10:35
20161213 | 20161213044 | 44 | Preparing Foundation for Asphalt Paving | For the item 211.011 Preparing Foundation for Asphalt Paving, I am looking for the location of this. | This item would be used for any of the side streets that are have asphalt paving. From back of radii on the side street to the end of construction on many of the side streets are asphalt paved. | Scott Lawry | 19 | 2016-12-12 11:09 | 2016-12-12 11:09
20161213 | 20161213044 | 44 | Recycled Concrete and existing base for Trench Backfill. | Can we use Recycled Concrete and existing base for Trench Backfill. The following Section 608.2.2.1 states the following: (1) Furnish virgin materials consisting of either sand-sized particles or sand-sized particles mixed with gravel, crushed gravel, or crushed stone. Do not us materials classified under 301.2.4.3 as crushed concrete, reclaimed asphalt, reprocessed material , and blended material. The contractor may use material from the work site. The last sentence states the contractor may use material from the work siteâ€¦..does this include crushed concrete and existing base? | The NW Region has also had problems with cracked concrete pavement in the City of Superior using recycled concrete as breaker run backfill for EBS under a full pavement structure. Due to the historic problems of premature pavement distress, the NW Region is unwilling to take the risk of using of recycled concrete in Trench Backfill. The salvaged base course could be utilized if itâ€™s not contaminated too badly. Reused of low level contaminated materials would be directed by the Environmental Consultant in the field. | Scott Lawry | 20 | 2016-12-12 13:38 | 2016-12-12 13:39