## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170711 | 20170711001 | 1 | DESIGN FILES | 1. Would it be possible to post the design files for the 1005-10-76 project (similar to what is posted for 1003-10-84)? 2. Are there line work files that show the edge of pavement for both project IDs? 3. Is the design file data shown on the prelim plans page for the 1003-10-84 project up to date? | There have been additional files added for ID 1003-10-84. The information that can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1005-10-76_1005-11-71 | Scott Lawry | 1 | 2017-06-07 21:56 | 2017-06-16 12:24
20170711 | 20170711001 | 1 | Soils Report | Could we get a copy of the geotechnical report? | The soils report and other documents regarding the project can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1005-10-76_1005-11-71 | Scott Lawry | 2 | 2017-06-21 09:51 | 2017-06-21 10:10
20170711 | 20170711001 | 1 | Bid item 1240 Prestress girder I45W | It appears the quantity for bid item 1240, Prestress girder I45W is incorrect, it is listed at 2,464LF. The quantity for B-53-333 is listed on the plans at 1132LF, but should be 1332LF, the same as B-53-332. (12 girders x 111LF/girder). The total bid quantity should be approx. 2664LF. | The quantity for Bid Item Number 503.0146, Prestressed Girder Type I 45W-Inch, shown for Structure B-53-333 on sheet 1054 should be 1,332 LF. The quantity for proposal be 2,664 LF. This will be corrected via addenda. | Scott Lawry | 3 | 2017-06-22 07:17 | 2017-06-23 10:38
20170711 | 20170711001 | 1 | Seismograph | Currently payment for the bid item "Seismograph" is listed as Lump Sum. Would the Department consider revising the method of payment to "Day" or "Each". We have encountered this on past projects and it provided a good communication method between the Project Engineer and the contractor and establishes a fair way to track with a reasonable unit price by the day. | The contractorâ€™s means and methods dictate the seismograph need. Without knowing the exact methods the contractor will use, WisDOT cannot know the exact seismograph needs. Keeping this item as a LUMP SUM informs the contractor that WisDOT believes the need is there but is not dictating or suggesting a specific quantity. | Scott Lawry | 4 | 2017-06-26 16:26 | 2017-06-29 12:33
20170711 | 20170711001 | 1 | Crack and Damage Survey | currently the bid item for "Crack and Damage Survey" is set up to be paid as a Lump Sum. Would the Department consider providing for payment by the "Each"? this way should there be additional locations a unit price would already be established. | The contractorâ€™s means and methods dictate the Crack and Damage Survey needs. WisDOT has speculated on some locations, but without knowing the exact methods the contractor will use, WisDOT cannot know the exact Crack and Survey needs. Keeping this item as a LUMP SUM informs the contractor that WisDOT believes the need is there but is not dictating a specific quantity. | Scott Lawry | 5 | 2017-06-26 16:29 | 2017-06-29 12:34
20170711 | 20170711001 | 1 | Milwaukee Street Closures | Milwaukee Street is allowed four consecutive calendar days for removal operations (assumed per bridge) and two consecutive calendar days for girder placement (again assumed be bridge). Considering the items of "Removing and Resetting Steel Girders", it would appear the time frame may be short on both the removal replacement of the steel. Could two additional days be added to both the removal operations and the girder replacement at each structure? | WisDOT has worked with the City of Janesville to minimize impacts to the locals as much as possible. Milwaukee Street is part of the bus route network in the city. The timetable for full road closure of Milwaukee Street should allow the scheduled work to be completed. As noted earlier in the Specials, the contract time for completion is based on an expedited work schedule and may require extraordinary forces and equipment. Milwaukee Street closure may be a time for extra forces. Along with the full shut down of Milwaukee Street, single lane closures are permitted along Milwaukee Street in each direction if required by work operations. Utilizing lane closures on both sides of the full shut down may allow for extra set up and take down operations. | Scott Lawry | 6 | 2017-06-26 16:36 | 2017-06-29 12:35
20170711 | 20170711001 | 1 | Structural Steel, HS Diaphragm Connections | This question is in regards to structures B-53-214/215. For the new lines of steel girders to be added, and girder line 10 on B-53-214 which is to be reset at a new spacing, the plan is calling for additional diaphragm connection plates for the new steel diaphragms. Is there a detail as to how the new connection plates are to be attached to the existing girders? Will they need to be field welded to the existing steel or will it be a bolted connection into the web of the girder only? If these are field welded what will be the requirements for inspection/testing of the welds? The girder details in the plans only seem to give information for the new shop welded girders, nothing on this field connection. | Girder lines 3 and 9 require new diaphragm connection plates as shown in the plans (Sheets 23 & 25). The new diaphragm connection plates, for both the new and existing girder lines, are detailed on Sheet 25 for diaphragm bays 2 & 9. The details as shown on Sheet 25, for attaching the diaphragm connection plates, apply to all new and existing girder lines. All welds required for the installation of the new diaphragm connection plates shall adhere to the most current requirements of the ANSI/AASHTO/AWS Bridge Welding Code D1.5. The existing girders lines, that are to be salvaged, are required to be removed, stored and reset to a new girder spacing as shown in the plans. This work is covered under the bid item "Removing and Resetting Steel Girders B-53-214", Item SPV.0105.701. Work that is required to prepare the existing girders for resetting to the new girder line spacing, is intended to take place after the existing girders are removed and properly stored. Thus, the installation of the new steel diaphragm connection plates will be completed in a controlled environment and field welding will not be required. | Scott Lawry | 7 | 2017-06-28 07:36 | 2017-06-29 15:14
20170711 | 20170711001 | 1 | MSE Wall Reinforcement Length | On MSE Wall R-53-35, the External & Overall Stability Evaluation on Sheet 1239 requires a reinforced length of 1.8H or 18.1â€™ at Sta. 2+04.96. Is the intent to have 18.1â€™ reinforced lengths in the entire abutment section between Sta. 0+52.33 and 2+27.58, or is the minimum required length to be 1.8H under the abutment? If the 1.8H length is to control throughout, Sta. 0+52.33 would require 27.5â€™ reinforcement lengths. Wall R-53-36 is similar. | R-53-35 At this location, while the eastern quadrant of the wall is generally shorter than the western quadrant, the soil conditions in the east are weaker. This results in a longer minimum reinforcing length of 18.1 ft and a larger reinforcing length to total height ratio (L/H) of 1.8 for the shorter wall height compared to the west part of the wall, where the wall is taller but the soil conditions are stronger resulting in a minimum reinforcement length of 17.8 ft and L/H of 1.1. We recommend that the larger of the two minimum reinforcement length calculated during our analysis, 18.1 ft, be rounded up to the nearest 0.5 to 1 ft (18.5 to 19 ft) and be used as the minimum reinforcing length along the entire wall at R-53-35. R-53-36 While the reinforcing length to total height ratio (L/H) is larger for the eastern quadrant of the wall than in the western quadrant at this location (1.9 vs 1.2), the minimum reinforcing length for the east and west quadrants are the same, 17.3 ft. This is due to the western portion of the wall, which although taller, has stronger soil conditions than in the east where the wall is shorter but has weaker soil conditions. We recommend that the minimum reinforcement length of 17.3 ft be rounded up to the nearest 0.5 to 1 ft (17.5 to 18 ft) and used as the minimum reinforcement length along the entire wall at R-53-36. | Scott Lawry | 8 | 2017-06-28 15:51 | 2017-06-30 12:32
20170711 | 20170711001 | 1 | Noise Walls | The special provision for the noise barriers states that drilled shaft foundations shall be designed using the Broms Method. The notes on the plan sheets for the noise walls say that the foundation design shall be in accordance with the latest version of AASHTO, which requires a soil-structure interaction approach [these provisions appear to conflict]. | The department would accept either Broms Method or a p-y Method for the foundation design. Future specifications are anticipated to include both methods. An addendum will be developed to revise the specification language. | Scott Lawry | 9 | 2017-06-29 12:42 | 2017-06-29 12:43
20170711 | 20170711001 | 1 | Noise Walls | The design wind load is inconsistent between the two documents. | The correct design wind loads are 28.5psf for ground-mounted, and 37.5psf for structure-mounted. This is a WisDOT modification to LRFD. There is a discrepancy for N-53-10/18, where the plans indicate 29psf and the specials indicate 28.5 psf. 28.5psf should be used in all cases for wind load on ground-mounted noise barriers on the above projects. An addendum will be developed to revise the specification language. | Scott Lawry | 10 | 2017-06-29 12:44 | 2017-06-29 12:45
20170711 | 20170711001 | 1 | Existing Typical Section vs Proposed Typical Section especially Southbound Widened Lanes | Can 1-1/4â€ Base Course be used/substituted instead of Select Crushed (all or a percentage)? There is almost 2â€™ thick X 70â€™ wide of existing Asphalt/Concrete/Base Course available to be crushed onsite into 1-1/4â€ base course (No trucking on local/state roads equally less impact to the traveling public which also improves safety at a huge cost savings) A suggestion would be to allow by addendum the substitution of 1-1/4â€ Base Course instead of Select Crushed at Contractor Option with the Payment for that material to be paid under the bid price of Select Crushed regardless of material used Select Crushed or 1-1/4â€ Base Course within the identified area of the Select Crushed section in the plan. | The typical section will remain as shown on the plan. | Scott Lawry | 11 | 2017-07-02 11:25 | 2017-07-07 14:15
20170711 | 20170711001 | 1 | Alternative Subgrade Improvements (Instead of Select Crushed) 1 of 2 | The Select Crushed material is considered a Subgrade Improvement (not considered in pavement design). The FDM identifies other equal materials such as sand and base course, these materials are more cost effective in this project area. Rock County has an abundant supply of Sand & Gravel vs a limited supply of quality Limestone which is used for Select Crushed. DOT has allowed substitution of these materials before. DOT has even bid this item as contractor option before. Allowing more completion which equals cost savings. SP 6351-00-78 and SP 1430-00-74 are two WisDOT past project examples. | The typical section will remain as shown on the plan. | Scott Lawry | 12 | 2017-07-02 11:32 | 2017-07-07 14:16
20170711 | 20170711001 | 1 | Alternative Subgrade Improvements (Instead of Select Crushed) 2 of 2 | A suggestion would be to allow by addendum the substitution of any allowable material type per the FDM at its associated thickness instead of Select Crushed at Contractor Option with the Payment for that material to be paid under the bid price of Select Crushed regardless of material or thickness used within the identified area of the Select Crushed section in the plan and any quantity change to the excavation items are incidental. Changing the Select Crushed item to be paid as Cubic Yards measured in place could be done also to make is easier to measure vs by the ton especially if the thickness changes. Example if Grade 2 sand is used which requires 30â€ per the FDM to be equal to 16â€ of Select Crushed, the payment for the Grade 2 Sand would only be 16â€ at the bid price of Select Crushed even though there will be 30â€ placed. And no adjustment to common excavation or embankment. | The typical section will remain as shown on the plan. | Scott Lawry | 13 | 2017-07-02 11:34 | 2017-07-07 14:16
20170711 | 20170711001 | 1 | Batch Plants on the Right of Way | Can a Batch Plant be sited on the ROW? If so what are the requirements? Can a well be drilled on the ROW? Batch Plants and Wells have been allowed all over the State on many projects in the past. Are there areas within the ROW that canâ€™t be disturbed outside the limits of grading? Environmental or any other unknown reasons? | Please see Standard Specification 107.9 Contractor's Use of the Highway Right-of-Way: http://wisconsindot.gov/rdwy/stndspec/ss-01-07.pdf#ss107 Approval for a batch plant cannot be granted before reviewing detailed information such as, but not limited to, location, environmental controls and traffic patterns into and out of the plant. Well drilling requires following other state rules and regulations including coordination with the DNR. There are areas within the RW outside of grading limits that cannot be disturbed. | Scott Lawry | 14 | 2017-07-02 11:35 | 2017-07-07 14:16
20170711 | 20170711001 | 1 | Materials located within the ROW | Can materials located within the ROW be used to construct this project? Can materials be excavated outside the slope intercept within the ROW? Are there areas within the ROW that canâ€™t be disturbed outside the limits of grading? Environmental or any other unknown reasons? Can materials be excavated outside the 1:1 Slope Intercept and be replaced with Embankment materials. Can materials be excavated within/under the roadway if replaced with Embankments meeting the specifications within the plans and specification. (No different than any other fill areas within this project or any other projects all over the state. Every bridge abutment in the state sits on multiple feet of embankment.) If allowed can the contractor base their bid on this with the understanding the materials have to meet all the required specifications? | Please see Standard Specification 104.8 Rights in the Use of Materials Found on the Project: http://wisconsindot.gov/rdwy/stndspec/ss-01-04.pdf#ss104 There are areas within the RW outside of grading limit that cannot be disturbed. | Scott Lawry | 15 | 2017-07-02 11:36 | 2017-07-07 14:17
20170711 | 20170711001 | 1 | Crack & Damage Survey | The special provisions state that 3x5 glossy photos are required for the crack and damage survey. This hasn't been done in this manner for years. We have been using digital photos submitted on a CD/DVD that provide high definition and allow zooming capability to provide even better inspection and comparison. We create a digital file for each property with a series of images to allow best comparisons before and after construction. Will this be acceptable in place of the 3x5 glossy photos? | WisDOT is fine with digital photography in place of the 3x5 glossy photos. | Mike Coleman | 16 | 2017-07-05 10:17 | 2017-07-05 11:40
20170711 | 20170711001 | 1 | Noise Walls | The plan notes state that"Details shown are general guidelines for a variety of applications that may not all be utilized for the subject noise barrier. Specific details shall be provided by the noise barrier fabricator and shall be approved by the Engineer prior to construction." Does this note apply to allow revised post spacing and alternative fabricator / contractor designed foundation systems? | Post spacing can be revised and sound engineering principles meeting AASHTO design criteria must be used for the designed foundations systems. The contractor is responsible for providing the complete design of the wall selected from the WisDOT Approved Product Listing. | Mike Coleman | 17 | 2017-07-06 09:27 | 2017-07-07 06:38
20170711 | 20170711001 | 1 | Pre-boring Unconsolidated Material | Can the department elaborate on the intent of the Preboring Unconsolidated Material bid item and how the quantity(s) were arrived at? Is the pay quantity the first 25'/30' of the pile shaft length or the bottom 25'/30' of the pile length? For example, for B-53-229, the Note under Foundation Data on Sheet 400, states "Preboring estimated to be 30 Feet each abutment" and the pile lengths 60' & 65' at the abutments. Is the pay quantity for the upper or lower portion of the estimated pile length? Thanks | The preboring for the bridges is due to the embankment fill. CIP piles driven into embankment fill greater than 10 feet need to be prebored through the embankment fill. The preboring starts at the bottom of the abutments and continues for a depth as stated on the plans below the abutment. | Mike Coleman | 19 | 2017-07-06 09:57 | 2017-07-07 06:48
20170711 | 20170711001 | 1 | SP 138 - Boring and Jacking | Is an oversized steel casing pipe required for all of the storm sewer and culverts installed by boring and jacking, or will direct-jack installation of the RCP be allowed? | The special provision calls for and requires a steel casing as part of the boring and jacking item. Direct-jack installation will not be allowed. | Mike Coleman | 20 | 2017-07-06 13:59 | 2017-07-07 06:30
20170711 | 20170711001 | 1 | Existing Concrete Pavement | What does 10" Continuously Reinforcement Concrete Pavement mean, Mesh Reinforcement or Rebar Reinforcement? | The as-built plans show #6 rebar @ 6.5â€ center-to-center was to be used for the Continuously Reinforced Concrete Pavement. | Scott Lawry | 21 | 2017-07-06 16:52 | 2017-07-07 11:44
20170711 | 20170711001 | 1 | Pipe Boring & Jacking - RCP Class | Can you please clarify the class of RCP that will be required for the bored and jacked crossings? SP 138 states all pipe must be class V, but if it is also required to be installed inside a steel casing pipe, will class III be allowed, as it has in the past? Also, on the second set of plans (1005-10-76) pipe 21B1-21C is shown on profile sheets 281 and 283 to be class III RCP, however on the storm sewer pipe schedule of sheet 649, the full run of pipe (312 feet) is stated class V. This also contradicts the SP 138 requirement of class V. | Class V pipe shall be used for all boring and jacking. The specifications and miscellaneous quantities show all Class V pipe for these locations. The profile sheets referred in the question (pages 281 and 283) are mislabeled as Class III, but the Estimate of Quantities currently show them as a Class V pipe, so the bid would still reflect the appropriate item(s). | Scott Lawry | 22 | 2017-07-07 09:41 | 2017-07-07 11:47
20170711 | 20170711001 | 1 | Crack & Damage Survey | There are certain residences listed that are at each end of a block; however, the residences between are not part of the crack & damage survey. For example, 229 and 201 Sioux Court are listed; however, 221, 213, and 207 Sioux Court are not. Is there a reason for this? Are we to bid with the assumption that the residences not listed will not be added in at a later date? Since this a lump sum bid item, and based on a previous answer given regarding the crack and damage survey not being switched to a bid item for each address, if more residences are added, will we be able to adjust our bid at that time? | Bid the project per the advertised documents. The crack and damage survey item does not absolve the contractor from following standard spec. 107 and conducting additional surveys where they choose. | Scott Lawry | 23 | 2017-07-07 14:41 | 2017-07-10 14:34
20170711 | 20170711001 | 1 | Pipe Boring and Jacking | If Class V pipe is required for all boring and jacking, where is a steel casing required? What is the quantity and sizes? | A1--According to Article 138 of the special provisions, a steel casing pipe is required for all boring and jacking locations. Refer to the storm sewer plan sheets and miscellaneous quantity plan sheets for locations (also for ID 1003-10-84, refer to the Pipe Boring & Jacking Construction Details for additional information). A2--Quantities are identified in the miscellaneous quantity plan sheets and the steel casing size shall be in accordance with the pertinent requirements of Article 138 of the special provisions. | Scott Lawry | 24 | 2017-07-07 15:10 | 2017-07-10 16:31
20170711 | 20170711001 | 1 | Unuseable ROW | Please identify the areas within the ROW outside of grading limit that cannot be disturbed. | All areas outside the excavation limits must be approved by the engineer as noted in the specifications below. Please see Standard Specifications 104.8 and 107.9. http://wisconsindot.gov/rdwy/stndspec/ss-01-04.pdf#ss104 http://wisconsindot.gov/rdwy/stndspec/ss-01-07.pdf#ss107 | Scott Lawry | 25 | 2017-07-07 16:06 | 2017-07-10 16:38
20170711 | 20170711001 | 1 | Salvage Topsoil | Per the Special Provision Article 63 Salvage Topsoil, it appears that all salvage topsoil must be 1-Inch Minus for the top 2-Inch even along the interstate. This requirement usually is for Urban areas not interstate highways. Does the DOT want this? This is a huge cost. | Bid the project as advertised. | Scott Lawry | 26 | 2017-07-09 23:52 | 2017-07-10 14:35
20170711 | 20170711003 | 3 | Finishing Roadway (project) 01. 1023-06-64 | Where can I find information that will tell me what the pay item "Finishing Roadway (project) 01. 1023-06-64" entails? | You can find the information in Section 213 of the State of Wisconsin Standard Specifications for Highway and Structure Construction, 2017 Edition located at the following location: http://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/rdwy/stndspec.aspx | Mike Coleman | 1 | 2017-07-06 14:51 | 2017-07-07 06:28
20170711 | 20170711003 | 3 | Contract time | This project needs to be completed in 25 days? | The contract time as indicated on the proposal cover sheet is 25 working days. A Working Day is defined in the State of Wisconsin Standard Specifications Section 101. http://wisconsindot.gov/rdwy/stndspec/ss-01-01.pdf#ss101 | Scott Lawry | 2 | 2017-07-10 16:33 | 2017-07-10 16:36
20170711 | 20170711004 | 4 | Plan Changes | Is there a summary of plan changes available versus the previous set dated "not for construction 2-27-17"? | No, the preliminary plans that were posted previously were for informational purposes only. The plans and provisions that are on the website are the ones that should be used for developing the bid. Industry should review the contents in their entirety to ensure they are complying with standard specification 102.5 Examining Contract Documents and Work Site. | Scott Lawry | 1 | 2017-06-15 16:14 | 2017-06-15 17:25
20170711 | 20170711004 | 4 | Project Cad Files | Can you please release the cad files for this project? Thank you. | The files have been posted and are on the SW Preliminary Plans page ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170711004 | Scott Lawry | 2 | 2017-06-19 14:46 | 2017-06-21 08:30
20170711 | 20170711004 | 4 | SPV 0090.007 & 0090.016 Department owned barrier items | Does the contractor have to supply loading & unloading equipment at the stockpile site or will our trucks be loaded & unloaded by the state? | The contractor will need to provide equipment to load and unload temporary barrier at the stockpile site. | Scott Lawry | 3 | 2017-06-20 14:42 | 2017-06-21 17:29
20170711 | 20170711004 | 4 | Pay Limits of Structure Backfill Bridge B-13-833 | Please refer to the detail on sheet 1009 "Typical Section Thru Body". The upper pay limit (per dashed line) ends at the beam seat elevation. If the backfill material from the beam seat elevation to the bottom of the roadway structure is common excavation then the bid quantity appears to be off significantly. The note on page 1009 states Backfill beyond pay limits shall be "incidental" to excavation for structures. Please Clarify. | Structure Backfill is to be placed behind the abutments from the bottom of the abutment to the bottom of the pavement section. The structure backfill limits above the beam seat elevation should be defined by extending the 1:1 slope as shown in the detail from the beam seat elevation to the bottom of the pavement structure. This intent is consistent with the General Notes on page 1005, the detail on page 1009, and the Backfill Structure Type A quantity on page 1006, all of the project plans. The comps have been checked and are accurate. The structure backfill material goes to the bottom of the concrete approach slab. | Scott Lawry | 4 | 2017-06-22 15:45 | 2017-06-27 13:57
20170711 | 20170711004 | 4 | SPV.0180.001 Asphaltic Surface Safety Islands Special | What is the depth of the Special Provision Asphaltic Surface Safety Islands, to be paid by the SY? | The depth/thickness of the Asphalt Surface Safety Island Special is 2 inches. | Scott Lawry | 5 | 2017-06-28 11:51 | 2017-06-29 12:34
20170711 | 20170711004 | 4 | Storm Sewer - Staging Summary | Can a storm sewer summery broken out by stages be provided? | The storm sewer is provided in the plans by stage within the traffic control plan, plan sheets 384 through 542. | Mike Coleman | 6 | 2017-06-30 08:05 | 2017-07-03 12:12
20170711 | 20170711004 | 4 | Concrete Barrier Temporary Precast Delivered - Department Owned | In the special provisions on pages 45 & 46 it is stated that there is "approximately 12,200 LF of department owned barrier located on site. This concrete barrier temporary precast should be utilized in lieu of contractor owned concrete barrier temporary precast whenever possible". There is a bid item, line item 5520 Special 016 Concrete Barrier Temporary Precast Delivered - Department Owned, with a quantity of 8070 LF. The special provisions for this bid item states that the "department owned" barrier can be picked up "within" 5 miles of the project site at a department stock pile. Is the 8070 LF of department owned barrier part of the 12,200 LF of barrier on site, or is it in addition to the 12,200 LF of Department owned barrier on site? If it is in addition to the barrier on site can you supply the location of the stockpile or is it in place on an existing roadway? | The 8,070 LF of Concrete Barrier Temporary Precast Delivered - Department Owned is included in the 12,200 LF of Department owned barrier on site. The barrier is located throughout the current project for use on project 1206-07-75 in the appropriate traffic control stage. | Mike Coleman | 7 | 2017-06-30 14:22 | 2017-07-03 12:15
20170711 | 20170711004 | 4 | Item 204.0235 - Removing Buildings (parcel) 001.TPP 1206-07-30 - Asbestos/lead paint reports | Is there any asbestos or lead paint present in the Benjamin Plumbing building? If so, where can a copy of the reports be obtained? | Article 14 of the special provisions states that asbestos containing material for the commercial building will be removed by the department prior to construction. This asbestos has since been removed from the building. A copy of the asbestos and lead report for this building will be posted on the HCCI site. The report shows that two paint samples taken contain less than 0.06% of lead, which is defined in the report as lead free paint. | Mike Coleman | 8 | 2017-07-05 10:59 | 2017-07-05 14:16
20170711 | 20170711004 | 4 | GeoFoam | Our supplier for the Geofoam mentioned that the specs are missing the density. Could you please provide the actual density required? Such as: EPS12, EPS15, EPS19, EPS22, EPS29, EPS39, EPS46. I have a spec sheet from them that I can email if needed. | The contractor is responsible for the design and detailing of the geofoam embankment in accordance with the plans and the special provision for Expanded Polystyrene (EPS) Geofoam. | Mike Coleman | 9 | 2017-07-06 10:16 | 2017-07-07 06:32
20170711 | 20170711004 | 4 | Earthwork at Salt Shed | Common = 2,627 CY and Embankment = 7,768 CY, do these quantities account for the Backfill Granular Grade 2? | The quantity of Backfill Granular Grade 2 is separate from Common Excavation and Embankment and the quantity can be found on page 701. | Scott Lawry | 10 | 2017-07-06 14:58 | 2017-07-07 11:43
20170711 | 20170711004 | 4 | Casing Pipe | A general contractor has state that the casing must have a minimum ID of 24â€ (per Article 157 ), but Iâ€™m certain you and everyone else wants a minimum 24â€ steel casing pipe which is measured by OD. Once we get to 12â€ then we start calling out pipe by its ID. Can you confirm this? | The casing pipe referred to in Article 157, Item SPV.0090.609 may have an outside diameter of 24 inches. | Scott Lawry | 11 | 2017-07-07 12:50 | 2017-07-07 12:51
20170711 | 20170711004 | 4 | Temporary Shoring - Line Items 910 thru 940 | If tieback anchors are required for the temporary shoring and they extend past the PLE of TLE limits, can they be left in place post construction (permanently)? | Any temporary shoring, including tie back anchors or any other kind of anchoring system permanently left in place canâ€™t extend past the PLE limits unless an agreement is obtained from the property owner. Any temporary shoring left in place must be a minimum for 24 inches below finished grade and not interfere with future maintenance for the wall as determined by the engineer and in accordance with Section 511 of the Standard Specifications. | Scott Lawry | 12 | 2017-07-07 14:08 | 2017-07-10 11:08
20170711 | 20170711005 | 5 | Q2 Elevation for B-41-301 | Please review the accuracy of streambed elevation and high water elevations on sheet 22. It appears that the Q2 is 0.4 feet below streambed. | The Q2 elevation shown on the plan is incorrect. The correct Q2 elevation is 954.50. An addendum will be issued to correct this. | Mike Coleman | 1 | 2017-06-30 08:05 | 2017-07-05 12:59
20170711 | 20170711007 | 7 | Abutment backwall repair | On page 107, sheet 4 of 8 for B-11-1 it asks the contractor to repair the abutment back wall. It does not say which back wall to repair...Also how is the excavation handled for this repair? The excavation will need to be protected from traffic potentially as well. Even though the traffic will be on the opposite side from the repair it will not be an osha safe excavation and will probably need shoring as well. The plan needs a serious adjustment to incorporate this work. Please advise. | All excavation to complete the abutment repairs is incidental to the bid item â€œConcrete Masonry Bridges.â€ The abutment backwall to be repaired is the west abutment. An addendum is being prepared to clarify. The excavation is contained within the abutment and wingwalls, therefore we do not anticipate the need for shoring. | Mike Coleman | 1 | 2017-06-30 10:46 | 2017-07-06 12:31
20170711 | 20170711017 | 17 | Fiber Optic Splices, Terminations and Communication system testing | Who will be performing the fiber splices, terminations and doing the system testing? I don't see a bid item for any of those. | Those work items will be completed by a separate contractor with a purchase order under a state vendor contract. | Scott Lawry | 1 | 2017-06-29 09:03 | 2017-06-29 13:30
20170711 | 20170711019 | 19 | Competitive Culvert Bid Items | Based on the low ADT, will contractors be permitted to submit bid items based on updated competitive bid items? (Culvert Pipe Class III-A or Class III-B) | This project involves 8 culvert replacements and resetting culvert ends along its length. It was determined that we would not allow metal pipes due to corrosion concern. The majority of replacements are too shallow to allow Class III A/B Non-Metal Pipes. For these reasons and to avoid a lot of bid items with minimal quantities, thus we decided to specify the concrete culvert pipe. | Scott Lawry | 1 | 2017-06-14 11:52 | 2017-06-14 14:47