## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190115 | 20190115001 | 1 | Turbidity Barrier Q-2 Elevation | What is the Q2 elevation for these bridges? | Due to the scope of the project, the Q2 elevation was not calculated. General Note 5 on standard detail drawing for Turbidity Barrier (sheet 14 of the plan set) states that minimum barrier height shall be 2â€™ greater than either the Q2 elevation or the estimated high water elevation during construction, whichever is greater. Since no Q2 elevation was calculated, use the HW100 elevation given on the plans. | Mike Coleman | 1 | 2018-12-14 10:38 | 2018-12-19 13:04
20190115 | 20190115001 | 1 | Pile Rehabilitation | Can different materials be used at different elevations of the repair? | Bid the project according to the specifications. Any changes in materials may be considered after contract execution. | Mike Coleman | 2 | 2019-01-08 10:37 | 2019-01-08 10:39
20190115 | 20190115002 | 2 | Expansion Bearing Anchors | On sheet 3 for B-29-39, the notes show "New anchors required" only at 3 locations for the West Abutment and 2 locations at the East Abutment. Is this note supposed to apply to all new bearing locations and replace all the existing anchor bolts? | The intent is to replace the anchor bolts at all locations where the bearing is being replaced and at locations receiving Bearing Maintenance. An addendum will be issued to clarify this in the plans. | Jill Fehrman | 1 | 2018-12-20 09:34 | 2019-01-03 09:23
20190115 | 20190115002 | 2 | Fiber Wrap Reinforcing Non-Structural, Item SPV.0165.01. | In previous versions of the Fiber Wrap Non-Structural Special Provision, the fabric's minimum tensile strength and the wrap's minimum thicknesses had been listed. The Fiber Wrap Special Provision for this project addresses neither of these aspects. Please provide the requirements, if any, for both of these items. | The contractor shall provide a non-structural fiber wrap that conforms to the requirements listed within the SPV for the contract. | Mike Coleman | 2 | 2019-01-08 10:39 | 2019-01-09 08:50
20190115 | 20190115002 | 2 | Line Item 160 Temp Rem Tape | There is an item for temporary marking line removable tape but the plans do not show where this item goes and it is not in the miscellaneous quantities. Can you add that information? Thanks | Temporary Pavement Marking 4-Inch is to be used with lane closures, as shown on Page 50 (S.D.D. 15 D 3-4) and Page 51 (S.D.D. 15 D 12-6A). | Jill Fehrman | 3 | 2019-01-10 09:57 | 2019-01-11 16:09
20190115 | 20190115003 | 3 | SMA Surface and temporary/permanent markings | While there is a temporary paint item for the lower layer, there is not one for the upper layer prior to scarifying the SMA in order to prepare it for the permanent markings. There are also no temporary paint quantities for the upper layer skips prior to placing the permanent tape. Given that you cannot groove the upper layer for a minimum of 5 days after placement, what are your plans to have pavement markings in place prior to opening the road to traffic? Will you be adding quantities for these areas via addendum or is there another plan in place? Thank you. | Quantities for temporary pavement marking will be increased through an addendum. Remarks will be modified to clarify use of temporary pavement marking for both layers. | Jill Fehrman | 1 | 2018-12-27 07:11 | 2019-01-03 09:25
20190115 | 20190115003 | 3 | Butt Joint quantities, etc | Sheet 14 top 1/2 of sheet indicates that butt joints will be milled for both the lower layer (44' Long) and for the SMA Layer (43.5' Long)and that these butt joints will be paid for as Removing Existing Asphaltic Surface Butt Joints. The Miscellaneous Quantities indicate that there will be one butt joint milled at each location and it will be 50' long and these butt joints will be paid for as Removing Pavement Butt Joints. Could you please clarify what bid items will be used (we recognize that the driving and passing lanes are concrete and the shoulders are asphalt) and could you please clarify the length of each butt joint and if there is to be a butt joint for both layers or just one. | One butt joint for each layer; two per location. Lengths shown on the detail are correct (44â€™ and 43.5â€™) Butt joints will be paid under â€œRemoving Pavement Butt Jointsâ€ Sawing paid for under â€œSawing Concreteâ€ An addendum will be issued to reflect updated quantities for both bid items. | Mike Coleman | 2 | 2019-01-02 07:24 | 2019-01-03 12:50
20190115 | 20190115003 | 3 | Butt Joints at Median Crossovers | Please point out or include the median crossover quantities in the Misc Quantities and what bid item will be paying for them. Please note that the detailed butt joint (lower half, left side of sheet 14) is not a standard width and with 1/2 of it having a 12:1 taper and will be expensive to build. | Miscellaneous Quantities will be updated via addendum to reflect payment for butt joints at maintenance crossover locations under the â€œRemoving Pavement Butt Jointsâ€ item. Detail will not be changed. | Mike Coleman | 3 | 2019-01-02 07:57 | 2019-01-03 12:53
20190115 | 20190115003 | 3 | Removing Pavement Item | On page 30 of the Estimate of Quantities, why is there a removing pavement item for the Concrete Pavement Replacement SHES Item 7, under section 416. Removals are part of the Concrete Pavement Replacement SHES. | The â€œRemoving Pavementâ€ item will be deleted from the project via an addendum. | Jill Fehrman | 4 | 2019-01-07 11:33 | 2019-01-10 17:24
20190115 | 20190115003 | 3 | Conc Pavement Replacement SHES overstated? | On page 30 of the Estimate of Quantities Concrete Pavement Replacement SHES - The square yards for a 30ft Replacement does not add up to 420 SY. It appears this item is overstated. Can you clarify this? | The quantity shown was incorrectly given in SF; a prior addendum corrected this. Also, Concrete Replacement areas that are being overlaid will be switched to be covered under Concrete Base Patching via an additional addendum. | Jill Fehrman | 5 | 2019-01-07 15:35 | 2019-01-10 17:26
20190115 | 20190115003 | 3 | Scheduling of Concrete Work | Will the DOT allow the completion of all concrete work (base patching, concrete SHES, concrete pavement repair SHES, Concrete Pavement Replacement SHES) in section 1,2 and 3 prior to the start of asphalt work on section 1? Note - work will not begin in Section 2 until Section 1 is complete. | Provided the restriction on maximum closure length and gap between closures are followed, any or all concrete work can be completed prior to asphalt work. The intent is to keep the area near the Mauston interchange open and not allow a lane closure to continue through that area. Also, concrete pavement repair that is being overlaid will be switched to Base Patching Concrete via an addendum. | Jill Fehrman | 6 | 2019-01-07 15:43 | 2019-01-10 17:27
20190115 | 20190115003 | 3 | Permanent Markings | Being that most other markings along the I-90 & I-94 corridor are wet reflective markings, will an addendum be issued to change the Permanent markings on this project to wet reflective epoxy? Being that the surface is SMA, it might be the prudent thing to do. | â€œMarking Line Epoxy 4-Inchâ€ will be changed to â€œMarking Line Grooved Wet Ref Epoxy 4-Inchâ€ via an addendum. | Jill Fehrman | 7 | 2019-01-09 12:34 | 2019-01-10 17:28
20190115 | 20190115004 | 4 | As Built Plans | Are there any as-built plans available for this project? | The As-Built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115004/ | Mike Coleman | 1 | 2018-12-10 10:53 | 2018-12-12 09:00
20190115 | 20190115004 | 4 | Lane Closures on IH 90 | Can the closures at the La Crosse River Bridges and CP Railroad bridges be setup in one continuous closure as long as the same lane is being constructed on each bridge? If yes can the same lane be closed at the CTH M structure concurrently? | The lane closures and respective quantities were figured to be continuous per lane including 3 structures per direction. There will be breaks in some of the traffic control items where concrete barrier temporary precast is to be delivered and installed. | Jill Fehrman | 2 | 2018-12-20 11:59 | 2019-01-03 08:54
20190115 | 20190115005 | 5 | Landscaping Items | The MQ's for each section of roadway state a matching quantity of erosion mat and mulch. Each section also states the same amount of #20 and #40 seed when adjusted for application rate. Are these areas of topsoil being "double counted?" Also, the quantity of temp seed seems high. Are all of these quantities correct? | The areas of erosion mat and mulching were incorrectly double counted. An addendum is forthcoming to reduce the mulching quantity to 1000 SY. The seed quantities are correct. | Mike Coleman | 1 | 2019-01-07 15:22 | 2019-01-09 11:50
20190115 | 20190115005 | 5 | Soil Borings | Can you please make available the soil boring log for this project? | The boring logs can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115005/ | Mike Coleman | 2 | 2019-01-08 10:32 | 2019-01-09 12:13
20190115 | 20190115005 | 5 | Earthwork | Note 13 on Sheet 70 says the expanded fill factor = 1.42. How did the Department arrive at 1.42? | The fill factor of 1.42 was based on typical soils for the area, as called out in the soils report. | Mike Coleman | 3 | 2019-01-08 11:37 | 2019-01-09 12:14
20190115 | 20190115005 | 5 | Earthwork | Note 15 on Sheeet 70 says 16348 Cy of material is available for the needed 1186 Cy of fill. 2 questions 1. Can you explain where these numbers come from? I don't see them on the sheet 2. Can you clarify the 2nd part of Note 15? It says based on project soils, assume majority of available material will not be suitable for fill sections. | Note 15 is being deleted in a forthcoming addendum. The intent of the note was to call out the quantity of waste material is greater than the required fill material, however not all the waste material may be suitable for fill. This point is included in standard specifications and will be deleted from the plans. | Mike Coleman | 4 | 2019-01-08 11:50 | 2019-01-09 12:16
20190115 | 20190115006 | 6 | Full Depth Deck Repairs-Reinforcing Steel B-12-27 | Regarding work on B-12-27 In the areas of the full deck depth repairs some of this rebar will be very difficult to install with full length bars, especially in the areas where the existing longitudinal reinforcement is not getting replaced. With the rebar be able to be cut and lapped for installation purposes? | The intent is for the bars in each stage to be placed full length. This may require bars to be placed from below once the deck is removed. | Jill Fehrman | 1 | 2018-12-20 09:51 | 2019-01-03 09:36
20190115 | 20190115006 | 6 | Access to B-12-27 and B-12-28 | Per the traffic control details on these structures, barrier wall is to extend full length with the only access points being at the ends. Due to the narrow work zones and anticipated quantities of full depth repairs, portions of these structures will not be easily accessible for extended periods of time. Will openings in the block be allowed? What type of protection would be required on the blunt barrier ends? Could permanent openings be installed at locations determined in the field, or would they have to be closed up during non-work hours? Would existing bid items be used to pay for this work (ie. Temp Crash Cushions, Temp Barrier Install, etc.) or would this be a contractor risk item that would be incidental to the contract? | Due to the narrow work zone, anticipated full depth repair work, and length of the structures, four access points will be allowed per structure during Stage 2. An addendum has been prepared detailing the typical layout of an access point and the adjusted quantities of temporary crash cushions and concrete barrier delivered/installed. | Jill Fehrman | 2 | 2019-01-09 11:15 | 2019-01-10 17:41
20190115 | 20190115006 | 6 | Haunch Removal | Is haunch removal for Plate girders only or is it anticipated on the stringers as well? For measurement purposes, would the removal of the haunches on both sides of one foot of girder length be 2' of haunch removal? What is the anticipated method for marking out areas to be removed? Will the engineer need access to the top flange of all girders for the full length of both bridges? | The quantities for haunch removal account for the full length of the plate girders, with additional undistributed amounts on the stringers anticipated. Since some sections along the plate girders have already fallen off, and portions will be removed during full depth deck repair, the estimated quantity should be enough to cover any additional removal along the stringers. Any removal along a stringer will be measured per side. The engineer will need access to the top flange of all girders for the full length of both bridges. Access provided by mobile platform or snooper is acceptable. | Jill Fehrman | 4 | 2019-01-09 11:27 | 2019-01-10 17:43
20190115 | 20190115006 | 6 | Delaminated Concrete Removal on Parapet Face | The 'Parapet Partial Removal' detail on sheet 2 of the structure plan for B-12-27 indicates that the contractor is to remove any loose and delaminated concrete at parapet face where directed by the engineer. Payment is included in a Lump Sum item without any indication of an estimated quantity. There is approximately 9,000 sf of this surface on the bridge, and no way for a contractor to safely observe prior to lane closures. Could this be changed to payment by SF to reduce risk for both owner and contractor? | The estimated quantity is approximately 10,000 SF, assuming roughly 2 SF/LF of parapet. This estimated quantity is for informational purposes only and should account for removal at both the toe and face of parapet. | Jill Fehrman | 5 | 2019-01-09 22:32 | 2019-01-11 16:14
20190115 | 20190115007 | 7 | Soil Borings | Are there soil borings available? | The Geotech Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115007/ | Mike Coleman | 1 | 2019-01-08 09:08 | 2019-01-09 06:47
20190115 | 20190115010 | 10 | Clarifacation | On page 3 of 12 of the special provision under fish spawning 1. it lists Blotz Creek, Ley Creek, and Gordon Creek for no instream disturbance from May 15th to September 15th. Are those dates inverted? 2. In the Plan and Profile it shows all the drainage channels as Unnamed Tributaries Is there even any work in the 3 listed Creeks? If there is can the 3 creeks be listed by station or put on the plan and profile sheets? | An addendum will be issued to clear up the following: 1. The Special Provision should read as the following: There shall be no instream disturbance of Blotz Creek, Ley Creek, or Gordon Creek, nor to immediate or close proximity tributaries to these creeks, as a result of construction activity under or for this contract, from September 15 to May 15 both dates inclusive, in order to avoid adverse impacts upon the spawning of trout. 2. Instream Disturbance Locations: Tributary to Creek Location Immediate Tributary to Blotz Creek B-25-190 (Sta. 199+30 to Sta. 200+45) 36â€ CPRC (Sta. 203+40 to 204+50) Immediate Tributary to Ley Creek C-25-58 (Sta. 299+50 to Sta. 300+50) Close Proximity Tributary to Gordon Creek C-25-3009 (Sta. 899+00 to Sta. 901+00) | Mike Coleman | 1 | 2018-12-12 10:04 | 2018-12-13 10:24
20190115 | 20190115010 | 10 | Temporary Bypass Channels | What are the channels to be backfilled with & how is this material being paid for? |  |  | 2 | 2019-01-10 10:59
20190115 | 20190115012 | 12 | Vertical Scale on cross section sheets 121 & 122 | Can you please varify the vertical scale for the cross section sheets 121 & 122. The numerical labels along the right side show each major square as 10 ft but the arrow diagram just to the left show every 2 major squares as 10 ft. | The vertical label on the arrow is incorrect on cross section sheets 121 & 122. The vertical label on the arrow should be 20 FT instead of 10 FT. The numerical labels and elevations along the right side are shown correctly with each major square as 10 FT. An addendum will be issued to correctly show the scale. | Mike Coleman | 1 | 2018-12-27 13:56 | 2019-01-03 12:55
20190115 | 20190115012 | 12 | Geotech Report | Can you provide the Geotech Report for this project? | The Geotech Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115012/ Deanna, please create a link in the SE Region Preliminary Plans Page for proposal #12. | Mike Coleman | 2 | 2019-01-04 06:39 | 2019-01-04 06:41
20190115 | 20190115012 | 12 | Noisewall N-40-90 Overhead Power Lines | Can clearance distance from existing grade to the overhead power lines that N-40-90 runs underneath be provided? It appears that there are two (2) sets between stations between stations 213+50.00 and 215+00.00 | There is approximately 65ft to 70ft of clearance from the existing grade to the overhead lines, between Sta 213+50 and Sta 215+00, that N-40-90 will run underneath. Clearance to the wires varies with temperature and wind speed. | Mike Coleman | 3 | 2019-01-04 14:20 | 2019-01-08 07:35
20190115 | 20190115012 | 12 | Underground Utility Locating - Potholing? | With the numerous underground utilities shown on the plans and listed in the specifications. Will locating/potholing be done prior to the start of construction? If so, how will this be paid? | It is up to the contractor to contact Diggers Hotline for utility locates prior to excavation. They would then locate and mark the horizontal location of utilities. If there are utilities at the excavation locations, itâ€™s up to the contractor to carefully excavate in these areas to avoid hitting the utility. There will not be a pay item for locating/potholing for this project. | Mike Coleman | 4 | 2019-01-07 11:08 | 2019-01-09 06:41
20190115 | 20190115012 | 12 | Mounting bracket for the blank identifier blades | Do you have a detail or spec. that shows these brackets or are they simply an aluminum cantilever bracket? | The detail for the mounting bracket is shown on Page 7 of the Plans. | Jill Fehrman | 5 | 2019-01-13 18:00 | 2019-01-13 18:01
20190115 | 20190115014 | 14 | Night Time Hours | Are night time hours the same for both NB and SB? Special Provisions only show NB night time hours. | The heading for Southbound hours is missing. Southbound should have appeared between the second and third lines under Northbound. An addendum will be issued to add the heading for the Southbound hours. | Jill Fehrman | 1 | 2018-12-20 14:22 | 2018-12-27 12:53
20190115 | 20190115014 | 14 | Drain slotted vane | are the drains 3' or 6' | Drain slotted vane are meant to be undistributed in case one needs to be replaced. Based on the as-built plans and pictures, the existing vanes are 6â€™, the same should be used if replacement is required. | Jill Fehrman | 2 | 2019-01-08 12:13 | 2019-01-10 17:20
20190115 | 20190115014 | 14 | PWL Test Strips | PWL Test Strips are listed as 6 each. How did the department determine this quantity and what are the anticipated locations or base materials they will be performed on? Also, will there be any leniency on lane closure times and lane rental fees due to the required quantity of testing after the milling and paving are completed? | The number of PWL strips (6 per project) was assigned for the 3 main lanes for both lower and upper asphalt layers. There will not be any leniency on lane closure time or lane rental fees do to testing after milling or paving operations are completed. | Jill Fehrman | 3 | 2019-01-09 10:11 | 2019-01-13 20:37
20190115 | 20190115014 | 14 | Asphalt Wedge Between Lanes | Traffic Control: Construction Staging Typicals show a wedge from both binder up to existing surface (1') and from new surface down to new binder (2') for a lane transition between nights of paving. Will the asphalt quantity, and subsequent milling removal, of this wedge be paid by the ton or is it incidental? | The asphalt quantity, and subsequent milling removal, of this wedge be paid by the ton, the Miscellaneous Quantities were updated in Addendum 2 to specify the items and quantities in the wedges. | Jill Fehrman | 4 | 2019-01-09 10:23 | 2019-01-10 17:49
20190115 | 20190115014 | 14 | PWL Testing | Given that the asphalt binder is variable thickness, and PWL density testing is based upon consistency of results, has the department given any additional consideration to these testing requirements or do they have any anticipation for constructability issues to maintain consistency, e.g. wedging or scratching? Similar situation with the longitudinal joint density. Some of the binder course will be placed over existing concrete base/pavement and some will be directly over asphalt joint and crack repair performed that same night. | No wedging or scratching is planned. If the contractor expects the variable thickness or the underlying area to affect the ability to get adequate or consistent density, then the contractor should account for those variables in their bid. The department expects adequate density to be achieved in the variable thickness areas as well at the longitudinal joint. | Jill Fehrman | 5 | 2019-01-09 10:59 | 2019-01-10 17:48
20190115 | 20190115014 | 14 | Item 465.0125 Asphaltic Surface Temporary | What is the intended use of this item? | The Asphaltic Surface Temporary is for placing asphalt where we pull out the sign bases and median barrier. Due to the operations of pulling out and replacing light pole bases and areas of median barrier, some asphalt will need to be cut out to do the operation. The temp asphalt is needed to restore the shoulder areas while completing the barrier upgrades. These patches will eventually be milled off during the repaving stages. | Jill Fehrman | 6 | 2019-01-10 09:51 | 2019-01-11 09:30
20190115 | 20190115014 | 14 | Cold Weather Pavement Markings | With a paving completion date of November 1st how come there was not any cold weather pavement markings put in the bid to cover adverse weather conditions for that time of year? | As per Special Provisions Prosecution and Progress section, pavement marking should be immediately following the pavement. With operations completion in October it is anticipated that no Cold Weather Pavement Markings will be required. | Jill Fehrman | 7 | 2019-01-10 16:12 | 2019-01-11 16:54
20190115 | 20190115014 | 14 | Work during Off-Peak Hours. | Performing SHES Base Patching with closures Starting at 9:30pm to 5:30pm leaves little to time to perform the SHES Base Patching work. Between putting up the lane closures, cleanup, and cure time there is about 3 hours when work can be performed. First, would WisDOT consider extending the hours allowed to work. Please note, an additional hour would nearly double daily production. Secondly will WisDOT allow work during off peak hours as long as the Lane Rental Fee is paid? | All Base Patching work has to be completed as specified in plans and specifications: Most of the lanes during Night Time Hours Some lanes possible during Off-Peak Hours Please see B Definitions Section of Prosecution and Progress of Specifications Page 7 of 97 for specific hours. | Jill Fehrman | 8 | 2019-01-10 20:45 | 2019-01-11 16:23
20190115 | 20190115014 | 14 | Work during Off-Peak Hours. | Performing SHES Base Patching with closures Starting at 9:30pm to 5:30pm leaves little to time to perform the SHES Base Patching work. Between putting up the lane closures, cleanup, and cure time there is about 3 hours when work can be performed. First, would WisDOT consider extending the hours allowed to work. Please note, an additional hour would nearly double daily production. Secondly will WisDOT allow work during off peak hours as long as the Lane Rental Fee is paid? |  |  | 9 | 2019-01-10 20:45
20190115 | 20190115014 | 14 | High Mast Lighting Foundations L-67-131 to L-67-135 | The details for reinforcing steel on the drilled shaft are conflicting. 4" of cover on a 54" diameter shaft would give a hoop/bar diameter of 3'10". However the detail for the H402 hoop bars indicates a diameter of 3'4". Which dimension is correct? |  |  | 10 | 2019-01-11 14:08
20190115 | 20190115014 | 14 | Base Patching | On previous projects it has been the direction of the Department that men and equipment cannot work beyond the 2â€™ buffer of the drumline. This has been due to safety concerns. Therefore the drumline has been pushed into the third lane so that the center lane could be base patched in a safe manner. The detail on sheet 174 does not allow for this work to take place in a safe manner and within the guidelines previously established by WISDOT. The detail on sheet 177 allows for a safe method of performance of this work. Is there a reason that this detail is not prescribed for base patching as well as asphalt pavement placement? | At night, they are only required to keep one lane of traffic open at a time. We would agree they could use the stage 3 typical for stage 1 base patching. In areas of longitudinal joint repair, they could shift the traffic to the aux lane or shoulder as they mentioned. The use of the 42â€ cone was to gain an extra foot. | Mike Coleman | 11 | 2019-01-14 12:11 | 2019-01-14 12:13
20190115 | 20190115015 | 15 | As-Built Plans | Are there any as-built plans available for this project? | The As-Built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115015/ | Mike Coleman | 1 | 2018-12-10 10:53 | 2018-12-12 09:09
20190115 | 20190115016 | 16 | Concrete Pavement Fast Track | Item 415.1150.S.001 - Miscellaneous quantities appear to include 10% in each area for the Fast Track Concrete. Is the Department intending that small areas in each station range shown will include this fast track mix or is this a way of distributing an undistributed quantity? What is the timeframe required to develop 3500 PSI to open to traffic as specified in the Special Provisions? Will the Department require an action plan per section C.3 (2) for each of the areas listed in the Miscellaneous Quantities? Please provide more specific locations and associated quantities. | The guidance for the STSP usage on fast track concrete says to use the item when opening traffic â€œas soon as possibleâ€, but we do not see any specific guidance on that timeframe. In order to provide enough information on location, opening strength, and timeframes, we are electing to change the bid item to the standard HES paving items and make the updates in the MQâ€™s to provide clarity to the contractors and also the engineers in the field. This change will be included with addendum number 1. | Mike Coleman | 1 | 2018-12-12 12:51 | 2018-12-17 10:51
20190115 | 20190115016 | 16 | CAD Files - Call Order #16 CTH H | Can the department please supply the CAD files for this project. Thank you. | The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115016/ | Mike Coleman | 2 | 2018-12-14 08:10 | 2018-12-21 09:17
20190115 | 20190115016 | 16 | Bank Run Alternate. | Would WisDOT consider using Bank Run rather than Breaker Run. The savings would be considerable. | Per Section 311 of the 2019 State of Wisconsin Standard Specifications for Highway and Structure Construction, Pit Run is not an acceptable substitute for Breaker Run. WisDOT will not consider it. | Jill Fehrman | 3 | 2018-12-30 23:26 | 2019-01-04 15:11
20190115 | 20190115016 | 16 | Earthwork - Asphaltic Surface Material in Common? | Sheet 323 the Earthwork Summary note 2 says "Cut Volume includes existing concrete and asphaltic surface material", in reviewing the Earthwork Data sheets this seems to be not the case. There are multiple fill cross sections that have zero common excavation that should have quantity for the Asphaltic Surface removal. Please verify. | The Earthwork Summary Table will be updated via addendum with additional volume for Excavation Common and Roadway Embankment to reflect the estimated volume of asphaltic material in fill sections that needs to be removed and replaced. | Jill Fehrman | 4 | 2019-01-02 10:25 | 2019-01-04 15:13
20190115 | 20190115016 | 16 | Fish Spawning - No Instream Disturbance | Fish Spawning - No Instream Disturbance on page 14 of the specials says March 1 to June 1 and on page 16 it says March 1 to June 15. Which date is it? Either way based on the schedule for this Project, the new pipe and removal of the old one needs to be completed around the May 1st timeframe. Seeming this is the start of the Lamparek Creek, can these dates be changed to March 1 to May 1st? | March 1 to June 1 is the correct timeframe. The Special Provisions will be updated via addendum. | Jill Fehrman | 5 | 2019-01-02 17:29 | 2019-01-04 15:15
20190115 | 20190115016 | 16 | ATC Concrete Encased Duct Package | If ATC doesn't start to extend the four concrete-encased duct packages before June 1, 2019 and it takes 30 calendar days (Or working days) to complete, this project will not be completed on time. This work needs to be completed by June 1st, 2019. Please advise this can be accelerated. | The ATC concrete-encased duct packages are located in the R/W and should not interfere with roadway construction. The westerly R/W is located 39.5 ft from the proposed CTH H southbound back of curb. Grading operations near the westerly R/W will need to be coordinated. | Jill Fehrman | 6 | 2019-01-02 18:05 | 2019-01-04 15:19
20190115 | 20190115016 | 16 | ATC Thermal Backfill | Where is the ATC Thermal Backfill required? There is a Special Provision and Detail in the plan, but no location in the plan? A Station Range? Or plan sheet showing where this detail is needed? Will the 69,000 - 138,000 volts be turned off during the operation of excavation, supporting and backfilling? | The locations of the ACT duct packages are included in the Utility Article in the special provisions are as follows: Sta. 838HN+02, Sta. 838HN+27, Sta. 838HN+57 and Sta. 838HN+93. This facility has been constructed within the R/W and shows as an existing utility in the removal plans and plan/profile sheet. The facility is not anticipated to be energized during construction. Coordination with ATC is required to confirm. | Jill Fehrman | 7 | 2019-01-02 18:46 | 2019-01-04 15:21
20190115 | 20190115016 | 16 | Current/Utility Winter Work | Currently within the project limits there is a lot of utility and earthwork happening throughout the winter and it is scheduled to be completed before this project is scheduled to start. Please confirm that the project site will be restored to the existing conditions represented in the plan? | The utilities are required to restore their work sites to existing condition at the completion of their projects. It is WisDOTâ€™s expectation that this will occur. Bidders should also note that as detailed in the Special Provisions, utility work will be ongoing during the CTH H project. | Mike Coleman | 8 | 2019-01-04 11:40 | 2019-01-09 12:18
20190115 | 20190115016 | 16 | Non-Mandatory Pre-bid Meeting | Can you provide the Power Point presentation from the non mandatory pre-bid meeting? | The Non-Mandatory Pre-bid Meeting Power Point presentation can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115016/ | Mike Coleman | 9 | 2019-01-08 07:29 | 2019-01-08 07:32
20190115 | 20190115016 | 16 | Lane Rental Assessment | Will we be allowed to flag traffic on CTH H to perform the NB widening without being assessed lane rental fees? | No. | Mike Coleman | 10 | 2019-01-11 11:01 | 2019-01-14 13:51
20190115 | 20190115016 | 16 | Flagging CTH H, CTH KR & Braun Road | Can traffic on CTH H, CTH KR and Braun Road be flagged to construct this project during the day? Need to for Stage 1 and possibly other stages also. | No. | Mike Coleman | 11 | 2019-01-12 14:37 | 2019-01-14 13:52
20190115 | 20190115016 | 16 | Time for Completion | Please provide a copy of the Contract Time for Completion (DT1923). | The Contract Time for Completion (DT1923) can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115016/ | Jill Fehrman | 12 | 2019-01-13 17:13 | 2019-01-13 17:27
20190115 | 20190115016 | 16 | EBS Backfill - Alternate Materials | On previous DOT projects we have worked on, in lieu of breaker run, Project Engineer has approved use of earthen fill with sound properties to be utilized as EBS backfill. The areas that were ultimately a fill area to construct the roadway foundation similar to details on this project. Will the DOT allow an alternate material for the EBS backfill? | Areas designated as â€œLamparek Creekâ€ in the EBS Excavation table of the Special Provisions shall be backfilled with breaker run per the EBS Backfill item (SPV.0035.003). For areas designated as â€œUndistributedâ€ in the EBS Excavation table, the engineer will decide if material meeting the requirements of Roadway Embankment (Item SPV.0035.001) can be used. EBS areas that use Roadway Embankment material as backfill will be paid for under the Roadway Embankment item (SPV.0035.001). | Jill Fehrman | 13 | 2019-01-13 17:36 | 2019-01-13 17:37
20190115 | 20190115017 | 17 | Geoasynthetic Reinforced Soil Abutment | Backfill is specified to be Open Graded Base as given in 310 310.2(2) says no.1 Concrete Agg can be used if this material is used does this fall under "such that nuclear density testing is not possible"? | If the contractor chooses to use No. 1 Concrete Aggregate nuclear density testing will not be possible and they will have to follow the requirement of a minimum of 4 passes with a vibratory compactor. | Mike Coleman | 1 | 2018-12-18 17:07 | 2018-12-21 09:01
20190115 | 20190115017 | 17 | Existing Structure Plans | Are there as built plans available for the existing structure P-31-28 that needs to be removed? | There are no know plans for the existing bridge. | Mike Coleman | 2 | 2018-12-19 10:16 | 2018-12-21 09:02
20190115 | 20190115017 | 17 | Geogrid conflicts on NE Corner | It appears that the geogrid reinforcement along the NE quadrant may conflict with the guardrail placement in the NE quadrant. The guardrail on this corner is "Steel Thrie Beam Structure Approach" and "Steel Plate Beam Guard Short Radius." With wood posts being required with these 2 bid items, we believe it may be not be possible to install the posts through the geogrid reinforcement along this quadrant of the bridge. Augering is definitely not an option. Has the Department seen wood posts driven through the reinforcement grid like this on previous projects? We've seen I-beam posts driven through, but wood posts may have too much surface area to "break through" the numerous layers of geogrid reinforcement. Please advise. | The geotextile will be in conflict with the post for the steel thrie beam structure approach and the steel plate beam guard short radius. It will not be possible to drive wooden posts for these items. The post will need to be pre-set. An addendum will be issued to address this issue. | Jill Fehrman | 3 | 2019-01-09 09:46 | 2019-01-10 17:36
20190115 | 20190115017 | 17 | RSF |  |  |  | 4 | 2019-01-10 17:18
20190115 | 20190115017 | 17 | RSF | B.2.1 - Says if bottom of the RSF is above the 100 year elevation you are to use Base dense. What is the 100 year water elevation? | The Geosynthetic Reinforced Soil Abutment special provision was written with stream crossings in mind. Since this project is a grade separation, there is no stream flow involved. Therefore, the RSF should be considered â€œabove the 100-year water elevationâ€ and Base Aggregate Dense shall be used in the RSF. | Jill Fehrman | 5 | 2019-01-10 17:40 | 2019-01-11 09:27
20190115 | 20190115017 | 17 | Beam Guard Post | In reference to addendum #1 guardrail installers are concerned with being able to install the wood post before the bridge is up. The radius area is also a concern. The way the addendum says post have to be installed might be impossible to do before the bridge is built. There is no way to set these post to the correct x,y,z without the road and bridge being installed prior. Will other means and methods be allowed? | It will be challenging to get the posts in the correct locations before the bridge is in place, but it is possible. The designer will provide coordinates and elevations for each post affected. With this option it is recommended that longer posts are used so they can be cut to the proper height following completion of the parapets. Other options to pre-setting the posts will be allowed with the approval of the engineer. One option would be to place void forms(12â€ Sonotube or similar) during construction of the abutment (with a gap in the geotextile) at each post which would allow some leeway in placing the post. Another option would be to construct the abutment as normal (leave a gap in the geotextile) and drill a cased hole for each post. With both of these options the post will be set in the supported hole and it will be backfilled with foundation backfill similar to posts set in bedrock (see SDD14b15a). | Mike Coleman | 6 | 2019-01-11 23:42 | 2019-01-14 13:55
20190115 | 20190115018 | 18 | Traffic Staging | The staging plan is a pretty vague on the staging outside of the area from Milwaukee street to Racine. Could the staging be clarified? Maybe a complete staging plan? | A specific staging plan will not be provided for Broad Street between Tayco Street and Milwaukee Street. Stage 1C can be completed at anytime during the project. The only requirement is that access to the properties is maintained as noted in Traffic Section of the special provisions. Traffic control for work between Tayco St and Milwaukee St is shown as Stage 1C in the plans. | Mike Coleman | 1 | 2018-12-28 10:41 | 2019-01-03 12:57
20190115 | 20190115018 | 18 | Integral curb | Is integral curb required in the areas of concrete pavement that have limited clearance? Will scab on or free standing be allowed in these areas? | Integral curb is required where shown in plan to meet the requirements for bicycle accommodations. Accommodations as part of the project design require no joint between the curb and the pavement. | Mike Coleman | 2 | 2019-01-04 13:45 | 2019-01-08 13:40
20190115 | 20190115018 | 18 | HMA QTYs | It appears that the quantities for the 3LT and 4LT are flipped. Please verify quantities. | The HMA quantities are flipped and will be corrected in an upcoming addendum. | Jill Fehrman | 3 | 2019-01-07 08:53 | 2019-01-10 17:32
20190115 | 20190115018 | 18 | Concrete - Sealing Joints | Regarding Concrete Sealing Joints: Is it going to be required, if so will it be incidental or will a pay item be added? | Concrete joint sealing will be required. This item will be added to the plan in an upcoming addendum. | Jill Fehrman | 4 | 2019-01-09 11:36 | 2019-01-10 17:33
20190115 | 20190115020 | 20 | Work Within Railroad Right-Of-Way | Special Provision 3, Work Within Railroad Right-Of Way, Paragraph 3 discusses the completion of specified work within the railroad right-of-way within one week of the railroad's completion of the track reconstruction. Will the contractor be required to provide and pay for a railroad flagger during this one week time frame to construct their work or will the track be closed for this time frame by the railroad as part of the overall track reconstruction and not require a railroad flagger. Please advise. Thank you. | A railroad flagger will be needed at all times that our contractor needs to work within 25â€™ of the tracks. There is no plan to close the track except for a short (few hours) time to replace the track through the crossing. CN RR will have their own flagman for their work and the roadway contractor will be limited in what if any work can be done at that time near the RR workers for safety reasons. Once the RR leaves, so does their flagman. The roadway contractor will need to have their own flagman set up through CN RR for their work before and after the RRâ€™s work. | Mike Coleman | 1 | 2018-12-18 10:56 | 2018-12-19 07:34
20190115 | 20190115020 | 20 | Rail Road Coordination | I am somewhat confused by all the permitting requirements expected of the contractor. Can these requirements be clarified and does the Department have any idea how long the permitting process may take? | The railroad coordination information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115020/ | Mike Coleman | 2 | 2019-01-04 16:36 | 2019-01-09 08:34
20190115 | 20190115020 | 20 | Special Provision Article 8 Notice To Contractor | Are the stamped engineered plans required to be submitted with the permit to the railroad under this article the same as the stamped engineered (OMNNI Associates) WisDOT plan set provided fot this project or is the contractor required to provide some other stamped engineered plans. Also,has the $1,350.00 application fee been paid already or is this the responsibility of the contractor. Thank you. | Yes, the stamped engineered plans are the WisDOT plan set (prepared by Omnni Associates) and attached in the completed permit application. No additional stamped plans are necessary. Per the 10th bullet on page 2 of the Permit for Utility Crossing and/or encroachment, A $0.00 paid deposit is required to begin the permit processing. | Jill Fehrman | 3 | 2019-01-09 14:57 | 2019-01-11 16:12
20190115 | 20190115021 | 21 | Travel Lane Requirements | The special provisions state under part 4 Traffic, "During non-working hours, adjacent travel lanes must be at the same elevation". This is becoming common practice for milling, but we have not seen this for paving, as it will create safety issues with traffic control by having to set back in the middle of the day. Paving with the tapered joint would be a much safer option. Could this section of the special provisions under the part 4 Traffic section be changed to reflect only the milling operations and remove the paving from this requirement? | An addenda will be issued to revise this provision to only apply during the milling operations. A tapered joint will be allowed during HMA paving. | Jill Fehrman | 1 | 2019-01-02 11:48 | 2019-01-04 13:39
20190115 | 20190115021 | 21 | Traffic Control - Typical Sections | In the traffic control typical sections (page 26 of project 9150-29-60) it shows the milling/paving being completed one lane at a time. Is this the intent? Or can the entire road width be milled off at one time? | The intent of the typical section is to show available clear widths for traffic when working on each side of the roadway. Staging of the milling and HMA pavement placement is not dictated by the graphics of this typical section. | Jill Fehrman | 2 | 2019-01-02 16:06 | 2019-01-04 13:45
20190115 | 20190115021 | 21 | Shoulder Widening | In the typical sections showing the 2' paved shoulder widening (preparing foundation for asphaltic shoulders), is the intent to remove any of the gravel off of the job, or just loose this excess gravel on the existing shoulder? | It is anticipated the excess gravel in the paved shoulder widening areas may be used on site but some of the material may have to be moved longitudinally along the project area. An addendum will be issued to add Item 305.0504.S, Hauling Excess Shoulder Material. | Jill Fehrman | 3 | 2019-01-02 16:10 | 2019-01-04 13:48
20190115 | 20190115022 | 22 | Storm Sewer Abandons and removals | Is there a storm sewer removal/ abandonment plan available to show locations of existing pipe, pipe sizes, depths and also which pipes are intended to be abandoned versus removed. | No there is not a storm sewer removal abandonment plan for the project. The removals and abandonments are shown in the miscellaneous quantities. The entire mainline pipe for the storm sewer will be abandoned with the exception of the last 210 feet from 80+34 to 82+44. All of the laterals within the project limits not being connected to the proposed storm sewer will be removed. | Mike Coleman | 1 | 2019-01-04 09:23 | 2019-01-09 07:18
20190115 | 20190115022 | 22 | Optimized Aggregate Gradation | On other jobs bid in the past there has been an item for Optimized aggregate gradation incentive. Should this job have that item or can this item be used and will incentives be paid? | An addendum has been issued to add optimized gradation incentive to the contract. | Jill Fehrman | 2 | 2019-01-09 13:44 | 2019-01-11 16:25
20190115 | 20190115022 | 22 | Storm Sewer at Holmgren |  |  |  | 3 | 2019-01-09 13:45
20190115 | 20190115022 | 22 | Asphaltic Surface Thickness & Quantity | For the Asphaltic Surface bid item, it appears the plan quantity may have been mis-calculated, by overlooking a square-foot to square-yard conversion factor, before multiplying by the expected yield. For the Asphaltic Surface Driveways and Field Entrances, is any information available that would indicate the anticipated or existing thickness of asphalt to be replaced in the driveways for the commercial and industrial properties? | The quantity of â€œasphaltic surfaceâ€ bid item is correct. There is one error in the â€œasphaltic surface driveways and field entrancesâ€ bid item. The quantity for the driveway from station 80+53 â€“ 80+88 should be 5 not 40 reducing the quantity to 330 ton instead of 365 ton. The thickness for most driveways is calculated to be 3 inches. The exceptions are the driveway for Paper Converting from station 71+80 to 79+75 and the driveway for Conger Industries from station 74+46 to 80+75. The pavement thickness for these two driveways is calculated to be 4 inches. An addendum has been issued to revise the miscellaneous quantities table including revised quantities and pavement thicknesses. | Jill Fehrman | 4 | 2019-01-09 13:50 | 2019-01-11 16:26
20190115 | 20190115022 | 22 | Storm Sewer at Holmgren | Storm Sewer at Holmgren will have to be placed and traffic will be directed over these trenches. Will these trenches be required to be a hard surface or can they remain gravel? If asphalt is required will this be paid as temporary asphalt? This same item might have to be used during the intersection switch from stage 3 to 4. | Asphaltic Surface Temporary will be required at the Holmgren way intersection to provide a hard surface for the mainline storm sewer line crossing Holmgren Way and for transitioning between existing and proposed concrete at the Holmgren Way intersection. An addendum has been issued adding this item to the contract. | Jill Fehrman | 5 | 2019-01-09 13:52 | 2019-01-11 16:44
20190115 | 20190115022 | 22 | Earthwork | Given the amount of EBS, have the underground utilities been cleared for this additional excavation? | The EBS location and depth was provided to the utilities when they prepared their workplans for relocation. Anticipated conflicts and relocations are addressed in the utilities article of the special provisions. | Jill Fehrman | 6 | 2019-01-10 16:52 | 2019-01-11 16:49
20190115 | 20190115024 | 24 | As-Built Plans | Are there any as-built plans available for this project? | The As-Built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ Another As-Built plan has been added to the same location. It is from 1934. | Mike Coleman | 1 | 2018-12-10 10:53 | 2018-12-13 10:20
20190115 | 20190115024 | 24 | Storm Sewer C-IIIA | The storm sewer pipe selection guide in the FDM allows for alternate pipe materials based on certain criteria; one of which is an AADT below 7000. With the projects design having an AADT of 8200; Please explain the selection of pipe materials that do not fit that criteria. Also, what are the testing requirements if C-IIIA storm pipe is utilized? | The actual AADT for the portion of the project west of Park Street is approximately 5000, and all storm sewer pipes in that area have been designated based on that ADT. Class IIIA pipe materials will be allowed between the west project limits and Park Street. The portion of the project from Park Street to the east project limits is designed based on 8200 AADT. Testing of pipe materials will be based on the 2019 Standard Specifications, any pertinent ASP 6 modifications included with the proposal, and the guidance provided in the Construction and Materials Manual Chapter 8. | Mike Coleman | 2 | 2018-12-17 13:53 | 2018-12-19 13:33
20190115 | 20190115024 | 24 | Geotechnical Data | Please provide soil boring information available for the project area. | The Soils Reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ | Mike Coleman | 3 | 2019-01-03 08:30 | 2019-01-08 13:36
20190115 | 20190115024 | 24 | Specs Clarification | Special Provisions Number 59 Lists numerous bid items. Are there more specific specifications for these items? IE; Montello's standard specs? | Article 8 of the special provisions was developed for the contractors use, and provides contact information to obtain the latest specs from MSA (Cityâ€™s Municipal Engineering Representative). | Mike Coleman | 4 | 2019-01-03 09:38 | 2019-01-08 13:35
20190115 | 20190115024 | 24 | Cold Weather Epoxy & Permanent Markings | I see there is a bid for cold weather epoxy for the final markings which is a great idea based on the mid-November completion date. However, there is no item for the permanent markings that are needed for the project. Per spec (page 458 646.5.2 (1) and (2), the cold weather epoxy item covers initial placement and removal in the spring and the permanent epoxy item would cover the markings placed in the spring after the cold weather markings are removed. Will there be an epoxy bid item added to this project to cover the permanent markings? | An addendum is being prepared to add permanent epoxy pavement marking quantities. | Mike Coleman | 5 | 2019-01-07 10:49 | 2019-01-09 09:46
20190115 | 20190115024 | 24 | Flaggers? | Per the traffic specials (pages 5-6), stages 2 thru 5 of STH 23 is to be closed to through traffic and detoured. Will flaggers need to be used for these stages, as section 39 Traffic Control of the specials states that flaggers need to be used? | Flagging is not anticipated for work operations occurring within areas fully closed to through traffic. However, since the contractor must â€œMaintain emergency, local, and pedestrian traffic during constructionâ€ (per Traffic article) some flagging is anticipated in the areas that are closed to through traffic, but open to local circulating traffic. | Mike Coleman | 6 | 2019-01-07 11:43 | 2019-01-09 09:09
20190115 | 20190115024 | 24 | Contaminated Soils | Can you post any info on the contaminated soils at Montello? Also they mention possible contaminated groundwater that may be a concern if dewatering is needed. Can you shed some light on that as well? Do you have an idea where that may need to go if encountered? | A Phase 2.5 Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ For landfill of contaminated soil, soil samples B2B and B2D are representative. For contaminated groundwater, if dewatering is required at the same contaminated soil location, it can be discharged to sanitary sewer with City permission (608-297-2416). | Mike Coleman | 7 | 2019-01-08 13:26 | 2019-01-08 13:32
20190115 | 20190115024 | 24 | files not uploaded | The files for the previous questions that are supposed to be at the following link are not showing up. When we go to that link all we see are the 2 as built files. Can this get fixed? ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ | The files have been re-uploaded to the ftp site at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ If you still donâ€™t see the files, you may need to refresh your browser window. | Mike Coleman | 8 | 2019-01-09 08:04 | 2019-01-09 09:00
20190115 | 20190115024 | 24 | Sanitary and Water Miscellaneous Quantity tables | The data on the sanitary and water miscellaneous quantity tables for project 1430-00-87/89 is not viewable. Can the tables be resent? | The sanitary sewer and water miscellaneous quantity sheets will be resubmitted as part of addendum #2. | Mike Coleman | 9 | 2019-01-09 13:15 | 2019-01-09 13:57
20190115 | 20190115024 | 24 | WPDES Permit, Design Construction Schedule and 404 permit | Please post the WPDES permit, design construction schedule and the 404 permit. | The WPCES Permit and Time Schedule have been posted at the following site: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115024/ As the special provisions indicate; A 404 Permit is not required. There is no planned discharge of fill material into wetlands associated with the project. The 404 permit would only need to be obtained as a result of contractor directed operations. | Jill Fehrman | 10 | 2019-01-09 13:33 | 2019-01-11 17:01
20190115 | 20190115024 | 24 | Discharge of petroleum affected groundwater to the City Sanitary Sewer System | Will the City of Montello allow the discharge of petroleum affected water to the city sewer system? Will there be any user fees related to the discharge of petroleum affected water to the city sewer system? What is the maximum flow rate that may be discharged to the city sewer system? |  |  | 11 | 2019-01-14 11:24
20190115 | 20190115025 | 25 | As-Built Plans | Are there any as-built plans available for this project? | The As-Built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190115025/ | Mike Coleman | 1 | 2018-12-10 10:54 | 2018-12-12 10:11
20190115 | 20190115025 | 25 | Silt Fence Installation | The specials state to install silt fence prior to May 1st. Does all 6,375 LF need to be installed by this date? If the project does not start before this date due to the fish spawning in stream disturbance limitations from March 1 to June 1, how will contract time be handled for this installation. Will traffic control installation or construction staking have to take place prior to the layout of silt fence? | All silt fence except the undistributed 200 LF shall be installed by May 1. Traffic control and staking for the project would not be required to be completed before the silt fence installation. However, any traffic control or construction staking required to completed the silt fence work will be required. Contract time will be charged for the initial silt fence work and will be suspended if project work will resume at a later date. | Jill Fehrman | 2 | 2019-01-03 12:59 | 2019-01-10 17:22
20190115 | 20190115025 | 25 | Removing Asp. Butt Joints | The asphaltic surface butt joint quantity includes butt joints at the two bridges and the east end of the job. There is no quantity figured for the west end of the job or the intersections and driveways. Will the 2â€™ cross cuts at these locations be paid as a butt joint or be incidental to the milling item? | The west limits of the project match into existing concrete. No additional payment for a butt joint will be paid at this location. Milling at this location will be paid as Removing Asphaltic Surface Milling. No additional payment for a butt joint will be made at intersections. Milling at all the intersections will be as shown in the construction details on page 14 and be paid as Removing Asphaltic Surface Milling. All existing paved driveways will be paid as removing asphaltic surface by the SY as shown in the construction details on page 14 . | Mike Coleman | 3 | 2019-01-03 13:05 | 2019-01-08 13:39
20190115 | 20190115025 | 25 | Structure Repaintng | What is the purpose of changing the degree of cleaning from a SSPC SP10 (near white) down to a SSPC SP6 (commercial grade)? |  |  | 4 | 2019-01-14 12:25
20190115 | 20190115026 | 26 | Completion Date | Since the Detour is anticipated to be in place from May through October 2019 ( Page 3 of 14 SP), Can the completion date be extended to October 2019 as well? | The completion date will remain August 29, 2019. The August 29 completion date ensures the structure painting will be completed during ideal temperatures. The detour route is being implemented and maintained by the City of Wausau west of the structure for their reconstruction project. The contractor is only responsible for the traffic control items shown on the traffic control plans as shown on sheets 4 and 5 of the plans and will be removed at the conclusion of the project. | Mike Coleman | 1 | 2019-01-02 17:03 | 2019-01-03 14:16
20190115 | 20190115027 | 27 | Asphalt Butt Joints | Using the details provided on sheet 5 for asphalt butt joints and work on Gravel side roads it does not seem possible to reach the quantities provided for the gravel side roads on sheet 17 in the Misc. quantities. The misc. quantities show 12,480 s.y. for the locations defined on sheet 5 as gravel side roads (detail on sheet 5 shows only a small asphalt apron). Please review quantities and advise. Thanks. | It appears additional quantities at the sideroads are not correct. An addendum will be issued to update the quantities. | Jill Fehrman | 1 | 2018-12-21 07:02 | 2019-01-03 08:32
20190115 | 20190115028 | 28 | Asphaltic Surface | This bridge project includes a small quantity of HMA pavement, which requires density testing. Shouldnâ€™t the item of asphaltic surface be adequate? | Yes, due to the small quantity of HMA pavement on the project, we will use the item of asphaltic surface instead. This will be addressed with an upcoming addendum. | Mike Coleman | 1 | 2018-12-19 07:31 | 2018-12-19 07:32
20190115 | 20190115029 | 29 | Stageline Shoring for R-61-16 & R-61-17 | MSE Walls R-61-16 & R-61-17 call for a "Wall Staging Joint" to account for the staged construction of the bridges, however there is no pay item or detail associated with the "Wall Staging Joint(s)". Please advise. | We do not typically have separate details or bid items for staging joints. In this case, that not was called out to ensure that the fabricator/contractor consider and coordinate construction of that portion of the wall and is incidental to it. | Mike Coleman | 1 | 2018-12-13 15:22 | 2018-12-17 10:52
20190115 | 20190115029 | 29 | Interim Completion - Stages 1 thru 4 | What is the Department looking for on structures B-61-41 and B-61-43 at the edge of deck during the winter months of 2019/2020? Is the Temporary Precast Concrete Barrier to be shifted and pinned? | At the end of stage 4, the intent is to shift/reinstall the temporary precast concrete barrier and pin to the decks of bridges B-61-41 & 43. An addendum will be issued to clarify the intent and revise miscellaneous quantities as needed. | Jill Fehrman | 2 | 2018-12-27 15:23 | 2019-01-03 11:10