## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190312 | 20190312001 | 1 | Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedule | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | Please contact Derek Potter, 608-884-7135, or derek.potter@dot.wi.gov, to obtain the metadata files. Remaining files/reports that are available can be found on the HCCI site on the SW Region preliminary plans page. | Mike Coleman | 1 | 2019-02-06 10:01 | 2019-02-12 15:34
20190312 | 20190312001 | 1 | CULVERT PIPE | There are multiple discrepancies in the culvert items between the plan and profile/cross sections vs the miscellaneous qtys as to which size/class pipe is to be constructed. For example the culvert at station 1135+50 show this pipe to be a 24â€ class III in the misc quant table and the cross sections show a 24x38 CL V. Could the Department review the size/class of the culvert pipes and update accordingly? | 1. Station 1041+50: The MQs call for two Pipe Grates 48-inch, but the culvert pipe at this location is only a 24-inch so pipe grates will not be needed. 2. Station 1120+50: The MQs should be updated to show the pipe as Class V, not Class III. 3. Station 1135+50 NB: The culvert is proposed to be 24â€x38â€-Inch culvert pipe class IV as shown in the plan/profile. The MQs should be updated to switch the quantity to 24x38-inch culvert pipe class IV and 24x38-inch apron endwalls. 4. Station 1141+50/1141+56: The MQs call for salvaging 24-inch apron endwalls, but these should be salvaging 24x38-inch apron endwalls. An addendum will be issued in the future to address these changes. | Mike Coleman | 2 | 2019-02-12 10:17 | 2019-02-15 08:44
20190312 | 20190312001 | 1 | Stage 4 Phase 3 Timeframe | In reviewing the Design Schedule Stage 4 Phase 3 work assumes it can be advanced before September 1, 2020 (Schedule shows starting July 22, 2020), how can this happen? This doesn't appear allowable according to the traffic pattern in Stage 4 Phase 2 and with the traffic pattern on the project to the south. Therefor Stage 4 Phase 3 items of work and their durations in the Design schedule if started after September 1, 2020, there is no way the work can be completed before the completion date of October 30, 2020. 2 months to complete Stage 4 Phase 3 is not enough time. Please review the completion date of October 30, 2020. It should be extended by 6 weeks according to Design Schedule durations. | There is sufficient time between 9/1/20 and 10/30/20 to complete the new/additional work area included on SB I-39/90 in Stage 4 Phase 3. The PCS design schedule shows â€œPOSSIBLE Advanced Stage 4, Phase 3 Workâ€ because the Department believes some of the work could be started prior to 9/1/20, but does NOT have to. | Mike Coleman | 3 | 2019-02-13 14:42 | 2019-02-14 13:49
20190312 | 20190312001 | 1 | Removal of Temporary Epoxy bid items | Do you have quantities included in the H2O removals to include the temporary epoxy or are you considering this removal to be incidental? Thank you. | The removal of Temporary Marking Line Epoxy (Size) is to be removed by water blasting and is incidental to the bid item per the standard specifications. | Mike Coleman | 4 | 2019-02-13 15:57 | 2019-02-15 06:41
20190312 | 20190312001 | 1 | Plan Details | Is there a reason the plan details from STA 1161-1191, 1215-1285 and 1303-North project limit have been excluded from the plans? | The plan details were only shown for unique areas (ramps, bridgesâ€¦). The plan detail locations that were not included in the plan are standard and follow the typical sections. | Mike Coleman | 5 | 2019-02-18 10:05 | 2019-02-19 10:17
20190312 | 20190312001 | 1 | Stage 4 Phase 3 Timeframe #2 | It appears that 2 lanes of SB traffic will be still on this section of roadway (when it is possible to advance Stage 4 Phase 3 according to the Design Schedule), which after reviewing the cross section doesn't seem to be the case. Removals & Excavation are on both sides of existing traffic, so maybe 10 - 25% can be advanced but can't be removed or hauled efficiently especially along traffic on the outside where there is no barrier wall. Because you can't do very much subgrade grading there is 0% chance of doing any Aggregate/Concrete work. Advancement of this stage seems very unlikely. The design schedule shows the items of work overlapping way to much and doesn't account for adequate cure time during the paving operation & doesn't account for the traffic control switch. It doesn't appear the October 30, 2020 date is achievable. Please review this date again. Is there a significance to the October 30, 2020 date? Traffic to the South will be is the same configuration well into 2021. | There is sufficient time between 9/1/20 and 10/30/20 to complete the new/additional work area included on SB I-39/90 in Stage 4 Phase 3. The PCS design schedule shows â€œPOSSIBLE Advanced Stage 4, Phase 3 Workâ€ because the Department believes some of the work could be started prior to 9/1/20. It is up to the contractor to determine if they want to advance some of the Stage 4 Phase 3 work, but they do NOT have to. Additional time beyond whatâ€™s listed in the proposal is not needed for project 1005-10-78. | Fred Schunke | 6 | 2019-03-04 17:58 | 2019-03-05 15:04
20190312 | 20190312001 | 1 | Wage Rates | Please confirm that the Ironworker wage rate for this project will be based on the Iron0383-001 rates- for the vicinity of Edgerton and Milton. The structure work on this project falls in the Local 383 Ironworkers Union jurisdiction, which is how these rates are set. |  |  | 7 | 2019-03-11 10:55
20190312 | 20190312001 | 1 | B-51-351 & 352 Bridge Excavation | There is no Bridge Excavation for B-51-351 & 352, please add an item. |  |  | 8 | 2019-03-11 11:27
20190312 | 20190312002 | 2 | Pavement Marking Quantities | It appears that, in some parts of this project, you have double the edge line quantities you need. For example, on page 37, from station 305+00-329+87 (2,487' section) you have 9,948 lineal feet of edge line rather than 4,974. Your thoughts and an addendum, if necessary,would be appreciated. | Yes, the white edge line was doubled by mistake. An addendum will be issued to correct this. | Mike Coleman | 1 | 2019-02-15 09:35 | 2019-02-18 08:16
20190312 | 20190312002 | 2 | Pavement Marking Quantity | Thank you for issuing the addendum. However, the entire edge line appears to have double the quantity needed rather than just the example section submitted in the previous question. Will you please address the entire project quantities in an addendum? Thank you. | Yes, the pavement quantities for edge lines were mostly doubled. An addendum will be issued to correct this. | Mike Coleman | 2 | 2019-02-21 08:30 | 2019-02-21 12:03
20190312 | 20190312004 | 4 | Milling & Paving Operations that are under full lane closure | On pg 3 of Special Provisions 3. Prosecution and Progress first paragraph says begin final surface paving within 24-48 hours of the binder layer placement. The lower layer (binder layer) is a same shift mill & pave. This means every other night we stop mill & pave lower lift to pave surface. We are milling 2" and paving a 2.25" lower lift HMA which means the lower lift HMA will be a stronger pavement structure than currently exists. Wondering if the time between paving the lower lift and the surface could be changed so that the entire lower lift could be paved before paving surface or at a minimum change it to 7 days between lower lift HMA and surface HMA? | The question regarding clarification on elevation difference will be updated in Addendum #1. The Prosecution & Progress and Traffic article has been updated. The 24 â€“ 48 hour requirement will not be changed. | Mike Coleman | 1 | 2019-02-14 10:14 | 2019-02-21 08:42
20190312 | 20190312004 | 4 | Low side shoulder slope | The general notes on sheet 2 of the plan says that the low side shoulder slope is to be 4% when the superelevation of the drive lane is less than 4%. To do this the 6' shoulder will have to be paved separate from the 12' drive lane. In the typical cross sections the drive lane and shoulder lane are both 2% which would allow the drive lane and shoulder lane to be paved in one paver pass at 18' wide. Do you want the 6' shoulder paved separate from the 12' drive lane? | The general note will be removed in an upcoming addendum. | Mike Coleman | 2 | 2019-02-18 15:00 | 2019-02-20 06:25
20190312 | 20190312004 | 4 | CTH PF Intersection traffic control | Is there a traffic control plan for CTH PF intersection? We cannot flag against stop and go lights! | Guidance on coordinating traffic signals at CTH PF intersection will be added in Addendum #1. The Traffic article in the Specials will be updated. | Mike Coleman | 3 | 2019-02-19 08:28 | 2019-02-21 08:45
20190312 | 20190312004 | 4 | Excavation & Curb work at PF intersection | Is the excavation and curb work at PF intersection to be done at night or can it be done during daytime? | All work in this segment is expected to be performed at night. | Mike Coleman | 4 | 2019-02-19 08:46 | 2019-02-20 12:04
20190312 | 20190312004 | 4 | Removing Pavement Sta 110+44 - 111+04 EB | There are no details of this work. Is this in driving lane, shoulder, or median? What is going back in it's place? | This specific section referred to is concrete median. Asphaltic Surface Safety Island is going back in its place per Typical Finished Sections. | Mike Coleman | 5 | 2019-02-21 09:46 | 2019-02-22 07:30
20190312 | 20190312004 | 4 | Filling Rumble strips on outside shoulder | The rumble strips will need to be filled before setting up Stage 1 Traffic Control. Are we going to set up Stage 2 traffic control first to fill the rumble strips or are we filling the rumble strips using flaggers to move traffic over? | This is a means and method issue. The Contractor can use flagging operation or full temporary lane closure. No standalone staging was set up for this. | Mike Coleman | 6 | 2019-02-21 10:02 | 2019-02-22 07:30
20190312 | 20190312004 | 4 | Same Day Epoxy Rt Lane Edge and Centerline in the 4 lanes | Are we going to paint same day epoxy on right lane edge in stage 2 before shoulder gravel is installed? Are we going to paint same day epoxy centerline while traffic control is in stage 2 set up? Not sure there will be room to move barrels over into the live lane. | The intent is for the Same Day Marking to be used on the C/L, this is per standard spec. The edge line can be done whenever. | Mike Coleman | 7 | 2019-02-21 11:38 | 2019-02-22 07:31
20190312 | 20190312004 | 4 | Curb & Gutter, Inlet Covrs, Safety Island Work in 2 Lane portion (Z & PF Intersections) of Project | Can this work be done in Stage 1 and/or Stage 2 as long as it is done at night with flaggers to allow concrete cure time prior to starting Stage 3 Milling & Paving? | Yes it can. | Mike Coleman | 8 | 2019-02-25 09:43 | 2019-02-27 08:05
20190312 | 20190312004 | 4 | CTH Z Intersection Traffic Control | I am trying to figure out how the Flagging - traffic control is going to work to Mill & Pave mainline through this intersection. Can you please tell me the station(s) that separates Stage 1 & 2 from Stage 3? On the plan it looks like it could be where the milling depth changes from 2" to 4" sta 409+64 EB, however from driving the job and looking at google earth the 4 lanes end at around +/- 403+00. | Addendum #2 will be submitted shortly that addresses this question. It will better clarify the flagging limits. | Mike Coleman | 9 | 2019-02-25 10:43 | 2019-02-28 07:00
20190312 | 20190312004 | 4 | 3 MT HMA Patching along new Curb & Gutter | Plan sheet 14 shows 3' wide HMA patching along new curb & Gutter on the Concrete Safety Island detail and 2' wide HMA patching on the Curb & Gutter Remove & Replace detail. Is it supposed to be different for each or is it supposed to be all 2' or all 3' wide? | The 3â€™ wide removal limit along C&G is only for the proposed safety island and C&G at the Historical Marker area at STA 347+00 â€“ 348+00. All other C&G replacement requires a 2â€™ removal limit. | Mike Coleman | 10 | 2019-02-26 11:17 | 2019-02-28 06:58
20190312 | 20190312004 | 4 | Wayside Milling | The plan quantities for milling on plan sheet 29 does not list the Wayside. How many Square Yards is the wayside milling? | The wayside milling quantities were included in the EB computations from STA 50+00 to 157+75. It amounted to approx. 1373 SY. | Mike Coleman | 11 | 2019-02-26 11:40 | 2019-02-28 06:59
20190312 | 20190312004 | 4 | Chip Seal Questions | Plan shows to chip seal over new pavement with .45 gal/SY using a larger stone. Our experience with chip sealing new pavement recommends using a smaller Granite stone (FA2) and less oil to prevent flushing/bleeding of wheel paths. We request that the agency addendum the seal coat item oil application rate of .30gal/SY and a 1/4" (FA 2) Granite sized stone. Also, the plan shows to perform same day epoxy following new pavement and prior to seal coat. We recommend on the sealcoat section to temporary stripe this section with waterborne paint rather than epoxy to assure the seal coat sticks to the pavement. | The current chip seal spec will remain. The pavement marking was addressed in Addenda #3. | Fred Schunke | 12 | 2019-03-06 13:39 | 2019-03-11 11:08
20190312 | 20190312004 | 4 | Safety Concerns working at night with flaggers at CTH PF and CTH Z intersections | Would it be possible to either put up detours for; or possibly hire local law enforcement agency to flag, the night work in those intersections? | Any closure or detour would need to be coordinated with Sauk Co. If the contractor wants to hire law enforcement for flagging that is up to them, flagging is an incidental item. | Fred Schunke | 13 | 2019-03-06 13:54 | 2019-03-07 10:17
20190312 | 20190312004 | 4 | Pavement Marking Seal Coat on Hill Section 85+00 to 165+00 | Is the epoxy paint in this section to be done after the HMA paving and again after seal coat or do you want temp paint after the HMA paving and then epoxy after the seal coat is done? | This question was addressed with Addenda #3. | Fred Schunke | 14 | 2019-03-06 15:25 | 2019-03-08 09:27
20190312 | 20190312004 | 4 | Chip Seal | Is chipseal being done in drive lanes only or entire width of pavement? | The entire pavement width including shoulders will receive the seal coat. | Fred Schunke | 15 | 2019-03-08 07:05 | 2019-03-08 09:31
20190312 | 20190312005 | 5 | Pavement Markings | Do you anticipate any pavement markings being needed for the north and west landing parking lots? Currently, it does not appear there are any included in the plan and proposal. Thank you. | Pavement marking is required for both the North and West landing parking lots. An addendum will be submitted to clarify the quantity, type and location. | Mike Coleman | 1 | 2019-02-18 07:19 | 2019-02-25 07:51
20190312 | 20190312005 | 5 | Push In Place Concrete Launch | Is it permissible to use a cofferdam and dewater the boat launch and cast the boat launch in place instead of pushing into final position underwater. We have had better products working in dry conditions. | It is not permissible. The Army Corps of Engineers will not allow the use of cofferdams at any of the boat landings. | Mike Coleman | 2 | 2019-02-28 13:32 | 2019-03-01 06:15
20190312 | 20190312005 | 5 | Push-In-Place Concrete Launch | If shop drawings are provided, is it permissible to have a WisDOT approved pre-cast concrete manufacturer pre-cast the launch at their facility and then deliver it to the jobsite? | Bid the project as it is currently shown in the plans and special provisions. | Fred Schunke | 3 | 2019-03-05 06:55 | 2019-03-07 09:48
20190312 | 20190312005 | 5 | Line 216 Special 01: 16 inch x 2 inch Select Crushed Material | Questioning if not a typo or error in size, and should be 6 inch x 1 1/2 inch? | No, please refer to the special provisions for the material gradation. | Fred Schunke | 4 | 2019-03-06 09:20 | 2019-03-06 15:45
20190312 | 20190312007 | 7 | Temporary Portable Rumble Strips | What are the temporary portable rumble strips intended to be used for? | The temporary portable rumble strips were added as an additional safety precaution prior to each temporary traffic signal. | Mike Coleman | 1 | 2019-02-26 10:04 | 2019-02-28 06:37
20190312 | 20190312011 | 11 | Concrete Masonry Overlay Decks | Will grade C concrete be allowed for the concrete masonry overlay deck on the Riverwalk bridge? | No, since this is a thin, un-reinforced overlay, Grade E concrete should be used. | Mike Coleman | 1 | 2019-02-13 12:10 | 2019-02-18 07:17
20190312 | 20190312013 | 13 | Pavement Markings | Can you please take a look at the pavement marking quantities on this project? It appears you have road length rather than actual quantity placed for the 4" epoxy. Thank you. | There is an error in the 4-inch epoxy length. An addendum will be issued to correct this. | Mike Coleman | 1 | 2019-02-18 15:40 | 2019-02-19 10:19
20190312 | 20190312013 | 13 | Soils Reports | Can you provide the borings and soils report for this project? | The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312013/ | Mike Coleman | 2 | 2019-02-27 12:37 | 2019-02-28 08:12
20190312 | 20190312014 | 14 | Soil Reports | Can we get a copy of the soils reports for Proposal 014 for the March Letting? | The Soils Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312014/ | Mike Coleman | 1 | 2019-02-14 11:01 | 2019-02-14 14:15
20190312 | 20190312014 | 14 | Paint Specs for building | In the salt shed the building cross section on Sheet 32 calls for a concrete sealer on the interior face of the perimeter retaining walls but there is no specification for the material we are to apply. The section also calls for a 12â€™ tall wall plank. Does that get painted or coated? With what? Same with the 2 x 4 fill height marker and the treated CDX plywood liner panels. In the brining building do we paint the interior masonry walls and the precast concrete ceiling plank? Again nothing is called out or specified. The painting spec is totally dedicated to painting exposed piping and metals with nothing listed for masonry, concrete or wood. I need some guidance as to what I should provide. |  |  | 2 | 2019-03-05 13:21
20190312 | 20190312014 | 14 | Brick Spec For Brining Building | For the brining building, the spec is unclear, can you clarify is there a brick selection or brick allowance for the Brining Building? |  |  | 3 | 2019-03-07 09:59
20190312 | 20190312015 | 15 | Monotube Delivery | The suppliers quoted 26-39 week estimated delivery of materials on the January & February lettings. Assuming the delivery will now be the same if not longer how will the project handle these long lead times regarding the completion date if the materials are not here in time. | The City will allow the contractor to install the monotubes after the interim completion date of November 22, 2019 but must be completed prior to the 2nd interim completion date of May 15, 2020. All excavation for the bases, or constructed bases without poles, that are left in place must be protected by the contractor at their cost. A addendum 1 has been prepared to address this language. | Mike Coleman | 1 | 2019-02-22 12:41 | 2019-02-28 07:01
20190312 | 20190312015 | 15 | Line #0374 SPV.0060.224 Video Detection System | What are the specs and approved video systems that can be used for the vehicular video detection system for this project? | The City will approve the Econolite Autoscope Vision, Iteris RZ-4 Advanced, or equal, video detection systems. It is recommended that the contractor contact Scott Reinbacher at the City of Milwaukee (414.286.3232) to determine if other video detection systems are compatible with the existing City equipment. | Fred Schunke | 2 | 2019-03-01 10:05 | 2019-03-05 12:47
20190312 | 20190312016 | 16 | Soils Report | Can the soils report be provided? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312016/ | Mike Coleman | 1 | 2019-02-20 07:05 | 2019-02-20 08:24
20190312 | 20190312016 | 16 | Monottube material delivery | The suppliers quoted 26-39 week estimated delivery of materials on the January & February lettings. This contract is 100 working Days. Assuming the delivery will now be the same if not longer how will the project handle these long lead times regarding the completion date? | The contractor is to be expected to meet all the terms of the contract including installation of the monotubes for the project. The contractor should engage a supplier that can meet the schedule of the contract. | Mike Coleman | 2 | 2019-02-22 12:36 | 2019-02-28 07:11
20190312 | 20190312016 | 16 | Common Excavation | The Earth work Summary shows in Addendum #1 24,407 CY for Cut plus 4,840 CY for undercut on project for a total Common Ex # of 29,047 CY. But the Earthwork summary also show 27,613 CY of Salvaged/Unusable pavement which is 3,200 CY above the entire cut for the project. While leaving 1,434 CY of available material on site for possible fill. If the Salvaged/Unusable pavement exceeds the CUT how is there available material still available? Is there a miss calc in the quantities? | Two values shown on two columns were calculated wrong. The amount shown on these columns have been revised. Salvaged/Unusable Pavement Material should be (Excavation common â€“Available material )24207-1434= 22,773 SY instead of 27613 SY The Waste amount shown on the table should then be Salvage Material- Mass Ordinate) 22,773 + (-114)= 22,659 SY. The above revisions do not result in estimate quantities revisions. The revised sheet will be submitted with addendum #2. | Fred Schunke | 3 | 2019-03-05 15:23 | 2019-03-06 14:46
20190312 | 20190312016 | 16 | Concrete Pavement 8.5 Inch | With the add of Addendum no. 1 there has been a change to the plan in to the Begin Construction limits from 00+77 to 3+82.4. With the reduction in Scope and Concrete pavement 8.5 Inch, how did the quantity increase from 58,189 SY to 62,377 SY? Also can you please explain on the addendum sheets what is being added on Plan sheet No. 57 of the plan and profile? The entire sheet is bubbled but no Notes are given on what is changed with the addendum? | Concrete Pavement will be paid by what is completed and measured in the field per spec 415. | Fred Schunke | 4 | 2019-03-07 13:55 | 2019-03-08 14:06
20190312 | 20190312016 | 16 | Integral Curb | Typical sections show a 1â€™ Flange on the median curb ( See Attached) but it calls out for all this median curb island work to be integral. Can you please clarify if this curb can be 18â€ curb poured separate from the pavement or must be integral. Since these island areas are scattered through the project and with turn lanes it makes it all hand work to pour these integral. That adds up to a lot of handwork on this project. | The reason for the integral curb is due to much needed widths to accommodate for bike lanes requirements and also the typical section needs to show 1 ft flange for pay items, showing what is paid for pavement versus CC&G. The curb must be integral as shown on the plans for the above reason of bike lanes minimum widths requirement. | Fred Schunke | 5 | 2019-03-08 14:08 | 2019-03-08 14:08
20190312 | 20190312017 | 17 | Monotube materials Delivery | The suppliers quoted 26-39 week estimated delivery of materials on the January & February lettings. Assuming the delivery will now be the same if not longer how will the project handle these long lead times regarding the completion date if the materials are not here in time? | Per Addendum 1, monotube (poles, arms, signals, wiring) installation has a revised completion date of August 2, 2020. | Mike Coleman | 1 | 2019-02-22 12:43 | 2019-03-01 09:06
20190312 | 20190312017 | 17 | Epoxy 12-Inch crosswalk | Plan shows 26 legs of 12-inch crosswalk was it left out intentionally? | The quantity for item Epoxy 12-Inch Crosswalk is in the plans, special provisions and estimates under item SPV.0090.002. | Fred Schunke | 2 | 2019-03-05 15:24 | 2019-03-07 09:55
20190312 | 20190312018 | 18 | Type 3 Poles | A Type 3 Pole is asked for in the plans, which is a steel pole. The notes specify that this pole is to be anodized and powder coat will not be accepted. You cannot anodize steel poles, you can only anodize aluminum. Do we need a type 5 aluminum pole or do we need to allow the Type 3 Pole to be powder coated? | An addendum will be submitted to revise the Special Provision to require painting or powder coating. | Fred Schunke | 1 | 2019-03-04 11:56 | 2019-03-05 11:39
20190312 | 20190312018 | 18 | Material questions | Item 656.0200.01, Electrical Service Meter Breaker Pedestal: 1) Special Provisions call for the service installation or relocation costs to be paid by the Contractor. These costs should be paid by the maintaining authority since WeEnergies wonâ€™t provide a price for this prior to the bid. 2) Special Provisions call for the meter pedestal to have an anodized black exterior finish. The meter pedestal is steel and steel does not anodize effectively. Can the meter pedestal be painted or powder coated instead? Item 657.0310, Type 3 Poles: 3) Type 3 poles are galvanized steel and are typically painted black since steel doesnâ€™t anodize effectively. The Special Provisions say that painted or powder coated finishes are not acceptable. An alternate would be to install aluminum Type 2 poles and install the video detection cameras on mast-style mounting posts. Item SPV.0060.01, Traffic Signal Cabinet and Controller: 4) Special Provisions call for the cabinet to have a natural aluminum finish inside and outside. Is this cabinet supposed to have a black finish? Item SPV.0060.03, Local- Whitefish Bay Street Signs: 5) Special Provisions call for coordination, transporting and installing the signs. Will these signs be furnished to the Contractor by the Village of Whitefish Bay? Item SPV.0060.04, TAPCO Swing Bracket (Street Signs on Trombone Arm): 6) Special Provisions call for coordination, transporting and installing the signs. Will these signs be furnished to the Contractor by the Village of Whitefish Bay? | 1) An addendum will be submitted to revise the Special Provision to indicate that the Village of Whitefish Bay will provide payment. 2) An addendum will be submitted to revise the Special Provision to require painting or powder coating. 3) Addendum #1 was submitted to revise the Special Provision to require painting or powder coating. 4) The cabinet shall be provided with a natural aluminum finish as indicated. 5) An addendum will be submitted to clarify that signs will be provided by Village of Whitefish Bay. 6) An addendum will be submitted to clarify that signs will be provided by Village of Whitefish Bay and that contractor shall obtain and provide swing brackets. | Fred Schunke | 2 | 2019-03-06 07:54 | 2019-03-07 12:10
20190312 | 20190312018 | 18 | SPV0060.02 Decorative signal pole | Item SPV.0060.02, Decorative Traffic Signal Pole & Concrete Bases Type 5 Modified: 1) Special Provisions call for installing relocated decorative twin arms on the new poles. There are only (2) existing poles being removed but the project is calling for (4) new poles. Will the Village be providing the additional twin arms needed for the added poles? | An addendum will be submitted revising sheets to indicate that existing lights are to be relocated to poles at signal bases 3 and 7. Decorative poles at signal bases 1 and 5 shall be for signals only. | Fred Schunke | 3 | 2019-03-06 08:39 | 2019-03-07 12:10
20190312 | 20190312019 | 19 | Design Schedule | Can the design schedule be provided? | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312019/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2019-02-08 17:01 | 2019-02-14 07:25
20190312 | 20190312019 | 19 | SHES Base Patching Night Work Quantity. | Night work SHES Base Patching is far more expensive than Day work SHES Base Patching. Can we figure an even distribution of SHES Base Patching Between the areas shown as Day work vs Night work? Secondly, can we figure all area behind barrels as day work and any areas outside of the barrels as night work as shown on SHEET 113 going forward to SHEET 135? |  |  | 2 | 2019-03-11 10:13
20190312 | 20190312021 | 21 | Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedule | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | The metadata, soils report, and design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312021/ | Mike Coleman | 1 | 2019-02-06 10:02 | 2019-02-12 12:42
20190312 | 20190312021 | 21 | Prebid Meeting Presentation | Can you post a copy of the power point presentation from the prebid meeting? | The presentation from the Prebid meeting can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312021/ | Mike Coleman | 2 | 2019-02-26 13:20 | 2019-02-26 13:25
20190312 | 20190312022 | 22 | Concrete Masonry Overlay - Method of Measurement | This proposal has changed the Method of Measurement for the Standard Bid Item 'Concrete Masonry Overlay' from CY to SY. The area of the decks is easily calculated from the plans and an average thickness has been provided for each bridge by the engineer. How will variations (plus or minus) from the provided average thickness be handled? Also, this item is used to pay for the concrete used in Deck Prep, Joint Repair, Curb Repair, and Full Depth Repair items. These items always vary from plan quantities and present the same issue of possible overruns or underruns. | Variations would be addressed consistent with Standard Specification 104.2.2.4.. The items of Deck Preparation, Joint Repair, Curb Repair, and Full Depth Repair have been modified as indicated in Article 18 of the proposal. For the Preparation and Repair bid items, providing concrete is incidental to payment under standard spec 509.5. For the Overlay bid items added in Article 18, the department will measure the Concrete Masonry Overlay bid items by the square yard acceptably completed under standard spec 509.4, and the volume of concrete required under associated Preparation and Repair is not included in payment under standard spec 509.5. The department will not measure volume of concrete placed and will not make separate payment for volume of concrete placed for any of the items identified in Article 18. | Mike Coleman | 1 | 2019-02-26 14:34 | 2019-02-28 07:09
20190312 | 20190312022 | 22 | Concrete Masonry Overlay - Method of Measurement | The only part of section 104.2.2.4 that would potentially apply would be 104.2.2.4.3 - Changed Quantities. This assumes that DOT would recognize a volume increase as a reason for changed condition for an item that is measured and paid by area, which is debatable. Assuming this is the case and the Concrete Masonry Overlay is a major item, the contractor has no grounds for pay adjustment unless the quantity is less than 75% or more than 125% of plan quantity. If this is a minor item, no adjustments are made unless the quantity changes by 50%. This seems to be transferring all the risk onto the contractor and will likely end up with disputes in the field on original deck profile, mill depth, final profile and ride performance. Please confirm that section 104.2.2.4.3 will be used for payment adjustment if volume changes and area does not. | Changes in work would be addressed under Standard Specification 104.2.2.4. | Fred Schunke | 2 | 2019-03-04 10:25 | 2019-03-05 11:33
20190312 | 20190312023 | 23 | Hydroseeding | Since the specd material is NO LONGER produced can we substitute Soil Stabilizer TYPE A? | Yes Soil Stabilizer TYPE A can be used. | Fred Schunke | 1 | 2019-03-07 09:47 | 2019-03-07 12:12
20190312 | 20190312033 | 33 | Section 4 traffic | The third paragraph states, " Provide and even cross-sectional profile of the roadway at the end of each day's milling and/or paving", and as a matter of practice this is done with our milling operations, but this problematic with the paving operations. A mid-day set back paving would create a weave situation while the finish rolling and density operations are finishing and creating an unnecessary safety issue and diminishing the quality of the final product with additional joints. Can the statement be changed to include the milling operations only? | The language will be revised in an upcoming addendum. | Mike Coleman | 1 | 2019-02-18 16:30 | 2019-02-20 08:26
20190312 | 20190312033 | 33 | culvert pipe detail on sheet 10 | The sewer pipe detail on sheet 10 shows the depth and mix type, but the culvert does not. Can the depth and mix type be shown on that detail also? | The depth and mix type will be added to the construction detail via addendum. | Mike Coleman | 2 | 2019-02-25 12:11 | 2019-02-26 10:31
20190312 | 20190312033 | 33 | Strm Sewer | Sheets 34 and 35 of plan show a sump on the manholes while other sheets do not; will these structures have sumps or is the profile on the bottom not correct. Sheets 34 and 35 also show the top rim elevation approximately 1.5 ft higher than the existing ground. Is something missing in the plan? Is the existing line shown on the profile not correct or are the manhole elevations not correct? | The structures in question on Sheets 34 and 35 will be revised via addendum. | Mike Coleman | 3 | 2019-02-28 08:40 | 2019-02-28 18:51
20190312 | 20190312033 | 33 | Base Aggreggate Dense 1 1/4" Quantity | Typical Section on page 5 shows 12" of BAD 1 1/4" in beam guard areas, but Misc Quantities Table for Base Aggregates doesn't show any 1 1/4" (even though 49 tons of 3/4" shown). Please provide with updated quantities | The quantities for Base Aggreggate Dense 1 1/4" will be updated via addendum. | Fred Schunke | 4 | 2019-03-04 13:14 | 2019-03-05 12:48
20190312 | 20190312033 | 33 | Culvert Pipe Transitions | The misc. qty breakdown on page 52 makes it look like the culvert pipe transition item pays for all the granular material to support the culvert, to backfill the culvert, and backfill the transition cuts. It is confusing because the table on page 52 list common excavation + foundation backfill = Culvert Pipe Transition. But further confusing by the wording associated with the detail on plan sheet 10 kind of points in a different direction. Plus not sure how you would plan on keeping the paid work separate from the incidental work. | The items Excavation Common and Foundation Backfill shown in the table on Page 52, are for information only to assist in bidding the item â€œCulvert Pipe Transitionâ€. These items correlate accurately to the detail shown on Page 10. The table on Page 52 does not detail all incidental items of work for â€œCulvert Pipe Transitionâ€. | Fred Schunke | 5 | 2019-03-04 16:05 | 2019-03-05 12:49
20190312 | 20190312033 | 33 | Base Aggregate 1 1/4" Quantity | Typical Section on page 5 shows 12" of 1 1/4" base in beam guard locations, but Misc Quantity sheet on page 48 does not reflect it for these stations (even though 3/4" is shown for that location). Would quantity for Base Aggregate Dense 1 1/4" be adjusted? | The quantities for Base Aggregate Dense 1 1/4" will be updated via addendum. | Fred Schunke | 6 | 2019-03-05 09:45 | 2019-03-05 12:50
20190312 | 20190312034 | 34 | 0138 SPV.0060 1.000 EACH Special 02. Traffic Control Contract | WHAT IS THIS LINE ITEM FOR? NOTHING IN THE PROPOSAL SPECIFYING THIS SPV ITEM. | The bid item will be removed in an upcoming addendum. | Mike Coleman | 1 | 2019-02-25 08:17 | 2019-02-25 09:03
20190312 | 20190312035 | 35 | Misc Quantitiy Sheets | Would it be possible to get the misc quantities sheets in excel? Primarily interested in the culverts, storm sewer, storm sewer structures and earthwork sheets. | Miscellaneous quantity tables cannot be provided in EXCEL format. | Mike Coleman | 1 | 2019-02-26 12:58 | 2019-02-28 07:11
20190312 | 20190312035 | 35 | Culvert and storm sewer bid items | With the low ADT and the acceptable cover heights for the Class III pipe bid items, will contractors be permitted to utilize the competitive specs? (i.e. Class III-A or Class III-B) | No. The contractor should use the material as specified in the bid documents. Material selection was coordinated with local municipalities. | Fred Schunke | 2 | 2019-03-06 13:11 | 2019-03-07 16:00
20190312 | 20190312036 | 36 | Soils Info. | Can you post the borings and soils info for this project? | The soils reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312036/ | Mike Coleman | 1 | 2019-02-19 12:17 | 2019-02-21 08:24
20190312 | 20190312036 | 36 | Excel Sheets | Can you make the storm sewer and pipe sheets including storm laterals and earthwork data available in Excel format? | The storm sewer and pipe sheets including storm laterals and earthwork summary files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312036/ Please note, the department does not have the incremental earthwork (plan sheets 173 â€“ 179) in Excel. | Mike Coleman | 2 | 2019-02-19 12:20 | 2019-02-21 08:29
20190312 | 20190312036 | 36 | Field Office | The Schedule Of Items does not include a Bid Item for a Field Office. Will this project be managed out of the Project Office on Aerotech Drive? Thank you. | Yes. This project will be managed out of the WIS 441 project office at W6214 Aerotech Drive, Appleton, WI 54914-8543. | Mike Coleman | 3 | 2019-02-21 07:52 | 2019-02-21 08:40
20190312 | 20190312036 | 36 | Utilities | Special Provision No. 5 discusses the relocation of a number of utility facilities prior to construction. Generally these utilities are scheduled to be completed on or before March 1, 2019. Can an update be provided as to the status of conflicting utilites within the project limits? During site review it looks like there is still quite a bit of on going utility work. Thank you. | The utility status update can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312036/ | Mike Coleman | 4 | 2019-02-21 08:04 | 2019-02-22 07:14
20190312 | 20190312036 | 36 | PVC Laterals | The plan shows 3 locations where a connection needs to be made to an existing pipe for the pvc laterals. Is this all that there is and the others will be capped? Or are there other connections not shown on the plan? | After extensive coordination with property owners on the locations of existing pipes, the known connection points are shown on the plan. It is possible that there are others that need to be connected and will be considered extra work if identified during construction. As noted on the construction detail for storm sewer lateral (plan sheet 11), connections are to be made to the existing pipes as shown on the plan or as directed by the engineer. The construction detail and the special provision includes direction to cap the laterals where there is no connection being made to existing pipes. | Fred Schunke | 5 | 2019-02-27 15:26 | 2019-03-07 10:25
20190312 | 20190312036 | 36 | 3 LT QTY | With a typical section of 3.5" of binder for mainline Spencer St. I get a greater quantity of 3 LT. Could the typical section of 3.5" be confirmed for the mainline and the quantity be rechecked? | The HMA quantities will be revised via Addendum No. 1. | Mike Coleman | 6 | 2019-02-28 08:07 | 2019-02-28 18:53
20190312 | 20190312037 | 37 | Salvage Aggregates | Will we be allowed to salvage the aggregates that are existing on this project and also will they need to go through QMP testing? I question this because they are already part of the existing road. Please advise, Thank you for your time. | CMM 2-31: Contractor is allowed to use the material in the excavation limits as long as it meets the specification requirements. The contractor would need to perform the required testing for the bid item they are using the material for. Example: if using for granular backfill, will need to pass the acceptance gradation testing. If using for ¾â€ BAD, need to comply to QMP Base Aggregate. | Fred Schunke | 1 | 2019-03-07 09:54 | 2019-03-07 09:54
20190312 | 20190312038 | 38 | Pavement Marking Quantities | Looking at the pavement marking pages, and the miscellaneous quantities for the arrows, and symbols, there seem to be some missing pages. The bid items for Arrows have a quantity of 53, and t drawings only show 17 arrows. Symbols have a bid item quantity of 41, an the drawing only sows 7. Can you check the quantities, or add the missing pages? Webster Ave from Stationing 18+70(?) to 22+00(?) and 25+25(?) to 29+60(?) and 34+25(?) to 51+50(?) | There is an error in the quantity for Marking Arrows Epoxy and Marking Words Epoxy and these will both be reduced to match plans. An upcoming addendum will correct this. Pages are not missing from the plan. The station ranges questioned fall under a Typical Sideroad marking sheet found on page 86 of the plans. | Mike Coleman | 1 | 2019-02-15 10:16 | 2019-02-19 10:21
20190312 | 20190312038 | 38 | Geotechnical Report | Can you post a copy of the Geotechnical Report? | The Geotechnical Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312038/ | Mike Coleman | 2 | 2019-02-20 06:35 | 2019-02-21 08:48
20190312 | 20190312038 | 38 | Type a curb | The detail on page 12 for type A 18" curb and gutter does not follow the cities or the dot's standards. Is there continuous steel required in type A curb and gutter? | Detail shown in page 12 for Curb and Gutter 18â€ Type A and D has continuous steel required in it. This detail is a City of Green Bay Standard Detail as shown in their 2019 specification. The detail was provided by the City of Green Bay for inclusion in the plans at their request. | Mike Coleman | 4 | 2019-02-21 13:19 | 2019-02-25 07:50
20190312 | 20190312038 | 38 | Grading and shaping alley turnarounds and Temporary Pavement | Will removals and saw cutting be paid as separate items or will they be lumped into the grading and shaping alley turnarounds? Will the removals of temporary roads for stages 1b and 2 be paid for? If so are they included in the Common Ex quantity? | Payment section of special provision will be updated in an upcoming addendum to define better what is covered and what is not by the pay item. | Mike Coleman | 5 | 2019-02-25 13:11 | 2019-03-01 08:54
20190312 | 20190312038 | 38 | Storm Sewer | item 41 Storm sewer On page 24 of 63 second to last paragraph under 41 storm sewer, it says " Testing of storm sewer is incidental to the individual items" but it does not reference a City of Green specification number. Is this limited to 402.3 Sewer Testing, construction methods? Looking to verify that Green Bay specification 403 Sewer Televising is not included in this incidental work. | Sewer Televising per section 403 of the City of Green Bay Standard Specifications will not be required for storm sewer. | Mike Coleman | 6 | 2019-02-26 07:13 | 2019-03-01 08:56
20190312 | 20190312038 | 38 | Prosecution and progress | The fitfh paragraph of (3) Prosecution and progress states: "Complete construction operations on Webster Ave. to reopen to through traffic by September 30th." Can you elaborate on this entire paragraph/statement relative to the November 1, 2019 completion dates on proposal form? | Construction staging was re-evaluated. Updated staging and timelines will be provided in addendum 1. | Fred Schunke | 7 | 2019-02-28 09:27 | 2019-03-05 10:42
20190312 | 20190312038 | 38 | Pavement marking symbols | Thank you for addressing the arrows quantities with addendum #1. There is still a discrepancy with the Epoxy Symbols. Bid item quantity is still for 41, but the drawings only show 7. Also, the reduced quantity of words from 7 to 1 is wrong, as you are missing the 6 "BIKE" "LANE" "ENDS" words(2 each). Can you please recheck the quantities for the Epoxy words, and the Epoxy Symbols. Will you address this with an addendum? | An addendum will be coming to address the quantities. Not all symbols and arrows are shown on sheets. Per note on bottom of the page additional symbols and arrows are required per SDD for Bicycle Lane Marking, which is 1 per block minimum or every 250 feet. Therefore in a normal block two bicycle symbols and two bike arrows are required per side. | Fred Schunke | 8 | 2019-03-06 08:23 | 2019-03-06 14:44
20190312 | 20190312038 | 38 | Onsite crushing | Due to the stage changes and now being able to close the road will onsite crushing be allowed? | Onsite crushing will not be allowed. | Fred Schunke | 9 | 2019-03-06 11:06 | 2019-03-07 09:58
20190312 | 20190312038 | 38 | Stage change | Could the area 2A and 2B South of Station 16+00 be constructed prior to the area North of University? Can this area be closed prior to June 3rd? | No, the areas for Stage 2A and 2B cannot be constructed before June 3rd due to the lead time to get the traffic signal poles. If the poles were ordered when the contract is executed we have been told it would take until late summer to get the poles. The existing signals need to stay active for traffic control at University. Reconstructing the intersection would disturb the existing signals. | Fred Schunke | 10 | 2019-03-07 08:31 | 2019-03-07 10:19
20190312 | 20190312038 | 38 | Prior to June 3rd | If work would start prior to June 3rd can traffic be set up as prior to the addendum as it would have been in stage 1B? If so will the traffic control and other items be paid under items in the contract? | Work needs to be bid as shown. Before June 3rd, single lane closures will be allow. Per Special Provision #48. Traffic Control, â€œ Submit to engineer for approval a detailed traffic control plan for any changes to the proposed traffic control detail as the plans show. Submit this plan 10 days before the preconstruction conference.â€ | Fred Schunke | 11 | 2019-03-07 08:53 | 2019-03-07 15:44
20190312 | 20190312038 | 38 | Complete Closure | S.P. 3. Complete closure of Webster can't start until June 3rd. Does this pertain to Stage 2B? Completely close Webster and University intersection? | An addendum will be posted clarifying when closure for stage 2B is allowed. | Fred Schunke | 12 | 2019-03-07 09:58 | 2019-03-07 15:47
20190312 | 20190312038 | 38 | Addendum 2 - Staging | If the railroad holds to the October 19th completion date for their work will or is the completion date going to be extended? | The current completion date took into consideration the railroad work. Crossing surface is required to be completed by October 7th. Then pavement can be installed to the crossing. The roadway pavement work and the signals and gates work will be concurrent. After October 19th, topsoil and finishing can then be completed before the completion date in the crossing area. | Fred Schunke | 13 | 2019-03-07 15:02 | 2019-03-07 16:17
20190312 | 20190312039 | 39 | CIPP | â€¢ What is the pipe composition of the segments that are being CIPP lined? â€¢ What proximity to the job location will water be for cleaning and lining the pipe? â€¢ Are any videos or TV reports available for these segments to be lined? â€¢ What the warranty is on the CIPP lining? | 1. The pipe to be lined is ARMCO Truss pipe. 2. Hydrants are onsite, the contractor should coordinate with the Sheboygan Water Utility about hook up and billing. Contact Joe Trueblood at the Sheboygan Water Utility at 920-459-3800. (Contact information also provided in the plans and special provisions.) 3. Videos are available from the City of Sheboygan. To request copies, contact either Kevin Jump by email at Kevin.Jump@sheboyganwi.gov or Ryan Sazama by email at Ryan.Sazama@sheboyganwi.gov. (Contact information also provided in the plans and special provisions.) 4. Please refer to the following sections in the Standard Specifications for Highway and Structure Construction, 2019 Edition: 105.11.2.3(2) and 106.5(2). Update: We have an updated answer from the City of Sheboygan regarding the warranty on the CIPP lining. The city standard contract documents specify a 1 year warranty for CIPP lining. | Mike Coleman | 1 | 2019-02-13 15:18 | 2019-02-21 07:03
20190312 | 20190312039 | 39 | Monotube Material Delivery | The suppliers quoted 26-39 week estimated delivery of materials on the January & February lettings. Assuming the delivery will now be the same if not longer how will the project handle these long lead times regarding the completion date if the materials are not here in time? | The department is not considering this as an industry-wide shortage and contractors should bid the contracts accordingly. Liquidated damages will be assessed and any efforts to mitigate the liquidated damages will be the responsibility of the contractor. | Mike Coleman | 2 | 2019-02-22 12:44 | 2019-03-01 09:07
20190312 | 20190312039 | 39 | Sanitary Sewer 8 inch | C.2 Sanitary Sewer Mainline Testing--- Lists low pressure Air Test as a required test to be performed. With this being a relay section with potential active laterals and mainline flows. Is this test going to be required? Air tests are generally waived in relay situations because of these issues, trying to understand if we need to include costs to make these accommodations. | Correct, there are active laterals. The low pressure air testing will be removed from required testing in Addenda 1. | Fred Schunke | 3 | 2019-02-22 13:53 | 2019-03-07 10:23
20190312 | 20190312040 | 40 | Monotube material delivery | The suppliers quoted 26-39 week estimated delivery of materials on the January & February lettings. This contract is 90 working Days. Assuming the delivery will now be the same if not longer how will the project handle these long lead times regarding the completion date? | Any delay will be handled according to standard spec 108. A future addendum will modify the language in Article 19 of the special provisions. Note: Construction Oversight has made the following comment after multiple inquiries on this topic. The department is not considering this as an industry-wide shortage and contractors should bid the contracts accordingly. Liquidated damages will be assessed and any efforts to mitigate the liquidated damages will be the responsibility of the contractor. | Mike Coleman | 1 | 2019-02-22 12:38 | 2019-02-28 19:07
20190312 | 20190312040 | 40 | Sanitary Sewer 8 inch | C.2 Sanitary Sewer Mainline Testing--- Lists low pressure Air Test as a required test to be performed. With this being a relay section with potential active laterals and mainline flows. Is this test going to be required? Air tests are generally waived in relay situations because of these issues, trying to understand if we need to include costs to make these accommodations. | Low pressure air testing will not be required for this project. A future addendum will remove the low pressure air testing language. | Mike Coleman | 2 | 2019-02-22 13:57 | 2019-02-28 19:10
20190312 | 20190312040 | 40 | HMA Pavement | The project specifies a 4 LT 58-28 S and a 3 MT 58-28 S. Was the intent to have a different mix on the lower layer or was this a mistake? Can the designer clarify if an LT or MT mix is required. | The MT mix will be required. An addendum will remove the LT mix and replace with the MT mix. | Fred Schunke | 3 | 2019-02-26 07:52 | 2019-03-04 12:59
20190312 | 20190312040 | 40 | Item #44 Base Patching | Item #44 Base Patching references the 315 spec which specs a 25mm asphalt mix. These patches appear to be a permanent surface so would the department consider changing the item to an Asphaltic Surface or allow a 12.5mm asphalt mix to be used? | A 12.5mm asphalt mix will be allowed. | Fred Schunke | 4 | 2019-02-26 08:02 | 2019-03-04 13:02
20190312 | 20190312040 | 40 | CIPP related questions | 1. Are TV reports or videos available on the pipe segments for CIPP? 2. What proximity to the job location will water be available? 3. What are the working hours? 4. What is the pipe compostion of the pipe segments to be lined? 5. What is the CIPP warranty? | 1. Videos are available from the City of Sheboygan. To request copies, contact either Kevin Jump by email at Kevin.Jump@sheboyganwi.gov or Ryan Sazama by email at Ryan.Sazama@sheboyganwi.gov. 2. Hydrants are located throughout the City. The contractor should coordinate with the Sheboygan Water Utility about hook up and billing. Contact information is provided in the plans and special provisions. 3. Please refer to the Standard Specifications section 107.8(6). 4. The pipe composition varies throughout the project. Pipes are concrete, corrugated concrete, PVC, and vitrified clay. Videos can be made available (see #1 above). 5. Please refer to the following sections in the Standard Specifications: 105.11.2.3(2) and 106.5(2). | Fred Schunke | 5 | 2019-03-03 20:36 | 2019-03-05 14:54
20190312 | 20190312040 | 40 | Work by Railroad | Does the DOT know how long the work by the Railroad will take to perform? And does the DOT know if the Railroad will be putting rail traffic back on the track at the completion of their rail work? Or is the rail going to be out of service for the full 6 week period? Questions are all related to figuring out Railroad Flagging costs. | Contact the UP Railroad representative listed in the special provisions for information regarding the UPâ€™s schedule. | Fred Schunke | 6 | 2019-03-05 16:54 | 2019-03-07 10:11
20190312 | 20190312040 | 40 | phase 5 earthwork qty | I think you'll need qty in phase 5, probably common excavation and borrow to remove temp asphalt/gravel and construct the medians. No qty is shown in the earthwork table for phase 5 |  |  | 7 | 2019-03-08 08:11
20190312 | 20190312041 | 41 | SPV.0165.50 - Fiber Wrap Reinforcing Non-Structural | The plans currently do not show the length of the wrap length. Please provide the desired wrap length so that we can perform a proper takeoff. The Estimated Quantities table shows 130 SF for this item. If we back out the wrap length from this total, we get a length of approximately 12" at each girder which seems very small compared to previous projects and the way the wrap length is depicted on the plans. A typical girder wrap length of 48" would produce a quantity of 494 SF vs. 130 SF shown in the Estimated Quantities table. | The Fiber Wrap Reinforcing Non-structural is not used for structural purposes, just to control the small hair line cracks. The Fiber Wrap Reinforcing Non-structural has a maximum estimated length of 9â€™-6â€ with a minimum 12â€ width for approximately 10SF per wrap location. 13 girders have been identified for the use of Fiber Wrap meaning that a total of 130 SF is needed. | Fred Schunke | 1 | 2019-03-04 11:27 | 2019-03-05 12:40
20190312 | 20190312041 | 41 | PCB Contaminated soils | The special provisions say that any PCB contaminated water that is generated during the excavation MAY be pumped into the sanitary sewer line with the approval of the local sewer utility. What happens if this approval is not granted? What is the procedure for disposing of contaminated water and who will be responsible for the costs? Do we know what level of treatment could be involved to satisfy the City Sewer department? I can see this being potentially a major issue. |  |  | 2 | 2019-03-11 11:27
20190312 | 20190312042 | 42 | Traffic Control Detour | Proposal under #4 Traffic states that you have to sign and maintain a detour route as shown in the plans. There is not a detour route in the plans. | The #5 Traffic article in Proposal 042 states: Grosse Road shall be closed to through traffic during construction. A signed detour route will not be provided. Property access will not be interrupted. Any additional travel time is expected to be minimal. | Mike Coleman | 1 | 2019-02-28 09:14 | 2019-02-28 19:04
20190312 | 20190312042 | 42 | Bridge Approaches | The Plan shows the bridge approach slab coming back 34â€™ from the bridge deck, is the intent a 15â€™( short side) approach panel off of the abutment and the balance of the slab , 12â€ non reinforced concrete or reinforced approach slab? | SDD 13 B 2-8a, detail for skews >20 degrees, in the plan set should be utilized to determine reinforcement in the concrete pavement approach slab. | Fred Schunke | 2 | 2019-03-04 12:24 | 2019-03-04 12:24
20190312 | 20190312044 | 44 | Bridge 63-17 | On sheet 66 in the elevation view there is a note stating "PLACE GROUT MATS, GROUT BAGS, AND SCOUR REPAIR GROUT (BOTH PIERS) SEE DETAILS." There are no mats shown on the details. Are grout mats requires? Also, on sheet 67 in the estimated quantities table under bid item SPV.0035.02 SCOUR REPAIR GROUT BAGS there are 44 CY's listed. The only grout bags shown on the details are for the anchorage of the vinyl sheet piling which should be covered under bid item SPV.0060.01 PEREPARATION AND ANCHORAGE FOR VINYL SHEET PILING. "Payment is full compensation for preparing and leveling the ground surface under the piers and for furnishing and installing grout bags." Are additional grout bags required? | Question 1 â€“ Page 66 â€“ Regarding the Grout Mats. There are no grout mats required on the project. This note should be modified to remove the grout mat reference. Question 2 â€“ Page 67 = The quantities table refers to 44 CY of Scour Repair Grout Bags. SPV.0060.01 - PEREPARATION AND ANCHORAGE FOR VINYL SHEET PILING refers to grout bags to secure the plastic piling is incidental to the piling item. This note at the end of Payment should be modified to read the Grout Bags are paid for under separate bid item. Plan changes were made in a recent addenda. | Fred Schunke | 1 | 2019-02-28 16:18 | 2019-03-07 10:27
20190312 | 20190312044 | 44 | Existing Pavement - North end B-43-41, Minocqua | The existing pavement at the north end of the B-43-41 structure (USH 51) in Minocqua is concrete pavement. The concrete pavement on USH 51, north of the bridge, is expected to be repaired under project 1170-19-60 from the January 2019 letting. The plan shows an area of "Removing Asphaltic Surface Butt Joints" in order to pave Asphaltic Surface at 2-inches thick, in the area where concrete pavement currently exists. What is the intent of the "Removing Asphaltic Surface Butt Joints" item, specifically where there is concrete pavement? | Addendum 1 will remove the Removing Asphaltic Surface Butt Joints item and make the plans more clear. | Fred Schunke | 2 | 2019-03-01 14:58 | 2019-03-05 10:48
20190312 | 20190312044 | 44 | Underwater Concrete Surface Repairs | Are alternate methods of placement allowable as long as the performance criteria is met? | Contractor should bid the project as shown in the plans and discuss alternate methods after award. | Fred Schunke | 3 | 2019-03-05 08:51 | 2019-03-05 15:01
20190312 | 20190312045 | 45 | Stage 1 Milling Limits | The typical section on Sheet 8 of the plans shows that in Stage 1, both 12-ft lanes of W. Kemp Street are intended to be milled to a 2" depth from Station 909+75WB to 932+41WB (Bridge Deck); in summary a total of 24-ft wide by 2,266-ft in length. The miscellaneous quantities sheets shows the same station range, and identifies a plan quantity only 4,300 SY of "removing asphaltic surface milling" for this area. Within this station range there is an intersection with Sutliff Ave, multiple widened areas for turn lanes, and a merging section where the divided EB & WB lanes converge into a counter-directional 2-lane roadway (immediately west of the Wisconsin River bridge). Can a plan detail be provided to show the intended limits for the milling and paving work in this area, specifically from the referenced bridge to the west, through the Sutliff Ave intersection, and widened turn lanes? | A plan detail showing the milling limits and revised quantities for â€œremoving asphaltic pavement millingâ€ will be included in Addendum #2. | Fred Schunke | 1 | 2019-03-01 15:33 | 2019-03-05 14:59
20190312 | 20190312045 | 45 | IRI Ride for mill and overlay section | The section of USH 8 (Kemp St) WB that will be milled and overlayed exceeds 1,500 LF, if the station range provided by the typical section is accurate. Will IRI Ride be required for this section of pavement? If so, can the incentive item be added to the contract? | IRI Ride incentive is not required for this project. Kemp Street is a local road that is being resurfaced as part of the detour route. It is not the mainline for the project or the mainline for a county, state or U.S. highway crossroad that is being reconstructed under this contract. | Fred Schunke | 2 | 2019-03-04 13:18 | 2019-03-06 13:56
20190312 | 20190312046 | 46 | Pier Construction | The B-58-132 structure plans do not include at cofferdam and the erosion control plan does not include turbidity barrier around the pier. Please clarify if pier construction will require any turbidity control measures. | Since the water depth from the Q2 Elevation to the bottom of Pier Elevation is greater than 5 feet, a cofferdam and seal will need to be added to the bridge plans. An addendum will be required for the structure plan and special provisions. | Fred Schunke | 1 | 2019-02-27 06:00 | 2019-03-04 11:37
20190312 | 20190312046 | 46 | IRI Ride | Based on stationing, the job appears to be 1500-feet in length, but with a bridge reconstructed within the project limits. Per specifications, will IRI Ride be needed due to the project length? If so, can the item for IRI Ride Incentive be added to the job? | IRI Ride will not be required for this project. Per FDM: 2.2.1 Payment for Incentive IRI Ride; Item 740.0440 Include the Incentive IRI Ride bid item on projects with greater than 1,500 feet of continuous concrete or asphalt pavement. 1.) The total project length is 1500â€™, which is not greater than 1500â€™. 2.) With the structure being located approximately 2/3rds into the project, there is not 1500â€™ feet of continuous concrete or asphalt pavement. | Fred Schunke | 2 | 2019-03-01 15:05 | 2019-03-05 15:03
20190312 | 20190312046 | 46 | Contract Time | An addendum was issued and a cofferdam and seal were added to the bridge plans. The contract time should be extended to allow for installation/removal of cofferdam, pouring the seal and the three days of cure time required after pouring the seal prior to dewatering the cofferdam. A minimum of six days should be added. Will the contract time be extended? | An addendum for adding additional time is not warranted. The contractor knows the schedule and tasks to be completed. The six days stated below assumes that nothing else can or is happening onsite at the time. The current contract time allows for adequate to complete the cofferdam, seal and misc. work. Common practice would be to let cure over the weekend. | Fred Schunke | 3 | 2019-03-06 10:49 | 2019-03-07 09:50
20190312 | 20190312047 | 47 | Pavement Marking Quantities | Good afternoon. Plan sheet 5 shows center line skips throughout the project and plan sheet 9 has enough quantity for double yellow centerline throughout the project, which is correct and, if it is indeed skips, will you issue an addendum to correct the bid item? Thank you. | The quantity is correct, it will be a double yellow throughout the project. | Mike Coleman | 1 | 2019-02-25 13:45 | 2019-02-28 18:59
20190312 | 20190312047 | 47 | Asphalt Section | On sheet 2 of the plans, it is stated "3-inch pavement to be placed in two 1.5-inch layers". Per the spec, this would require the two lifts to be 9.5mm asphalt. Would one 3-inch lift of 12.5mm be acceptable? | No, it will not. | Mike Coleman | 2 | 2019-02-27 14:27 | 2019-02-28 18:57
20190312 | 20190312048 | 48 | Bid Item Clarification | Can you provide clarification of bid item 213.0100 Finishing Roadway (project) 01. 6620-01-60? |  |  | 1 | 2019-03-04 08:25
20190312 | 20190312048 | 48 | Underwater Concrete Surface Repairs | Are alternate methods of placement allowable as long as the performance criteria is met? | Contractor should bid the project as shown in the plans and discuss alternate methods after award of contract. | Fred Schunke | 2 | 2019-03-05 08:50 | 2019-03-05 15:00
20190312 | 20190312050 | 50 | Rock Excavation | Iâ€™m inquiring about the rock excavation bid items #0126 and #0340. . I would propose that they be changed from CY to LF, based on only 1 boring indicating rock. I would also like to know if there is additional information available that prompted the note on plan page 53 indicating utility trench rock anticipated from station 34+00 to station 39+00. | The note was added based on the elevation of rock from one boring that was then projected parallel along the roadway profile. We anticipate there is rock along this hill. Based on use of this item with a CY measurement on past City utility projects (this was adapted from City utility specs), the City is comfortable with the quantities as shown in the plans/contract and as measured at CY. We feel the CY measurement allows for best addressing any fluctuation in actual quantities in the field. We are not proposing any changes at this time. Both of the items mentioned are to be measured according to Standard Specification 608.4.2, which should help to simplify the measurement. | Mike Coleman | 1 | 2019-02-22 07:24 | 2019-02-22 07:25
20190312 | 20190312050 | 50 | Railroad Crossing | By the looks of it, the steel casing for the proposed sanitary sewer is shown to be jacked and bored through the existing sanitary pipe and manhole. Is that the intention? If so, I would ask that you reconsider the design and offset the proposed sanitary away from the existing line so that the new pipe is not bored through any existing structures. Your consideration is appreciated. | The manholes are shown to be removed, so this would need to happen prior to the boring. The existing pipe is old clay tile and can be bored through. The proposed sanitary line will remain in the same location as the existing pipe. Note, the special provisions address the possible need for sanitary pumping when this work is ongoing through the RR. | Fred Schunke | 2 | 2019-03-07 14:13 | 2019-03-08 10:00
20190312 | 20190312050 | 50 | Are there soil boring logs available? |  | They are available at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312050/ | Fred Schunke | 3 | 2019-03-08 12:36 | 2019-03-08 14:36
20190312 | 20190312050 | 50 | Soil Borings | Is it possible to review the actual soil boring information for this project? | They are available at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190312050/ | Fred Schunke | 4 | 2019-03-08 14:14 | 2019-03-08 14:36
20190312 | 20190312050 | 50 | Railroad Jack and Bore Followup | Following up on Q&A #2: Just so I am sure I am understanding correctly, you expect us to bore through the 15" pipe having a grade 1.07% with a new pipe at 0.30%? Downhill, under the railroad tracks, in sand, all while hitting a 3" window (0.30% in 86')? It would be one thing to follow the existing line AND grade, but to try to put it in at a new grade, boring through the bottom half of an existing pipe with the pipe sloping down faster than the bore is proposed to do. I ask again to reconsider offsetting the alignment of the sanitary sewer from the existing line, at least for the portion to be bored and jacked beneath the track. |  |  | 5 | 2019-03-08 16:56
20190312 | 20190312055 | 55 | Temporary pavement marking paint quantities | In looking at the miscellaneous quantities for the temporary pavement marking paint, it appears you have quantities on the surface layer both for the entire upper lift as well as another application for the center line rumble strips. It would appear that you only need the 51,420 linear feet of markings to match the actual center line quantities under the marking line 4" item. In addition, the markings on the surface layer should be temporary or same day epoxy rather than temporary marking paint. Will an addendum be issued to 1. correct the quantities and 2. to change the temporary markings on the surface layer from paint to epoxy? Thank you. | An addendum will be issued for this project to correct the quantity and to change the temporary markings on the surface layer from paint to epoxy. | Mike Coleman | 1 | 2019-02-27 09:00 | 2019-02-28 18:56
20190312 | 20190312055 | 55 | Barrier System Grading Shaping Finishing | Are there any cross sections available for the Barrier System Grading Shaping Finishing item? | No cross sections were developed for the beam guard replacement areas. | Fred Schunke | 2 | 2019-03-01 13:17 | 2019-03-04 12:58
20190312 | 20190312058 | 58 | Barrier System - Grade/Shape/Finish | Is the borrow being paid separately as shown in the plans? Also, are there any quantities for seed, fertilizer, and mulch? | Changes are being made in an upcoming addenda to address these concerns. | Fred Schunke | 1 | 2019-02-28 13:34 | 2019-03-05 12:32
20190312 | 20190312058 | 58 | Erosion Mat - Barrier Terminals | The addenda specifies that erosion mat is incidental to the item however mulch is specified in the materials. What is needed for the restoration and if erosion mat is required, which Class and Type is needed? | Erosion mat Class 1 Type B is required per the â€œinformational purposes onlyâ€ table in the addenda. | Fred Schunke | 2 | 2019-03-08 07:07 | 2019-03-08 11:35
20190312 | 20190312059 | 59 | Staking Supplemental Control | The bid lists Staking Supplemental Control. What is the intent behind this item? Will this item be eliminated? | The Staking Supplemental Control is included in the proposal because it is a required item to be included in all projects. The item will not be removed. Please bid accordingly. If you have further questions in regards to projects in the letting, please go through the Bid Express Questions/Answers process. You can find the instruction on the HCCI site at the following location: https://wisconsindot.gov/hccidocs/qa/bid-express-qa-user-guide.pdf | Mike Coleman | 1 | 2019-02-27 07:37 | 2019-02-27 07:41
20190312 | 20190312060 | 60 | Milling & Paving | Special provisions are calling for the milled surface to be paved the same day and surface to be completed within 7 days of paving the lower layer. The cost of milling increases when the milling machine is tied to the asphalt paving operation as milling can occur in inclement weather and if the milling contractor's risk is increased the more equipment is involved. Would the department consider having the milled surface paved within 7 days of milling or something similar so that the milling operation is not tied to the paving operation? What is the reason to require the upper layer to be paved within 7 days of paving the lower layer? There are 10-12 days of milling the job. To satisfy this requirement the milling contractor will have to mobilize off the job and then return. Once the lower layer is paved, what is the concern? | There will be no change made to the same day paving requirement. The requirement that the surface paving begin within 7 days of paving the lower layer will be extended to 14 days with the expectation that the surface will follow right after the lower layer. An addenda will be issued. | Mike Coleman | 1 | 2019-02-21 14:30 | 2019-02-25 11:42
20190312 | 20190312060 | 60 | PWL Density | From the table in the misc quantities it appears the department has intentions to have PWL Density on the 12' driving lane for the leveling layer. I believe the layer beneath the surface was labeled a "leveling layer" because there are the potential for differing thicknesses. In the existing typical sections there is a section of mainline with only 3" of pavement after milling 2.25" there will only be 0.75" of pavement remaining. This brings up two concerns. One the potential for gravel areas or existing pavement to be damaged by the cleanup and trucking operation. Second the remaining existing pavement will be different thickness thus affecting the results of the nuke density gauge. Therefore we feel the lower layer should not have density requirements. | PWL Density will be removed from the lower leveling layer and acceptance will be by ordinary compaction. An addendum will be issued. | Mike Coleman | 2 | 2019-02-27 14:23 | 2019-03-01 06:17
20190312 | 20190312060 | 60 | Reheating Longitudinal Joints | Special Provisions item 20 section D. ...acceptably completed, as measured along each joint for each layer of asphalt placed. Is the department looking to utilize this item on the leveling layer as well as the upper layer? | 460.4110.S Reheating HMA Pavement Longitudinal Joints: Yes this item will apply to the leveling layer as well as the upper layer. Quantity will be increased to include both layers. An addendum will be issued. | Mike Coleman | 3 | 2019-02-27 14:25 | 2019-03-01 06:19
20190312 | 20190312060 | 60 | Migratory Birds - Clearing and Grubbing | Is it the intent that all of the clearing would need to be performed either prior to May 1st or after August 30th or what would define a tree or shrub that is likely to support an active nest? Would a conditional start be given for clearing operations to be performed under temporary traffic control prior to May 1st without Working Days being charged? | Clearing shall be performed prior to May 1st or after August 30th. All work shall be completed within 65 working days as stated in the Contract Proposal. | Fred Schunke | 4 | 2019-02-28 09:20 | 2019-03-04 11:05
20190312 | 20190312060 | 60 | Pipe Grates and Endwalls | Is there any information regarding the type of pipe the endwalls are for (CMP or RCP) and the size of pipe for the grate at 110+31? Any info for size of pipe for the culvert cleanings? Very difficult to locate any pipe on site. | All pipes are CMP. The information below will be added to the pipe table on the miscellaneous quantities sheet. An addendum will be issued. Thank you. CULVERT PIPES STATION Existing Pipe Size (Inches) Existing Pipe Type 101+36 42" CMP 110+31 48" CMP 126+13 60" CMP 126+25 60" CMP 142+16 48" CMP 199+73 36" CMP 219+67 60" CMP 225+47 30" CMP 266+63 24" CMP 274+26 24" CMP 292+57 30" CMP 323+75 72" CMP 335+35 36" CMP 347+41 30" CMP 358+72 30" CMP 365+00 18" CMP 397+41 30" CMP 397+80 18" CMP 398+00 - 399+00 n/a n/a 409+36 24" CMP 419+33 48" CMP 423+32 24" CMP 429+15 18" CMP 433+07 18" CMP 435+41 24" CMP 439+62 24" CMP 453+34 48" CMP 466+92 30" CMP 484+83 30" CMP 486+79 48" CMP 494+79 30" CMP 498+61 30" CMP 504+95 30" CMP 508+97 72" CMP 509+11 72" CMP 513+57 30" CMP 518+66 30" CMP 548+64 24" CMP 558+96 24" CMP 564+01 24" CMP 578+17 30" CMP 586+51 30" CMP 590+86 30" CMP 599+12 30" CMP 626+14 30" CMP 645+11 30" CMP 659+72 30" CMP 670+70 30" CMP 681-99 24" CMP 687+38 24" CMP 693+30 24" CMP 700+76 72" CMP 721+14 120" CMP 750+14 36" CMP 753+90 36" CMP 785+28 30" CMP 792+88 84" CMP 811+54 30" CMP 816+98 72" CMP 840+92 24" CMP 855+89 36" CMP 865+96 48" CMP 891+86 36" CMP cmp = corrugated metal pipe All pipe sizes and type should be field verified | Fred Schunke | 5 | 2019-03-01 11:26 | 2019-03-05 12:45
20190312 | 20190312060 | 60 | Temporary pavement marking quantities | with the expectation that the lower layer will be installed the same day as the milling takes place (except in Diamond Bluff), the temporary paint quantities should be close to or the same as the same day epoxy quantities, can you provide more information on how you came up with the quantities for the temporary paint? Thank you. | Plan quantity for 649.0105 Temporary Marking Line Paint 4-inch is double the amount needed due to same day paving. An addendum will be issued. | Fred Schunke | 6 | 2019-03-04 10:27 | 2019-03-05 12:44
20190312 | 20190312061 | 61 | CIR | Existing typical sections show 5" of asphalt pavement. Finished typical section show 2" removing asphaltic surface milling and 4" CIR. Is it the Department's intent to incorporate 1" of CABC into the CIR process? | Ground Penetrating Radar was performed prior to the design. There are locations that have greater than 5â€ of asphalt. CIR should be adjusted in the field if we run into base. | Mike Coleman | 1 | 2019-02-27 09:19 | 2019-02-28 09:51
20190312 | 20190312061 | 61 | Prosecution and Progress | Paving operation is required to begin within 72 hours of the start of the milling operation. The CIR process has to occur between the milling and paving. CIR is required to reach a moisture content of 2.5% prior to paving. It doesn't seem possible to complete all these operations in this time frame. Can you please clarify the intent of this special provision. | An addendum will be issued to solve this matter. | Mike Coleman | 2 | 2019-02-27 09:39 | 2019-02-28 19:14
20190312 | 20190312061 | 61 | Typical Finished Section | Typical Finished Section shows widening the road 3', placing 4" millings prior to the CIR. There are several areas that have a paved shoulder already. The typical finished section does not differentiate these areas. Can you please confirm the intent for the areas that have an existing paved shoulder. | Corrections have been made to cross-sections to reflect field conditions. The typicals will be part of an upcoming addendum. | Mike Coleman | 3 | 2019-02-27 09:42 | 2019-02-28 19:12
20190312 | 20190312061 | 61 | Salvaged Asphaltic Pavement Milling / Salvaged Asphaltic Pavement Base | These quantities appear to be overstated. According to the typical section the salvaged asphaltic pavement base course is required in the 3' widening and it shall be 4" thick. Can you confirm the quantity of these items. | The Salvaged Asphaltic Pavement Base, Item SPV.0195.02 Payment for Salvaged Asphaltic Pavement Base is full compensation for processing to size; for preparing the foundation; and for placing, compacting, shaping, and maintaining the base. The Salvaged Asphaltic Pavement Milling, Item SPV.0195.03 Payment for Salvaged Asphaltic Pavement Milling is full compensation for partial-depth salvaging, and for hauling and stockpiling the salvaged material. The quantities are overstated, because under the â€œSalvaged Asphaltic Pavement Millingâ€ this will cover the hauling and stockpiling. The â€œSalvaged Asphaltic Pavement Baseâ€ Item does not cover hauling and stocking piling. | Mike Coleman | 4 | 2019-02-27 09:45 | 2019-02-28 19:03
20190312 | 20190312061 | 61 | CIR | 1. sheet 32 left hand side shows detail for side road butt joints. The cold in-place recycling is shown to extend to the limits of construction at each intersection. Is this truly the intent? or should the CIR be shown to stop 15' off centerline? most projects only do CIR on the through lane and paved shoulder (15' wide in this case). Performing CIR back to the limits of construction on each intersection will be very time consuming and expensive. | The CIR should be shown to stop 15â€™ off the centerline. This will be corrected in an upcoming addendum. | Mike Coleman | 5 | 2019-02-27 14:28 | 2019-02-28 19:01
20190312 | 20190312061 | 61 | 3/4" Dense | There is not a 3/4" Dense Base Course item. We realize the widening of the shoulder will create some material, however often times there is a need to add some tonnage to make the shoulder slopes and make the shoulders look good. | There is no ¾â€ Dense Base Course Bid Item # on the job, because the current existing shoulders are wider than normal. | Mike Coleman | 6 | 2019-02-28 14:03 | 2019-03-01 06:20
20190312 | 20190312061 | 61 | Pavement Markings | With the note included on page 3 of 24 stating "replace all centerline marking removed by mill or pavement overlay prior to reopening the closed lanes to traffic and the fact that STH 40 has to be reopened to 2 way traffic during non-working hours, it appears that there should be bid items for temporary paint (milled surface and CIR) and Same Day Epoxy (upper layer). Will you be adding those per addendum or how should those be handled during the bid process? Thank you. | The Temporary Pavement Marking will added to the addendum. | Fred Schunke | 7 | 2019-03-04 14:56 | 2019-03-05 14:57
20190312 | 20190312061 | 61 | Shaping Shoulders / Prep of Foundation for Asphalt Shoulders | The proposal has bid items for Shaping Shoulders and Prep of Foundation for Asphalt Shoulders. Two questions. 1.) It appears the special provisions for the shaping shoulders item defines the work that should be done under the Prep of Foundation for Asphalt Shoulders item. 2.) Under the verbiage of the special provisions when it calls out "furnish supplemental base aggregate dense 3/4-inch as required to create a level foundation". There is no 3/4-inch dense item, is the contractor supposed to include the pricing for this material in the item? | Article 9 will be removed from the addendum. No additional Base Aggregate Dense ¾ - Inch is anticipated. | Fred Schunke | 8 | 2019-03-04 17:20 | 2019-03-05 14:57
20190312 | 20190312062 | 62 | Line Item 154 Temp Paint | The miscellaneous quantities to the bid item quantity do not add up. The marking line removal has issues also that do not add up. | the quantity on Line Item 0154 isnâ€™t correct. It should match the plan at 5534 LF. Regarding the marking line removal, Line 0146 isnâ€™t correct â€“ it should match the plan at 16,083 LF. Not sure how, it looks like some items got double entered in AASHTOWARE as a different bid item. Line Item 0010, 0158, 0162, 0166 should be deleted. An addendum will be issued to correct. | Mike Coleman | 1 | 2019-02-27 15:26 | 2019-02-28 09:38
20190312 | 20190312063 | 63 | Breaker Run for Foundation Stone | If Breaker run is required to support the pipe. Will the material be paid for as a change order? | Breaker Run was not anticipated, but if it would be needed, a change order would need to be submitted. | Fred Schunke | 1 | 2019-03-07 08:51 | 2019-03-07 10:30
20190312 | 20190312064 | 64 | Changes? | What has changed from the original (proposal 16) project bid in the December 2018 letting to this project? | The amount of work has changed; the limits of work go from Maritime Dr to 14th Street Vs December Let had limits of Maritime Dr to CTH R; also MPU is going to supply the watermain material for the project; and a fourth leg to the roundabout has been added. | Mike Coleman | 1 | 2019-02-21 06:57 | 2019-02-21 06:58
20190312 | 20190312064 | 64 | Sanitary Manholes 4 ft | Under C. Construction It says " Excavate a minimum area of 5 feet from the outside walls of the manhole structure" This requirement would require a 15' wide excavation. Seems to be a rather large excavation? Is this really what is wanted? | The minimum width for excavation will be updated in an upcoming addendum. | Mike Coleman | 2 | 2019-02-22 13:28 | 2019-02-28 06:36
20190312 | 20190312064 | 64 | Schedule | What assumptions for crews were used in the development of the schedule for the project? | It was assumed that multiple crews would be working at the same time to expedite the work to complete schedule as laid out. | Mike Coleman | 3 | 2019-02-28 19:16 | 2019-02-28 19:17
20190312 | 20190312064 | 64 | Light Pole and Signal Delays | Will extra time be given to contractor for the installation of light poles and signals due to long lead times in getting materials? | The department is not considering this as an industry-wide shortage and contractors should bid the contracts accordingly. Liquidated damages will be assessed and any efforts to mitigate the liquidated damages will be the responsibility of the contractor. The contractor should engage a supplier that can meet the schedule of the contract. | Fred Schunke | 4 | 2019-03-05 11:26 | 2019-03-05 11:45