## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190514 | 20190514051 | 51 | Picking up and Installing State furnished Decorative Fencing | This project contains a bid item for picking up and installing state-furnished decorative fencing. Would be OK stop by the facility and take a look at the fencing, to better help prepare our bid? | The department furnished decorative fence and components are located at 935 S. 60th St., West Allis WI 53214-3362 Contact Mitzi Dobersek at (414) 266-1150 or (262) 875-1252 to coordinate viewing the fencing. | Mike Coleman | 1 | 2019-04-17 06:46 | 2019-04-17 06:49
20190514 | 20190514051 | 51 | Project Schedule | 1. Can the design schedule be provided for this project? 2. The completion date for this project is challenging, would the Department consider extending this deadline to be completed during this construction season? | 1. The design schedules can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190514051/ 2. The project time for completion cannot be extended based on coordination with the DNR. It must be open by mid-September. | Mike Coleman | 3 | 2019-04-29 10:02 | 2019-04-30 06:32
20190514 | 20190514051 | 51 | Lighting Pull Boxes | There are 6 pull boxes in Lighting Plan but not listed in proposal line. Are these quantities missing? | The plan and quantities will be updated in an upcoming addenda. | Fred Schunke | 4 | 2019-05-07 09:16 | 2019-05-07 09:18
20190514 | 20190514051 | 51 | Pedestrian Signs for RRFB Systems | Are the Pedestrian signs for the RRFB Systems (Line Items 0360, 0362, 0364, 0366, 0368, 0370, 0372)supposed to be included in these line items, or are they part of a separate bid/line item? The proposal spec they should be shall be supplied and installed under a separate bid item, but the Detailed Drawing of the RRFB system on the Plans states that they should be included in these line items. Also, what about the Poles/Bases/Anchor Bolts for these RRFB systems? | The pedestrian static signs are paid for under the miscellaneous quantities table for permanent signs attached. So, they are a separate bid item (637.2230) The poles, bases, bolts, solar, etc. are all part of the RRFB bid item as noted in the spec. Turnkey operation. Everything but the static warning signs. The RRFB drawing doesnâ€™t say that the sign is part of the RRFB, so not sure why that is being questioned. The RRFB drawing simply has to show the sign to make it clear that there is a sign. On the last page of the RRFB spec it says under â€œD Measurementâ€ that it is an RRFB system as a lump sum. On the second page of the spec it clearly says the sign is a separate bid item and the permanent signing miscellaneous quantities clearly show the sign numberâ€™s and pay item. | Fred Schunke | 5 | 2019-05-07 12:38 | 2019-05-09 14:26
20190514 | 20190514051 | 51 | Plan Holders List | Will a plan holders list be provided? | Plan Holders Lists is provided on the HCCI Site for all proposals, each letting. Here is the link for HCCI Page of the May 14, 2019: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2019/20190514.aspx The Plan Holders List for the May 14, 2019 Letting is found at the following location: https://wisconsindot.gov/hccidocs/bid-let/2019/20190514/planholders.pdf | Fred Schunke | 6 | 2019-05-10 08:06 | 2019-05-10 09:22