## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190709 | 20190709001 | 1 | Design Files | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709001/ Please note: The design schedule will be provided next week. The design schedule has been uploaded. | Mike Coleman | 1 | 2019-06-04 18:32 | 2019-06-06 14:40
20190709 | 20190709001 | 1 | Design Files | Can the Department provide the Contractor Data Packet as specified in Article 16 of the Special Provisions? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709001/ Please note: The design schedule will be provided next week. The design schedule has been uploaded. | Mike Coleman | 2 | 2019-06-05 08:01 | 2019-06-06 14:40
20190709 | 20190709001 | 1 | Plan Sheet 2272 Earthwork Data | Stage 2A Phase 2 - 'X2a-2' I believe that the department have inadvertently left out some of the earthwork data. stationing starts at 159+00 with a mass ordinate of -8603 CY. Please review and clarify. Thank you. | An addenda will be issued to revised sheet 2271 of the plan. | Jill Fehrman | 3 | 2019-06-06 14:33 | 2019-06-07 09:09
20190709 | 20190709001 | 1 | expanded polystyrene ASTM type and quantity | There are numerous locations on the plans calling out â€˜expanded polystyreneâ€™, is there a specification we can reference somewhere calling out the specific ASTM type of expanded polystyrene, and also the quantity requirement. | The department does not have specs for the expanded polystyrene at the top of the MSE wall/coping interface. If it is expanded polystyrene, it is acceptable. | Mike Coleman | 4 | 2019-06-13 07:55 | 2019-06-18 11:06
20190709 | 20190709001 | 1 | Contractor Data Packet as specified in Article 16 of the Special Provisions | All the information in Article 16 of the Special Provisions was not provided in the response/answer link on question #1 and #2. There are no surfaces, XML. Please provide these surfaces and the remaining information in Article 16. | The Contractor Data Packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709001/ | Mike Coleman | 5 | 2019-06-18 10:38 | 2019-06-26 08:41
20190709 | 20190709001 | 1 | Pre-boring quantity at B-53-306 pier 3 | Note on sheet 2042 states that piles are to be placed in pre-bored holes cored 3 feet into rock, no driving required. (total of 174 LF of pre-boring) However this pier also has an estimated piling length of 20' for a total of 1,160 LF. Is it assumed pre-boring will go 15-20' before hitting competent rock? It appears from the boring at pier 3 rock is a few feet below bottom of footing. | Although there is rock just below the footing at pier 3, it is moderately to highly weathered and only had a blow count of 9 at about five feet below the footing. For design, the top of competent rock is considered to be at auger refusal. That being said, the pre-boring items are measured from the bottom of footing to the end of the pre-bored hole (3 feet below competent rock). For B-53-306, Pier 3, that distance is estimated to be 17 feet. Since there are 58 piles at pier 3, the pre-boring quantity should be 58 x 17 LF = 986 LF. The Pre-boring Rock or Consolidated Materials quantity will be updated with an addendum. | Mike Coleman | 6 | 2019-06-25 16:37 | 2019-06-27 11:46
20190709 | 20190709001 | 1 | Chain Link Fence | The fencing plan is only showing 3,745' of the 15,975' the chain link fence, while there is a lot of Woven wire fence in the same area. Can you clarify where the chain link fence is to be installed? | Location of fence type and fence quantities will be clarified in Addendum 2. | Mike Coleman | 7 | 2019-06-26 09:57 | 2019-07-02 09:02
20190709 | 20190709001 | 1 | Addendum 1 - Line item 0568 - 632.9101 - Landscape Planting Surveillance and care cycles | Addendum 1 for this item indicates a reduction on quantity from 26 each to 13 each but both the schedule of items in the proposal and on Bid Express are still at 26 each. Which is the correct quantity to use for bidding? | That is correct. The item is going from 26 care cycles to 13 care cycles. This will be corrected in an upcoming addendum. | Mike Coleman | 8 | 2019-06-27 09:47 | 2019-06-27 10:26
20190709 | 20190709001 | 1 | Stay in place forms | Re; Stay in place form clips. On page 1940 of the plans specifically B-53-304. Are the galvanized clip angles or the galvanized metal form supports in detail A required to be painted? On page 2070 of the plans specifically B-53-306. Are the galvanized clip angles or the galvanized metal form supports in detail A required to be painted? | Painting is not required on galvanized clip angles and galvanized metal form supports. | Jill Fehrman | 9 | 2019-06-28 07:25 | 2019-07-01 15:25
20190709 | 20190709001 | 1 | Line Item 0434 Crash Cushion Permanent | The plan calls for 11 permanent crash cushions wide from 4 feet to 8 feet in widths. Per the WISDOT all cushions bid after the December 2018 letting need to be MASH compliant. None of the approved suppliers for wide crash cushions have a MASH compliant unit. How are we supposed to bid this item? | Of the 11 permanent crash cushions, 8 locations are protecting the end of concrete barrier type S42. These locations should use MASH compliant crash cushions. The other 3 locations (202+72â€™FBâ€™, 310+61 and 311+39) will require a wider width and NCHRP-350 approved crash cushions can be used at these locations. | Mike Coleman | 10 | 2019-07-01 09:17 | 2019-07-02 10:17
20190709 | 20190709001 | 1 | FIELD OFFICE | What is the anticipated end date for use of the field office? | The field office is anticipated to be needed until June of 2022, but per the specification, the field office and laboratory shall remain available for department use until the engineer approves their closure or removal. | Mike Coleman | 11 | 2019-07-01 10:11 | 2019-07-02 12:04
20190709 | 20190709001 | 1 | Seismograph | The specification requires a seismograph to monitor vibration adjacent to buildings/structures. What buildings/structures are required to be monitored during construction activities? | The seismograph item was added due to the vibration-inducing construction activities (such as pile driving) near buildings and the need for the Department and Contractor to defend their practices. Per the specification, seismographs will need to be placed at the building/structure nearest to the construction operation for vibration-inducing construction activities or as the engineer directs. For example, if a Hormel structure is determined to be the closest structure during pile driving activities at B-53-300, then this structure will be monitored per the specification during these vibration-inducing operations. | Mike Coleman | 12 | 2019-07-01 16:46 | 2019-07-02 10:07
20190709 | 20190709001 | 1 | Contractor Data Packet as specified in Article 16 of the Special Provisions | There is no existing surface provided in the information on the FTP site, please provide it. | The existing surface files are in the contractor data packet on the ftp site. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709001/Contractor Data Packet\10031080.zip\10031080\CD-Design\CD-BaseData\ | Mike Coleman | 13 | 2019-07-02 10:41 | 2019-07-02 13:58
20190709 | 20190709001 | 1 | Flange to Web Welding | Does Wisconsin allow flange to web welding in the horizontal position, or is it flat position only? | We now require flange to web welding in the flat position. This was an intentional change in our specifications, so we would not be allowing welding in the horizontal position if it was requested. | Jill Fehrman | 14 | 2019-07-02 12:10 | 2019-07-02 12:17
20190709 | 20190709001 | 1 | Full Shop Assembly | Regarding 100% full shop assembly, which is very costly for the Department: Would the Department consider waiving full shop assembly for this project? Would the Department consider a test assembly to prove accuracy and fit opposed to 100% assembly? If a test assembly is acceptable, what would that entail for each of the structures on this project? | Would the Department consider waiving the full shop assembly for this project? Full assembly will not be required for this project. Partial assembly will be required. The fabricator will be required to use a minimum of 3 girders for each assembly, holding a girder back for subsequent assemblies. Would the Department consider a test assembly to prove accuracy and fit opposed to 100% assembly? If a test assembly is acceptable, what would that entail for each of the structures on this project? The Department will not consider a test assembly to prove accuracy and fit in lieu of partial assembly. | Jill Fehrman | 15 | 2019-07-02 12:13 | 2019-07-02 12:17
20190709 | 20190709001 | 1 | B-53-304/306 piers, threaded bar coupler construcability | The pier caps for B-53-304 and B-53-306 show a â€œTHREADED BAR COUPLERâ€ connection from the 1113 and 1114 bars for each pier cap to the 1112 bars in the pier stem. These bars are a bent â€œLâ€ bar and there is no way they would be able to be threaded into place as the plan is detailed. The first bar would be able to be installed, but after that the tail of each following bar would hit the first and could not be installed. Would another type of mechanical coupler be acceptable, or could the 1112 dowels be lengthened to extend into the cap, allowing for the couplers to be removed completely? With the current design, this rebar will be impossible to install. |  |  | 16 | 2019-07-05 09:36
20190709 | 20190709002 | 2 | Design Files | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | The CAD Files, Earthwork Excel Spreadsheet, Soils Reports, and Design Schedules are posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709002 | Jill Fehrman | 1 | 2019-06-04 18:33 | 2019-06-16 15:09
20190709 | 20190709002 | 2 | Cad Files | Can we please get a copy of the cad files for this project? Thank you. | The CAD Files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709002 | Jill Fehrman | 2 | 2019-06-12 08:21 | 2019-06-16 15:12
20190709 | 20190709002 | 2 | Contractor Data Packet as specified in Article 54 of the Special Provisions | All the information in Article 54 of the Special Provisions was not provided in the response/answer link on question #1 and #2. There are no surfaces, XML. Please provide these surfaces and the remaining information in Article 54. | The additional soils reports and contractor data packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709002/ | Mike Coleman | 3 | 2019-06-18 10:43 | 2019-06-24 07:24
20190709 | 20190709002 | 2 | Northbound right and left lane closures | Project 1007-11-80 has all traffic on the northbound side divided by temp barrier wall. The plans call out for widening in the northbound median and outside shoulder along with setting temp barrier wall. The lane closures would need to start back in the two way traffic area of the other project and there is no room to stage equipment on either side. So you would have to close the lane in order to set traffic control equipment and close the lane. With an 8 hour window performing the lane closures every night by bringing the equipment in and hauling it out the other subs are going to lose about 4 hours every night. Is the state patrol going to help support this activity? This is not a safe situation for the traveling public or the workers. | Depending upon when these work activities take place and the current 1007-11-80 traffic configuration, there may be a need to develop a single lane closure within the 1007-11-80 project limits. No state patrol assistance will be provided for these traffic control activities. | Mike Coleman | 4 | 2019-06-18 14:49 | 2019-06-24 07:27
20190709 | 20190709002 | 2 | Award Date & Construction Start Date vs Completion Dates | There are completion dates of September 12th, 2019 and November 16th, 2019 for 2 stages of work with a bid letting of July 9th, 2019. The DOT's schedule shows a construction start of August 12, 2019. If for some reason DOT doesn't award the contract fast enough or doesn't allow the contractor to start work August 12th, 2019 like the schedule shows, will the DOT extend these completion dates and include weather impacts after the original completion dates? | The Department will work with the contractor with respect to the schedule should awarding the contract be delayed. | Mike Coleman | 5 | 2019-06-21 16:43 | 2019-06-25 09:05
20190709 | 20190709002 | 2 | Department Owned Field Office | What is the end date for the contractor providing and maintaining the department owned field office? | The department owned field office shall be maintained until January 31, 2021. | Mike Coleman | 6 | 2019-06-22 08:38 | 2019-06-24 10:37
20190709 | 20190709002 | 2 | EBS Quantity | On both the -74 & -75 projects there are larger amounts of EBS called out in the earthwork summary within certain stages and work areas. For example on the -75 job under stage 1B, IH 39 SB (sta. 2410+90 - 2546+77) there is an EBS excavation quantity of 9956 CY. When you go to the cross sections or the earthwork data sheets within any area where EBS is called out (like the example stated above) there is no EBS shown in either location. Where is DOT thinking this EBS is within these areas? How was the EBS calculated within the areas? If it was calculated can it be provided in the earthwork data sheets? | The earthwork data spreadsheets located on the HCCI site provide the locations of the EBS under the EBS and Geogrid tab. As well, marked-up cross sections have been uploaded to help define the locations of EBS. These files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709002/Earthwork/ | Mike Coleman | 7 | 2019-06-22 08:58 | 2019-06-27 13:41
20190709 | 20190709002 | 2 | Stormwater Treatment Filter Strip | The sand spec that is called out for this item (as shown in the table on page 131 of the special provisions) is an extremely specialized spec and from our research will be very difficult (near impossible) to manufacture. Therefore the price will be astronomical. Can this spec be looked at to make sure it is correct or could alternatives be provided for the material that would work in place of the sand spec. | This item has been used on previous projects along the corridor without issue. | Mike Coleman | 8 | 2019-06-24 17:27 | 2019-06-26 08:41
20190709 | 20190709002 | 2 | Question on bid item 0054 Removing (item description) 001. Temporary Shoring L.I.P. By Others | 204.9165.S Quan 2975 SF See Note on sheet 54 Project plan set 1007-12-75 "Remove Temporary Shoring Left In Place By Others Approx Sta 2467+60 - Sta 2468+10 LT (Constructed during Project ID 1007-10-71 in 2014), which is again referenced on sheet 284 of the same plan set (project 1007-12-75) Misc Quantities plan section. Is this item of work referring to the same "semi permanent shoring to be removed INCLUDED IN REMOVE OLD BRIDGE" listed on the General Plan sheet of Structure B-13-728 "Starred Note" Sheet 536 plan set 100-12-75? During site visit there doesn't appear to be any existing shoring in this location. There is a smaller amount of shoring off the abutments of B-13-727. Please clarify. Incidental to removal? Pay Quantity? or nonexistent? | Yes, these are referring to the same item. Temporary shoring left in place will be removed under item 204.9165.S Removing 001. Temporary Shoring L.I.P. By Others. | Mike Coleman | 9 | 2019-06-25 14:46 | 2019-06-27 13:42
20190709 | 20190709002 | 2 | Structure Backfill Type A | What is the 1920 tons of type A backfill used for in conjunction with the concrete barrier. See misc. quantities page 299 of the -75 plan. Can a detail be provided? | Refer to SDD 14B 41-3b for structure backfill detail. | Mike Coleman | 10 | 2019-06-25 16:54 | 2019-06-27 13:43
20190709 | 20190709002 | 2 | Department Owned Field Office | Article 68 requires the contractor to provide and maintain the field office services beginning July 15, 2019. With the job being bid July 9th, there will not be an executed contract and may not even be awarded by then. Is the apparent low bidder expected to take on these costs without an executed contract? | Field office to be equipped and maintained beginning September 1, 2019. | Mike Coleman | 11 | 2019-06-28 11:38 | 2019-07-03 07:52
20190709 | 20190709002 | 2 | Earthwork Data Sheets | On the Earthwork Data Sheets pages 264 thru 267, the incremental volume (CY) add up to more than cumulative volume (CY), which total is correct? | Upon further investigation there are a few minor variations in the earthwork quantities. These minor variations will not have a significant impact on the overall earthwork quantities and amount to roughly a 3% increase to Excavation Common for project 1007-12-74 and roughly a 1% increase to Excavation Common and 3% decrease to Roadway Embankment on project 1007-12-75. The final quantities will be determined in the field as there may be variations in existing soil conditions. | Mike Coleman | 12 | 2019-07-02 13:41 | 2019-07-03 15:31
20190709 | 20190709002 | 2 | Filter Strip Depth | The depth of the filter strip sand in the locations called out is 20", correct? | The subsoiling depth is 20-inches. Subsoiling involves the mixing of sand and soil to the 20-inch depth. | Mike Coleman | 13 | 2019-07-02 17:07 | 2019-07-03 15:28
20190709 | 20190709002 | 2 | Earthwork Data Sheet | On sheet 607, it appears the Siggelkow Road Bridge in not removed from the earthwork, please verify the common excavation and fill quantity between STA 2466+00 - 2470+00? | Upon further investigation there are a few minor variations in the earthwork quantities. These minor variations will not have a significant impact on the overall earthwork quantities and amount to roughly a 3% increase to Excavation Common for project 1007-12-74 and roughly a 1% increase to Excavation Common and 3% decrease to Roadway Embankment on project 1007-12-75. The final quantities will be determined in the field as there may be variations in existing soil conditions. | Mike Coleman | 14 | 2019-07-02 20:32 | 2019-07-03 15:32
20190709 | 20190709002 | 2 | Earthwork Summary Sheet | Page 285, Stage 3A 524+64 - 533+28 TRNB Roadway excavation and fill is not in the Subtotal or Project totals, please verify. | Upon further investigation there are a few minor variations in the earthwork quantities. These minor variations will not have a significant impact on the overall earthwork quantities and amount to roughly a 3% increase to Excavation Common for project 1007-12-74 and roughly a 1% increase to Excavation Common and 3% decrease to Roadway Embankment on project 1007-12-75. The final quantities will be determined in the field as there may be variations in existing soil conditions. | Mike Coleman | 15 | 2019-07-02 21:17 | 2019-07-03 15:33
20190709 | 20190709002 | 2 | Filter Strip Sand | LIKE THE PREVIOUS QUESTION ASKED, WHAT IS THE DEPTH OF THE SAND? BEFORE IT IS SUB SOILED? | 30% sand by volume is mixed with the native soil to a depth of 20 inches. | Mike Coleman | 16 | 2019-07-05 07:56 | 2019-07-08 09:58
20190709 | 20190709004 | 4 | RE: Bid Item Obtaining and Installing Bar Steel Reinforcement | Will The department load the rebar on contractor supplied truck at the WDOT La Crosse Yard or does the contractor have to supply the loading equipment and labor? | The contractor is responsible for providing the loading equipment and labor. | Mike Coleman | 1 | 2019-06-13 16:56 | 2019-06-17 10:43
20190709 | 20190709005 | 5 | Design Files | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709005/ | Mike Coleman | 1 | 2019-06-04 18:33 | 2019-06-17 10:30
20190709 | 20190709005 | 5 | CAD Files - Existing and Proposed | We would like to request the following CAD files to assist with our planning and quantity verification processes. 1. Existing Conditions Survey Surface CAD files (with past projects completed "clipped" in) (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (with past projects completed "clipped" in) (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709005/ | Mike Coleman | 2 | 2019-06-12 08:32 | 2019-06-17 10:30
20190709 | 20190709005 | 5 | EBS Special | The special Provision SPV.0035.001 EBS Excavation C.2 states "Dipsose of all excavated materials offsite at no cost to the department". Can EBS be used as nonstructural fill outside of the structural fill 1:1 sideslope as in previous projects? Please clarify. | Contractors shall assume all EBS to be wasted offsite. | Mike Coleman | 3 | 2019-06-17 11:32 | 2019-06-19 08:31
20190709 | 20190709005 | 5 | Schedule | Can a copy of the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709005/ | Mike Coleman | 4 | 2019-06-24 19:24 | 2019-06-26 13:00
20190709 | 20190709005 | 5 | Recycling of material for crushed aggregate base. | Can existing base and asphalt be recyled on site and reused as crushed aggregate base course? | Per Section 301.2.4.2, existing base and asphalt can be recycled on site and reused, provided it is processed to meet the requirements of Section 305.2.2.2. All material stockpiles must follow the requirements of Article 31 in the project Special Provisions (Material and Equipment Staging). | Mike Coleman | 5 | 2019-06-26 05:03 | 2019-06-26 13:42
20190709 | 20190709005 | 5 | Schedule | The project schedule is unrealistic and simply doesn't provide the contractor with enough time. WisDOT needs to have realistic schedules that are far more thorough. | The contract requires expedited work schedule and may require extraordinary forces to complete the project. This has been stated in the fourth paragraph of Article 5 Prosecution and Progress. The contract time for completion takes into account multiple crews working on the project based on the expedited schedule. We believe the project can be constructed as shown on the plan within the estimated time frame and meet committed obligations and future let projects schedule. | Mike Coleman | 6 | 2019-06-30 21:46 | 2019-07-02 06:48
20190709 | 20190709005 | 5 | Cold weather heating and covering | Can items for cold weather heating and cold weather covering be added given the staging of the project and the fact stage work will be completed late in the year? |  |  | 7 | 2019-07-06 07:14
20190709 | 20190709005 | 5 | Exhibitied Contract Execution. | Will WisDOT Expedite contract execution on this project like it has on other projects? As long as the Contractor follows through on their submissions, can a contract be turned around in 14 days from bid and if not what is an expected time frame for a executed contract? |  |  | 8 | 2019-07-06 11:09
20190709 | 20190709005 | 5 | Staging | Why are there two stages each year when the work can be done in one stage? Given the extreme schedule why has WisDOT staged the project as it has and can the staging be combined so there is only one stage each year. |  |  | 9 | 2019-07-06 12:02
20190709 | 20190709005 | 5 | Staging | Why are there two stages each year when the work can be done in one stage? Given the extreme schedule why has WisDOT staged the project as it has and can the staging be combined so there is only one stage each year. |  |  | 10 | 2019-07-06 12:02
20190709 | 20190709006 | 6 | Design Files | Can we get a copy of the Design CAD Files, Excel Earthwork Sheets, Soils Reports and Design Schedules for these projects? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709006/ | Mike Coleman | 1 | 2019-06-04 18:34 | 2019-06-17 10:20
20190709 | 20190709006 | 6 | CAD Files - Existing and Design | We would like to request the following CAD files to assist with our planning and quantity verification processes. 1. Existing Conditions Survey Surface CAD files (with past projects completed "clipped" in) (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (with past projects completed "clipped" in) (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709006/ | Mike Coleman | 2 | 2019-06-12 08:33 | 2019-06-17 10:26
20190709 | 20190709006 | 6 | Design Schedule | Can a copy of the design schedule be provided? | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709006/ | Mike Coleman | 3 | 2019-06-24 19:25 | 2019-06-26 12:59
20190709 | 20190709006 | 6 | Porposed Surface | Can you provide the proposed surface (breaklines and/or triangles) in LandXML file format? In the previously posted data there is was only provided proposed 2D linework and not a proposed 3D surface. Thank you. | The proposed surface files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190709006/ | Mike Coleman | 4 | 2019-06-25 14:45 | 2019-07-03 07:51
20190709 | 20190709006 | 6 | Use of Existing Materials. | Can existing aspahlt and crushed aggregate base be used as crushed aggregate base course? | Per Section 301.2.4.2, existing base and asphalt can be recycled on site and reused, provided it is processed to meet the requirements of Section 305.2.2.2. All material stockpiles must follow the requirements of Article 32 in the project Special Provisions (Material and Equipment Staging). | Mike Coleman | 5 | 2019-06-26 05:08 | 2019-06-26 13:43
20190709 | 20190709006 | 6 | Winter Maintenance - Prosecution & Progress | What is the intent of the "Winter Maintenance" paragraph in the Prosecution and Progress article of the special provisions? | As stated in the article, the Village of Mount Pleasant will perform snow removal operations for local roads that are open to the public. They will not do so for closed roads. | Mike Coleman | 6 | 2019-07-01 13:55 | 2019-07-01 13:58
20190709 | 20190709006 | 6 | Item 415.1100 | How is item 415.1100 Concrete Pavement High Early Strength 10-Inch intended to be used? | It has been determined this item wonâ€™t be needed. It will be removed from the contract via addendum. | Mike Coleman | 7 | 2019-07-01 13:56 | 2019-07-01 13:58
20190709 | 20190709009 | 9 | Average Haunch Depth | The last General Note on sheet 2 of 5 in the structure plans indicates that "The haunch concrete quantity is based on the average haunch shown on sheet 'Steel Diaphragm & Girder Details'." There is no plan sheet with this description and I am not able to find the assumed average haunch. Since 'hat bars' are included in the plan the assumption is that higher than average haunches are to be expected, we would like to know how high. | The average height of the haunches at the interior girders is approximately 5 inches. This height may change slightly depending on the exact elevation of the existing girders. | Mike Coleman | 1 | 2019-06-13 07:49 | 2019-06-18 11:34
20190709 | 20190709009 | 9 | Average Haunch Depth | The last General Note on sheet 2 of 5 in the structure plans indicates that "The haunch concrete quantity is based on the average haunch shown on sheet 'Steel Diaphragm & Girder Details'." There is no plan sheet with this description and I am not able to find the assumed average haunch. Since 'hat bars' are included in the plan the assumption is that higher than average haunches are to be expected, we would like to know how high. | The average height of the haunches at the interior girders is approximately 5 inches. This height may change slightly depending on the exact elevation of the existing girders. | Mike Coleman | 2 | 2019-06-13 07:49 | 2019-06-18 11:35
20190709 | 20190709010 | 10 | CTH E Milling Butt Joints | For the portion on CTH E that is getting a mill and overlay there is no item for milling the 2' butt joint at the limits of the project. Should this item be added? | Removing asphaltic surface butt joints will be added via addendum. | Mike Coleman | 1 | 2019-06-24 18:04 | 2019-06-26 08:52
20190709 | 20190709010 | 10 | Tack QTY | The Asphaltic Surface item states that it has to be done in two lifts. No tack was calculated, should this be added to the project? | Tack Coat quantity will be increased via addendum. | Mike Coleman | 2 | 2019-06-24 18:06 | 2019-06-26 08:55
20190709 | 20190709011 | 11 | Completion date | The Completion date for this project is listed as August 16, 2019. Is there any flexibility where that date can be pushed farther out? Also can the bridges be done at the same time? |  |  | 1 | 2019-07-08 11:20
20190709 | 20190709012 | 12 | Asphaltic Surface | would the region consider changing the 305 tons that will be used to pave the transitions on the 3 culvert pipes to Asphaltic Surface? | The region will consider changing the asphaltic pavement used over the culvert patches to Asphaltic Surface for purposes of testing and acceptance only. The mix used must still meet all requirements for HMA pavement, as specified for use in this contract. | Fred Schunke | 1 | 2019-06-29 09:33 | 2019-07-05 11:09
20190709 | 20190709012 | 12 | Lane Closure | This project is 4 miles long, and the work zone length is limited to one mile and you need 2 miles between work zones. Can the work zone length be increased? | Lengthening the work zone up to a maximum of 2 miles will be considered post let, and if agreed to, will be applied via contact modification. | Fred Schunke | 2 | 2019-07-01 10:21 | 2019-07-05 11:09
20190709 | 20190709012 | 12 | Temporary Markings | Good morning. It appears you have enough temporary paint quantities for the milled layer as well as the surface layer on this project. On other projects, the surface layer quantities were for a temporary or same day epoxy item rather than a temporary paint item. Will an addendum be issued to add a temporary or same day epoxy item or is it up to the temporary paint contractor to remove the temporary paint prior to placing the permanent markings? Thank you. | Placing of epoxy pavement markings on the finished surface prior to installing centerline rumble strips, instead of removing and replacing temporary pavement markings, will be considered post let. If agreed to, this change will be applied post let via contact modification. | Fred Schunke | 3 | 2019-07-01 11:16 | 2019-07-05 11:09
20190709 | 20190709015 | 15 | Completion Date | Since this job is being bid later in the season, can the completion date be moved to 11/15/2019 or to an acceptable time beyond 9/20/2019? | The completion date is going to remain September 20, 2019. The schedule is aggressive to get the work done and minimize impact to the cranberry harvest and delay to the public. | Mike Coleman | 1 | 2019-06-15 14:20 | 2019-06-18 11:09
20190709 | 20190709015 | 15 | Classification | This job is advertised and listed under General Construction. It should be list under the classification of Bridge Painting. | The advertisement and Counter Sheet has been revised to show this project classification as AH (General/Bridge Painting). This can be viewed at the following location: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2019/20190709.aspx | Mike Coleman | 2 | 2019-06-15 14:26 | 2019-06-18 10:16
20190709 | 20190709015 | 15 | railroad | Proposal is stating railroad insurance is required and to coordinate with railroad. Where would painting of STH54 bridge over the Yellow River interfere with the railroad? STH54 bridge does not cross over the railroad tracks. | Railroad insurance is required as the contract indicates because WISDOT and RailRoad property abuts. No planned project work is over or across the railroad tracks but insurance is still required. | Mike Coleman | 3 | 2019-06-26 10:53 | 2019-06-27 09:17