## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200114 | 20200114003 | 3 | Plan Set | Can a Project Overview sheet be provided? | The design team did not do a project overview. There is not one available. Please see the plan details for the project limits. | Mike Coleman | 1 | 2019-12-20 12:02 | 2019-12-27 07:55
20200114 | 20200114003 | 3 | IRI RIDE | This Project has IRI Ride incentive and the road is in very poor condition. The plan calls for a 2 lift 4'' thick overlay. It is likely that defects will reflect through new hma. Will additional consideration be made to reduce IRI ride disincentive or will a profile mill be considered? | An addendum will be submitted to remove IRI Ride Incentive. | Fred Schunke | 2 | 2020-01-03 10:26 | 2020-01-06 11:54
20200114 | 20200114003 | 3 | Removing Asphaltic Surface Milling | What is this item being used for? Stations are identified but what thickness is being removed? When during the project will this work occur in relation to other operations? | The Removing Asphaltic Surface Milling bid item is being used for matching into existing asphalt driveways due to the profile increase from the HMA pavement overlay on US 14. See Page 10 (Construction Details) for details including mill depth. See Page 30 (Miscellaneous Quantities) for locations. Follow Article 4. Traffic of the special provisions for guidance on when this work can be done. | Fred Schunke | 3 | 2020-01-03 10:29 | 2020-01-06 11:28
20200114 | 20200114003 | 3 | Temp Rumble Strips | Will temp rumble strips be required for this project? If so, when will the use of them be applicable? | Utilize Temporary Portable Rumble Strips on all flagging operations. See SDD 15C12-07, costs for flagging and required equipment is incidental to the contract. | Fred Schunke | 4 | 2020-01-03 10:30 | 2020-01-03 13:11
20200114 | 20200114003 | 3 | Rumble Strips | This project has centerline and shoulder rumble strips. Will the excess millings generated from the rumbles strips be allowed to be swept on to the shoulder aggregate or will they need to be removed from the project? | Refer to Section 465.3.3(3) of the current edition of the Standard Specifications for Highway and Structures Construction. The spec states what is expected for cleanup and removal/disposal of milling debris. | Fred Schunke | 5 | 2020-01-03 10:32 | 2020-01-06 11:51
20200114 | 20200114003 | 3 | Prepare Foundation for Asphaltic Shoulders | In review of the current agg. shoulders on the project, it would appear material will need to be added to get them up to grade prior to shaping/ hma paving. Will this material be 3/4'' CABC and be paid under the 3/4'' CABC Item? | It is understood that the existing shoulder is low in areas throughout the project length. The undistributed quantity may be used to fill in low shoulder areas throughout the project length. | Fred Schunke | 6 | 2020-01-06 13:08 | 2020-01-07 14:41
20200114 | 20200114005 | 5 | Railing Attachment | On sheet 13 of 20 for Structure B-53-0379, would it be acceptable to provide an A325 bolt for the railing attachment to box beam? It would be similar to how diaphragms are attached to concrete girders. | A325 bolts would be acceptable provided the couplers are long enough to allow tightening of the bolts. | Mike Coleman | 1 | 2019-12-17 14:49 | 2019-12-23 08:28
20200114 | 20200114005 | 5 | Railing Attachment | On sheet 13 of 20 for Structure B-53-0379 can you verify the grade for item #2 "1/2-inch dia. stud with nut & washer"? Generally, A325 is not utilized as a specification for all-thread rod because of the forged head requirement. | This was addressed with A449 steel in an addendum issued January 6. | Fred Schunke | 2 | 2019-12-17 14:52 | 2020-01-08 08:12
20200114 | 20200114005 | 5 | 404 Permit | Could the 404 Permit be posted on the public site? | The 404 Permit is at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/5989-05-26/ | Fred Schunke | 3 | 2020-01-07 13:06 | 2020-01-08 08:31
20200114 | 20200114006 | 6 | MGS 3K Locations | We are confused by the layout of MGS 3K locations approaching short radius locations. MGS 3K has a rail height of 31", but at these locations it is bordered by "Class A LHW" and "MGS Short Radius", both of which have a height of approx. 28". It would seem more consistent to extend the Class A LHW into "Steel Plate Beam Guard, Short Radius" and "Steel Plate Beam Guard, Short Radius Terminal" bid items. Is the intent of the current layout to allow the MGS 3K to remain at the approx. 28" height? | Yes, the intent was that the MGS 3K installations would transition from a height of 27â€ at the end of the MGS Guardrail Short Radius to the 27-3/4â€ height of the Guardrail Stiffened LHW. We indicate â€œtransitionâ€ on our plans to try and convey that the pieces of MGS Guardrail 3 K will need adjustment from the standard. The SDD 14B53 â€œShort Radius MGSâ€ spells out clearly in the design notes that the piece of guardrail off the end of the short radius requires a height transition. The reason we are using the MGS Guardrail 3K as the transition piece instead of additional Guardrail Stiffened LHW is because SDD 14B53 â€œShort Radius MGSâ€ points to SDD 14B42 â€œMidwest Guardrail System (MGS) as the required SDD associated with this drawing. | Mike Coleman | 1 | 2019-12-13 10:23 | 2019-12-18 13:29
20200114 | 20200114006 | 6 | HMA Mix Type | Wondering if the mix type for this project should be changed from LT mix to MT mix per the new FDM 14.10 for greater than 1 Million ESALs? | An addendum will be issued to change the mix type to MT. | Mike Coleman | 2 | 2019-12-16 09:33 | 2019-12-18 13:31
20200114 | 20200114006 | 6 | Lower Lift HMA Sta 102+00 to 105+50 | The paving thickness for the lower lift in this portion of the job is only 1-1/4" with a 4 MT mix. Should this HMA be excluded from the PWL requirements? | The tonnage of HMA of the lower lift from Sta. 102+00 to Sta. 105+50 was included in the eligible tonnage for both â€œIncentive Density PWL HMA Pavementâ€ and â€œIncentive Air Voids HMA Pavementâ€. However, HMA PWL Test Strips for Volumetrics and Density should not be paced in this station range. No addendum will be issued, as the quantities will remain the same. | Mike Coleman | 3 | 2019-12-18 14:59 | 2019-12-23 08:58
20200114 | 20200114006 | 6 | Guardrail | Section 3. "Prosecution and Progress - Guardrail Operations" on page 4 of the proposal says that guardrail and terminals shall be installed within 48 hours after removal. According to the staging for the HMA the surface will not be paved within 48 hours of the lower lift HMA. Is the intent to remove and install the guardrail after all the HMA is complete or will the guard rail be installed to a height measured up from the lower lift HMA prior to paving the surface HMA? | When the removal of existing and placement of new guardrail occurs, will ultimately be up to the contractor to decide. The intent was to have the guardrail removed, graded and placed prior to the surface layer of HMA being placed. This would require the guardrail height to be set from the milled or lower lift surface and therefore account for the upper HMA surface to be placed afterwards.. It was our thought that in order to meet the July 17th completion date, guardrail work would need to be started prior to final lift of HMA. | Mike Coleman | 4 | 2019-12-18 15:09 | 2019-12-23 08:56
20200114 | 20200114006 | 6 | Base Aggregate Dense 3/4", Item 305.0110 | On page 8 of the Special Provisions Table of Contents in the Highway Work Proposal, does the description of the aggregate base disallow natural gravel base to be used? | The swr-305-001 â€œBase Aggregate Dense ¾-Inch, Item 305.0110â€ does require crushed stone. Crushed gravel is not acceptable material for this item. Other versions of this specification actually included the words â€œfrom an approved quarryâ€ which may help clarify this point. The crushed stone is called for because of its greater stability and resistance to erosion on the exposed aggregate shoulders. | Fred Schunke | 5 | 2020-01-07 14:13 | 2020-01-08 11:47
20200114 | 20200114006 | 6 | Temp Rumble Strips | Are temp rumble strips required on this project? | Yes, temporary rumble strips (The Portable type) are required for this project. Please see SDD 15C12-07 for more information. Temporary portable rumble strips are incidental to the Traffic Control item as per standard spec 104.6.1.2.2. | Mike Coleman | 6 | 2020-01-09 16:29 | 2020-01-13 09:50
20200114 | 20200114006 | 6 | HMA Material type | Will the HMA material type for bid item 122 â€œExtra Depth Asphaltâ€ also be changed to 4MT 58-28S? | Yes, under the Mixture section of the special provision for â€œExtra Depth HMA Pavement, Item SPV.0195.01â€ indicates the use of â€œHMA Pavement 4 LT 58-28 Sâ€ for the extra depth mixture. Because the mainline mix type has been revised through addenda to â€œHMA Pavement 4 MT 58-28 Sâ€ the extra depth mixture should be revised to the â€œMTâ€ type as well. Having just one HMA pavement type will improve efficiency of paving operations. | Mike Coleman | 7 | 2020-01-10 09:01 | 2020-01-13 09:59
20200114 | 20200114007 | 7 | MGS QS Note | SDD 14B42-06b, page 645 of plan, note 9 states, "25 feet of half post spacing is required on approach and departure ends of quarter post spacing." Will this note be eliminated for this project? | Bid item 614.2310 (MGS Guardrail 3 HS) will be added to the project via an addendum. The quantities for 614.2300 (MGS Guardrail 3) and 614.2320 (MGS Guardrail 3 QS) will be revised slightly as a result of adding the HS item. With this change the SDD note inquired about would be applicable. | Mike Coleman | 1 | 2019-12-13 10:10 | 2019-12-17 07:30
20200114 | 20200114007 | 7 | MGS Reflector Placement | SDD 14B42-06b, page 645 of the plan, note 8 states, "...Rail splice locations are the only acceptable locations for reflectors." For the MGS 3 on this project, where no post is located on the rail splice, will this this note be eliminated? | The old steel plat beam guard item required reflectors that were installed along the face of the rail and would be included at rail splices locations when applicable. But the newer MGS guardrail no longer uses the triangular shaped reflectors. Instead, 4â€x12â€ delineator reflectors are now required and are attached to posts instead of the face of the rail. The problem is that rail splices for guardrail donâ€™t always end up at posts. Yet note #8 on SDD 14B42 indicates â€˜Rail splice locations are the only acceptable locations for reflectors.â€™ Essentially the question was saying that note #8 needs to be modified on the SDD and there wasnâ€™t anything specific on proposal #7 that needed to be addressed. This information has been forwarded to the team that works on the standard detail drawings. | Mike Coleman | 2 | 2019-12-13 10:14 | 2019-12-17 09:06
20200114 | 20200114007 | 7 | DESIGN FILES | CAN THE DEPARTMENT PROVIDE? 1. ALL DESIGN FILES FOR THE PROJECT. 2. DESIGN SCHEDULE 3. SOIL BORINGS/GEOTECHNICAL REPORT. | The design schedule, soils report and design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114007/ The design schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2019-12-13 12:50 | 2019-12-17 08:22
20200114 | 20200114007 | 7 | Stage 5 Lane closures for HFST and Polymer Overlays | It is not clear when the lane closures are allowed for stage 5 during the HFST and Polymer Overlays. It only addresses the diamond grinding. | The lane closures associated with the HFST and polymer overlays are not limited to specific timeframes during stage 5. They can be completed at any time during that stage. The work/closures need to be coordinated with the other activities that require lane closures during stage 5 while also meeting the specific requirements of the items such as temperature and previous cure time required. | Mike Coleman | 4 | 2019-12-19 10:04 | 2019-12-27 07:43
20200114 | 20200114007 | 7 | Earthwork Data Sheet | Could the Department provide the earthwork data sheets in excel format? | The earthwork data sheets can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114007/ | Mike Coleman | 5 | 2019-12-19 11:29 | 2019-12-27 07:40
20200114 | 20200114007 | 7 | apron endwall quantities | bid quantities and miscellaneous quantities for the 24" and 30" apron endwalls do not match the information given on the plan pages. Which quantities are correct? Also are joint ties required on the salvaged apron endwall items? | The bottom table on sheet 525 inadvertently listed four apron endwalls as 24-inches but per plan sheet 93 they are in fact 30-inch endwalls. The quantities for those two items will be revised with an addenda. | Jill Fehrman | 6 | 2019-12-26 08:12 | 2020-01-02 16:19
20200114 | 20200114007 | 7 | Concrete Repairs and Replacements. | After looking over the project, it appears significantly more Concrete Repairs and Replacements will be needed on the project than currently is shown in the plans. Are the quantities going to be revised? | The concrete base patching and concrete repair items will be increased slightly via an addendum. The current quantities were based on a field review completed in April of 2019. The quantities were not increased to account for the increase in truck and construction traffic expected during the project as well as the 2 year time period between when the field inspection was completed and when the base patching/repair would be done. | Fred Schunke | 7 | 2019-12-26 14:05 | 2020-01-03 12:16
20200114 | 20200114007 | 7 | Grinding Slurry | The last project that was performed on this section of road the slurry from the diamond grinding process was allowed to be spread along the shoulder slopes. Will this be allowed again on this project? | The as advertised plans and specs address the side-discharging of the diamond grinding slurry. In general, the slurry can be side-discharged along the project. However, there are many environmental locations where side-discharging cannot be done. These locations are noted in the Erosion Control plans as â€˜Non-approved Diamond Grind Slurry Discharge Locationsâ€™. Also, special provision article 14 (Erosion Control) includes language on page 25 of 88 regarding side-discharging of the diamond grinding slurry. | Mike Coleman | 8 | 2019-12-27 08:24 | 2019-12-31 12:08
20200114 | 20200114007 | 7 | Over winter pavement markings | On most other similar projects, the agency has included or switched to epoxy markings for over the winter rather than paint markings. Is it in the plans to change the over winter paint item on plan sheet 549 to epoxy to insure they will survive the winter months? If it is, it would be better to do this now rather than the last minute as it will allow for the contractor to prepare accordingly and have materials, equipment, and forces available as needed. Thank you. | The winter shutdown pavement markings on sheet 549 will be changed to epoxy material by means of an addenda. | Jill Fehrman | 9 | 2019-12-27 12:49 | 2020-01-02 16:12
20200114 | 20200114007 | 7 | Pavement Markings | looking at plan sheet 548, I do not see any temporary lane or edge line markings during the diamond grinding phase of the project. On other similar projects, the agency has included same day paint or temporary paint to delineate the lane and edge lines until such time that permanent markings are put in upon completion of the diamond grinding. What is the agencies plan to delineate the lane and edge lines throughout the project during the diamond grinding phase (stage 5)? Thank you. | An Addenda will be issued to revise the temporary pavement marking quantity table, on plan sheet 548, to add temporary markings in stage 5 for the diamond grinding work. | Jill Fehrman | 10 | 2019-12-27 13:33 | 2020-01-02 16:18
20200114 | 20200114007 | 7 | Pavement Markings on Polymer Overlays | Per spec, the permanent markings on top of polymer overlays should be standard epoxy. I do not see where there are any standard markings called out for the bridges as they all appear to have tape skips and ground in edge lines associated with them. Will the agency be addressing this pre-bid? Thank you. | An addenda will be issued to revise the applicable permanent pavement marking plan sheets and miscellaneous quantities to reflect the standard epoxy items that should be applied to the 10 bridge decks that will have polymer overlays applied to them. | Jill Fehrman | 11 | 2019-12-27 15:08 | 2020-01-02 16:15
20200114 | 20200114007 | 7 | HFST on Shoulders | The Resin Binder High Friction Surface treatment states in the specs under C.3 "Extend the HFST application 6' into the shoulders as shown in the plans." So will the rumble strips be ground in after the HFST, or will the HFST go over the rumble strips? I do not find that detail in the plans. | Itâ€™s the contractorâ€™s discretion for the order of the rumble strip grinding and HFST tasks. | Fred Schunke | 12 | 2020-01-02 14:16 | 2020-01-06 11:22
20200114 | 20200114007 | 7 | B-64-63, 64 and 107 bridge overhang issues | On structures B-64-63 and 64 the overhangs that are on the existing deck during stage 2A are very dangerous and unsafe for the existing beam spacing. The notes state that the support is part of bridge removal. No support is shown. With the heavy loads of traffic on I43 this support design should have been a part of the contract documents. The easiest and safest solution to eliminate stability issues for these two structures would be to move the temporary barrier wall towards the closest beam in that stage, shorten the overhang removal and add length to the new staged overhang. Can traffic be pushed tight to existing parapet and temporary barrier wall moved in? Will the temporary loads of the deck requiring support be provided to the contractors? On structure B-64-107 the new staged overhang in 2A is too long. This overhang makes construction of this structure during 2A very unsafe and the quality of the bridge deck surface would be jeopardized. The plans allow only for a 6â€ gap between the existing bridge and the new deck. This space does not allow enough room for the contractor to adequately construct/finish the structure. Can the overhang dimension between stages be shortened to make construction safer and better quality. Will the temporary loads of the deck requiring support be provided to the contractors? | The intent of the legend note on traffic staging sheet 3 of 15 for B-64-63/64 and sheet 3 of 14 for B-64-107 is for the contractor to design and provide temporary support for the large deck overhangs. This is an approach that has been used for similar situations on previous bridge re-deck projects. Assuming that the temporary supports will provide a bearing surface at the overhang ends, reactions for the support design are as follows: B-64-63/64 (existing deck overhang support) Service dead load = 0.64 kips/ft along the overhang edge Service traffic live load = 9.9 kip wheel point load (includes 33% impact) B-64-107 (new deck overhang support) Service dead load = 0.53 kips/ft along the overhang edge Service traffic live load = 2.5 kip wheel point load (includes 33% impact) Regarding the 6â€ staging gap as shown, the contractor could remove up to an additional 1-ft of Structure B-64-107 in Stage 2A to aid in construction. | Fred Schunke | 13 | 2020-01-06 14:15 | 2020-01-08 14:32
20200114 | 20200114007 | 7 | No Excuses Contract | Why is this project a "no excuses" contract in regards to weather delays? | Use of the weather clause was evaluated for the project and deemed appropriate with the 2 year construction schedule and the need for all work scheduled in the first year to be completed on time. | Fred Schunke | 14 | 2020-01-07 13:59 | 2020-01-08 08:44
20200114 | 20200114007 | 7 | Rumble Strips/HFST | Will the rumble strips be milled in after the HFST is installed or will they be filled with the HFST? | As noted in the response to question 12, itâ€™s the contractorâ€™s discretion for the order of the rumble strip grinding and HFST application. If the contractor opts to grind the rumble strips prior to placing the HFST, the contractor would be responsible to prevent/protect the rumble strips from being filled with HFST material. | Fred Schunke | 15 | 2020-01-08 12:41 | 2020-01-08 14:32
20200114 | 20200114007 | 7 | Debris and Vegetation Removal | Per the Prosecution and Progress Article of the Special Provisions, there is a provision for debris and vegetation removal at 3 box culvert locations in the project limits. Per the notes, contractors are required to remove â€œdebris depositsâ€ and trim vegetation. This work is specified as incidental to the contract. Could the Department identify further what â€œdebris depositsâ€ include? Does this mean getting rid of brush and vegetation or is this for cleaning the endwalls in the creek of washed in material/muck out of the bottom of the endwall? | Includes removal and disposal of any vegetation (both growing and dead) or any man-made debris within the culverts, overhanging the ends of the culverts and at the entrances or exits of the culverts. Also included is the removal and disposal of sediment mounds that rise above the normal water line. The normal water line is defined as the elevation of the water surface after three days with no precipitation. | Fred Schunke | 16 | 2020-01-08 15:04 | 2020-01-09 15:23
20200114 | 20200114007 | 7 | Concrete Surface Repair - Superstructure | Can some guidance be provided on where the surface repair is anticipated on the bridge superstructure quantities. Looking at the bridges it appears that the intent is on the inside faces (traffic side) of the parapet walls and not underdeck, edge of deck or back side of parapet walls. There is a significant quantity of this work and more detail is warranted due to large variance in costs between inside vs. outside/underside. Large quantities are listed in the superstructure for structures 105, 106, 108, 109, 116, 117, 124, 125, 136, 137, 138, 144, and 145. | The majority of concrete surface repair occurs on the inside and top surfaces of the parapets. Other smaller areas to consider include the following: B-64-106: approximately 10 SF of deck underside delaminations B-64-108: approximately 27 SF of deck delamination at the fascias, spall at parapet outside corner B-64-109: some deck overhang spalls B-64-117: approximately 10 SF of deck overhang spalls B-64-124: 4 SF girder delams/spalls B-64-125: 1 SF girder delams/spalls, approximately 9 SF of deck overhang spalls, outside top corner parapet spall B-64-137: 5 SF girder delams/spalls B-64-138: 1 SF girder delams/spalls, 2 SF outside top corner parapet spall B-64-144: localized girder spalls at abutment ends & over roadway B-64-145: localized girder spalls at abutment ends & over roadway | Fred Schunke | 17 | 2020-01-08 16:28 | 2020-01-09 11:35
20200114 | 20200114007 | 7 | Concrete Joints for HFST | Our inspection of the project for the HFST treatment, we noticed the existing transverse neoprene joints have failed. The longitudinal center line paving joint is open as well. There will not be a consistent application of the epoxy during construction with open joints. Will there be an addendum issued to remove and reseal these joints? We believe there will be significant snowplow failure if the joints are not addressed. | Refer to page 86 of 88 within the project special provisions. Specifically, section C.2.1 (Pavement Surface Repair) of article 77 addresses how cracks/joints are to handled as part of the HFST application. | Fred Schunke | 18 | 2020-01-08 17:08 | 2020-01-09 11:35
20200114 | 20200114007 | 7 | Strip seal median plates, B-64-109 | Median plates reference note 10, but note 10 was omitted from the notes. Please advise if anti-slip surface is required and confirm this is a 3/8" x 26" plate. |  |  | 19 | 2020-01-09 16:06
20200114 | 20200114007 | 7 | Line 0004 203.0200 Removing Old Structure 0005 STA 99+94 | We can't find this structure in the plans. Where is it located (in the plans) and what kind of structure is it? | B-64-109 | Mike Coleman | 20 | 2020-01-10 15:30 | 2020-01-13 08:33
20200114 | 20200114007 | 7 | Concrete Repairs and Replacements SHES | Is there a specific location for the SHES Repairs and Replacements. | In general, SHES concrete patching and pavement repairs are for the outside driving lanes (traffic canâ€™t be moved onto the inside shoulder due to the narrow width and existing rumble strips) and any interchange ramps that require overnight closures in order to complete base patching and repairs. Concrete base patching and pavement repairs are needed throughout the project and not at any one specific location. | Mike Coleman | 21 | 2020-01-12 14:44 | 2020-01-13 09:38
20200114 | 20200114008 | 8 | Traffic Control Sign days overstated | Miscellaneous Quantities, Stage 4, the sign days are listed as 73,125 which would be 585 signs. Should this be listed as 13,125 days which would be 105 total signs? The other stages were all around 100-180 signs at a time. Thanks | The signs in Stage 4 are overstated. Corrected value is based on 150 signs for 18750 sign days. Revised undistributed amount is 29,220 for an estimated total of 80,000 sign days. An addendum will be issued to correct this. | Mike Coleman | 1 | 2019-12-11 14:59 | 2019-12-16 07:09
20200114 | 20200114008 | 8 | Contractor Data Packet Request | Can you provide the Existing Ground CAD Surface, Design CAD Files (Subgrade & Base Aggregate Surfaces with Alignments & Linework), Excel Earthwork Sheets, Design Schedule and Soils Reports? | The Electronic CAD data is being developed and currently not available. The Earthwork spreadsheet is included in the Miscellaneous Quantities as a pdf and was updated per the Addendum 1. The Design Schedule assumed to mean the estimated schedule (time chart) to complete construction operations. The allowable time to complete the project is two construction seasons. Contractors have differing opinions on production rates, size of crews, etc. The staging is shown in the plans and the special provisions. The project is expected to start by April 2020 and shutdown for winter in 2020. Then resume construction in spring 2021 and complete construction by July 31, 2021 (not the end of November 2021 as originally stated). A copy of the design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114008/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. The Soils Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114008/ | Mike Coleman | 2 | 2019-12-23 08:47 | 2019-12-31 11:48
20200114 | 20200114008 | 8 | Design Schedule | Can the Design Schedule be provided? | Design Schedule assumed to mean the estimated schedule (time chart) to complete construction operations. The allowable time to complete the project is two construction seasons. Contractors have differing opinions on production rates, size of crews, etc. The staging is shown in the plans and the special provisions. The project is expected to start by April 2020 and shutdown for winter in 2020. Then resume construction in spring 2021 and complete construction by July 31, 2021 (not the end of November 2021 as originally stated). A copy of the design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114008/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2019-12-23 09:46 | 2019-12-31 11:51
20200114 | 20200114008 | 8 | Confirmation of parts | The proposal states that the cabinet and EVP will be state furnished for this project. Can you please confirm which companies controller is being used in the cabinet, and what companies EVP products is being supplied? | Cabinet, Controller and EVP will be state supplied and below is the requested information: â€¢ Cabinet â€“ Siemens â€¢ Controller â€“ Econolite â€¢ EVP â€“ Tomar Electronics | Mike Coleman | 4 | 2019-12-24 08:12 | 2019-12-31 11:18
20200114 | 20200114008 | 8 | Storm Sewer Connections to Existing | A note to "See Note 6 in Miscellaneous Quantities" appears in numerous locations on the Storm Sewer plan sheets. It seems to be related to Connecting to existing Storm Sewer, or to Concrete Collar work. There does not appear to be a "Note 6" in the Miscellaneous Quantities, or anywhere else for that matter, that deals with Storm Sewer work. Could we get clarification on what Note 6 is about? | Missing Note 6 text is â€œALL ELEVATIONS OF CONNECTIONS TO THE EXISTING STORM SEWER SHALL BE CONFIRMED BY THE CONTRACTOR PRIOR TO ORDERING OF MATERIALâ€. | Fred Schunke | 5 | 2020-01-06 10:12 | 2020-01-07 08:49
20200114 | 20200114008 | 8 | Borrow and EBS | The amount of borrow seems considerably high (based on our takeoffs and reviewing the cross sections). Addendum 1 added another 4,000 CY of borrow. Also , the EBS as noted is to be backfilled with select borrow. There is not an item for select borrow. It may be possible borrow item should be select borrow? | The borrow item is being eliminated in addendum #02. EBS stabilization areas are backfilled with Select Crushed Material. | Mike Coleman | 6 | 2020-01-07 15:23 | 2020-01-10 09:57
20200114 | 20200114008 | 8 | 8 FT MANHOLE CONSTRUCTION | FOR THE BID ITEM 8 EACH MANHOLES 8 FT DIAMETER ARE THESE MANHOLES TO BE BUILT TO THE FULL DEPTH OF THE EXISTING 66" PIPE OR CAN THEY BE DOGHOUSED ON TOP OF THE PIPE? ALSO DO YOU KNOW WHAT MATERIAL THE EXISTING 66" PIPE IS MADE FROM? MANHOLES FOR 66" RCP OR BRICK SEWERS ARE RECCOMENDED TO BE A MINIMUM OF 108" DIAMETER ON A 66" SEWER. | In addendum #02, revised plans show construction of full depth, 9-foot diameter manholes at the locations connecting to the existing 66-inch concrete storm sewer pipe (SSPRC). Inverts of new 9â€™-0â€ diameter manholes are shown in the storm sewer plans and should be confirmed in the field. The existing 66-inch is concrete storm sewer pipe. In addendum #02, revised plans show 9-foot diameter manholes connecting to 66-inch concrete storm sewer. | Mike Coleman | 7 | 2020-01-08 11:31 | 2020-01-10 10:00
20200114 | 20200114008 | 8 | Storm Sewer Connections | Can you please clarify in detail how the structures connecting the proposed storm to the existing 66-inch storm trunk line in STH 11 is to be made? Will a â€œdoghouseâ€ type connection be allowed? Or are the new manholes to be cut in full depth and collars poured on either side of the connection? A doghouse connection could avoid the need for bypassing any flow during construction, but would likely require a larger diameter MH than what is currently specified. Structure 236 would be an example of this situation, along with others spread throughout the work. | In addendum #02, revised plans show construction of full depth, 9-FT diameter manholes at the locations connecting to the existing 66-Inch concrete storm sewer pipe (SSPRC). Inverts of new 9-FT diameter manholes are shown in the revised storm sewer plans and should be confirmed in the field. No "doghouse" type connection will be allowed. the plans show new manholes and should be bid that way. | Mike Coleman | 8 | 2020-01-08 13:02 | 2020-01-10 10:03
20200114 | 20200114008 | 8 | Can the soils report be provided? | Can the soils report be provided? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114008/ | Fred Schunke | 9 | 2020-01-09 14:07 | 2020-01-09 14:36
20200114 | 20200114008 | 8 | EBS / Borrow / Select Crush | In reviewing the Earthwork Summary and performing takeoffs and reviewing cross sections and Computer Earthwork data, it appears that the amount of Borrow stated for the prject is considerably high. The EBS is noted to be backfilled with Select borrow material but yet there is no Select Borrow item. Also in the Bid documents there is a item for Select Crush material to be used on the project, to be used in the EBS stabilization areas as call out in the Misc. Qty's. Is the intent of the Contract to utilize the Select Crush material for the EBS excavation that is represented in the Earthwork Summary? Is the Borrow item that is called out for in the plans supposed to be Select crush material as used in past practices? Are there Known EBS areas that are not represented in the plans (or Identified in Cross sections)that the Select Crush material and Borrow Material will be utilized in? |  |  | 10 | 2020-01-09 15:35
20200114 | 20200114008 | 8 | BID ITEM 611.2008 MANHOLES 8 FT DIAMETER | CAN THESE 8 EACH MANHOLES 8 FT DIAMETER BE DOGHOUSED TO FIT ON THE EXISTING 66" STORM SEWER OR DO THEY NEED TO BE BUILT AT FULL HEIGHT FROM RIM TO INVERT? |  |  | 11 | 2020-01-10 09:03
20200114 | 20200114009 | 9 | Pavement Marking - Thermoplastic or Tape? | Bid items 0336 and 0338 are for Preformed Thermoplastic Bike Line symbols and Arrows. The proposal calls out specification 647. There is no specification for section 647 any more. The proposal also has the Tape spec instead of the thermoplastic specifications. What material do you want to use? Thermoplastic is no longer on the Approved product list. | An addendum will be issued to clarify. | Fred Schunke | 1 | 2019-12-18 16:24 | 2020-01-03 07:52
20200114 | 20200114010 | 10 | Street Name Signs | Does WisDOT now allow, and on this project require, the contractor to install street name signs on top of stop signs? We thought this was strictly forbidden on projects. Also, does WisDOT have a detail or product acceptability list for attaching these street name signs to the top of square tube posts? | The DOT does not allow Street name signs on top of stop signs when the roadway is a state highway and under the jurisdiction of WisDOT. Since this is a local road, it is up to the municipalityâ€™s preference as to the location of the street name signs. Since the street name signs are currently located on top of the stop signs today, the City would prefer to maintain this layout. WisDOT does not have a detail or acceptability list for this item. The City has indicated mounting hardware for the street name signs is commonly purchased from TAPCO. | Mike Coleman | 1 | 2019-12-13 11:27 | 2019-12-18 14:14
20200114 | 20200114010 | 10 | Concrete Pavement and the location of dowel bars | I have reviewed the typical sections and would like to clarify whether or not you are looking for dowel bars in the bike lane of the roadway. The dollar value of supplying the steel for the bike lane is significant. Therefore, we would like this clarified. I have received calls from two steel suppliers on this topic so the question is being floated around. Some urban projects have required it due to the presence of bus routes and significant truck turning movements. Other projects have left the bike lanes undoweled. So, history does not give us clear precedence and the question needs to be answered. Thanks. | Since it has been found that edge loadings play a significant role in the deterioration of concrete pavements, so much so that we require extra width to our rural concrete pavements. I would think we would follow the same requirements, regarding dowels, as we do for concrete shoulders and include them in both bike lanes and extended gutter pans. A future addendum will be issued to show this. | Mike Coleman | 2 | 2019-12-17 09:26 | 2019-12-18 08:50
20200114 | 20200114010 | 10 | Soils Report. | Can the soils report be provided? | The soils report is at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114010/ | Fred Schunke | 3 | 2020-01-03 07:32 | 2020-01-08 08:42
20200114 | 20200114010 | 10 | Locate and Replace Existing Property Monuments | Were the property pins located as part of the plat or are they anticipating that the contractor surveyor relocate/identify property pins along the entire project? | Addendum #1 will clarify the question. | Fred Schunke | 4 | 2020-01-03 12:39 | 2020-01-03 14:13
20200114 | 20200114010 | 10 | Utilities at Doghouse Structure Shafts | Plan sheet 51 depicts a sanitary sewer through the shaft footprint for Doghouse Structure at STA 17+01. Utility section of SPs does not note this as a conflict. Is this sewer in conflict with the shaft excavation? Plan sheet 51 depicts a waterline through the shaft footprint for Doghouse Structure at STA 17+01. Utility section notes the waterline will be replaced but does not note the new location. Will the waterline be relocated outside the shaft footprint? Plan sheet 53 depicts two waterlines through the shaft footprint for Doghouse Structure at STA 26+28. Utility section notes the waterline will be replaced after storm sewer construction. Will the waterline be relocated outside the shaft footprint prior to construction? If not, please provide additional info on waterline size, material etc. | For both doghouse manholes, the sanitary sewer is relatively the same depth (~35â€™-40â€™) as the storm sewer mainline and is not in conflict with the shaft excavation. The waterline and gas lines are being relocated around the shaft OR capped and reconnected after the shaft is removed prior to backfilling around the manhole. | Fred Schunke | 5 | 2020-01-09 09:02 | 2020-01-10 14:00
20200114 | 20200114010 | 10 | 66-inch curb and gutter payment section | In special provision 33, Concrete curb and gutter 66 inch integral. The payment section states foundation excavation and disposing of surplus excavation materials is incidental to this item of work. Is this accurate or is the excavation and disposal of excavated materials included in the excavation common item? | The excavated material for the Concrete Curb & Gutter 66-Inch Integral is quantified under excavation common. There will not be additional quantity for removal of material in the location of the curb & gutter. | Fred Schunke | 6 | 2020-01-09 14:49 | 2020-01-10 14:10
20200114 | 20200114010 | 10 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114010/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2020-01-12 08:42 | 2020-01-13 09:22
20200114 | 20200114010 | 10 | Soils Report | Can the soils report be provided? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114010/ | Mike Coleman | 8 | 2020-01-12 08:43 | 2020-01-13 08:45
20200114 | 20200114011 | 11 | Contractor Data Packet | Can you post the Contractor Data Packet information for this project? | The contractor data packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ Current Department practice uses longitudinal break lines representing proposed roadway features to define design surfaces. The design surfaces provided in the contractor data packet were developed with older design techniques and standards using transverse break lines representing roadway cross section patterns. Longitudinal break line data is not available in the contractor data packet. Additional effort may be required by the contractor when using surface data provided in the contractor data packet to create construction surface models for field use. The vertical and horizontal control provided in the contractor data packet prior to the bid letting will have data obtained in 2019. Due to anticipated ground disturbance from freeze/thaw during the 2019/2020 winter, the department will resurvey the control points in spring of 2020 and make the updated vertical and horizontal control data available to the contractor in an updated contractor data packet. | Mike Coleman | 1 | 2019-12-12 06:14 | 2019-12-12 06:19
20200114 | 20200114011 | 11 | Misc Quantities | Can Miscellaneous Quantities and Computer Earthwork Data be provided in EXCEL format | The miscellaneous quantities and earthwork data can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ | Mike Coleman | 2 | 2019-12-13 12:49 | 2019-12-16 13:57
20200114 | 20200114011 | 11 | Design Schedule | Please provide a copy of the Departments design schedule. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2019-12-18 12:56 | 2019-12-23 08:08
20200114 | 20200114011 | 11 | Geotechnical Report/Information | Are there any additional borings or other geotechnical information that could be made available near the culvert locations? This information could be used to design the temporary shoring. | No additional borings were performed at culvert locations on this project. The soils report and Soil Conservation Service maps for this portion of the county can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ | Fred Schunke | 4 | 2019-12-26 09:55 | 2020-01-06 11:10
20200114 | 20200114011 | 11 | East Bound Profile Line | Can plan and profile sheets be provided for the East Bound Lane? | Plan and profile sheets will not be provided for the STH 23 eastbound lanes because they are not necessary and have not been developed. Adequate information has been provided in the plans to construct the project based on the STH 23 westbound alignment and profile. However, the STH 23 eastbound alignment and profile data is provided in the contractor data packet which has been made available as part of the supporting documents for proposal 011 at the following DOT website: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx | Fred Schunke | 5 | 2020-01-02 15:51 | 2020-01-03 13:27
20200114 | 20200114011 | 11 | Use of DOT excess lands | Can the DOT excess lands in the SE quadrant of the STH 23 and Division Road intersection and in the NE quadrant of the STH 23 and CTH T (north) intersection be used for setting up a batch plant for the project? | DOT excess lands may be used by the contractors provided they complete the required environmental documentation and receive approval from DOT. See ASP-6 for new language for standard spec 104.8(2) that describes requirements for excavating materials on the right-of-way thatâ€™s not within the horizontal and vertical excavation limits the plans show. | Jill Fehrman | 6 | 2020-01-02 16:29 | 2020-01-02 16:32
20200114 | 20200114011 | 11 | Size of the DOT excess lands | What size are the DOT excess lands in the SE quadrant of the STH 23 and Division Road intersection and in the NE quadrant of the STH 23 and CTH T (north) intersection? | The DOT excess land in the SE quadrant of Division Road intersection is 2.19 acres and the excess DOT land in the NE quadrant of the CTH T (north) intersection is 4.51 acres. I noted that the DOT excess land in the NE quadrant of the CTH T (north) intersection consists of two adjacent parcels, one at 0.32 acres and the other at 4.19 acres. | Jill Fehrman | 7 | 2020-01-02 16:30 | 2020-01-02 16:31
20200114 | 20200114011 | 11 | ECIP Information for Pit Run Sources | Can you please provide any ECIP info that was submitted for potential pit run sources under STH 23 grading project 1440-13-76/77? | Relycoâ€™s subcontractor, James Petersons Sons, Inc., had submitted a draft ECIP amendment for a selected site that was proposed as a pit run source prior to it being eliminated from that contract. Below is the location of the draft ECIP amendment. Please note the amendment is draft and was never approved. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ | Fred Schunke | 8 | 2020-01-03 09:26 | 2020-01-06 11:12
20200114 | 20200114011 | 11 | Detour Plans | The Traffic article describes 4 nighttime STH 23 closures and associated detours. Why are no detour plans or quantities provided in the plans? | Nighttime STH 23 closures and associated detours are not necessary for this project. The 2nd and 7th paragraphs shown under the Traffic article were mistakenly inserted into this proposal from a different project. The paragraphs will soon be removed from the Traffic article as part of a future addendum. | Fred Schunke | 9 | 2020-01-03 12:28 | 2020-01-03 12:29
20200114 | 20200114011 | 11 | SPV.0090 Removing Centerline Rumble Strips | The special provisions state that the Removing Centerline Rumble Strips item includes applying tack and furnishing and placing 4-MT 58-28 S however, there appears to be quantity in the miscellaneous quantities for the Tack and HMA 4 MT 58-28 S items specifically called out for this on pages 286-288 and included is those items bid quantity. Was this mistakenly included our will tack and hma be paid separately under the corresponding items? | The tack and HMA MT 58-28 S is to be covered under the Removing Centerline Rumble Strips item. The tack and HMA quantities associated with this item will not be paid separately and will be removed from the miscellaneous quantity sheets as part of a future addendum. | Fred Schunke | 10 | 2020-01-06 10:12 | 2020-01-07 09:00
20200114 | 20200114011 | 11 | Status of the 1440-13-76 project | What is the current status and anticipated completion date of the current project 1440-13-76? Is the start of project 1440-13-72 anticipated to be delayed in any way? | Projects 1440-13-76 and 1440-13-77 are anticipated to be completed by mid-August 2020 and no delay to project 1440-13-72 is anticipated. Ongoing construction activities under 1440-13-76 and 1440-13-77 may impact immediate work zone accessibility for project 1440-13-72. Coordination will be required with the prime contractor, Relyco Construction, as described in Article 7. | Fred Schunke | 11 | 2020-01-07 16:23 | 2020-01-08 14:24
20200114 | 20200114011 | 11 | Status of the 1440-13-76 Project | The special provisions state that it is anticipated that this current project will be completed mid-August 2020. It is assumed that any additional contractual delays (weather?) could extend this project further. Stage 1 construction, STH 23 WB, is to be completed on the current project bidding by Oct. 28, 2020 but does not include any liquidated damages if this date is not met. Can it be assumed that any delays to 1440-13-76 will then be reflected in a revision the interim and final completion dates on project 1440-13-72? It seems that minimal work may be accomplished in 2020 on 1440-13-72 since 1440-13-76 is only currently approximately 50% complete based on contract payments. | The intent of the October 28, 2020 interim completion date is to complete the proposed grading, pit run, base aggregate and pavement for Stage 1 in the same construction season as described in Article 3. It is anticipated that work on 1440-13-72 may be performed concurrently with the ongoing construction activities under 1440-13-76 and 1440-13-77 and coordination will be required with the prime contractor, Relyco Construction, as described in Article 7. The 1440-13-72 schedule and contract time was developed to accommodate the ongoing construction activities of 1440-13-76 and 1440-13-77. Any revisions to the completion date for delays will be addressed through Standard Specification 108.10 during construction. | Fred Schunke | 12 | 2020-01-08 10:26 | 2020-01-09 14:28
20200114 | 20200114011 | 11 | Common Excavation | The plan cross sections and incremental earthwork table show grading from station 745 to 755 WB which is all or partially where the current traffic is running. In what stage will traffic not be on this portion of the existing roadway so this work can be performed? | The cross sections and quantities in the earthwork table from 745+00 to 755+90 WB are shown incorrectly in the plan. The existing STH 23 mainline pavement structure in this station range will be salvaged and widened to accommodate the STH 23 WB tie-in. The intent is to construct this widening for the tie-in under stage 1 while traffic uses the existing lanes. Traffic in this section may be reduced to a single counter-directional lane via flagging operations during daytime hours only with minimum available width of 16 feet during HMA paving. An addendum will be issued to address this error and will provide a revised typical section, revised cross sections, revised earthwork quantities, revised miscellaneous quantities, and revised provision language in Article 4 Traffic for the subsection titled HMA paving Station 746â€™WBâ€™+90 to Station 755â€™WBâ€™+90. | Fred Schunke | 13 | 2020-01-09 14:03 | 2020-01-10 13:02
20200114 | 20200114011 | 11 | Soil Borings | There are no soil borings at the ftp site. Only the soils report. Are there any actual borings? | The only soil boring information available for this project is for STH 23 EB structure B-59-315 over the Ice Age Trail. That boring information is already provided on page 516 of the plan. No other soil borings were taken for this project. The soils report and Soil Conservation Service maps for this portion of the county can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114011/ | Fred Schunke | 14 | 2020-01-09 14:24 | 2020-01-10 13:02
20200114 | 20200114011 | 11 | Common Excavation | In Division 1 station 754 to Sta 776 the common excavation shown in the cross sections does not have a match line shown. The excavation shown to the right side of the cross sections I assume is included in the earthwork quantity in the table. This work is in the existing hwy 23 roadway where traffic is now. It appears that this volume of cut will not be available until after the traffic switch and should be in Division 2. Will this be corrected in the earthwork data sheets and summary? | The excavation shown under the existing STH 23 roadway from station 754+00 to station 776+00 should be shown in Division 2 instead of Division 1. An addendum will be issued to correct the earthwork tables and quantities and to revise the match line in the cross sections. | Fred Schunke | 15 | 2020-01-09 17:02 | 2020-01-10 13:03
20200114 | 20200114011 | 11 | Earthwork Tables per Addendum # 3 | Can earthwork tables adjusted per Addendum # 3 be provided in EXCEL |  |  | 16 | 2020-01-13 09:26
20200114 | 20200114012 | 12 | Asphalt Shoulder | The new asphalt typical section (340+43 to 343+00) shows a 4% asphalt shoulder, could this be a 2% shoulder due to the new concrete street and existing asphalt street are both at 2% where this pavement ties in? | The intended asphalt shoulder cross slopes of the rural section in question are 4% per the finished typical section on sheet 6. From the concrete/asphalt joint at STA 340+53 going east there will be a transition of cross slopes due to the super elevation. No addendum is intended to be sent out for this topic. | Fred Schunke | 1 | 2020-01-02 11:28 | 2020-01-03 08:01
20200114 | 20200114012 | 12 | Miscellaneous Quantitiesand Earthwork Data | Can Miscellaneous Quantities and Computer Earthwork Data be provided in EXCEL format | The Excel files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114012/ | Fred Schunke | 2 | 2020-01-03 11:56 | 2020-01-07 09:20
20200114 | 20200114012 | 12 | Soil Boring Information and Proposed Timeline Schedule | Can any soil boring information and proposed timeline schedule be provided for this project? | The soils report and preliminary time chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114012/ | Fred Schunke | 3 | 2020-01-06 09:54 | 2020-01-07 09:20
20200114 | 20200114012 | 12 | TRAFFIC | ARTICLE #4, PARAGRAPH #3 OF THE SPECIAL PROVISIONS STATES: MAINTAIN TRUCK ACCESS TO THE QUARRY AT 601 PLANK. WHAT ARE THE DETAILS AND SPECIFICS OF THIS REQUIREMENT? | Traffic entering/leaving the commercial quarry will be allowed as through traffic during construction since Plank to STH 96 is the only local truck route approved by the City of Kaukauna. Please coordinate with the quarry staff as work within the STH 96 project limits progresses to ensure safe/efficient passage of truck traffic. | Fred Schunke | 4 | 2020-01-06 14:13 | 2020-01-07 09:52
20200114 | 20200114012 | 12 | SPECIAL PROVISIONS | SPV'S ARTICLE #19 STORM SEWER ADJUSTING RINGS, ARTICLE #25, ADJUST SANITARY MANHOLE COVER ARE RUBBER ADJUSTING RINGS REQUIRED ON THIS PROJECT? | Rubber rings are allowed, but not required. The SPV articles are only indicating the requirements of each material, if used. Ring selection is contractorâ€™s choice as long as they meet the stated requirements. | Fred Schunke | 5 | 2020-01-06 15:04 | 2020-01-07 09:53
20200114 | 20200114012 | 12 | Storm Lateral 4" | SPV.0090, 4" Storm Lateral, Article 28, C Construction, paragraph #3 calls for 2" insulation over storm lateral How is this being paid? | Per the Payment section of item SPV.0090.02 Storm Lateral 4-inch, providing and laying the insulation is incidental to the item. | Fred Schunke | 6 | 2020-01-06 15:49 | 2020-01-07 12:12
20200114 | 20200114012 | 12 | 209.2100Backfill Granular Grade 2 | Would it be acceptable to substitute any material that is allowed for backfilling the storm sewer trenches, mainly 305 material either 1.25" or .75 inch base aggregate dense? that way the trench backfill could be consistent thru out the project? | The use item 209.2100 Backfill Granular Grade 2 is for the backfill of removed storm sewer along the project and removed structure (at STA 321+12). Material used for backfilling of these removals shall meet the requirements of Standard Spec 209.2. | Fred Schunke | 7 | 2020-01-07 07:54 | 2020-01-07 15:07
20200114 | 20200114012 | 12 | SPV 0090.02 storm lateral 4 inch | In the payment section it says that the Sawing of the sidewalk and patching with asphalt is included in the work, yet there is an item for temporary pedestrian surface asphalt. The way the breakdown for the temporary pedestrian does not help in clarifying this or not either. Is this patching incidental or paid. It is also hard to tell since the storm laterals do not show on the plan sheets. | Sawing, removal and replacement of the sidewalk surface in relation to the storm lateral work is incidental to the SPV 0090.02 Storm Lateral 4-inch item. The 644.1410 Temporary Pedestrian Surface Asphalt item is intended to be used as noted/located on the Sidewalk Construction Staging plan (sheets 51 â€“ 60) to maintain pedestrian traffic and provide temporary crossings during roadway reconstruction. | Fred Schunke | 8 | 2020-01-07 14:49 | 2020-01-08 08:44
20200114 | 20200114013 | 13 | Prepare Base for Asphalt Paving | Brown County will be installing asphaltic surface on CTH R and requires two working days. Does that include final preparation of base course for paving or DOT contractor have to figure on doing it? | The contractor will be required to construct the base course in accordance to 301.3 of the standard specifications. The two working days for Brown County includes the final preparation for asphalt paving in accordance to section 211 of the standard specifications. It is the contractorâ€™s responsibility to supply additional base aggregate dense material, if it is needed during final preparation for asphalt paving. | Mike Coleman | 1 | 2019-12-16 16:56 | 2019-12-18 13:25
20200114 | 20200114013 | 13 | Prepare Base for Asphalt Paving | Brown County will be installing asphaltic surface on CTH R and requires two working days. Does that include final preparation of base course for paving or DOT contractor have to figure on doing it? | The contractor will be required to construct the base course in accordance to 301.3 of the standard specifications. The two working days for Brown County includes the final preparation for asphalt paving in accordance to section 211 of the standard specifications. It is the contractorâ€™s responsibility to supply additional base aggregate dense material, if it is needed during final preparation for asphalt paving. | Mike Coleman | 2 | 2019-12-16 16:56 | 2019-12-18 13:26
20200114 | 20200114013 | 13 | B-5-438 Structure Excavation / Devils River Trail Access | SPV Article 9 prohibits stockpiling materials and driving/parking construction equipment on Devils River Trail. What is the purpose of this? OSHA compliant structure excavation limits for the B-5-438 pier footings will include portions of the Devils River Trail unless temporary shoring is utilized. Taking into consideration SPV Article 9, will this be allowed or will temporary shoring be included in the plan to prevent impacts to Devils River Trail? | Article 9 of the special provisions does not prohibit disturbance of the Devils River Trail for construction of the bridge. The article does not allow the contractor to access the bridge site by driving down the trail or use the trail to store materials. The trail should not be disturbed outside of the project limits. All disturbance to the trail must remain within the highway easement shown on the right-of-way plat in the plan. Items are included in the plan to restore the Devils River Trail within the work zone. | Mike Coleman | 3 | 2019-12-17 14:04 | 2019-12-18 06:27
20200114 | 20200114013 | 13 | B-5-38 Removing Concrete Slope Paving | Is removal of the concrete slope paving under existing structure B-5-38 incidental to structure removal or will item 204.0175 Removing Concrete Slope Paving be added to the project? | Item 204.0175 Removing Concrete Slope Paving will be added to the project as part of an addendum. | Mike Coleman | 4 | 2019-12-17 14:51 | 2019-12-18 07:15
20200114 | 20200114013 | 13 | Slope Paving Basecourse | The concrete slope paving typical section does not show basecourse being placed under the slope paving. Will it be required, and if so how will it be paid for? | See Section 604 of the Standard Specifications. Prepare the foundation in accordance with 604.3.1 and 604.3.4.1. | Fred Schunke | 5 | 2020-01-06 12:36 | 2020-01-07 09:23
20200114 | 20200114013 | 13 | Slope Paving Draintile | You show draintile under the slope paving in your typical section. Is this included in the bid quantities? If not, how many lineal feet are required and how will it be paid for? | The item of pipe underdrain is missing from the bid quantities. The item for pipe underdrain will be added to the quantities as part of an addendum. | Fred Schunke | 6 | 2020-01-06 12:52 | 2020-01-07 09:23
20200114 | 20200114014 | 14 | Plan PDF Issue | We can't seem to succesfully open this plan on the website. Is anyone else having trouble opening this link? | I have tried several different ways and have not had a problem opening this plan. Below is a direct link to the ftp site. Copy and paste into your browser. ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2020/01January_14/20200114014plan.pdf | Mike Coleman | 1 | 2019-12-13 12:17 | 2019-12-16 07:26
20200114 | 20200114014 | 14 | Misc Quantities and Earthwork Data | Can Miscellaneous Quantities and Computer Earthwork Data be provided in EXCEL format? | The Miscellaneous Quantities cannot be provided in EXCEL format. The Earthwork data table in EXCEL format can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114014/ | Mike Coleman | 2 | 2019-12-13 12:50 | 2019-12-23 08:18
20200114 | 20200114014 | 14 | Misc Quantities and Earthwork Data | Can Miscellaneous Quantities and Computer Earthwork Data be provided in EXCEL format? | The Miscellaneous Quantities cannot be provided in EXCEL format. The Earthwork data table in EXCEL format can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114014/ | Mike Coleman | 3 | 2019-12-13 12:50 | 2019-12-23 08:18
20200114 | 20200114014 | 14 | Asphalt Qty | It appears that the 3 LT and 4 LT tonnages seem to be calculated incorrectly. The 3 LT should be more than the 4 LT item. | Items were flip-flopped, and error was found in one line item. The following changes will be made by addendum: Update HMA thickness on some sideroads typical sections; change to MV mix on sideroads; update to sideroad paving details for change in HMA thickness; and update to miscells & schedule. | Fred Schunke | 4 | 2020-01-02 11:32 | 2020-01-07 08:13
20200114 | 20200114014 | 14 | SPV 0090.13, 0090.14, and SPV 0090.15 | C.2 Embedment and Backfill. The last sentence says that if the material excavated from the trench is unsuitable for backfill, use backfill granular grade 2 as trench backfill. There is no item for Granular backfill, would this be considered incidental that the contractor is to supply granular if the native is unsuitable or should there have been a item for granular? | An item for Backfill Granular Grade 2 will be added by addendum along with a construction detail that shows the pay limits. | Fred Schunke | 5 | 2020-01-03 11:42 | 2020-01-07 08:01
20200114 | 20200114014 | 14 | SPV 0090.13, SPV 0090.14 and SPV 0090.15 | C.2 Embedment and Backfill. This says that " all undesirable material below the trench bottom which cannot adequately support the main shall be replaced with 1.5" graded stone, it further states that this will be considered incidental to the water main item. How is a contractor supposed to quantify this? Are we supposed to just guess? | We do not anticipate need for additional stone. If needed, the amount should be minimal. A watermain trench backfill construction detail will be added by addendum to clarify standard bedding/backfill requirements. | Fred Schunke | 6 | 2020-01-03 11:46 | 2020-01-07 08:01
20200114 | 20200114014 | 14 | 24" Steel Casing | For are you looking for in terms of pipe load calculations as referenced under C. Construction? Certification of E-80 good enough or are we supposed to include engineering( PE Stamped) calculations based on soil conditions, depths and live loads? | The requirement to submit pipe loading calculations will be eliminated by addendum. | Fred Schunke | 7 | 2020-01-03 11:50 | 2020-01-07 08:02
20200114 | 20200114014 | 14 | SPV 0090.08 79 x 117 PACS aluminum coated | Under materials it tells us to provide backfill conforming to 608.2 so I interpret this as requiring granular backfill for this pipe. I am asking because the special provision tells us to construct per 521.3 which does not require granular backfill. Which is it? | Correct as written: Granular backfill conforming to 608.2 is required, and the construction shall conform to 521.3. | Fred Schunke | 8 | 2020-01-03 12:31 | 2020-01-07 08:02
20200114 | 20200114014 | 14 | Soil Boring and Timeline Schedule Information Request | Can any available soil boring and schedule information be provided for this project? | Soil boring and preliminary schedule information is at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114014/ | Fred Schunke | 9 | 2020-01-06 10:00 | 2020-01-08 07:46
20200114 | 20200114014 | 14 | SOIL BORINGS | Are there soil borings available for this project? | Soil boring information is at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114014/ | Fred Schunke | 10 | 2020-01-06 11:44 | 2020-01-08 07:46
20200114 | 20200114014 | 14 | Follow-up to Question 5 | Per the answer to question 5 there will be added an item for granular backfill grade 2. Which is fine but would it be acceptable to substitute for the grade 2 any material that is allowed for backfill in the storm sewer trenches. | Storm sewer trench back fill is required to meet Granular Backfill Grade 1, Granular Backfill Grade 2 or 520.2.5.2.2. Since Granular Backfill Grade 1 and the gradation outlined in 520.2.5.2.2 both should fall within the gradation requirements of Granular Backfill Grade 2, the answer would be yes with the following exception: 520.2.5.2.2 (2) allows the contractor to substitute ¾-inch and 1 ¼-inch dense graded base course. Those materials may fall outside of the Granular Backfill Grade 2 specification. | Fred Schunke | 11 | 2020-01-07 14:54 | 2020-01-08 14:30
20200114 | 20200114014 | 14 | Storm Sewer Removal trenches | Would it be acceptable to backfill the storm removal trenches with materials that are acceptable for use in the new storm sewer trenches? | 204.3.2.2.1 (13) requires backfilling trenches resulting from storm sewer removals with granular backfill conforming to 209.2 which would be Grade 1 or Grade 2. Answer would be the same as the answer to question #11. The 520.2.5.2.2 gradation should fall within the 209.2 specification, but substation of ¾-inch or 1 ¼-inch material may fall not meet 209.2 gradations. | Fred Schunke | 12 | 2020-01-07 15:01 | 2020-01-08 14:31
20200114 | 20200114014 | 14 | Storm Sewer CL-IIIB | The storm sewer pipe selection guide in the FDM allows for alternate pipe materials based on certain criteria; one of which is an AADT below 7000. With the projects design having an AADT of 12,900; Please explain the selection of pipe materials that do not fit that criteria. Also, what are the testing requirements if C-IIIB storm pipe is utilized? | Please refer to FDM 17.3.1 which outlines use of alternate materials outside of traffic lanes (behind curb and gutter) on roadways the design year traffic volume is equal to or exceeds 7000 AADT. Both Class III reinforced concrete pipe and corrugated polypropylene pipe are allowed materials under the Class III-B bid item. If corrugated polypropylene pipe is used, testing requirements are outlined in 608.3.7 of the Standard Specifications. | Jill Fehrman | 13 | 2020-01-09 14:46 | 2020-01-09 17:32
20200114 | 20200114014 | 14 | Underground Detention system east & west | The plans for this detention systems project, call for the pipe to be made using a manufacturing process referred to as lock-seam spiral. (some refer to it as Hel-Cor) Currently our manufacturing facility, located in Evansville Wisconsin (Which is certified to supply WI DOT) does not have the capability to produce lock-seam spiral pipe. Our Columbia, MO facility would need to produce this pipe, but it is not currently on the approved list to supply WI DOT culverts. I am emailing you and requesting approval to manufacture some of the pipe needed for this project at our Columbia, MO location. | Pipe material furnished under Item SPV.0105.05 & .06 is not required to be from an approved vendor. | Mike Coleman | 14 | 2020-01-10 10:53 | 2020-01-13 07:08
20200114 | 20200114015 | 15 | Diamond Grinding Limits | The plans show polymer overlay limits from curb face to curb face. Are these the same limits for the diamond grinding on the bascule span? Diamond grinding equipment typically can't get tight to vertical faces. | The diamond grinding limits are from curb face to curb face. Smaller equipment may be needed near the curb faces. | Fred Schunke | 1 | 2019-12-19 10:00 | 2020-01-03 09:07
20200114 | 20200114015 | 15 | Stage 2a roadway closure clarification | Section 4 - Traffic, indicates that for stage 2a: 'For deck repair work, close bridge to roadway traffic for no more than five days within the stated closure restriction period'. The special provision further states that there are 3 allowed overnight closures for work on the bascule span on June 8th, 9th, and 10th. Is the intent that the only time frame available for the polymer overlay work on any portion of the structure is the 5 day window between 6:00 PM on Sunday June 7th until noon on Friday June 12th? Or, can the work on the non-bascule spans occur between 6:00 PM Sunday and Noon on Friday in an alternate work week? How will these dates be amended if there are weather issues that do not allow for installation of polymer overlay. | Polymer overlay work for the bascule span (preventing bridge openings) must only occur overnight on June 8, 9 & 10. Any work not affecting bridge openings (including polymer overlay work for non-bascule spans) may occur between 6:00 PM Sunday and Noon on Friday any work week. As stated in Article 3, â€œWeather delays will be coordinated with the USCG and Engineer as needed.â€ | Jill Fehrman | 2 | 2019-12-31 07:10 | 2020-01-02 16:45
20200114 | 20200114015 | 15 | Concrete patch strength - open to traffic | What is the required strength for concrete patches in order to open roadway to traffic? Is there a minimum cure period required prior to opening to traffic, or is this governed by cylinder strength test results? Will HES patching mixes be allowed to minimize number of bridge closures? | The contractor needs to follow standard spec section 502.3.10.1; Opening to Service. | Fred Schunke | 3 | 2020-01-02 15:29 | 2020-01-03 08:43
20200114 | 20200114015 | 15 | Concrete Patch Strength - Follow up question | 1.) Based on response from earlier questions, please confirm that concrete patches must have 3,500 psi prior to opening. 2.) Will HES patching material be allowed to minimize the number of closures? | 1.) Concrete patches must have 3,500 PSI prior to opening. 2.) Yes | Fred Schunke | 4 | 2020-01-03 11:15 | 2020-01-06 11:25
20200114 | 20200114016 | 16 | B-05-0443 Hydraulic Data | Is the water velocity of 1.52 F.P.S. that is listed under the "2 Year Frequency" accurate? | Yes, the stated velocity is accurate. The normal water elevation at the project location is the same elevation as the Bay of Green Bay and the channel is flat. The channel at this location is also relatively deep so the flow area is large compared to the Q2 flow. The Q100 velocity is also relatively low at 5.6 FPS. | Mike Coleman | 1 | 2019-12-13 12:27 | 2019-12-16 08:51
20200114 | 20200114016 | 16 | HMA quantities | Please check the HMA 3LT and 4LT quantities I believe they were input in reverse order. | We agree that the HMA item quantities are reversed. An addendum will be issued to correct this. | Mike Coleman | 2 | 2019-12-19 08:42 | 2019-12-27 07:51
20200114 | 20200114016 | 16 | Earthwork | According to the borings and existing conditions the water elevation is at 682 +/-. There are proposed ditch elevations of 579 +/- and match points of 577 +/- are these correct? On Page 18 there is a note that states Marsh Excavation to be filled with Granular Grade 2 or Can be filled with Borrow or Cut, with engineer approval. This area will be under the existing water elevation. Would Breaker Run be a better material for this application? Not sure if sand would work. | It appears that â€œ682 +/-â€œ is a typo that should have been 582. Based on survey and current Lake Michigan water levels, 582 is a reasonable value of what could be expected. The ditch elevations are accurate. Ditches are needed for times when Lake Michigan and river levels are lower, so that runoff does not pond or sheet onto the adjacent property. The marsh excavation backfill will be changed to breaker run to an elevation 1â€™ above existing ground. Geotextile Type C will be added to separate the breaker from underlying soils. An addendum will be issued to address these changes. | Fred Schunke | 3 | 2020-01-07 10:31 | 2020-01-08 11:54
20200114 | 20200114016 | 16 | Earthwork | With the water elevation known and predicted to stay or rise over the next year, is the expectation to "build the ditches to the best of our ability" and just cut them to grade? Or will topsoil, seed, and emat need to be placed? If complete restoration would be required should temporary shoring be added to the contract? | The ditches will need to be cut to the plan grades but restoration will be directed by the engineer and will be dependent on water levels at the time of construction. | Fred Schunke | 4 | 2020-01-09 09:59 | 2020-01-09 15:24
20200114 | 20200114018 | 18 | pipe bollards | the plan note on sheet 3 states pipe bollard work by others, the spec book states furnish and install 4 pipe bollards, which one prevails? | The contract should include an item for furnish and install 4 pipe bollards. We will need to add this as an addendum at a future date. | Mike Coleman | 1 | 2019-12-12 08:50 | 2019-12-16 07:12
20200114 | 20200114018 | 18 | Pavement Structure | Note on plan sheet 3 states asphaltic concrete pavement (by owner) with 4 inches of 1 1/4 gravel base and 8 inches of breaker, the detail on sheet 4 also shows sas geotextile, The bid form shows an item for each. Will the items be part of the primes work or the owners? | Both items, SAS fabric, and asphaltic concrete pavement are included with the work for this project as indicated on the bid form. The note on plan sheet 3 is in error and should be disregarded. There was consideration early in the project for this work to be done by Waupaca County, but the Department chose to include the work with the project. An addendum will be issued to clarify. | Mike Coleman | 2 | 2019-12-12 08:56 | 2019-12-16 07:14
20200114 | 20200114018 | 18 | Electircal service connection | Will this shed have a new meter socket on it or will it be fed from another building? | No separate meter socket, the State salt shed will be fed from another building. | Fred Schunke | 3 | 2020-01-03 07:10 | 2020-01-06 11:22
20200114 | 20200114021 | 21 | Schedule | Projects 1020-03-76/1020-03-77/1020-03-78/1020-03-79 to the West of this project has a completion date of July 1, 2020, would there be a conflict with traffic control on these projects to the this one prohibiting the contractor to start prior to July 1st? | There is nothing prohibiting the contractor from starting work prior to July 1st. Traffic control will need to be coordinated with other projects as stated in the Special Provisions Article 9, Other Contracts. | Mike Coleman | 1 | 2019-12-16 11:10 | 2019-12-23 08:23
20200114 | 20200114022 | 22 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114022/ | Mike Coleman | 1 | 2019-12-24 07:08 | 2019-12-31 12:06
20200114 | 20200114023 | 23 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114023/ | Fred Schunke | 1 | 2019-12-24 07:09 | 2020-01-06 11:13
20200114 | 20200114023 | 23 | Pavement Markings | Good morning. Other than the small amount of removable tape, I do not see any temporary markings for he lower or upper layer of pavement. In addition, on page 2 of 31 it references temporary and same day markings as well as the upper layer lanes matching up daily which does not seem possible based on the staging requirements (inside/outside/inside/outside). Will an addendum be issued to add a temporary item to place center and, if desired, edge lines daily on this project? Thank you. | An addendum will be issued for this project to include temporary markings. | Fred Schunke | 2 | 2020-01-02 09:13 | 2020-01-07 09:59
20200114 | 20200114023 | 23 | Prosecution & Progress | Last sentence of paragraph 5 states ...in constructing the surface layer of pavement, work on each side of the centerline must be matched up at the end of each day... With the traffic control closing the lanes, is this applicable? | This sentence of paragraph 5 is not applicable. | Fred Schunke | 3 | 2020-01-02 09:19 | 2020-01-07 09:58
20200114 | 20200114023 | 23 | Traffic | The traffic control is listed in stages 1-4. In the past for the hot mix asphalt paving, these projects have been staged so that the driving lane is completed first so when the passing lane is completed the traffic can utilize the wide shoulder. Is there flexibility to make that adjustment on this project? | Yes, Staging is flexible. Stages 1 & 3 could be switched with Stages 2 & 4 and the outside driving lanes completed first if desired. | Fred Schunke | 4 | 2020-01-02 09:22 | 2020-01-07 09:58
20200114 | 20200114023 | 23 | Earthwork | There is earthwork (with applicable contract items) shown for the guardrail location at STA 551+53 - 555+04 NB. There is also an item for Barrier System Grading Shaping Finishing within the same stationing. There are no "for information only" quantities in the plan for the Barrier System Grading Shaping Finishing item. Please clarify how grading/restoration will be paid in this location and also verify the accuracy/intent of the cross sections for this same location from STA 552+00 - 555+04 as the section appear to show a significant cut at 20'RT. | An addendum will be issued to address items at Beamguard location. The item for Barrier System Grading Shaping Finishing will be removed. Grading / restoration items are included in plans. Base Aggregate & breaker run quantities will be revised. | Fred Schunke | 5 | 2020-01-07 16:19 | 2020-01-09 11:35
20200114 | 20200114024 | 24 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114024/ | Fred Schunke | 1 | 2019-12-24 07:09 | 2020-01-06 11:06
20200114 | 20200114027 | 27 | Loading Analysis | Will a loading analysis for the bridge/ arch be made available? | The structural computations can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114027/ | Fred Schunke | 1 | 2020-01-03 09:50 | 2020-01-07 09:18
20200114 | 20200114027 | 27 | Time Extension | It appears 110 working days is an insufficient amount of time to complete the work given the unique scope of work with the arches. Has the department reviewed the time allocated and would there be consideration for a significant time extension? | We felt that the time was tight for the work but were also trying to fit it within the Construction season. The thought was that the new floor beams would be started before the newt columns were finished. We currently anticipate that the contractor would start on April 15th. 110 Working Days would have an estimated completion date of October 30th. We would not have an issue extending the time if needed, as long as the project is completed by the end of the year. There are no restrictions if they start before May 15th. (Swallow Nesting.) However, there is asphalt paving on the approaches that needs to be done towards the end of the project. | Fred Schunke | 2 | 2020-01-08 14:15 | 2020-01-09 07:44
20200114 | 20200114027 | 27 | Texas parapets | On page 34 (3 of 40) of the plans it states in the general notes the details of what is to be concrete stained and what is to be pigmented sealer. Due the unique style of the Texas parapets and the chamfers, could a more detailed drawing be provided for the distinct limits of what is to be stain and what is to be pigmented sealer? | The Pigmented Surface Sealer should be white. This should have been noted on the plans. A more detailed drawing should not be required. The Pigmented Sealer will be applied to the front face and tops of the parapet. It will extend half way at the front of the openings in the parapet. The white Concrete Staining will be applied to the back face of the parapet. It will also extend half way at the back of the openings in the parapet. It is anticipated that there would be a little overlap of the Concrete Staining and the Pigmented Sealer halfway thru the openings in the parapets. | Fred Schunke | 3 | 2020-01-09 08:54 | 2020-01-09 10:16
20200114 | 20200114027 | 27 | Time Extension | To follow up the previous question relating to time extension... will the department be issuing an addendum for the additional time needed to complete this project? It is anticipated that 13 months (260 WD) is what is needed to complete the project. |  |  | 4 | 2020-01-09 16:23
20200114 | 20200114028 | 28 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114028/ | Fred Schunke | 1 | 2019-12-24 07:10 | 2020-01-06 11:14
20200114 | 20200114029 | 29 | Traffic control quantities overstated/understated | Miscellaneous quantities for traffic control - First, the sign days shown should total 98778, however only the bottom line (1212) carried down to the overall total. Second, the message board days reflect the detour being in place for 98 days, but all the other traffic control quantities reflect 303 days. 303 days subtracted from the completion date gives a start date of 1/21/20, one week after the job is let. Should the quantities reflect the devices being in place for an estimated 98 days? Thanks | 1) The corrected amount of days in service is 233 days, not 303. This will change the following quantities: a. 643.0420 Traffic Control Barricades Type III to 20,038 days. b. 643.0705 Traffic Control Warning Lights Type A to 38,678 days. c. 643.0900 Traffic Control Signs to 95,958 days. 2) 98 days is correct for 643.1050 Traffic Control Signs PCMS. PCMS boards are to be installed 2 weeks prior to project start, 2 weeks prior to change in each of the four structures starting, 2 weeks for detour reinstallation for Rock Fest, and 2 weeks for detour reinstallation for Country Fest. An addendum will be issued to correct this. | Mike Coleman | 1 | 2019-12-12 12:53 | 2019-12-16 07:08
20200114 | 20200114029 | 29 | Construction Staking Structures | Will the item Construction Staking Structures be added to proposal? | Yes. â€˜Construction Staking Structure Layout (structure)â€™ will be added for all four structures. This will be added in an upcoming addendum. | Mike Coleman | 2 | 2019-12-17 05:04 | 2019-12-17 09:08
20200114 | 20200114029 | 29 | Soil Borings | Are there soil borings available for this project? | The site investigation reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114029/ | Mike Coleman | 3 | 2019-12-24 07:10 | 2019-12-27 08:55
20200114 | 20200114031 | 31 | Pipe on the West side of the bridge | There is a pipe that is on the abutments on the West side of the road. I asked a local person and they said it was a force main. Is it a force main sewer pipe and do we have to support or brace that pipe? | There is a gas line on the west side of the roadway that has been relocated after the PSE date, therefore the plans do not reflect the new location of the gas line. Here are what the specials state about this line: Xcel Energy has underground facilities located on the west side of Main Street throughout the entire length of the project. The line is within the west existing right- of-way. Xcel Energy will relocate the line in conflict between the west right-of-way line and the edge of the proposed riprap prior to construction and estimates the work will take approximately 4 days. Contact Murray Smerer, (715) 682-6928, 30 days prior to construction to verify relocation has taken place. There is a sanitary force main on the east side of the roadway that conflicts are not anticipated. There is a require site watch during guardrail installation. If contractor means & methods of excavation will expose the main, contractor should coordination with the Sanitary District to brace/support, however this is not anticipated. Below is what the specials state about this utility: Iron River Sanitary District has underground water facilities located on the south east side of Main Street as well as a sanitary force main facility located on the east side of Main Street throughout the entire length of the project. This force main is within the east existing right-of-way. Conflicts are not anticipated, however extreme care is required when working near the force main. A site watch is required during the installation of the guardrail on the northeast quadrant. Contact Lori Anderson at (218) 393-2576 (cell) or (715) 372-4710 (office) and Tim Ciembronowicz at (715) 813-7194 (cell), 14 days in advance of work. | Mike Coleman | 1 | 2020-01-10 20:17 | 2020-01-13 13:56
20200114 | 20200114033 | 33 | Riprap Heavy Special | What are the gradation requirements for the 3/8" Traffic Bond Limestone Screenings? | An addendum is being issued to change the gradation to the following: SIEVE PERCENT PASSING (by weight) 1-inch 90 â€“ 100 3/8-inch 45 â€“ 65 No. 4 15 â€“ 45 No. 10 0 â€“ 20 No. 40 0 â€“ 10 No. 200 0 - 5 The previous answer has been changed. | Mike Coleman | 1 | 2019-12-23 14:02 | 2019-12-31 11:16
20200114 | 20200114034 | 34 | Existing Sections | Were any cores taken at the WI 128/USH 12 intersection? Is there any information where the limits are of existing concrete pavement and what the thickness is of the existing asphalt? | The Soils Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200114034/ The soils report for the US 12/WIS 128 intersection is posted on BidX for informational purposes only. Although the soils report didnâ€™t identify concrete pavement from the samples taken, as-builts show concrete pavement is present per existing typical sections. Contractors should account for this in their bid. | Mike Coleman | 1 | 2019-12-18 09:32 | 2019-12-23 08:35
20200114 | 20200114034 | 34 | Terminal Pads on WI 128 | Will the terminal pads at the railroad bridge on WI 128 be paid out under the G/S/F item or will these be part of the earthwork and restoration quantities on the 8949-05-73 project? | The terminal pads at the railroad bridge on WI 128 would be paid out under the earthwork and restoration quantities on the 8949-05-73 project. | Mike Coleman | 2 | 2019-12-18 11:07 | 2019-12-23 08:36
20200114 | 20200114034 | 34 | Bid Item #104 - Concrete Surface Repair Special | Bid Item #104 is described as Concrete Surface Repair Special, however it has the standard item number and there is no Special Provision. Is there something unique about this item or does it follow the standard specification? | The bid item should follow standard specification. There is no â€˜specialâ€™ modification. | Jill Fehrman | 3 | 2019-12-27 10:05 | 2020-01-02 16:52
20200114 | 20200114034 | 34 | Parapet Removal | The general notes on plan sheet 195 indicate that "Any parapet removal necessary to complete the parapet modification on the superstructure is considered incidental to the bid item 'Cleaning Parapets'". Does this include the complete removal of parapets on the wings or should an item be added for 'Removing Old Structure'? | An addenda will be issued to add the bid item Removing Old Structure. | Jill Fehrman | 4 | 2019-12-27 10:26 | 2020-01-02 16:50
20200114 | 20200114034 | 34 | WisDOT Right of Way | Will we be allowed to dispose of excess material within WisDOT right of way at the USH 12 and WI 128 intersection? | Please refer to specification section 205.3.12 - Incorporating or Disposing of Surplus or Unsuitable Material. WisDOT is unable to approve the disposal of surplus materials without an ECIP and additional information regarding wetlands, historic sites, archaeological sites, etc. | Fred Schunke | 5 | 2020-01-06 09:32 | 2020-01-06 14:57
20200114 | 20200114034 | 34 | Traffic Control Fixed message Signs | Page 27 and 29 show signs on the detour route that are attached to existing Type 1 signs, but there are no sizes or specs for those 3 signs, should they be Fixed Message Signs? | An addendum will add quantity for Fixed Message Signs and a sign plate detail. | Fred Schunke | 6 | 2020-01-06 13:10 | 2020-01-09 09:55
20200114 | 20200114035 | 35 | Typical Pavement Cross Sections of Tapered and Notched Longitudinal Joints | Sheet 9 of the plans has a detail drawing of the notched wedge joint. On this type of urban paving with multiple lanes and intersections causing short pulls is the use of the notched wedge joint applicable. It is highly doubtful that planned production would leave a vertical longitudinal joint overnight. | We have reviewed the question regarding need for the â€œnotched longitudinal jointsâ€ on this project. The intent is to insure that traffic does not encounter vertical joints during construction. The use of the â€œnotched longitudinal jointsâ€ accomplishes this and allows the contractor flexibility in adjusting traffic control during construction. We recognize the HMA pavement quantity of some stages may be paved in less than a day, but feel it is unlikely that traffic control will be adjusted and a subsequent stage paved in the same day. We recommend that contractors bid the plans as shown. | Fred Schunke | 1 | 2019-12-30 10:26 | 2020-01-03 08:41
20200114 | 20200114036 | 36 | Barrier System Grading Shaping Finishing | Are the "for information only" quantities available for the item of Barrier System Grading Shaping Finishing? | An Addenda will be issued to provide the quantities "for information only". | Jill Fehrman | 1 | 2019-12-27 07:20 | 2020-01-02 11:06
20200114 | 20200114036 | 36 | Guardrail | Please verify the accuracy of the quantities for MGS 3 vs. MGS 3 L. The MGS 3 L requires more than 25LF per location to meet system requirements. | The length of MGS Long Spam shown in the plan is incorrect. An addendum will be issued to correct the quantity. | Jill Fehrman | 2 | 2019-12-27 07:55 | 2020-01-02 08:35
20200114 | 20200114036 | 36 | Earthwork | The cross sections are labeled "guardrail" and appear to show the entire roadway being reconstructed from STA 333+80 - STA 338+20. This does not reflect what is shown in the typical sections but there is an item for Barrier System Grading Shaping Finishing in which no "for information only" quantities are provided. Please clarify the intent of the sections or provide new sections that show what is incidental to the Barrier System Grading Shaping Finishing item. | An Addenda will be issued to address the cross-sections and provide quantities "for information only". | Jill Fehrman | 3 | 2019-12-27 08:07 | 2020-01-02 11:07