## qandasearchletting_results
Date: | 2020-04-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200414 | 20200414001 | 1 | Bearing Lead Time | This project requires new bearings at Piers #1 and #3 which will have a lead time of 10-12 weeks after shop drawing approval at this time of year. The last note on plan sheet 58 indicates that the bearings are to be replaced prior to beginning the deck overlay, which will make it impossible to complete by July 21st. | Due to the required lead time for shop drawing review/approval and bearing fabrication, the completion date of the project will be revised through an addendum. | Mike Coleman | 1 | 2020-04-06 16:11 | 2020-04-09 10:21
20200414 | 20200414001 | 1 | Lane closures for Pier 2 Joint Repair | Is the intent of the contract to complete the joint repair at Pier #2 during one week during the allowable lane closure hours (Sun @ 9:00PM to Thur. @ 3:00PM), or will multiple closures be allowed? How will the barrier wall and crash cushions be paid if multiple closures are needed? Can the cushion be installed such that the block could be moved to the shoulder rather than removed from the job to open for the weekend (pay additional Temp. Barrier Install to move in and out)? | There is no intent to limit joint repair work at Pier #2 to one week; this would be up to the contractorâ€™s schedule. The intent of the temporary traffic control is to place the temporary barrier wall and crash cushions on the IH-39 median shoulders when work at Pier #2 is occurring. The shoulder closure has no timing restrictions. Closure of the inside lanes of IH-39 would be temporary and accomplished utilizing traffic control drums. | Mike Coleman | 2 | 2020-04-06 17:02 | 2020-04-09 10:23
20200414 | 20200414002 | 2 | HMA 4 LT Quantity Median Shoulder sta 373+00 to 612+15 | Please double check quantity in bid for this. It appears to be to high. | In reviewing the plan details and the miscellaneous quantities we found that the quantity shown in the miscellaneous quantity sheet for this station range in the median is incorrect. The quantity should be 1050T, not 2100T. An addendum will be issued to correct this. | Mike Coleman | 1 | 2020-03-16 14:44 | 2020-03-17 10:15
20200414 | 20200414002 | 2 | 649.0150 Temporary Tape | For items 649.0150 and 649.0250, Temporary Marking Line Removable tape, the Traffic Control plan sheets in Stage 5 note these items as "Contrast" tape, but the Miscellaneous Quantities call for standard solid color Tape. Please clarify if this item is Standard or Contrast temporary tape. Thanks | The stage 5 plan sheets should say removable tape, not contrast tape. These sheets will be revised and included in an upcoming addendum. All of the quantity sheets and bid items in the proposal are correct, there will not be any adjustments to bid items. | Mike Coleman | 2 | 2020-03-19 15:24 | 2020-03-20 08:57
20200414 | 20200414002 | 2 | SHES Repair and Replacements. | The specifications allow lane closures for Repairs and Replacements from 10:00pm Sunday to 11:00pm Thursday. Other than the SB lanes of this area of work, all Repair and Replacement projects with similar weekday and weekend work restriction require the use of 100% SHES Concrete. SHES concrete also provides some additional safety benefit by allowing rapid curing and reducing the chance of vehicles driving into wet concrete. The quantities only show a small amount of SHES concrete. Can the item descriptions be changed to use all SHES concrete? On the SB lanes the roadway restrictions were opened up to allow a full week's work after the Labor Day Holiday. This may also be an option. | Concrete pavement sections are to be replaced the same day. No overnight pavement surface voids are allowed. There are 4 days allowed per week, Sunday to Thursday, for northbound lane closures, including cure time. The use of SHES is not allowed without the approval of the engineer. It is up to the contractor to utilize a mix that will meet the contract requirements. Off peak hours were determined by using recent traffic counts, allowed lane closure hours will not be adjusted at this time. | Mike Coleman | 3 | 2020-04-06 11:24 | 2020-04-07 14:40
20200414 | 20200414002 | 2 | Lane Restrictions. | Opening by 11:00 Pm Thursday seem a little odd. Normally we have to open in the morning. Is this an oversight. Can the opening time be extended to Friday morning in the am time period? | Lane restrictions were based on traffic counts and will remain as stated in the special provisions. | Mike Coleman | 4 | 2020-04-08 05:34 | 2020-04-08 14:40
20200414 | 20200414002 | 2 | Dynamic Late Merge System | In the plans for this project on page 233 there is a layout for the dynamic late merge system. I do not see any quantities for this system in the proposed schedule of items. Is a dynamic late merge system needed for this project? | The Standard Detail Drawing was in the plan by mistake. There is no dynamic late merge system needed for this project. | Mike Coleman | 5 | 2020-04-08 11:36 | 2020-04-08 14:42
20200414 | 20200414002 | 2 | Concrete Repair and Replacement Mix. | Can we be informed is an SHES mix or 8 bag mix will be approved? Can we be informed what will and will not be approved so that we bid the project accordingly. | The intention as detailed in the plans, is to have the patches identified in the plans be paid under the 416.1710 and 416.1720 bid items utilizing a mix that conforms to 416.2.4 and will cure out in the time constraints listed in the plans. These bid items allow several different mixes to give the contractor options to meet the timeframes in the contract. Per the special provisions lane closures are allowed for several continuous days not hours. There is a small quantity in the plans for 416.1715 and 416.1725, SHES would not be allowed unless approved by the field engineer in special circumstances. | Mike Coleman | 6 | 2020-04-08 14:50 | 2020-04-09 11:38
20200414 | 20200414002 | 2 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414002/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2020-04-10 07:53 | 2020-04-10 09:19
20200414 | 20200414003 | 3 | Milling & Paving | The fifth paragraph in Prosecution and Progress will lead to construct-ability issues. Would the dept consider milling the driving lane 4 inches and the parking lane 2 inches in one operation with paving the lower in the driving lane in the same day. Followed by surfacing the driving lane and parking lane with in the 5 days stated. | Due to the uncertainty of how well the parking lane will hold up with construction traffic after itâ€™s milled, WisDOT has determined that the bidders approach would leave WisDOT with too much risk in having the parking lane exposed as a milled surface for up to 5 days. Therefore, WisDOT will not allow milling of the driving lane 4 inches and the parking lane 2 inches in one operation with paving the lower in the driving lane in the same day. | Mike Coleman | 1 | 2020-04-07 14:48 | 2020-04-09 11:17
20200414 | 20200414004 | 4 | Pavement Markings | Good morning. Can you please take a look at the pavement marking quantities on sheet 38 of the plans. It appears you have the same day epoxy quantities for the center line as required prior to the rumbles but do not have any quantities for the center line after the rumbles are placed. Will an addendum be issued to cover these additional quantities? Thank you! | An addendum will be issued to address pavement marking. | Mike Coleman | 1 | 2020-03-26 09:54 | 2020-03-30 14:32
20200414 | 20200414004 | 4 | Prep Foundation for Asphaltic Shoulders | Prep for asph shoulders quantity looks to include curb sections for STA 521+65 to 527+55, as well as the climbing lane from 567+18 to 627+70 RT, which is not getting widened. | This will be addressed as part of an upcoming addendum. | Mike Coleman | 2 | 2020-03-31 08:55 | 2020-03-31 15:02
20200414 | 20200414004 | 4 | Soil Borings | Were any soil borings taken in the guardrail sections to the depths needed to install the posts to the proper depth? | No soil borings were taken at guardrail sections. | Mike Coleman | 3 | 2020-04-01 14:08 | 2020-04-02 08:52
20200414 | 20200414005 | 5 | PWL for Lower Lift HMA sta 1+75 to 123+50 | Could the Lower Lift HMA in the 3.5" thick HMA section on the west end of the job be changed from PWL to QMP testing? The borings show there are 3 cores where the existing asphalt is only 3" thick so there will be portions of the lower lift HMA that will be over base and portions over milled surface. This will result in un-uniform density results which goes against good PWL density results. In addition, same day mill and fill on lower lift and 48 hours for surface paving with 2 test strips mixed in is going to be a real challenge. Assuming good weather, with a test strip on lower lift it will take 2 days to mill & pave the lower lift. Then a test strip and pave surface is another 2 days. | From review of boring data on page 4 of the plan, the section from 1+75 to 123+50, the mill will probably break through to base and would require multiple test strips. Therefore, it is proposed that the lower section from 1+75 to 123+50 of 3781 tons be broken out into QMP density acceptance. An addendum will be issued to clarify. | Mike Coleman | 1 | 2020-03-17 16:03 | 2020-03-19 06:06
20200414 | 20200414005 | 5 | Same day Mill & Pave sta 123+50 to 405+99.66 | Since this project is going to be detoured, Can the time line for paving surface be changed to allow time for all the work that has to happen between milling and paving? The project requires milling off 1.75" asphalt, milling and widening of curves, milling and patching distressed pavement, wedging curves to correct super-elevations, and then paving surface all in one day. That is 3 milling operations and 3 paving operations. Each operation will only be working about 6 hours per day to make sure that milling limits get repaved each day. This is very inefficient, which is costly, and will result in more stop & start joints in the pavement. The wedging of the super-elevations will be 2" to 3" thick in places and will not even be cooled off yet prior to paving the surface so there is potential for unstable lower lift wedging. The work zone will stretch out the entire length of the limits that will be milled and paved per day. | This will be addressed in an upcoming addendum. | Mike Coleman | 2 | 2020-03-26 14:15 | 2020-03-31 13:59
20200414 | 20200414005 | 5 | HMA for Super-Elevation Correction | Is the mix for wedging the supers in the AS item or the HMA item? | Wedging of superelevation areas will be done in HMA pavement. | Jill Fehrman | 3 | 2020-03-27 08:24 | 2020-03-27 17:17
20200414 | 20200414005 | 5 | Asphaltic Binder Enhanced Friction Surface treatment | The contractors that do this work require 30 days cure time of HMA prior to application and will not warranty it if it is done after the end of August. Since this project requires Notice to Proceed after August 10th, there is now way to get the Friction Surface Treatment done this year. How would DOT like to handle this? | The ESFT special provision does not require a 30-day cure time or specify a warranty requirement. Per the specification, an ambient temperature of 60 degrees is required for placement along with the other requirements in Section C3 - Application of the EFST. The Contractor should schedule work operations accordingly to install the Asphaltic Binder Enhanced Friction Surface treatment by the contract completion date. | Mike Coleman | 4 | 2020-03-31 15:36 | 2020-04-02 14:22
20200414 | 20200414005 | 5 | EFST Spec | Due to the contractors concern of applying EFST without the proper cure time and after August, could the EFST be completed in the 2021 construction season? If not, can the spec be changed to the High Friction Surface Treatment as it is less sensitive to temperature? |  |  | 5 | 2020-04-08 12:47
20200414 | 20200414007 | 7 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414007/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-04-10 07:57 | 2020-04-10 09:58
20200414 | 20200414009 | 9 | Same day or temporary paint pavement markings | Good morning. In looking under prosecution and progress on page 2 of 21 of the proposal, it states that the lower layer is required to be paved within 48 hours of the milling operation. On sheet 17 of the plan sheet, I do not see any same day or temporary paint quantities for the milled surface. What is your plan to delineate the milled surface should the contractor choose to wait to pave the lower layer? Will an addendum be issued to cover the additional quantities of same day paint or is it your plan to utilize signing in lieu of markings? Thank you. | The plan is to utilize signing in lieu of markings on the milled surface. | Mike Coleman | 1 | 2020-03-30 11:38 | 2020-03-30 14:17
20200414 | 20200414011 | 11 | State Furnished Cabinet - Controllers | Are the traffic signal controllers in the state furnished cabinets EPAC or Econolite controllers? |  |  | 1 | 2020-03-23 10:54
20200414 | 20200414011 | 11 | Concrete Bridge Deck Methacrylate Flood Seal, Item SPV.0180.20 | Can TK-2414 MMA Bridge Deck & Crack Sealer be used instead of what is listed in the spec? | Bid as specified in the special provision. | Mike Coleman | 2 | 2020-03-30 14:13 | 2020-03-30 14:14
20200414 | 20200414011 | 11 | Existing Cable Barrier STA 320 - STA 330 | Between STA 320 and STA 330 there is existing cable barrier in the asphalt median. What are the limits for milling and paving in this area? Will a portion of the existing asphalt remain? | An addendum will be submitted this morning to show the updated milling and paving limits (10 feet of the inside shoulder through crossover area). | Mike Coleman | 3 | 2020-04-08 15:20 | 2020-04-09 08:26
20200414 | 20200414011 | 11 | Base Agg Dense 3/4" | The typical finished section does not show new shoulder aggregate but there is a qty of 1,500 tons. Are you expecting to shoulder the entire job with 1 or 2 inches of new aggregate? | The final proposed pavement elevation will match the existing pavement elevation. Currently, much of the aggregate shoulder along IH 94 is lower than the pavement elevation and will need to be raised. In addition to the shoulders being lower than the pavement, the paving operations are likely to impact the existing aggregate shoulders. This is what the quantity of aggregate in the plans is intended for. | Mike Coleman | 4 | 2020-04-09 10:53 | 2020-04-10 06:24
20200414 | 20200414011 | 11 | Cleaning and Sealing Concrete Girder Ends | Looking for clarification on how item 322 - Cleaning and Sealing Concrete Girder Ends will be quantified. This item has a unit of LF, we have previously seen this as an Each item. Is the LF to be measured as the length of deteriorated concrete removed? Or the length of the epoxy coating applied at each location (shown as 5' +/- per location). |  |  | 5 | 2020-04-09 10:55
20200414 | 20200414011 | 11 | SHES Concrete Base Patching | 18,290 s.y. of SHES Concrete Base Patching seems like a grossly overstated undistributed quantity in view of the existing pavement condition along with the number of concrete base patches that were installed over the past couple of years on prior projects. How was this quantity calculated and what criteria will be utilized for marking out the size and location of the patches at the time of construction? |  |  | 6 | 2020-04-09 16:53
20200414 | 20200414012 | 12 | CAD Files | Can the department please provide the CAD files for this project? Thank you. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414012/ | Mike Coleman | 1 | 2020-03-17 08:58 | 2020-03-20 06:53
20200414 | 20200414012 | 12 | Electronic Data Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement and Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414012/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-03-17 12:35 | 2020-03-20 06:53
20200414 | 20200414012 | 12 | Geotechnical Report | Please provide the geotechnical report or where it can be obtained. Thank you. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414012/ | Mike Coleman | 3 | 2020-03-17 15:47 | 2020-03-20 06:54
20200414 | 20200414012 | 12 | Line 22 Site Clearance I94 EW - 2702 W. Greves St. | Plan sht. 12 Advanced fill along I94 - Removals indicates retaining walls and silo foundation to be removed under this item. Visiting the site, one can see existing bituminous pavement & concrete pavement along with building slabs and I assume building foundations. the majority of the pavement and slabs appears to be covered with existing soils, so very hard to quantify areas.Is the existing bituminous pavement and concrete slabs/ftgs, (left from building demo previously performed) have to be removed? If so, are we going to be paid under pavement removal? Please clarify. |  |  | 4 | 2020-03-24 13:03
20200414 | 20200414012 | 12 | Soil Drying | Due to the availability of fly ash would the State consider allowing a different product to be used for this application? Quicklime for example? | After reviewing with the materials team, they determined that fly ash is the only alternative for this soil drying application. | Mike Coleman | 5 | 2020-03-30 10:03 | 2020-04-02 06:10
20200414 | 20200414012 | 12 | Fuel Cost Adjustment | With the current and futures fuel prices dropping below $1.00 per Gallon in March, can the Fuel Cost Adjustment be changed on this project? | ASP-5 was revised and an addendum was issued. | Mike Coleman | 6 | 2020-03-31 16:54 | 2020-04-09 10:26
20200414 | 20200414012 | 12 | Pond outlet trash rack | we cannot find a manufacturer to fabricate the specified trash rack. We propose an alternate product from Haala Industries. It is a cone grate trash rack part number CG36TM that has the same inside and outside measurements as detail shows. | After discussing with our drainage and construction teams, the contractor proposed trash rack (Haala Industries CG36TM) is acceptable. | Mike Coleman | 7 | 2020-04-03 12:35 | 2020-04-09 11:15
20200414 | 20200414012 | 12 | Common Excavation - WDOT #12 Zoo IC Detention Basin | using the WDOT supplied CAD files for the detention basin, we modeled the pond. One comes up with a total cut volumes of 192,848 CY. Subtract out the Contaminated soil 16,800 CY (28560/1.7) along with the low level contaminated soil 29,772 CY = 146,276 CY. Add in the 85 CY of common at the IH-94 dump site yields a total common excavation quantity of 146,361 CY. Plan sheet 59 Earthwork Summary table indicates a total common excavation quantity of 128,841 CY - same as the bid item #30. Please clarify the discrepancy. | The existing surface that WisDOT had originally provided on the ftp site was outdated and accounts for the discrepancy in common excavation calculations. The updated existing surface has now been uploaded to the ftp site. The plans, including the plan sheet number 59 that is in question, are correct and show the correct earthwork quantities. Additionally, WisDOT will have a survey crew conduct a field survey to verify existing surface elevations are correct as shown in the plan. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414012/ | Mike Coleman | 8 | 2020-04-07 10:23 | 2020-04-09 08:29
20200414 | 20200414012 | 12 | Buried Shaft Shoring System Removal | Can more detail be provided the existing shaft shoring system will be removed under this contract? What was the shaft backfilled with? What materials were used to construct the shaft and what is the estimated diameter? |  |  | 9 | 2020-04-08 15:47
20200414 | 20200414018 | 18 | Electronic Date Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement and Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-03-17 12:35 | 2020-03-23 08:34
20200414 | 20200414018 | 18 | Required Testing for County's Stockpile | Special Provision, Article 7, Notice to Contractor, Potential Aggregate Source. Will this available material if used on this project for Base Aggregate be exempted from testing wear and soundness as if it was sourced from the project limits? Or will it be considered a new source and all testing is required. If wear and soundness is required, was this performed already, if so please provide those results. | The County stockpile is located at the County maintenance facility which is located on Karow Rd, north of the newly aligned CTH F. The stockpile is at the back of the property, approximately 1,500 ft from the newly aligned CTH F. So, the stockpile is not within the project limits and therefore, it is not exempt from testing. The stockpile would be considered a new source material. And, no, there has not been any testing done on the material. | Mike Coleman | 2 | 2020-03-30 11:29 | 2020-04-01 06:25
20200414 | 20200414018 | 18 | Fuel Cost Adjustment | With the current and futures fuel prices dropping below $1.00 per Gallon in March, can the Fuel Cost Adjustment be changed on this project? | ASP-5 was revised and an addendum was issued. | Mike Coleman | 3 | 2020-03-31 16:53 | 2020-04-09 10:26
20200414 | 20200414018 | 18 | County of Kenosha Lands Adjacent to Project - Use for sourcing Materials | The County of Kenosha owns a lot of land adjacent to this project which would be great for sourcing materials needed for this project (like Borrow). If allowable this would reduce the cost of the project and potentially benefit the local park system by making more land useful. Can we use the County of Kenosha Land adjacent to this project for sourcing materials for this project? If so, what lands are available, royalty costs (if any) and any special conditions? | Kenosha County does not have enough time to analyze and review the potential adjacent parcels for borrow prior to the Letting date. | Mike Coleman | 4 | 2020-04-02 09:09 | 2020-04-09 06:16
20200414 | 20200414018 | 18 | Grading, Shaping, and Finishing Intersections Bid Items | Can the Department provide a STA range for each of these intersections (CTH F & CTH O, CTH F & CTH EM and CTH EM & Old CTH F) that will be paid under the Lump Sum bid items. Then the contractor can determine the quantities of excavation, borrow, topsoil, fertilizer, seed and mulch within these lump sum bid items. It appears the intersection quantities are already covered in individual bid items (excavation, borrow, topsoil, fertilizer, seed and mulch), if that is the case, why are these lump sum intersection bid items needed? Just pay the individual bids items through the intersections and delete the lump sum intersection items. |  |  | 5 | 2020-04-08 09:29
20200414 | 20200414018 | 18 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 1-1/4 Inch and Breaker Run? | The conversion factors are as follows: Base Aggregate Dense 1-1/4 inch: 2.0 Breaker Run: 1.8 CY * Factor = TON | Mike Coleman | 6 | 2020-04-08 09:33 | 2020-04-09 06:18
20200414 | 20200414021 | 21 | Pavement Markings | Good morning, can you please address the following differences between the miscellaneous quantities and plan sheets for the pavement markings? 1.The plan sheets show wet reflective edge lines on the entire project which is typical for similar projects while the miscellaneous quantities and bid items show a combination of regular and wet reflective for the edge lines? 2.The plan sheets show temporary paint for the center line while the miscellaneous quantities and bid items show epoxy which is typical for similar projects? 3.The plan sheets, miscellaneous quantities, and bid items show temporary epoxy in non-rumbled areas on the surface, this is typically a same day epoxy item? 4.Under project 4090-05-71 it has temporary paint on the surface presumably to layout the rumbles and the proposal(P. 35) states this should be temporary epoxy? Thank you. | 1. The edge line pavement marking quantity for station range 1660+00 â€“ 1934+69 is shown on the MQ sheets as 4-inch Epoxy but should be in the wet reflective column to match what is shown on the plan sheets. MQ pavement marking table and estimate will be revised though addendum. 2. The legend on the plan sheets indicates that both paint and epoxy are to be used at the centerline. Paint is to be applied after milling and after 1st (lower) overlay. Epoxy to be applied after 2nd (upper) overlay. See the construction detail â€œPavement Marking Detail For Asphalt Pavementsâ€. MQ table has quantity for both the paint and epoxy for each mainline station range. 3. The pavement marking in the areas mentioned will be revised to same day epoxy via addendum. 4. The standard NE Region special provision describing pavement marking operations in conjunction with centerline and type 2 shoulder rumble strips was included in the proposal. The plan specifies type 1 shoulder rumble strips for Project ID 4090-05-71, therefore the special provision will not pertain to the shoulder rumble strips for the project. Temporary paint edge lines will be used to assist in layout of the type 1 shoulder rumble strips and mark the edge of traveled way until the permanent markings can be grooved in. | Mike Coleman | 1 | 2020-04-03 08:49 | 2020-04-06 14:21
20200414 | 20200414021 | 21 | 643.0500 Flexible Posts & Bases | The miscellaneous quantities for this item shows 252 each, however it appears that it was accidentally calculated as 18 posts for 14 days (the duration of the stage) which would be 252. Please clarify if there are 252 or 18 Flex Posts & Bases needed for this stage. Thanks | The quantity for flexible posts and bases was calculated incorrectly in the MQ table. Quantity should be revised to 18 each for both the posts and bases. This will be revised through an addendum. | Mike Coleman | 2 | 2020-04-03 14:57 | 2020-04-06 14:23
20200414 | 20200414021 | 21 | HMA along Curb | The detail for curb on sheet 7 on 4090-05-71 shows HMA Pavement 3 LT 58-28 S between curb and existing roadway. There are quantities for this material as well. On sheet 13 of 4530-06-71 the plan calls for asphaltic surface between curb and existing roadway. There are no quantities for this material. Will the item for asphaltic surface and quantities be added or should this be 3 LT and quantities added? | The applicable construction detail will be revised to change asphaltic surface to HMA Pavement 3 LT 58-28 S and HMA Pavement 3 LT 58-28 S quantity will be revised via addendum. | Mike Coleman | 3 | 2020-04-06 14:28 | 2020-04-07 09:51
20200414 | 20200414021 | 21 | Asphaltic Base Widening | Will it be allowed to place the asphaltic base widening at the same time as the mainline wedge? I believe this will give a better product. If this is allowed, can the special provision for asphaltic base widening be addended to allow for 9.5mm HMA? The current SPV allows for 12.5mm | Yes this will be allowed. An addendum will be issued to reflect the change in the special provisions. | Mike Coleman | 4 | 2020-04-08 14:47 | 2020-04-08 14:49
20200414 | 20200414021 | 21 | Design Schedule | Can you please provide the design schedule? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414021/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2020-04-10 10:03 | 2020-04-10 10:04
20200414 | 20200414022 | 22 | Stage 1 Duration | Per SP Stage 1 detour is for replacement of two culvert between West County Line and CTH T and can not last longer than 3 days. During this period we need to replace two pipes (106"x68" and 34"x53"), construct diversion channel, remove diversion channel, rebuild the roadway, landscape it immediately while still maintaining a minimum 10' travel way for emergency responder vehicles. We don't think 3 days is sufficient time to perform all this work. Please advise on how 3 day time frame was achieved. | After review, the allowable Stage 1 detour duration will be lengthened. An addendum will be posted for this. | Mike Coleman | 1 | 2020-03-24 08:28 | 2020-03-26 13:52
20200414 | 20200414022 | 22 | Stage 1/ Project Working Days | With the start by date, staging requirements, and holiday detour restrictions it does not leave a lot of time for milling, paving, shouldering, rumble strips, and pavement marking (grooving 5 days after paving complete). If time is being added to stage 1, will working days be added to the overall project? | We anticipate the overall project will be extended. Any extension to the project duration will be addressed via addendum #1. | Mike Coleman | 2 | 2020-03-31 09:21 | 2020-03-31 10:47
20200414 | 20200414022 | 22 | Design Schedule | Can the departments design schedule be provided? |  |  | 3 | 2020-03-31 09:22
20200414 | 20200414022 | 22 | Traffic on Milled Surface | The Specials state â€œdo not allow STH 64 traffic to operate on milled surfacesâ€. Past projects have typically allowed for traffic to run on a milled surface for 72 hours. Would the department consider this change. | The department considered this and will keep as-is. This is due to minimal remaining asphalt thickness on shoulders after milling operations. | Mike Coleman | 4 | 2020-04-01 08:07 | 2020-04-01 13:47
20200414 | 20200414022 | 22 | HMA Pipe Patches | There is currently 524 TN of 4 MT 58-28 S called out for the pipe replacements. Currently the 4 MT item is being tested under PWL. Would the department consider changing the pipe patching tonnage to Asphaltic Surface to eliminate testing issues as these pipes will likely be paved prior to any PWL test strips? | This will be moved to asphaltic surface in an upcoming addendum. | Mike Coleman | 5 | 2020-04-01 08:08 | 2020-04-01 08:59
20200414 | 20200414022 | 22 | HMA Leveling Layer | Will density be waived on the 1-1/4â€ leveling layer as it will be under the minimum thickness per spec? | As shown in the â€œAsphalt Itemsâ€ MQ table on sheet 32 of the plan, not all HMA quantity is shown as eligible for PWL Density Incentive due to the leveling layer not being included. The leveling layer shall follow 450.3.2.6.2 â€“ Ordinary Compaction. | Mike Coleman | 6 | 2020-04-01 08:08 | 2020-04-01 13:50
20200414 | 20200414022 | 22 | Asphaltic Surface Patching | What is the 136 ton of undistributed intended for? | This item is intended for potential maintenance of traffic. Due to traffic not being allowed on milled surfaces, this quantity will be reduced in addendum #1. There is still a potential need for maintenance of traffic, but at a reduced amount. | Mike Coleman | 7 | 2020-04-01 08:09 | 2020-04-01 13:51
20200414 | 20200414022 | 22 | Hydraulic Calculations | Sp Provision #30 contains the following language: The 2-year recurrence interval stream discharges are as follows: Culvert at Station 29+20 â€“ 17 cubic feet per second Culvert at Station 213+60 â€“ 29 cubic feet per second Provide hydraulic calculations and temporary water diversion plan details at each required location. Include a summary of the temporary water diversion duration at each required location. All methods of diversion, calculations, and plans are subject to approval as part of the ECIP Is it the departments intention to have the calculations performed by a PE? | calculations performed by a PE is not a requirement of this special provision. | Mike Coleman | 8 | 2020-04-07 18:10 | 2020-04-09 06:20
20200414 | 20200414024 | 24 | Soil Borings | Are soil borings available for this project? | We do not have any soil borings for this project. | Mike Coleman | 1 | 2020-03-19 10:53 | 2020-03-19 14:52
20200414 | 20200414024 | 24 | HTCB Systems | What systems will be allowed in Marquette, Waushara, and Portage counties? | The Product Acceptability List (PAL) has been updated. The list can be found at: https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/tools/appr-prod/default.aspx The approved systems for each county are shown on page 3 and 4 of the document. | Jill Fehrman | 2 | 2020-03-19 11:27 | 2020-03-27 17:15
20200414 | 20200414024 | 24 | Soil Borings | With NO boring's available 1. Will the contractor need to be responsible to do the borings? 2.If so will the boring costs be paid for? 3. Is there enough time to have the borings completed (probably need 30 or more borings, 4 differant counties) and the reports written up, and still get the project completed before cold weather gets here???? This all needs to be done for the cable companies to design the anchors and line post footings!!! | The department will provide soil boring information and reports prior to construction. An addendum is being issued to update this informaion | Mike Coleman | 3 | 2020-04-01 11:57 | 2020-04-09 13:24
20200414 | 20200414025 | 25 | Superstructure Concrete Quantity | Check and confirm concrete quantity for bridge superstructure. |  |  | 1 | 2020-04-08 13:45
20200414 | 20200414025 | 25 | Superstructure Concrete Quantity | Check and confirm concrete quantity for bridge superstructure. |  |  | 2 | 2020-04-08 13:45
20200414 | 20200414026 | 26 | Design Schedule | Could the department provide the construction schedule that was developed during design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414026/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-03-26 15:11 | 2020-03-27 09:03
20200414 | 20200414026 | 26 | 20 Working Days | After reviewing the schedule made during design, contractor believes that the 20 days is not enough. PWL requires a day to complete 750 tons and get test results back. The 2,000 tons per day of paving including intersection seems like an over estimate. The average will probably be 15% - 25% lower. Per prosecution and progress, the project has to be covered every weekend, so full production for 5 days a week is not possible. Could 5 working days be added to the project? | An addendum will be issued to increase the contract days by 5 days and update/clarify the weekend work restrictions â€“ the requirement of placing asphaltic surface by the end of the work week does not preclude them from working on Saturdays. | Mike Coleman | 2 | 2020-04-01 08:27 | 2020-04-02 06:07
20200414 | 20200414027 | 27 | Pavement Markings | Good morning. A couple of questions on the pavement markings. 1.What is the plan for temporary markings and center line rumble layout on the surface? Can a temporary epoxy marking bid item be added? 2.The quantity of wet reflective epoxy in the miscellaneous quantities appears to be 50% of what it should be? For example, station 70+00-664+75 is 59,475' long and only has 56,700' of edge line rather than 113,700'? Will the department issue and addendum to address these questions? Thank you. | 1. The item Temporary Marking Line Paint is to be placed on the milled surface, the item Temporary Marking Line Removable Tape was to be placed on the HMA surface prior to Centerline Rumble installation. As suggested the item Temporary Marking Line Epoxy will be added to be contract to be placed on the HMA surface prior to the Center Rumble Installation in place of the Temporary Marking Line Removable Tape. The item Temporary Marking Line Removable Tape will be removed from the contract. 2. The quantity for the Marking Line Grooved Wet Reflective Epoxy is incorrect in the plan and will be increased. 3. Yes an addendum will be submitted adding the item Temporary Marking Line Epoxy 4-Inch and increasing the quantity for Marking Line Grooved Wet Reflective Epoxy 4-Inch. | Mike Coleman | 1 | 2020-04-04 07:17 | 2020-04-06 09:24
20200414 | 20200414028 | 28 | Matching pavement daily | On page 3 of the special provisions under traffic it states, "Match left and right lane paving limits daily to eliminate centerline and vertical edges." Setting back during the middle of the day is a large safety issue due to having the paving and QC operations in opposing lanes at the same time. This is especially true for a PWL project with the increased number of test. Can this be change to use the tapered approved by the central office to eliminate this dangerous issue? | This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2020-03-30 11:26 | 2020-03-31 14:03
20200414 | 20200414029 | 29 | Same Day Paint or Same Day Epoxy | Bid item 0126 for Same day paint has a note on page 20 of Project No. 9090-01-72 of the Misc quantities stating that Same Day Epoxy and epoxy be used for the rumble strips. Which should be the case, as Epoxy applied on paint will not stay, and would be out of spec. Will the department change the Same Day Paint to Same Day Epoxy via addendum? | This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2020-03-30 11:10 | 2020-03-31 13:58
20200414 | 20200414029 | 29 | working days | Would like to see the schedule the designer used to come up with 30 days. | The contract time for completion was revised from 30 working days to 55 working days in addendum #02. The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200414029/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-03-31 19:57 | 2020-04-06 06:45
20200414 | 20200414030 | 30 | Temporary Diversion Channel | SP describes briefly constructing of the Temporary Diversion Channel at STA 738+40 for the pipe installation. During the site visit it became apparent that there is a strong creek flow at this location (pictures could be provided upon request to the DOT personnel). Can flow rates and plan sheets with an additional bid items and staging made available, as it seems to be a multistage operation for constructing diversion channel, installing the pipes and removing the diversion channel while maintaining STH 32 traffic. Such staging plans and appropriate bid items were provided on the Project 9180-23-71(72) STH 22 Shawano Co. | Flow rates (cfs) for the temporary diversions are as follows: North Branch Oconto River STA 480+31 & 480+43 Q2: 59.83 Q5: 114.22 Camp Twenty Creek STA 738+40 & 738+50 Q2: 2.03 Q5: 8.34 There are multiple means and methods of staging the construction. Bid the contract as provided. | Mike Coleman | 1 | 2020-03-24 10:29 | 2020-03-24 15:11
20200414 | 20200414030 | 30 | Base Aggregate Quantities | Please double check the base quantities for this project. We believe the quantity is double what is needed. | We checked the quantities and came up with the same number that is in the plans. | Mike Coleman | 2 | 2020-04-07 14:43 | 2020-04-07 14:44
20200414 | 20200414032 | 32 | HMA Mix Type Selection | There is a section of the plan that shows 2 1/2" of 3MT, approximately 1,500 ton. The remainder of the mix on the project is 4MT. For quality control reasons it would be better to have all the mix 4MT. | Based on the pavement design the 3MT pavement should stay. Please bid accordingly. | Mike Coleman | 1 | 2020-03-30 11:56 | 2020-04-02 11:25
20200414 | 20200414032 | 32 | Intersection Mix | Plan detail call out intersection mix to be 3" total thickness of 3MT. Is that correct? | All intersection/sidestreet asphalt should be a total of 3â€ of 3MT as shown in the typical finished section for town roads, with the exception of 140th street. The 140th Street intersection asphalt should be the same as the asphalt in this segment between station 9+15 and 37+75 ( 4.5â€ total thickness). | Mike Coleman | 2 | 2020-03-30 11:57 | 2020-04-02 11:26
20200414 | 20200414032 | 32 | CTH GG & 140th | Sheet 7 of the plan. Note on left side towards bottom. "Remove pulverized asphalt between Sta 9+15 and Sta 10+75. Incidental to HMA Pavement". The removal of this material is associated with the pulverize and relay item and really has nothing to do with the HMA Pavement. Further more the removal of this material should not be incidental. DOT has an item for removing excess pulverized material and we feel that item is applicable in this situation. | Addendum #1 has been prepared to address this. A depth of material has been identified and material removal is being changed to incidental to pulverize and relay. | Mike Coleman | 3 | 2020-03-30 12:02 | 2020-04-02 11:27
20200414 | 20200414033 | 33 | Barrier Block - Weekend Rules | Section 5.B. of the specials states: Concrete Barrier Temporary Precast is not allowed on IH 39 beginning on Friday at 12:00 PM to the following Sunday at 6:00 PM. If block must be picked up for the weekend and then reinstalled at the same location to complete work, will this be paid for as additional quantity delivered and installed? | Operations should be scheduled so that a bridge requiring the polymer overlay to be placed in stages will be completed between the window of Sunday at 6pm and Friday at noon so that reinstalling temporary barrier at the same location is not required. | Mike Coleman | 1 | 2020-04-08 15:23 | 2020-04-09 08:17
20200414 | 20200414033 | 33 | Temporary Concrete Barrier | Is the use of Temporary Concrete Barrier necessary on this project? At the vast majority of locations each stage would be set up for a short period of time which would mean constant pulling and resetting of concrete barrier. Stage layout allows for a descent sized buffer area between traffic and work area. | In order to maintain safety for both the travelling public and the contractor, temporary concrete barrier should be installed per plan. | Mike Coleman | 2 | 2020-04-09 16:06 | 2020-04-10 08:44