## qandasearchletting_results
Date: | 2021-03-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210309 | 20210309001 | 1 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-02-12 10:45 | 2021-02-18 08:58
20210309 | 20210309001 | 1 | Epoxy Crack Sealing Locations/Details | The special provision for Epoxy Crack Sealing states that the locations are "in abutments as the plan details show.", however we are unable to find any details in the plan sheets. Please provide locations for repairs. | The special provisions will be revised by addendum. | Mike Coleman | 2 | 2021-03-01 14:50 | 2021-03-03 17:53
20210309 | 20210309002 | 2 | Geotechnical Report | Can the we get a copy of the geotechnical report? | The Geotechnical Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309002/ | Mike Coleman | 1 | 2021-02-23 14:32 | 2021-02-24 06:42
20210309 | 20210309003 | 3 | Spec. Prov. 7. Railroad Insurance and Coordination - Item A.2 Train Operation. Please confirm Data | The most current crossing data from the FRA.gov crossing inventory report for crossing ID 390627K does not match the data listed in the special provisions. Please confirm data. Total Trains/day, Total passenger trains/day, number of switching trains/day. | An addendum will be issued to address this. | Mike Coleman | 1 | 2021-02-11 11:10 | 2021-02-16 06:17
20210309 | 20210309003 | 3 | Work over the railroad. | Will there be any specific windows, slow orders or track outages allowed to facilitate work over the railroad tracks (removal of center span and setting of center span girders Etc.)? | The Department does not secure windows for future events controlled by the contractors means and methods. | Mike Coleman | 2 | 2021-02-16 13:50 | 2021-02-17 12:04
20210309 | 20210309003 | 3 | Geotechnical Report | Can the we get a copy of the geotechnical report? | The Geotechnical Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309003/ | Mike Coleman | 3 | 2021-02-23 14:34 | 2021-02-24 08:09
20210309 | 20210309003 | 3 | Clearing & Grubbing | Please advise how the clearing and grubbing is paid for on the project in the area of embankment. Current contract has no means for clearing and grubbing. | An addendum will be issued to add the items. | Mike Coleman | 4 | 2021-03-02 14:26 | 2021-03-03 13:55
20210309 | 20210309004 | 4 | Milling and Paving Shoulder Slope | Would the DOT consider milling the shoulder at the same slope (2% typical) as the driving lanes to allow the 12' mainline and 8' shoulder to be paved in one 20' wide pass of the paver? This will be easier to construct, saving time and money, and will eliminate the longitudinal joint between drive lane and shoulder resulting in a better quality finish product. | Please bid as it is currently proposed in the plan. | Mike Coleman | 1 | 2021-02-09 11:30 | 2021-02-16 12:17
20210309 | 20210309004 | 4 | STH 23/33 Widenings and Roundabout & Ramp Paving | The HMA for the 23/33 widenings don't have enough tonnage a PWL Test Strip would the DOT change that tonnage to QMP Density eliminating 3 Test Strips? PWL Mixture use table states that turn lanes/bypass lanes are supposed to be density tested under Incentive PWL. Should those be density tested for Acceptance by the Department per the PWL spec? The HMA tonnage for the Roundabouts & is approximately 500 Tons each. Roundabouts & Ramp paving is completely different than mainline paving. Would the DOT change that tonnage to QMP Density? If the Roundabouts get changed to QMP Density would it make sense to change them to a HT (High Traffic Mix) to accommodate the constant turning actions they endure and make them QMP Density and QMP Volumetrics testing? | The HMA for the 23/33 widenings don't have enough tonnage a PWL Test Strip would the DOT change that tonnage to QMP Density eliminating 3 Test Strips? The Department will change the widening sections shown in the table to Acceptance Testing by the Department and will eliminate the 3 test strips called for specifically at the STH 23/STH 33 intersection. These changes will be reflected in an upcoming addendum. PWL Mixture use table states that turn lanes/bypass lanes are supposed to be density tested under Incentive PWL. Should those be density tested for Acceptance by the Department per the PWL spec? These will be subject to Acceptance Testing by the Department. These changes will be reflected in an upcoming addendum. The HMA tonnage for the Roundabouts & is approximately 500 Tons each. Roundabouts & Ramp paving is completely different than mainline paving. Would the DOT change that tonnage to QMP Density? If the Roundabouts get changed to QMP Density would it make sense to change them to a HT (High Traffic Mix) to accommodate the constant turning actions they endure and make them QMP Density and QMP Volumetrics testing? The Department will change the mix type called for at the roundabout to 4 HT 58-28 H between STA 565+00 and 582+00 (including the work extending up the ramps). The mix quantity at the roundabout will not be sufficient to qualify for PWL. The Department does not intend to add Item 460.2000 â€“ Incentive Density HMA Pavement to cover this relatively small quantity of pavement at the roundabout since that would also add QMP Nuclear Density requirements which could needlessly complicate the overall projectâ€™s material testing needs. The revised Mixture Use Table will indicate that the Density Acceptance at the roundabouts will be handled through Acceptance Testing by the Department and that no incentive will be included in this area. These changes will be reflected in an upcoming addendum. | Mike Coleman | 2 | 2021-02-12 14:39 | 2021-02-17 13:17
20210309 | 20210309004 | 4 | Temporary and permanent pavement markings | Good afternoon. After going through this plan, it appears some additional pavement marking items may be needed in order to safely guide the traveling public through this project during the milling and lower layer phases of the project and, additionally, it appears that a temporary epoxy item will be needed to safely guide the traveling public through the surface layer phase of the project while also serving as a guide for the sinusoidal rumble strip operations. Lastly, in regards to the permanent pavement markings, is it the department's intent to have item 228 placed immediately after the sinusoidal rumble strips? If so, would it be prudent to make that a same day marking line sinusoidal wet reflective epoxy item so ? In sticking to this same item, what is the intent for the areas that there is a break in the rumbles? Would grooved in wet reflective markings be desired or would that simply be surface applied wet reflective epoxy? Thank you. | Adjustments have been made to the plans, quantities, and specifications in response to Question #3. The materials contained within that addendum should provide the additional clarification that the prospective bidder was looking for. The addendum materials relating to this question (and also covering updates in response to Question #2) were just sent to the proposal management section. | Mike Coleman | 3 | 2021-02-19 14:52 | 2021-02-25 06:19
20210309 | 20210309004 | 4 | Stage 5 Work Timeline | Per the Prosecution & Progress section of the proposal specs Stage 5 work can not start until after August 23rd. The contract completion date for this project is October 1st. There will be a better part of 2 weeks of work to complete in stage 5 after HMA paving is complete. This means we will need to be done paving stage 5 by September 17th. Completing the milling and paving between August 24th and September 17th could get a little tight, especially if we have any weather issues. In addition there is a lot of good paving season left after September 17th. What is the reason for the October 1st completion and could it be changed to add a couple more weeks to the completion date? | An October 1, 2021 completion date was chosen based on the projectâ€™s quantities and production rates. With the roadway closed and detoured, we want operations to return to normal as soon as possible. We donâ€™t have anything in the contract that eliminates excusable weather delays, therefore if the project runs into a stretch of bad weather, normal procedures for extending the contract for weather as specified in Section 108.10.2.2 would follow. | Mike Coleman | 4 | 2021-02-24 13:33 | 2021-02-26 07:29
20210309 | 20210309004 | 4 | Construction Staking | Is the curb and gutter staking quantity right? Is there going to be any electrical staking? | We agree that the quantity shown in the EOQ summary for item 650.5500 Construction Staking Curb and Gutter is incorrect. The quantity in the Miscellaneous Quantity table is correct and matches the amount of curb and gutter proposed for the project. We also agree that item 650.8500 Construction Staking Electrical Installations should be included with this project. Both of these issues will addressed in an upcoming addendum. | Mike Coleman | 5 | 2021-03-02 10:37 | 2021-03-03 12:31
20210309 | 20210309005 | 5 | Design Files | Can the Department provide design/staking files for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309005/ | Mike Coleman | 1 | 2021-02-05 13:01 | 2021-03-02 08:38
20210309 | 20210309006 | 6 | Design Files | Can the Department provide the design files for the project (design sch., exist/prop surfaces, alignments, etc)? | The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309006/ Note: A proposed surface was not prepared for this project based on the improvement scope. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-02-09 10:04 | 2021-02-15 06:20
20210309 | 20210309006 | 6 | Mill & Relay | Will a pulverize and relay be allowed in lieu of milling and relaying line item 36? | The answer to the question will be yes, we will allow. To be fair to all bidders and get a good bidding price we will issue an addendum changing the plan detail on page 8 showing pulverize and relay as opposed to mill and relay, will update quantity sheet as well. We feel pulverize and relay will give us a better product than mill and relay. | Mike Coleman | 2 | 2021-03-01 11:22 | 2021-03-02 12:15
20210309 | 20210309008 | 8 | Turbidity Barrier Information | Addendum 1 has replaced silt fence with turbidity barrier. Please provide the streambed elevation and Q2 elevation for this new bid item. | Streambed El. = 13.5-ft Q2 El. (estimated) = 17.2-ft | Mike Coleman | 1 | 2021-02-22 10:04 | 2021-02-23 13:30
20210309 | 20210309008 | 8 | Protective Surface Treatment Reseal Limits | Please define the limits for item 14 Protective Surface Treatment Reseal. Structure plan sheet 1 under the general notes calls for the limits to be entire surface of sidewalks and curbs but SPV 13.C says for entire top surface of bridge deck, curb, median, sidewalk and inside and top faces of parapets. | Protective Surface Treatment Reseal should only be applied to the sidewalk and curb surfaces as defined in the structure plan. | Mike Coleman | 2 | 2021-03-01 11:16 | 2021-03-02 09:18
20210309 | 20210309008 | 8 | Work Start Date Conflict | SPV 3 paragraph 2 indicates that construction can occur anytime during the 2021 construction season. Addendum 1 did not remove the previously mentioned paragraph but rather added a paragraph stating that work must start no later than April 21, 2021. Please advise which spec is to be followed for start dates. | The start date should follow ADDENDUM NO. 1: The Notice to Proceed will be issued such that work shall start no later than April 21, 2021, unless otherwise approved by the engineer. | Mike Coleman | 3 | 2021-03-01 11:23 | 2021-03-01 12:29
20210309 | 20210309009 | 9 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | The contractor should use the CPCS as identified in the bidding documents. This culvert pipe is replacing an existing culvert at a private entrance and the preference is to replace in kind. | Mike Coleman | 1 | 2021-02-12 10:47 | 2021-02-16 14:00
20210309 | 20210309011 | 11 | Electronic Data Request | Please provide the following files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | I have re-uploaded the files in whole. No zip files. If you have more issues, please contact us. The requested file can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ | Mike Coleman | 1 | 2021-02-08 14:34 | 2021-02-25 06:12
20210309 | 20210309011 | 11 | Earthwork Data Sheets | Please provide earthwork data sheets for ALL temporary work listed in the miscellaneous qtys - earthwork summary stages 1,2,3,4 | Earthwork data sheets will not be supplied for temporary earthwork. As shown in the miscellaneous quantities and as stated in the special provisions, these quantities were calculated using a surface to surface comparison. | Mike Coleman | 2 | 2021-02-10 13:17 | 2021-02-17 11:55
20210309 | 20210309011 | 11 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Additionally, breaker run and subgrade improvements can be counted towards sub-grade cover when used for stabilization (FDM 13.15.9). Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV? | The use of Storm Sewer Pipe Reinforced Class IV was required due to not meeting minimum cover for Class IIIA and Class IIIB storm sewer pipe during temporary staging requirements, heavy truck loads, or for final installation. | Mike Coleman | 3 | 2021-02-12 10:49 | 2021-02-17 13:25
20210309 | 20210309011 | 11 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, there appears to be numerous runs of SSPRC Class IV that have adequate cover for Class IIIA and IIIB bid items. Will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV in areas that meet this design guidance? | The use of Storm Sewer Pipe Reinforced Class IV was required due to not meeting minimum cover for Class IIIA and Class IIIB storm sewer pipe during temporary staging requirements, heavy truck loads, or for final installation. | Mike Coleman | 4 | 2021-02-12 10:56 | 2021-02-17 13:36
20210309 | 20210309011 | 11 | Drilling Shaft Item | It is our understanding that there should be a bid item '531.2024, Drilling Shaft 24-Inch' for the ground-mounted type I signs to coincide with the bid items of '531.1100, Concrete Masonry Ancillary Structures Type NS' and '531.1140, Steel Reinforcement HS Ancillary Structures Type NS.' Is the drilling shaft bid item for these footings missing or were we misinformed? | That is correct, the drilled shaft item was inadvertently left out and will be included in future addendum. | Mike Coleman | 5 | 2021-02-12 14:38 | 2021-02-18 13:28
20210309 | 20210309011 | 11 | Removing Buildings #42 to #58 | -Please provide a legible right of way plat map in the plan. -Removal Plan does not show any of the Removing bldg's items. Please add the locations for the removing building items so they can be located. | The plans will be updated to include the building removals in an addendum. The non-reduced ROW plat can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ | Mike Coleman | 6 | 2021-02-15 11:34 | 2021-02-18 07:30
20210309 | 20210309011 | 11 | Electronic Data Request- | Can the department provide misc quantities in an electronic format? | Yes, they in 11 Excel files and are at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ | Fred Schunke | 7 | 2021-02-16 11:33 | 2021-02-22 16:05
20210309 | 20210309011 | 11 | Use of DOT Property: South side of STH 23 - STA 193+00 | Can the contractor use this DOT parcel (South side of STH 23 STA 193+00 (4.5 Acres) for: 1. Staging area? 2. Field Office location? 3. Batch Plant site? 4. Waste material? 4. Excavate or remove material? If so, please indicate if this parcel was evaluated and permitted already per Spec Section 104.8, so that the contractor doesn't have to raise there bid by a $1.50 / CY to use this material. | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis. A field survey was performed in this area and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ Surveyed areas are marked in purple and green. Previously reported archaeological sites are marked in yellow. The parcel has not been evaluated and Section 104.8 Rights in the use of material found on the project will apply. | Mike Coleman | 8 | 2021-02-17 11:59 | 2021-02-24 05:33
20210309 | 20210309011 | 11 | Use of DOT Property: South side of STH 23 - STA 225+00 | Can the contractor use this DOT parcel (South side of STH 23 STA 225+00 (38.4 Acres) for: 1. Staging area? 2. Field Office location? 3. Batch Plant site? 4. Waste material? 4. Excavate or remove material? If so, please indicate if this parcel was evaluated and permitted already per Spec Section 104.8, so that the contractor doesn't have to raise there bid by a $1.50 / CY to use this material. | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis. A field survey was performed in this area and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ Surveyed areas are marked in purple and green. Previously reported archaeological sites are marked in yellow. The parcel has not been evaluated and Section 104.8 Rights in the use of material found on the project will apply. | Mike Coleman | 9 | 2021-02-17 12:09 | 2021-02-24 05:33
20210309 | 20210309011 | 11 | Use of DOT Property: South side of STH 23 - STA 128+00 | Can the contractor use this DOT parcel (South side of STH 23 STA 128+00 (2.62 Acres) for: 1. Staging area? 2. Field Office location? 3. Batch Plant site? 4. Waste material? 4. Excavate or remove material? If so, please indicate if this parcel was evaluated and permitted already per Spec Section 104.8, so that the contractor doesn't have to raise there bid by a $1.50 / CY to use this material. | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis. A field survey was performed in this area and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ Surveyed areas are marked in purple and green. Previously reported archaeological sites are marked in yellow. The parcel has not been evaluated and Section 104.8 Rights in the use of material found on the project will apply. | Mike Coleman | 10 | 2021-02-17 12:17 | 2021-02-24 05:33
20210309 | 20210309011 | 11 | Use of DOT Property: South side of STH 23 - STA 625+00 | Can the contractor use this DOT parcel (South side of STH 23 STA 625+00 (139 Acres) for: 1. Staging area? 2. Field Office location? 3. Batch Plant site? 4. Waste material? 4. Excavate or remove material? If so, please indicate if this parcel was evaluated and permitted already per Spec Section 104.8, so that the contractor doesn't have to raise there bid by a $1.50 / CY to use this material. This property is on the other project to the east and that contractor is not using it. | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis. A field survey was performed in this area and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ Surveyed areas are marked in purple and green. Previously reported archaeological sites are marked in yellow. The parcel has not been evaluated and Section 104.8 Rights in the use of material found on the project will apply. | Mike Coleman | 11 | 2021-02-17 12:48 | 2021-02-24 05:34
20210309 | 20210309011 | 11 | Use of DOT Property: South side of STH 23 - STA 695+00 | Can the contractor use this DOT parcel (South side of STH 23 STA 695+00 (93 Acres) for: 1. Staging area? 2. Field Office location? 3. Batch Plant site? 4. Waste material? 4. Excavate or remove material? If so, please indicate if this parcel was evaluated and permitted already per Spec Section 104.8, so that the contractor doesn't have to raise there bid by a $1.50 / CY to use this material. This property is on the other project to the east and that contractor is using only the front area. Can this contractor use the back part (behind there stockpiles) for this project? | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis. A field survey was performed in this area and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/ Surveyed areas are marked in purple and green. Previously reported archaeological sites are marked in yellow. The parcel has not been evaluated and Section 104.8 Rights in the use of material found on the project will apply. | Mike Coleman | 12 | 2021-02-17 12:56 | 2021-02-24 05:34
20210309 | 20210309011 | 11 | PEDESTRIAN SIGNAL FACE & PUSH BUTTON SIGNS | Proposal line number 0784 lists Pedestrian Signal Face "12-Inch". In looking at existing intersections in the area it appears "16-Inch" Pedestrian Signal Faces are being used. Can you please confirm if 12-Inch or 16-Inch Pedestrian Signal Faces should be quoted & if Push Button Signs should be standard WISDOT 9x15 R10-3E Signs? | The Pedestrian Signal Face should be 16-Inch, not 12-inch. This will be updated via addendum. The signs shall remain as shown in the plans. | Mike Coleman | 13 | 2021-02-19 15:39 | 2021-02-23 11:00
20210309 | 20210309011 | 11 | Pedestrian Signal & Push Buttons | Should the Pedestrian Signals be 16-inch instead of the 12-inch listed? Should push button quantity be 7 instead of 6 as there appears to be one in the median on sheet 489 of the plans? | The Pedestrian Signals should be 16-Inch instead of 12 and the quantity should be 7 instead of 6. An addendum will be issued to correct this. | Mike Coleman | 14 | 2021-02-22 08:33 | 2021-02-23 11:02
20210309 | 20210309011 | 11 | Removal Plans - Removing Asphalt Surface | On the Removal plans, it says Removing Asphalt Surface (incidental to the item "Excavation Common"). This is not standard DOT practice. Removing Asphalt Surface is not Incidental to Common Excavation. In cut sections it is paid as Common Excavation. In fill sections if removed it is paid as Removing Asphaltic Surface, which is a separate pay item. Please change this to the DOT Standard Practice. | The plans/quantities were updated in addendum #1 to correct the error. | Mike Coleman | 15 | 2021-02-24 10:48 | 2021-03-01 11:49
20210309 | 20210309011 | 11 | Concrete Barrier Wall | Is the Concrete Pad under the Barrier Wall incidental to the Barrier Wall item when it is adjacent to Concrete Pavement? Is the minimum 6-inch thick Concrete Pad under the Barrier Wall incidental to the Barrier Wall item when it is adjacent to Asphalt Pavement? The SDD is unclear on the limits of Pavement and the limits of Concrete Pad and how it is paid. | The pavement under the barrier wall is paid for as concrete pavement-10 Inch. There will be a slight quantity change in addendum #2. There is no barrier wall adjacent to asphalt. | Mike Coleman | 16 | 2021-02-24 12:44 | 2021-03-01 11:50
20210309 | 20210309011 | 11 | Item # 82 - Select Borrow, 208.1100 | The current bid quantity for the select borrow item is incorrect. Per the specials & spec 208.4.4 select borrow will be measured and paid in its final position with no allowance for shrinkage. The select borrow is used for EBS and Marsh backfill and in the plans miscellaneous qty's (pg 875-877) the marsh backfill qty is expanded by 1.5 and EBS backfill qty is at 1.0 (which is correct). Marsh Backfill should also be at 1.0, which will reduce the bid qty. | The contractor is correct. We will remove the factor from the select borrow. The updated earthwork table will be included in addendum #2. | Mike Coleman | 17 | 2021-02-25 15:31 | 2021-03-03 06:05
20210309 | 20210309011 | 11 | Parcel 40 | Where / what is Item # 58 204.0235 Removing Buildings Parcel 40? Parcel 40 is not shown in the right of way plat? | This property was purchased under a different project plat. It is shown on Sheet 85 of the plat, but without a parcel number. It is located at the corner of CTH UU and STH 23 in the SW quadrant. N6672 CTH UU. It is the Ledgeview Precast Concrete building. The removal plans will be updated to shade the building location a plat sheet showing the location and the building shaded will be added to the details as well. | Mike Coleman | 18 | 2021-03-01 10:01 | 2021-03-01 12:18
20210309 | 20210309011 | 11 | 9-Inch and 10-Inch Concrete Quantities | Please check and confirm the quantities for 9-Inch and 10-Inch concrete pavement items. The plan details Sheets 149-174 call out Pave 4 which is not shown in the legend on sheet 97. The Miscellaneous quantities have different station ranges for 9 and 10 inch concrete than the plan details. | The legend will be updated and quantity verified in addendum #2. PAVE-4 is concrete pavement 9-inch. | Mike Coleman | 19 | 2021-03-01 15:33 | 2021-03-02 12:55
20210309 | 20210309011 | 11 | Pond at UU | The earthwork table refers to a pond at UU. Where is the the pond located? It's not apparent in the plans. | The CTH UU Pond is the location shown on sheet 299. This will be made clear in addendum #2. | Mike Coleman | 20 | 2021-03-01 16:54 | 2021-03-02 13:47
20210309 | 20210309011 | 11 | 6'x6' Manhole | Where do i find the rim and invert elevation for the 6'X 6' manhole. I can not locate it on the plan. | the rim and invert elevations for the 6â€™X6â€™ manhole is in the Miscellaneous Quantity sheets, page 957. Rim elevation 997.90 Invert elevation 990.93 | Mike Coleman | 21 | 2021-03-02 09:48 | 2021-03-02 12:16
20210309 | 20210309011 | 11 | Marsh Ex & Select Borrow Backfill STA 337+00 - 353+00 | Why does the Select Borrow backfill show filling the marsh all the way up the 1:1 slope of the existing roadway. This seems like a waste of Select Borrow. It should only be 1 foot above the existing ground at the bottom of the cross section. The top of the Select Borrow should be level, not going up the 1:1 slope. The area above the level select borrow in the 1:1 Slope should be normal Embankment. | The select borrow for backfill is incorrect in this location. As the contractor noted, the top of the select borrow should not follow the 1:1 slope. The quantities will be corrected to Embankment. | Mike Coleman | 22 | 2021-03-03 08:25 | 2021-03-03 17:49
20210309 | 20210309011 | 11 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch, Breaker Run and Select Crushed? | Conversion factors requested: 2.1 Tons/CY for 3/4-Inch BAD 2 Tons/CY for 1 1/4-Inch BAD 1.75 Tons/CY for Breaker Run 1.9 Tons/CY for Select Crushed Material | Mike Coleman | 23 | 2021-03-03 08:27 | 2021-03-03 13:54
20210309 | 20210309011 | 11 | USH 151 Southbound Off Ramp | Could the department please provide a schedule on how they came up with a 10 calendar day schedule for the USH 151 SB offramp work? With grading, aggregates, electrical, curb and gutter, sidewalk, multiple concrete pavement pours, asphalt, restoration, and pavement markings, it seems unrealistic to get it done in 10 calendar days, especially without any high early concrete items such as pavement or curb and gutter. | The 10-calendar day was intended for the trail to be opened. Addenda #2 revised the time frame to 14 days for the ramp work. | Mike Coleman | 24 | 2021-03-03 08:54 | 2021-03-04 14:33
20210309 | 20210309011 | 11 | 38. Salvaged Topsoil, Item 625.0500. | This article reads, "Excavate topsoil up to one foot in depth, with no additional compensation, to produce sufficient volumes to cover the designated salvaged topsoil or topsoil areas to the depths required." Based on takeoffs of the available topsoil in the road excavation areas, all the topsoil material within the proposed roadway foundation in the fill sections in not need for Salvage Topsoil, there for all the Topsoil in the fill sections should be paid as EBS. (so the article in the specials is incorrect) If this is found to be true during construction, none of the topsoil in the fill sections is need for Salvage Topsoil, will the department pay for this topsoil removal as EBS, like the standard specifications state? | The intent of the article is to identify that excess salvaged topsoil will not be compensated for until greater than one foot of topsoil is excavated. As usual, excess topsoil should be utilized within the project limits or disposed of according to 205.3.12. | Mike Coleman | 25 | 2021-03-03 09:21 | 2021-03-04 14:32
20210309 | 20210309011 | 11 | Please Confirm | What would be the requirements to access DOT owned property (+/- 621+00 to 648+00 & 690+00 to 704+00, both south of STH 23)? The property mentioned above is located on the current state project 1440-15-72/73 and is being utilized by the prime contractor of 1440-15-72/73. Will the prime contractor of project 1440-15-72/73 be required to provide access to the sites from their work zone? | Per Article 3 â€“ Prosecution and Progress of this proposal STH 23 Right-of-Way Available for Construction Activities The contractor shall not perform construction activities nor store equipment nor materials on STH 23 right-of-way that is more than 20 feet beyond the grading limits indicated in the plan, unless approved by the engineer. Use of any areas outside these limits, for any reason, will be evaluated on a case by case basis Access to and from sites located in the limits of project 1440-15-72/73 will need to be coordinated with the prime contractor of that project. | Mike Coleman | 26 | 2021-03-04 07:19 | 2021-03-04 14:30
20210309 | 20210309011 | 11 | ftp site access | The ftp site (ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309011/) asks for a username and password to access the site. What is the username and password to access this ftp site? | We are aware of the issue. There is a checkbox on the login screen that says log in anonymously. Check that box and you will be able to get in as normal. Our IT people are trying to fix it now. | Mike Coleman | 27 | 2021-03-04 11:58 | 2021-03-04 12:06
20210309 | 20210309011 | 11 | Earthwork Summary - EBS Backfill Qty | On Sheet 876 the earthwork summary, Division = STH 23 WB 250+00+06.92/384+00, EBS Excavation equals 5,408 CY and EBS Backfill equals 31,050 CY. Why is the Backfill over 5 times the quantity of EBS excavation? | Quantities shown are correct. The areas paid for as EBS occur in areas that are greater than additional 1 foot of Salvaged Topsoil Removal (Article 38). With the additional 1 foot of fill above existing ground the additional backfill required can be as much as 6 times the amount of EBS excavation. Plan and profile sheets 1174-1176 cross section sheets 1924-1926, 1928-1928,1933-1934,1941-1945. | Mike Coleman | 28 | 2021-03-04 15:41 | 2021-03-08 08:27
20210309 | 20210309011 | 11 | 9-Inch Concrete Pavement | After reviewing addendum 2, I still find a discrepancy of 4800 SY in the 9-inch Concrete Pavement item. Are the turn lanes and intersections concrete or HMA? | 9-INCH Concrete pavement includes the turn lanes and intersections. Approximately 4,896 SY of 9-Inch Concrete is in the turn lanes and intersections adjacent to 9-inch concrete pavement. | Mike Coleman | 29 | 2021-03-04 16:46 | 2021-03-05 08:09
20210309 | 20210309011 | 11 | 9-Inch Concrete Pavement Quantity | The plan quantity is incorrect. The plans show 9-Inch Conc Pavement from STA 250+00 to STA 384+00 which is 13,400 LF and the road is 26 feet wide. 13,400x26 = 348,400 SF / 9 SF/SY = 38,711 SY. This is before the +/- 4900 SY of turn lanes and intersections are added. If the stationing in the misc. quantities is used (STA 254+04 to 384+00) there would be 12,996 LF x 26 Ft Wide, = 37,544 SY plus the turn lanes and intersections. Please confirm your quantities for 9-inch pavement as previously requested. | An emergency addendum has been issued to correct this. | Mike Coleman | 30 | 2021-03-05 08:33 | 2021-03-08 08:23
20210309 | 20210309012 | 12 | Temporary Barrier | The Temporary Barrier delivered and installed numbers don't seem to add up. If you need an additional 238 lf delivered in stage 2, wouldn't your total installed be 1756 lf? | The quantity of temp barrier delivered and installed that is shown in the plan/MQs is correct. The additional 238LF of delivered for stage 2 accounts for the assumed trucking needed for the taper sections, as well as the additional 22LF increase from stage 1B to stage 2. | Mike Coleman | 1 | 2021-03-02 10:57 | 2021-03-03 06:05
20210309 | 20210309013 | 13 | Schedule | Could you please provide the DOTâ€™s construction schedule for this job? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309013/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-02-19 13:55 | 2021-02-26 07:27
20210309 | 20210309013 | 13 | Prep of foundation for asphaltic shoulders | From STA 132+50 to STA 527+40, is it the departments intention to have the 2â€™ widening of the existing base aggregate shoulder, removed and hauled off site? | The department intends to utilize existing excavated shoulder material to shape remaining aggregate shoulders per standard spec 211. Payment for using excavated base to shape remaining aggregate shoulders is covered under the item of 211.0400 â€“ Prepare Foundation for Asphaltic Shoulders, see 211.3.5.1(2). Payment for incorporating or disposing of surplus or unsuitable material is covered under the item of 211.0400 â€“ Prepare Foundation for Asphaltic Shoulders, see 211.3.6. The department will issue an addendum to reduce the quantity of item 305.0110 â€“ Base Aggregate Dense ï¿½-Inch. | Mike Coleman | 2 | 2021-03-02 09:52 | 2021-03-03 06:06
20210309 | 20210309013 | 13 | Special Provisions Clarification | Page 3 of special, paragraph 1 reads the following. All traffic operations for milling, paving, frost heave reconstruction, culvert replacement, and shouldering will be done utilizing one lane, two-way traffic control using flagging operations. HMA pavement shall be placed by 3:00 PM of each work week. Base aggregate surface will not be allowed on Saturdays and Sundays. Contractor is asking for clarification on the sentence, â€˜HMA pavement shall be placed by 3:00 PM of each work week.â€™ | Clarification of paragraph 3 of Article 4 â€“ Traffic of the special provisions. The departmentâ€™s intention on noting that HMA pavement shall be placed by 3:00 PM of each work week is limited to the aggregate patches. Base aggregate surfaces will not be allowed on Saturdays/Sundays. Other work operations, such as mainline milling/paving may occur after 3:00PM on Fridays and/or on the weekends. | Mike Coleman | 3 | 2021-03-05 10:42 | 2021-03-08 08:22
20210309 | 20210309015 | 15 | Design Schedule | Could The Department Please Provide The Design Schedule For This Project. Thank You. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309015/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-02-10 12:05 | 2021-02-16 11:53
20210309 | 20210309015 | 15 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | This is a local program project. The Town prefers to utilize RCP as shown on the plans. The minimum cover heights in many areas require concrete pipe, as well as matching into existing RCP pipe outfalls. Also, many pipes are larger than 36 inches in diameter and require concrete pipe. Finally, there is also a significant amount of undistributed EBS that would reduce the cover over the pipes during construction. Given these variables, the Town prefers to utilize RCP throughout the project. | Mike Coleman | 2 | 2021-02-12 10:58 | 2021-02-18 05:52
20210309 | 20210309015 | 15 | Holiday Work Restrictions | Are there Holiday Work Restrictions on this project ?? I am assuming this was just missed ?? | There will be Holiday Work Restrictions on this project. An addendum will be prepared for this at a later date. | Mike Coleman | 3 | 2021-02-15 08:47 | 2021-02-17 05:57
20210309 | 20210309015 | 15 | Misc Quantities | Is it possible to get the misc. quantities and earthwork data in excel format? | Sorry, the miscellaneous quantities and earthwork data are not available in excel format. | Mike Coleman | 4 | 2021-02-16 11:29 | 2021-02-17 05:56
20210309 | 20210309015 | 15 | Excavation Management Plan | Is there an Excavation Management Plan that can be posted? | The Phase 2.5 Site Investigation Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309015/ | Mike Coleman | 5 | 2021-02-16 11:40 | 2021-02-16 11:56
20210309 | 20210309015 | 15 | Geotechnical Report | Is there a geotechnical report that contains information on existing asphalt thickness and concrete thicknesses? | The Geotechnical Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309015/ | Mike Coleman | 6 | 2021-02-16 11:42 | 2021-02-16 11:57
20210309 | 20210309015 | 15 | Digital Files | Are there any digital design files that can be provided? | Per FDM 19-10-43.1.1 Digital Data Exchange and Project Data Awareness procedure requirements apply only to projects on the state trunk highway system. No digital design files for local program projects are created or submitted at PS&E time. The successful bidder may be able to request digital files from the designer following contract execution. | Mike Coleman | 7 | 2021-02-16 14:42 | 2021-02-17 11:43
20210309 | 20210309015 | 15 | Base Course under Sidewalks | Was the quantity for base course under the sidewalks based on the typical section width of 5' wide....the same width as the sidewalk ?? If so, is this what is going to be paid for ? The width should be at least 1' wider (6" on each side), a total of 6' wide, to allow for the placement of forms. | The limits of sidewalk base course are to be paid as shown on the plans. Means and methods for base installation and form setting for concrete sidewalk are for the contractor to determine. | Mike Coleman | 8 | 2021-02-22 14:31 | 2021-02-23 13:28
20210309 | 20210309015 | 15 | SPV.0105.02 Management of Contaminated Groundwater | Can the unit of measurement and payment for Management of Contaminated Groundwater be changed to a Ton or Gallon, as it is really difficult to estimate the amount of water to be managed during bidding process, and it would be fair to the contractor and department, if the item is measured and paid for the actual amount of work performed. | No change to the unit of measure will be made from what is currently in the contract special provisions. | Mike Coleman | 9 | 2021-03-02 16:31 | 2021-03-03 17:51
20210309 | 20210309017 | 17 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB culverts shall be used at every opportunity possible, up to 20,000 design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culverts Class IIIA and/or IIIB in lieu of the sole specified CPRC IV? | The local municipality was consulted, and they agreed to the use of Class III-A Non-Metal culvert pipe in place of reinforced concrete culvert pipe. An addendum will be issued for this change. | Mike Coleman | 1 | 2021-02-12 11:02 | 2021-02-18 08:18
20210309 | 20210309017 | 17 | Contract Time | This slab deck has an existing steel truss removal on large concrete abutments, cofferdam and preboring. 45 WD's is too light to get this work done without excessive overtime. Can additional contract time be added? |  |  | 2 | 2021-03-05 11:00
20210309 | 20210309017 | 17 | Pier cofferdam | Sorry for the late question. Based on the borings, the pier will nearly be on bedrock and a traditional sheet pile cofferdam will likely be impossible to construct. We can work around this, but it will likely require additional quantities of turbidity barrier. If a proper seal cannot be obtained due to the close proximity of bedrock, will the Department cover the additional turbidity barrier costs to encapsulate the cofferdam? |  |  | 3 | 2021-03-08 12:09
20210309 | 20210309018 | 18 | Detour | No detour plan sheets seem to be included with this plan, the route is stated but no plan sheets. | An addendum will be sent out to add the missing sheets. | Mike Coleman | 1 | 2021-02-22 11:33 | 2021-02-23 10:58
20210309 | 20210309018 | 18 | TC sign days | Are the sign days quantity staying the same as in the plan or will they be changed with the detour plan being supplied now? | The quantities are staying the same. We only forgot to add the sheet for the detour. | Mike Coleman | 2 | 2021-03-02 15:19 | 2021-03-03 09:53
20210309 | 20210309019 | 19 | Base Patching Item | There is an item for Base Patching, 390.0103, within the pulverize and relay section of CTH B, STA 33+62 to 55+14. There is no construction detail provided to show how this item will be used. The existing typical section for this area shows an existing 4â€ Asphalt Pavement over 7â€ of Base Course Material; there is no concrete shown in the typicals that would be indicative of requiring Base Patching. Could DOT please provide a detail of how this item is intended to be used? If base patching is required, would the Department allow the contractor to use 3LT or 4LT HMA that is already supplied to the project, instead of the 1-inch nominal aggregate size mixture as specified in 315.2? | The item will be removed via addendum | Mike Coleman | 1 | 2021-02-23 09:48 | 2021-02-26 10:21
20210309 | 20210309020 | 20 | Pier excavation | Boring #2 shows bedrock elevation at 1351.5, which is higher than the pier bottom elevation of 1350.53. If these conditions hold true during construction, will the Department keep the preboring minimums in place and simply shorten the pier (i.e. raising the the excavation level to bedrock) or will the contractor be required to perform rock excavation in the middle of the waterway? Would such rock excavation be compensable? | If bedrock is encountered above the bottom of pier elevation shown in the plan (1350.83), the pier can be shortened to the bedrock elevation. The minimum of 10 feet of preboring below the new bottom of pier elevation would apply. | Mike Coleman | 1 | 2021-03-03 16:39 | 2021-03-05 08:10
20210309 | 20210309020 | 20 | Contract Time | This project requires preboring at each substructure unit and a solid shaft pier. This work coupled with cure times, 45 wd's is light on contract time. Can additional contract time be added? |  |  | 2 | 2021-03-05 11:03
20210309 | 20210309021 | 21 | Modular Expansion Joint item Special | Good Morning! Would the Department consider permitting a steel manufacturer from the steel component approved list to fabricate the plate(s) that need to be fabricated? From what I can discern, the Modular Expansion Device is completely untouched- it is just the plates that are attached to the parapet & wing that are required. A firm like Commercial Fabricators, Aura, USSI, or others would be able to fabricate the plate. There are 3 manufacturers listed in the specials, but two of them will not quote the project (one said it is too small, the other doesn't make that type of product). The third, is a large firm in NY that recommended we source the item locally. (PS: The phone number listed for R.J. Watson is a private residence. The correct number is 716-901-7020, although they only make finger joints) Please advise if you would permit other fabricators to fabricate and galvanize the required steel plate. Thank you! | BOS has no concerns with allowing a fabricator from our â€œFabricated Bridge Componentâ€ lists to provide the plates in question. Also, we will look into the issue raised regarding the phone number listed in the APL for R.J. Watson. | Mike Coleman | 1 | 2021-03-03 08:55 | 2021-03-03 12:28
20210309 | 20210309021 | 21 | Conduit | Is there a cable inside the conduit that will need to be addressed or is it empty? | The plans call for this conduit to be capped off at the end of the wing. Based on photographs from the field, this conduit appears to be empty. | Mike Coleman | 2 | 2021-03-05 10:13 | 2021-03-08 09:29
20210309 | 20210309023 | 23 | project schedule seems overly aggressive | In adding up the time to remove 2 separate structures, drive temp shoring, pre-boring, and cure times for abutments, bridge deck, approach slabs, curb & gutter, concrete paving, plus install guardrail and asphaltic paving, 40 days seems a CRAZY short period of time. Given the nature of the removal, we would burn up 30-40 days just to get the bridge built (not stripped) and then add for approach slabs, dirt work, curb & gutter and cure time so the guardrail doesn't break it up). We suggest something closer to 60 days for contract time. Please advise. | Addendum #01 has been issued that changes the contract completion time from 40 working days to 60 working days. | Mike Coleman | 1 | 2021-03-02 19:15 | 2021-03-03 12:27
20210309 | 20210309023 | 23 | #5 stirrup spacing | The spacing for the #5 stirrups in structure B-18-237 note a 5" leg with 4.25" spacing which will created a very congested area. Is this the design intent? | We reviewed the design computations and it is the design intent to us the stirrup sizes shown. | Mike Coleman | 2 | 2021-03-04 10:59 | 2021-03-04 14:29
20210309 | 20210309023 | 23 | Temporay Shoring / Utility Conflict | The proposal states that OH work is to stay clear 15' from the OH line but the plan shows the temporary shoring being installed directly under the OH line. For the temporary shoring to be installed the OH line needs to be relocated for installation and removal, can the OH line be relocated? | The lower distribution lines are being shifted to the west. The upper transmission lines are to remain in place. Language related to temporary outages was inadvertently not included with the specials. If the contractor does not feel they are able to adhere to the OSHA minimum working clearances while working in the vicinity of the energized 69kV transmission lines and needs to have the lines taken out of service, they will need to a 30 day minimum notice to Xcel Energy. Outage approval is contingent on the power demand in the area during the proposed time period. | Mike Coleman | 3 | 2021-03-05 12:45 | 2021-03-08 11:27
20210309 | 20210309024 | 24 | prosecution and progress | The prosecution and progress article states that HMA paving shall commence within 7 calendar days of commencement of pulverize and relay. Can this be adjusted to reflect the need for a cure period after completion of stabilized base reclamation and start of HMA paving? Most projects we see require a 7 day curing period from completion of stabilized base to start of HMA paving. | Yes, the Prosecution and Progress can be adjusted to allow more time for the stabilized base to cure. An addenda will be issued to require HMA paving to commence within 10 calendar days of commencement of pulverize and relay. | Mike Coleman | 1 | 2021-02-17 15:58 | 2021-02-19 06:49
20210309 | 20210309024 | 24 | pulverize and relay | The pulverize and relay special provisions on this project state that the existing shoulders are to be removed concurrently with reclamation and only within the same lane closure established for reclamation, removing no more shoulder than can be backfilled within a dayâ€™s production. 2 Questions: 1. Can the shoulder excavation be completed separately ahead of the pulverize and relay? Tying the two operations into a single work zone will slow operations significantly. The shoulder could be removed and a gravel fillet installed with barrels to protect the drop-off 2. Can the excavation common bid item quantity be adjusted to include the shoulder excavation work on this project? Therefore, removing that work from being an incidental within the pulverize and relay item as shoulder excavation is unrelated to pulverize and relay. | 1. Yes, the shoulder excavation may be completed separately ahead of the pulverize and relay. An addendum will be issued to allow shoulder removal prior to and during reclamation and without requiring use of the same work zone. For traffic safety, the addendum will also require that shoulders be backfilled within 48 hours of removal. 2. No, the incidental shoulder removal as shown on the plans will remain incidental to pulverize and relay. The removal limits and dimensions are shown on the Typical Sections. Using excess pulverized base in the new shoulders is closely dependent upon removing the adjacent old soils and vegetation above the subgrade. | Mike Coleman | 2 | 2021-02-17 15:59 | 2021-02-19 06:50
20210309 | 20210309024 | 24 | Temporary and same day pavement markings | Good morning. Being that CTH D is open to traffic for the duration of the project, what is the plan for pavement markings on the milled/pulverized layer and the lower layer? In addition, should the center line permanent markings on the surface be changed to same day epoxy so that they are placed on the same day as the upper layer is placed? Will an addendum be issued to address these markings? Thank you. | An addenda will not be issued to add these items. | Mike Coleman | 3 | 2021-02-25 06:16 | 2021-02-26 07:30
20210309 | 20210309027 | 27 | Geotechnical Reports | Can you post a copy of the Geotech reports? | The Geotech Reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210309027/ | Mike Coleman | 1 | 2021-02-11 13:27 | 2021-02-11 13:32
20210309 | 20210309027 | 27 | Landscape Surveillance | The misc quantities show a quantity of 10 cycles for two of the project ID's. Does this mean there is only one season of surveillance for each project ID? | Depending on when the trees are planted will dictate when the Landscape Planting Surveillance and Care Cycles are used. The typical growing period for the trees is between May 15 and October 15. If the trees are planted early in the summer then it is assumed that the 10 care cycles would be completed in 2021. If the trees are planted in the fall (which is most likely), then the 10 care cycles would not be able to be completed by October 15 and would be extended to the next summer. Also as specified in 632.3.18.1.3 if planted in the fall, the plant establishment period is extended until Oct 15 of the succeeding year. | Mike Coleman | 2 | 2021-03-01 08:54 | 2021-03-02 09:53
20210309 | 20210309031 | 31 | Traffic Signal Face 3 Section - Quantity | Line 0230 for Traffic Signal Face 3S 12-inch lists quantity of 4, but in the plans (sheet 79) it calls for signal heads 19, 9, 10, 24, & 25 which totals 5. Is the total of 5 traffic signal faces for the 3 section in the plans correct? | An addendum will be issued to clarify. | Mike Coleman | 1 | 2021-02-23 08:39 | 2021-02-25 06:13
20210309 | 20210309033 | 33 | Concrete Surface Drain | 1. The concrete surface drains are shown at Stations 12+19.5 and 12+24.5 on the plan sheet. The low point of the profile is located near Station 12+53. Will they need to be relocated? 2. The title sheet shows a 30 mph design speed. But the north approach has a proposed sag vertical curve that is less than 25 mph. Will this create a noticeable dip in the ride for the traveling public when the project is completed? | 1. No, the concrete surface drains cannot be moved further to the north because spacing of posts for the thrie beam transition do not allow enough width for a surface drain to be built between them. The profile is very flat in this area and there is only 0.01â€™ of elevation difference between the low point and the surface drain locations. The purpose of these surface drains is to catch the concentrated flow off the bridge gutter. Stormwater that falls outside the parapet/curb will drain off the roadway as sheet flow due to the crowned pavement. 2. The design speed should actually be shown as 25 mph per the approved Design Study Report for this project. For bridge replacement projects on local roads, approach work is limited and profile correction is not within the scope of the work. The proposed profile was established to match the existing profile as closely as possible, so ride of the newly constructed roadway will not change noticeably compared to the ride of the existing roadway. | Mike Coleman | 1 | 2021-02-10 12:24 | 2021-02-11 13:16
20210309 | 20210309035 | 35 | Proposal Line Number 0046 | Good afternoon, in looking at this project, it appears that bid item 0046 in the proposal should actually be a same day epoxy item rather than a same day paint item. On sheet 11 of the plan set, miscellaneous quantities, under the pavement marking items, these quantities are listed as same day epoxy which makes sense based on similar projects. Will an addendum be issue to rectify this discrepancy? Thank you. | This has been addressed in Addendum #02. | Mike Coleman | 1 | 2021-02-19 13:52 | 2021-03-03 06:03
20210309 | 20210309036 | 36 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB culverts shall be used at every opportunity possible, up to 20,000 design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA culvert pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culverts Class IIIA and/or IIIB in lieu of the sole specified CPRC IV? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-02-12 11:04 | 2021-02-19 06:45
20210309 | 20210309036 | 36 | Culvert Pipe Material | The following culvert runs have pipe sections with less than 2' of cover. Station Pipe Size <2' of Cover (Top of Subgrade) 361+40 30" 10 LF 343+65 30" 14 LF 330+48 24" 25 lf 318+92 18" 47 lf 307+89 24" 16 lf 304+36 24" 8 lf 301+45 24" 16 lf 289+38 24" 14 lf 285+55 24" 20 lf 240+99 24" 12 lf 236+02 24" 12 lf 230+29 24" 14 lf As per Table 17.1 Storm Sewer Materials Selection Criteria for Class III-A and Class III-B requires minimum fill height of 2 ft from top of subgrade. Also, as per Chapter 13 note, "Designers are not expected, for example, to change materials back and forth between manholes as fill heights change, or call out a few individual short runs of Class III-A or B pipe on a site where it otherwise doesnâ€™t fit the conditions." Should all those runs be specified as a CRCP IV since they do not meet the definition of a Class III-A or Class III-B, or is addendum 1 an exception to the requirement? Thank you | An addendum will be issued to clarify | Mike Coleman | 2 | 2021-02-22 15:19 | 2021-02-24 13:00
20210309 | 20210309036 | 36 | Road Closures | The Traffic SPV references maintaining access to residents/businesses and a two day notice for access closures. Are we allowed to close USH 12 as long as access is maintained from one direction if needed. One example would be the box culvert/pipe replacement at station 155+61. |  |  | 3 | 2021-03-04 09:58