## qandasearchletting_results
Date: | 2021-11-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20211109 | 20211109001 | 1 | 1074-00-71 WI-27 Detour | Regarding project 1074-00-71, WI-27, the special provisions and miscellaneous quantities reference a detour for the WI-27 closure, however it appears that the plan sheets for the detour have been omitted from the plan. Please address the details for the detour route and necessary signs. Thanks | An addendum will be submitted to add the missing plan sheets. | Mike Coleman | 1 | 2021-10-15 16:49 | 2021-10-19 11:38
20211109 | 20211109002 | 2 | Meta Data | Can the Department provide the meta data files for this project as well as any geotechnical report? | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 1 | 2021-10-05 16:42 | 2021-10-06 07:50
20211109 | 20211109002 | 2 | Geotechnical Report | Is there a Geotechnical Report for this project? | The Geotech Report can be found at the following location: https://wisdot.box.com/s/3t2hck0rcui48z0qkorh89gdomdhl5oe or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2021-10-13 05:28 | 2021-10-19 10:54
20211109 | 20211109002 | 2 | Lane Closures | In stage 1A can the single lane closure remain up continuously (24/7) or does it have to be pulled back at the end of each shift/day? | The stage 1A single lane closure can remain up continuously until that work is sufficiently completed and as permitted by the engineer. | Fred Schunke | 3 | 2021-11-03 16:32 | 2021-11-04 13:48
20211109 | 20211109003 | 3 | Design Schedule | Would the Department be willing to share the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/3zfa6wl59pc2imw66lieat1j5t1o9sdm or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-10-07 12:57 | 2021-10-12 10:57
20211109 | 20211109003 | 3 | 48 hour exposed milled surface from STH 146 to Columbus | Due to construction operations including milling, distressed milling, and paving operations as well as having the area detoured, would the department allow 72 hours of exposed milled surface in this area? | The project team reviewed the question and decided to keep the current Special Provision requirement of paving lower HMA lift within 48 hours of milling operations east of STH 146 (i.e. STH 146 to Columbus). | Mike Coleman | 2 | 2021-10-29 17:06 | 2021-11-03 06:43
20211109 | 20211109003 | 3 | B-11-172 Preboring Quantity | The plan quantity for preboring only allows for 3' of predrilling for each pile location at each abutment. From B/Abutment to Pile tip at north abutment it is +/- 20' From B/Abutment to pile tip at south abutment is is +/- 20.5' This would produce a total quantity of 283.5 LF. Is this a quantity error, or is the intent only to pay for the rock socket for the pre-boring pay item? The "rock socket" can't be drilled without drilling through the overlying overburden first. | The pre-boring requirements only pertain to the 2 piers, not the abutments (the HP abutment piles are to be driven with pile points per the plans) Regarding the pre-boring LF quantities for the piers, the quantities should have included the overburden in addition to the 3 feet into rock for each pile. I will be sending out an addendum this morning to address the changes to the pre-boring quantities. | Fred Schunke | 3 | 2021-11-03 08:44 | 2021-11-04 13:34
20211109 | 20211109005 | 5 | Turbidity Barrier Design | Current FDM guidance for t-barrier states, "Turbidity barriers are not recommended where currents exceed 5 ft/second. If currents exceed these limits, other measures should be considered to divert the water away from the area being worked on or disturbed. This may be accomplished by using diverters such as portable cofferdams, sheet piling, or jersey barrier." The bridge design for this waterway during construction shows the Q2 very close to this limit, while the temporary structure area exceeds this limit. Will the Department consider using the alternate diverters for bid items on this project instead of calling for t-barrier? | Having spoken with the design team, we understand that flows are very seasonal and that we can not say for certain what field conditions will be. We are fine with using alternate diverters if that is what field conditions dictate, understanding that all of these options will still need to go through the ECIP process. | Mike Coleman | 1 | 2021-10-15 10:57 | 2021-10-19 10:41
20211109 | 20211109006 | 6 | Girder Spacing | For estimating steel diaphragm replacement, there are no dimensions provided for center of girder to center of girder. | The existing girders in span 2 (where new diaphragms are required) of B-11-30 are spaced at 3â€™-10 ï¿½â€ according to the existing structure plans. In span 1, the spacing is 7â€™-9â€, if for some reason that dimension is needed. | Mike Coleman | 1 | 2021-10-15 09:47 | 2021-10-25 13:11
20211109 | 20211109006 | 6 | Removing Guardrail and Salvaging Guardrail | Both of these are removal bid items. The salvaged item is to stockpile and save reusable material. Is this an optional bid item to be determined at the time of removal? | This is an optional bid item. It was included with the assumption that more space would be needed for a crane to be positioned in the median for lifting girders. The guardrail is to be restored after the cranes are no longer needed. | Mike Coleman | 2 | 2021-10-15 11:03 | 2021-10-18 13:12
20211109 | 20211109006 | 6 | Removal/Traffic Control | For the traveling public safety, given the integrity of the prestress girder and its stability when the deck is removed, would WI DOT detour IH-90/94 EB for 6 to 8 hours during the removal of the deck and girder. | IH 90/94 will not be detoured. The traffic control plan is to utilize lane closures to do the overhead work and then use a rolling stop to remove the girder. It is a similar scenario for placing the new girder as well. | Mike Coleman | 3 | 2021-10-19 13:45 | 2021-10-20 11:41
20211109 | 20211109006 | 6 | Closure STH 33 | Would it be acceptable to temporarily close STH 33 during night hours for girder erection? |  |  | 4 | 2021-11-08 13:39
20211109 | 20211109007 | 7 | Designer schedule | It doesn't appear the designer schedule is located in the data folder. Could that please be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/8bcmkngby3bf6jzj6jsgz4xkcd6wrh7r or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-10-14 07:29 | 2021-10-18 09:50
20211109 | 20211109007 | 7 | jack and bore launch pit | The Plans show the jack and bore launch pit dimensions 10'wide x 20' long. A standard pit would be a minimum of 38' long to accommodate the installation of 20' casing pipe. To install 10' casing pipe would require a minimum 28' long pit and would increase the price of the work significantly. Can the launch pit be extended in either direction? | The dimensions shown in the plans for the jack and bore launch pit were approximated based on project constraints, which primarily includes traffic control (proximity of live traffic to the south within the intersection) and proximity to the railroad crossing to the north and its associated live loads. It was understood that the pit sizes may be less than typical. It is expected that the contractor will determine the actual pit size within the constraints of the project. See subsection 107.17 of the standard spec for requirements related to the proximity of the railroad crossing. | Mike Coleman | 2 | 2021-10-14 08:40 | 2021-10-18 10:02
20211109 | 20211109007 | 7 | Quantity of signal heads | Proposal line number 0550 shows a qty of 17 3-section heads & 0552 shows a qty of 4 4-section heads. The traffic signal plan, sheet 58 shows a qty of 15 3-section heads & 6 4-section heads. Can you please confirm which is correct? | The traffic signal plan sheet is correct. An addendum will be issued to revise the signal head and backplate quantities. | Mike Coleman | 3 | 2021-10-19 14:55 | 2021-10-22 07:40
20211109 | 20211109007 | 7 | Geotech Report | Is there a geotechnical report available for this bid? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/8bcmkngby3bf6jzj6jsgz4xkcd6wrh7r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 4 | 2021-10-21 13:59 | 2021-10-25 08:04
20211109 | 20211109008 | 8 | Shaping Shoulders & Prep Foundation for Asphaltic Surface | Would the Department be willing to add a prep foundation for asphaltic paving as well as a shaping shoulders item to this contract? The existing shoulders will need to be cut out as well as pulled up prior to paving and finish shouldering. | No. Final grading of the shoulders and any shoulder aggregate prep work is covered with the Base Aggregate Dense ï¿½-Inch bid item. | Mike Coleman | 1 | 2021-10-21 15:36 | 2021-10-25 08:36
20211109 | 20211109008 | 8 | Flagging Operations | Does the 1.5 mile flagging zone and 2 mile separation between zones apply to the coring crew? Considering this is a core only pilot project and cores are to be taken the next day, these restrictions pose issues performing both milling/paving operations as well as cutting cores. | Yes, the 1.5 mile flagging zone does apply to the coring crew, but an addendum will be submitted to revise the length of the flagging zone to 2.0 miles. An addendum will be issued to clarify. | Mike Coleman | 2 | 2021-10-27 07:35 | 2021-10-28 07:09
20211109 | 20211109008 | 8 | Response to Flagging Operations Answer | In response to the answer to question (2) on job #8, the line "Per the spec, the cores need to be completed the same day as the paving, prior to being opened to traffic" contradicts section 460.3.3.2.2 (2) in the proposal stating "Cores will be cut by the next working day not to exceed 48 hours after placement." Please advise Thanks | The department had a meeting with Bureau of Technical Services about the core pilot project, and the spec language about taking the cores before opening to traffic was referencing the PWL Test Strip language and does not apply to the cores the contractor was asking about. The contractor is correct that the "Cores will be cut by the next working day not to exceed 48 hours after placement." An addendum will be issued to clarify. | Mike Coleman | 3 | 2021-10-28 10:45 | 2021-10-29 06:50
20211109 | 20211109008 | 8 | Paving Intersections | Are intersections exempt from same day mill and pave? | No, the intersections are not exempt from the same day mill and pave. | Jill Fehrman | 4 | 2021-11-02 12:02 | 2021-11-04 07:33
20211109 | 20211109009 | 9 | Contractor Data Package | It appears this existing surface is damaged File Name: "12290476-Surf-Ex-Bonniewell-to-STH-60.xml". Its only 1 KB. Please provide another file. | The contractor data package has been restored and have an updated 12290476-Surf-Ex-Bonniewell-to-STH-60.xml. Sorry for the confusion. | Mike Coleman | 1 | 2021-10-11 10:28 | 2021-10-12 06:48
20211109 | 20211109009 | 9 | Abandoning Wells | Is there any information available for the depth of the wells that are to be abandoned? | Depth is typically 25â€™ to 35â€™. | Mike Coleman | 2 | 2021-10-13 08:44 | 2021-10-18 09:41
20211109 | 20211109009 | 9 | Non-mandatory pre-bid meeting | Can you post the slide show and QA notes? | The non-mandatory pre-bid meeting presentation and questions and answers can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2021-10-13 10:32 | 2021-10-13 10:40
20211109 | 20211109009 | 9 | Pipe Underdrain 6â€ | For items #442 (pipe underdrain 6â€), #444 (pipe underdrain unperforated 6â€) & #446 (pipe underdrain wrapped 6â€), totaling +/- 148,760 LF there are no special provisions or construction details showing / stating what is wanted for these items. Also, what may or may not be incidental to the pipe underdrain items. Most of the quantity for the above items look to be placed under the breaker run on IH 43 mainline. | Please refer to Typical Finished Sections; Pipe Underdrain 6-Inch is primarily used with the breaker run of IH-43 and the ramps of CTH C and STH 60. Pipe Underdrain Wrapped 6-Inch is used with Stage 1A and 1B, as shown on the Typical Finished Sections. Pipe Underdrain Unperforated 6-Inch is used at each lateral extension leading to the Apron Endwalls For Underdrain Reinforced Concrete 6-Inch, please reference note C on the Typical Finished Sections. Pipe Underdrain Unperforated 6-Inch is also used with retaining wall R-45-14. Underdrain trench construction detail sheet will be added, via Addendum No. 02, to clarify what is incidental to the Pipe Underdrain 6-Inch item. | Mike Coleman | 4 | 2021-10-13 15:59 | 2021-10-18 09:44
20211109 | 20211109009 | 9 | Abandoning Sewer & Backfill Controlled Low Strength Items | - On page 1102 of the miscellaneous quantities it shows both abandoning sewer and backfill controlled low strength items for all the locations for abandoning storm sewer as shown in the plans. Why in some locations is abandoning sewer used and in other location backfill controlled low strength used? In some instances, both items are used at the same location, why is that? What item is to be used to fill the pipes with slurry? Why is item # 74 Abandoning Sewer show a quantity of 100 CY in the schedule of items while the quantity shown on page 1102 of the plan is 134 CY? If the abandoning sewer item should be used for filling the pipe as the specials state, then the 134 CY quantity is incorrect. - Page 57 & 58 of the plan show construction details for backfill controlled low strength â€“ storm sewer trench plan view. In the plan it states that backfill controlled low strength cost is incidental to the pipe, but in special provision # 69 it states that backfill controlled low strength will be used as backfill in trenches for culvert, sewers, utilities or similar structures as shown on the plan. Why wouldnâ€™t the controlled low strength backfill be paid with this item? If backfill controlled low strength turns out to be incidental to the pipe in the location shown what is the quantity of material listed in the schedule of items used for? Is the locations for backfill controlled low strength, used for storm sewer backfill, limited to only structures 171, 172, 173, 175 and associated pipe? Is there any other spots, in the highland road vicinity or throughout the entire project that require backfill controlled low strength to be used? Can the plan view sheet(s) be highlighted for all culvert / storm sewer pipes / structures that require controlled low strength to limit confusion? | 1st bullet: Backfill Controlled Low Strength is to be used in place of the Abandoning Sewer bid item where the pipe is within the footprint of the roadway, from outside shoulder to outside shoulder. Pipe outside of that area can be backfilled according to the Abandoning Sewer item. This occurs almost exclusively at the existing cross culverts that are to be abandoned following Stage 4. The estimate of quantities for Abandoning Sewer is incorrect. The correct quantity of 134 CY for Abandoning Sewer is shown in the Miscellaneous Quantities table on page 1102. This will be corrected via a forthcoming addendum 2nd bullet: Backfill Controlled Low Strength for pipes and structures shown on Page 57 and 58 will be included in a forthcoming addendum. | Mike Coleman | 5 | 2021-10-13 16:02 | 2021-10-18 13:35
20211109 | 20211109009 | 9 | Electronic Miscellaneous Quantities | Can the DOT please provide electronic files for the miscellaneous quantities containing the storm sewer, culvert pipe, and common excavation? | The requested file can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 6 | 2021-10-14 10:51 | 2021-10-19 07:55
20211109 | 20211109009 | 9 | 21. Hauling Restrictions | Please remove this Article. The contractor can't bid this project without knowing if their proposed haul route will be approved or not. This is a big risk to the contractor. Let the Contractor haul where they want, so the department gets the best price. | No, this article canâ€™t be removed as WisDOT has no jurisdiction over the local road system. Coordinate as needed with the local maintaining authorities regarding potential use of their roadways for hauling. This will be revised in an upcoming addendum. | Mike Coleman | 7 | 2021-10-14 15:10 | 2021-10-19 10:11
20211109 | 20211109009 | 9 | 32. Material and Equipment Staging | Please remove this Article. The contractor can't bid this project without knowing where they can stockpile material or stage equipment. How does the contractor get written permission? No one will give that permission to the contactor. This is unachievable. Why does it matter where the contractor stores material and equipment? | No, the requested article canâ€™t be removed. WisDOT has made commitments to the Wisconsin Department of Natural Resources, the US Army Corps of Engineers and others to not store materials and equipment within environmentally sensitive areas. Additional restrictions are included in the project Special Provisions for the Ulao Creek area. | Mike Coleman | 8 | 2021-10-14 15:16 | 2021-10-19 10:12
20211109 | 20211109009 | 9 | Railing Panel Length/Post Spacing | In regards to the Railing Pipe, the standard detail is to provide a max panel length of 10-feet. The railing is to be designed with panels set on either side of coping expansion & contraction joints. The coping contraction joints are required to be spaced at a maximum of 12-feet on center. This will cause some conflict with railing panels only allowed to be 10-feet in length. Would it be allowable to use railing sections with 3 posts that can span up to 12-feet? Alternatively, can contraction joints be located within a railing panel and only expansion joints required to be between railing panels? | The spacing of the coping contraction joints is a MAXIMUM of 12â€™. The railing fabricator will need to coordinate with the wall manufacturer on the exact locations of the contraction and expansion joints. MSE wall panels are typically 10â€™x5â€™ or 5â€™xâ€™5, and the coping joints would likely be located in multiples of 10â€™. | Mike Coleman | 9 | 2021-10-14 15:27 | 2021-10-19 10:43
20211109 | 20211109009 | 9 | 12290476-Surf-Ex-Bonniewell-to-STH-60.xml | 12290476-Surf-Ex-Bonniewell-to-STH-60.xml is corrupted and will not open. Please fix and upload. | The updated files can be found at the following location: https://wisdot.box.com/s/7yo8zj0dhnp29zgfjjtf0a6cdesr21il or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 10 | 2021-10-15 09:58 | 2021-10-19 07:48
20211109 | 20211109009 | 9 | Precast Trench Drain / Temporary Precast Trench Drain | Can a construction detail(s) be provided for the above two items? | Yes, it will be provided in addendum #2. | Mike Coleman | 11 | 2021-10-15 11:58 | 2021-10-19 08:01
20211109 | 20211109009 | 9 | Removing Draintile and Removing Underdrain | These two items add up to 85,000 LF of quantity, all of which is undistributed. How did DOT come up with these quantities? Where is it, what is it, what is the difference between the two? Seems like a large unknown quantity. | Removing Underdrain has been estimated based upon the length of the project, with the assumption that there is one run of existing underdrain beneath I-43 in both the northbound and southbound directions. Removing Draintile has been estimated based on as-built plans that show potential filed tile crossings underneath I-43. The estimated quantity for Removing Draintile should be 2,000 LF, rather than 20,000 LF as currently shown. This quantity revision will be included in a forthcoming addendum. Underdrain is used to drain the roadway subgrade while draintile is used to convey subsurface water and is not necessarily associated with the roadway (such as agricultural field draintile). | Mike Coleman | 12 | 2021-10-15 13:25 | 2021-10-19 12:29
20211109 | 20211109009 | 9 | Concrete Barrier Wall Questions | Questions associated with barrier wall construction and end anchors at the end of structures. 1. Is the concrete barrier pad tied to the concrete shoulder in these areas? 2. Is it your intent to extend all of the concrete pavement joints in the mainline pavement and concrete shoulder through the concrete barrier pad and the concrete barrier? 3. The expansion joints that are constructed as part of the concrete pavement bridge approach slab, are these joints extended through the concrete barrier pad and the concrete barrier? 4. If the answer is yes to the question in number 3 above, are end anchors required on each side of the expansion joint? As well as at the structure? This essentially doubles the number of end anchors and the amount of hand work in these areas. Also adds significant time of construction. Sheet 16, comparing the two drawings in the center of the page and the lower center of the page. The detail in the center clearly shows the concrete barrier wall pad tied to the concrete shoulder. The detail in the lower center does not show any tie bars. Is the concrete barrier wall not tied to the concrete pavement in these sections? Just making sure? Sheet 16, General Note 16, reads as follows: â€œ16. CONCRETE PAD UNDER CBSS MAY BE PLACED INTEGRAL WITH BARRIER, PLACED SEPARATELY OR PLACED WITH CONCRETE SHOULDER AND SAWED FULL DEPTH. SAWING OF CONCRETE SHOULDER IS INCIDENTAL TO CONCRETE BARRIER BID ITEM.â€ Where are the locations where the concrete pad is sawed full depth? The barrier wall detail to the left of general notes both show the concrete pad being tied to the pavement/shoulder. Highland Road Ramp A-D, the typical section on sheet 16-24 and the plan details on Sheet 203-216, show the retaining wall at a significant distance out from the pavement and barrier wall. A slipform machine can be used to place this concrete. The cross sections for these areas at some locations show the retaining wall directly behind the concrete barrier. The concrete paver requires clearance outside the pavement for the tracks of the machine. When the track line is not available do you agree that hand placement of the concrete pavement is required. Finishing, jointing and curing of the barrier wall is also a concern when this occurs because there is no at grade access to the back of the wall. | 1. A construction detail will be included as part of a forthcoming addendum to clarify tie bar locations. 2. Yes, refer to Note #19 on Concrete Barrier Construction Detail sheet. Please note that the standard detail drawing (SDD) for concrete barrier has recently revised notes, the notes on the concrete barrier construction detail in the plans are based upon these SDD notes and will be revised on the construction detail to match where appropriate. This revision will be part of the forthcoming addendum. 3. Yes, at the expansion joint between the structural approach slab and the concrete approach slab. At the expansion joint between the concrete pavement approach slab and the concrete roadway pavement, the expansion joint will not extend through the concrete barrier pad and barrier. A construction detail will be added in the forthcoming addendum to clarify this. 4. Refer to the response to question #3, no expansion joint will be present in the barrier and barrier pad at the concrete pavement approach slab / concrete roadway pavement joint. As well as at the structure? An end anchor is required on the concrete pavement approach slab side of the expansion joint, but a Single Slope Parapet 42SS Modified is present on the structure approach slab side, please refer to bridge plans detail on the parapet foundation. Sheet 16: Concrete barrier pad should be shown tied in the lower center, this will be revised with the forthcoming addendum. General Note 16: See revision described in answer to question #2 above, Note #16 will be revised to be consistent with the changed SDD note; stating that the sawcut depth is 1/3 of the concrete depth, not full depth. Highland Road Ramp A-D: A portion of wall R-45-19 on Ramp D requires the retaining wall to be located directly behind the concrete barrier. The cross sections in the plan do not detail the proposed anchor slab required for the retaining wall. Please review the plans for R-45-19 to determine whether hand placement of concrete would be necessary. | Mike Coleman | 13 | 2021-10-17 12:41 | 2021-10-22 09:50
20211109 | 20211109009 | 9 | Geotechnical Reports | Please provide the geotechnical reports for the available segments. The specials reference Steve Hoff can provide, please post a link for the reports. | The geotechnical reports can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 14 | 2021-10-18 11:16 | 2021-10-19 10:19
20211109 | 20211109009 | 9 | UPRR Railroad Crossing | A.5 Temporary Grade Crossing: The specials state the department has made arrangements for temporary crossings appropriate for both contractors needs and railroad requirements. Please provide documentation of the agreement with UPRR and the intended locations that were discussed and approved by UPRR. Past project experience, the relationship with UPRR and the department is a challenge and things are not always what they seem. | The OCR Final Decision and Order for Highland Road can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 15 | 2021-10-18 11:28 | 2021-10-21 13:54
20211109 | 20211109009 | 9 | 404 Permit | Please provide a link to obtain a copy of the 404 Permit. | The 404 permit can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 16 | 2021-10-18 11:31 | 2021-10-19 10:38
20211109 | 20211109009 | 9 | Noise wall painting | Note on plan sheet 1812 states "Note: it is not the Department's intension [sic] to put color on this wall." Special Provision B.3.3.1 and B.3.3.2 reference various colors and painting requirements. Please clarify the Department's intention with respect to wall painting and staining. | This noise wall will not be stained or painted. | Mike Coleman | 17 | 2021-10-18 12:03 | 2021-10-21 07:11
20211109 | 20211109009 | 9 | Stage 1 inside pavement widening | Should the temporary inside/median typical section drawing on plan page 12 (stage 1A) be moved to page 13 (stage 1B)? Doing such would appear to be consistent with the note(s) on plan page 788, and with the stage 1A and 1B traffic control plan pages. If moved to plan page 13 (work completed in stage 1B), could the location of the temporary inside/median barrier wall be indicated on the typical section drawing? | Yes, the typical section drawing will be revised and the temporary barrier location will be indicated. Both will be done as part of a forthcoming addendum. | Mike Coleman | 18 | 2021-10-18 13:47 | 2021-10-22 07:33
20211109 | 20211109009 | 9 | MSE Wall Copings | Structures R-45-14 and R-45-19 have a note that states the concrete coping quantity is included as part of the Concrete Masonry Retaining Walls bid item. Typically this is incidental to the MSE wall item and it appears that is the case on all other retaining wall structures on the job. Please confirm the coping, and bar steel at copings is not incidental on structures R-45-14 and R-45-19. | The R-45-19 anchor slab/coping/parapet concrete and reinforcing are quantified in the Concrete Masonry Retaining Wall and Bar Steel Reinforcement HS Coated Structures bid items respectively for the entire length of the wall. The R-45-14 anchor slab/coping/parapet concrete and reinforcing are quantified in the Concrete Masonry Retaining Wall and Bar Steel Reinforcement HS Coated Structures bid items respectively for Segment A only. The R-45-14 Segments B and C coping concrete and reinforcement are included in the Wall Concrete Panel Mechanically Stabilized Earth SPV. | Mike Coleman | 19 | 2021-10-18 16:14 | 2021-10-22 09:53
20211109 | 20211109009 | 9 | Special Field Office Bid Item | We are requesting that the DOT eliminate the item for Field Office Special. An item of this magnitude should not be part of a competitive bid to build a major highway. These rental office spaces are open to anyone to rent at any time. There is no guarantee that the office space we find will still be available to rent by the time a low bidder is awarded the project. We canâ€™t enter into an agreement not knowing who the low bidder is. Then have to figure our renovation costs (if and what it allowed), furniture, wiring changes, etc. This is a very high risk and unnecessary item to put on the contractor. Past Mega Project corridors had designated DOT headquarters that were secured by the DOT, such as in Green Bay. We think the DOT should have procured and item of this nature on their own and not make it an integral part of a low bid process. Temporary Field Office â€œTrailersâ€ are one thing but office spaces that can have a high likelihood of influencing who the low bidder is should not be. | The requirements of the field office will be adjusted via an upcoming addendum. | Mike Coleman | 20 | 2021-10-19 09:23 | 2021-10-26 09:22
20211109 | 20211109009 | 9 | Temporary Drainage Manholes and Inlets | Per the temporary drainage plans there are many manholes and inlets to be installed into the existing pipes throughout the project in stages 1, 2, 3. To complete this work it will require to break the existing pipe, install temp structure, and reconnect to existing pipe with new pipe. Will DOT pay for the new pipe needed to connect from existing pipe to temp structure and associated concrete collars at contract unit prices? Currently, it looks like nothing is accounted for. | The Concrete Collars are shown in the drainage table in the plan. Due to the number of columns, the station locations repeat once. The concrete collars are in the first part of the table, and the structures are in the second part but at the same station row. The forthcoming addendum will include two feet of pipe replacement on each side of a drainage structure insertion on an existing pipe. | Mike Coleman | 21 | 2021-10-19 09:48 | 2021-10-22 09:54
20211109 | 20211109009 | 9 | Question to Answer to above: 32. Material and Equipment Staging | How can the contractor bid this, guess? If WisDOT has made commitments to DNR, USACE and others, please provide those commitments, so that if they effect the bid, the contractor can adjust their numbers prior to the bid. Unless the DOT will accept a Change Order if the contractorâ€™s submittal under this Article is not approved and is forced to relocate their equipment and materials elsewhere. Also, what necessary permits are required from property owners and local governments/agencies? So, the contactor is supposed to get written permission from the adjacent landowners to stockpile material and park equipment on the ROW? Really? Just the adjacent landowners or within 1,000â€™ of the equipment/material or what is the requirement? What landowner would give the contactor approval ever? Please remove this language and specify where the contractor canâ€™t store equipment and material. Therefor all other areas donâ€™t need permission, and this will save a lot of time for the DOT & Contactor. | Restricted areas include wetlands, as mentioned in the Special Provision article. Those are shown on the plan and profile sheets in the plan, pages 1291 through 1303. Adjacent landowners do not need to be contacted for activity occurring within the R/W. The DNRâ€™s Transportation Construction General Permit (TCGP) for the project can be found at the following location: https://wisdot.box.com/s/0zegvbretxta4npo2pb5r2dec8du7s5r or can be accessed on the HCCI November bid letting page under Supplemental Information. Revisions will be made in an upcoming addendum. | Mike Coleman | 22 | 2021-10-19 14:07 | 2021-10-26 09:41
20211109 | 20211109009 | 9 | EBS in Median | It appears the Earthwork Summary doesnâ€™t have any EBS quantity in Stage 2 to account for the Topsoil removal in the Median. Most of the Median grading is in fill sections and there is not enough Salvaged Topsoil to account for the removal of the Topsoil. Therefore, EBS should be added. 50â€™ x 1â€™ x 30,450 LF / 27 = 56,388 CY â€“ Salvage Topsoil (79,527 SY x 9 x 4â€/12 / 27) 8,836 CY = 47,552 CY of EBS. Embankment should go up by this amount also unless the DOT wants Breaker Run installed instead. | Soil borings indicate typical existing median topsoil depths of 2â€-4â€, with some areas up to 6â€. Removal of this topsoil is covered under the common excavation standard bid item. The Topsoil Special (SPV) bid item is used on this project, rather than the Topsoil and Salvaged Topsoil standard items. | Mike Coleman | 23 | 2021-10-19 14:43 | 2021-10-22 09:56
20211109 | 20211109009 | 9 | Stage 1A & 1B - Earthwork Summary | Can the Earthwork Summary for Stage 1 be split into Stage 1A and 1B? The cost to haul is different depending on if the dirt is on the outside or in the median? | Given the design approach to modeling Stage 1, it is not feasible to separate the volumes between Substages 1A and 1B. However, the approximate volume of Common Excavation on the median side in Stage 1B between Sta 1477+00 and 1542+00 is 5700 CY, and the approximate volume of Roadway Embankment for this same location is 900 CY. | Mike Coleman | 24 | 2021-10-19 14:48 | 2021-10-22 07:37
20211109 | 20211109009 | 9 | North & South Crossovers Earthwork | It appears the North & South Crossovers are not in the Earthwork Summary. Please verify. The removal of them is. | The volumes for the north and south crossovers will be added to the Earthwork Summary via a forthcoming addendum. | Mike Coleman | 25 | 2021-10-19 15:00 | 2021-10-22 07:31
20211109 | 20211109009 | 9 | QMP Subgrade vs Night Work | QMP Subgrade doesnâ€™t work at night. Stage 1 and Stage 2 must be done at Night due to accessing the work zone. Compaction can be achieved at night under QMP but the Moisture canâ€™t be controlled. The contractor canâ€™t disc and dry at night, no sunshine. And the outside must be backfilled the same night to ensure there is a safety slope next to the traveling public, no time. The only good option is to place the fills under the Standard Compaction Specification and then proof roll the subgrade and determine if the subgrade is hard enough to place the planned breaker run on it or if it is not good but ok just add geogrid and place the planned breaker run on it or if it is bad remove a foot, add geogrid and thicken the planned breaker run thickness by 1 foot. This has been the process for many years and still is the process all over the rest of the State. Please remove the QMP Subgrade item for night work and add a proof rolling item. | The QMP Subgrade requirement has been reviewed by the design and construction teams. This specification has been successfully executed on past projects involving night work. Contractors will need to plan appropriately regarding the time of year, time of day and weather conditions, and adopt appropriate methods to meet the specification. The article will remain in the proposal. | Mike Coleman | 26 | 2021-10-19 15:42 | 2021-11-02 08:47
20211109 | 20211109009 | 9 | Miscellaneous Quantity Clarification | Removing Pavement table on plan page 1097 indicates "STAGE 4/2". Can this be clarified? If there is removing pavement in both stage 2 and stage 4, could those stages be made separate in the table? | Due to the construction sequencing, the existing pavement of northbound I-43 will be removed in both Stage 2 (northbound inside) and Stage 4 (northbound outside), while the southbound I-43 lanes will be removed in Stage 3. The quantities in Stage 2 and 4 can be estimated using typical sections and traffic control plans. | Mike Coleman | 27 | 2021-10-20 14:08 | 2021-10-22 07:39
20211109 | 20211109009 | 9 | QMP Base Aggregate Dense 1 1/4-Inch Compaction | I thought this item (QMP Base Aggregate Dense 1 1/4-Inch Compaction) was not to be used on Concrete Projects? Only Asphalt projects. | This item is being removed from the project via a forthcoming addendum. | Mike Coleman | 28 | 2021-10-21 15:14 | 2021-10-25 07:15
20211109 | 20211109009 | 9 | Work in the Median | For the work in the median where there is only barrier wall on one side (NB Lanes), does all the equipment and material within that work zone have to be removed when not working? How close to the SB traffic lanes under a shoulder closure can Equipment Work (without a lane closure) and can salvaged topsoil/other materials be piled how close to that open lane of traffic? It appears Barrier Wall should be added to the Southbound lanes to protect construction and the traveling public. If it is not added, material and equipment will have to be removed and haul back in. Also, I am assuming the Cable Guard is removed prior to median work, to allow for construction and access, please confirm. | Per FDM 11-50-35, 20â€™ (typical) width should remain clear of obstructions and work operations from the southbound travel lane where concrete barrier temporary precast is not used. The remaining area in the median is available for equipment, materials and work zone. Cable guard in conflict with the work zone and/or construction operations should be removed as shown in the plans. | Mike Coleman | 29 | 2021-10-21 15:46 | 2021-10-28 07:05
20211109 | 20211109009 | 9 | Plan Sheet 73 - Fabric vertically between MSE Backfill and Embankment | Why is there Fabric Type DF Schedule A placed vertically between the MSE Backfill and the Embankment fill? Is this needed? This is going to be very difficult to place. How do you hold it in place during placement of Backfill and Fill? The fabric will not be vertical, it will be more "S" shaped, is that ok? What is the overlap requirement and what direction does the fabric get laid (assuming length of roll is horizontal)? | The intent of the vertical Fabric Type DF Schedule A is to keep the MSE Backfill and Roadway Embankment materials separated so they donâ€™t comingle. Due to the back-to-back MSE walls with roadway embankment fill in between, if clay or silt fines migrate into the MSE Backfill, excessive embankment fill settlement could occur, or properties of the MSE Backfill may be compromised. The Fabric Type DF Schedule A does not need to be completely vertical. What is meant by â€œSâ€ shaped? | Mike Coleman | 30 | 2021-10-21 16:43 | 2021-10-29 06:52
20211109 | 20211109009 | 9 | Cold Patch | Please reduce the current quantity (1,000 tons) to a realistic quantity. The current quantity could pave approximately a 10 ft wide x 3 in thick x 1 mile long lane. The current quantity is absolutely unnecessary for filling in potholes on existing pavement surfaces. | This quantity will be reduced to 100 tons in the forthcoming addendum. | Mike Coleman | 31 | 2021-10-22 16:04 | 2021-10-26 09:46
20211109 | 20211109009 | 9 | R-45-14 & 19 External Stability | For the 2 walls referenced above, note 3 below the "Wall External & Overall Stability Evaluation" table states the contractor and its wall designer is responsible for internal and external stability at all other stations of the wall. This is uncommon for the contractor and its wall designer to provide an external or "global" stability evaluation for a WisDOT wall. Please clarify. | Note 3 is explanatory and not prescriptive. It states that the analysis results only apply to the sections that were analyzed. Inclusion of the note on the structural plans is not intended to require contractor design services that are different from other walls in the letting. | Mike Coleman | 32 | 2021-10-25 16:25 | 2021-11-02 10:39
20211109 | 20211109009 | 9 | Bridge Operations - Full Freeway Closure Restrictions | As stated in the Special Provisions, based on the staging, the six "Full Freeway Closures" will not be adequate for bridge operations (demo and girder erection). Will the Department please clarify the intent of the given amount of closures and add more allowable Full Freeway closures to be more realistically aligned with nighttime bridge operations? | The intent is for the full freeway closures to be used for bridge demo and girder erection. The allowable quantity will be changed to twelve in the forthcoming addendum. | Mike Coleman | 33 | 2021-10-26 10:06 | 2021-10-27 07:26
20211109 | 20211109009 | 9 | Structure S-45-0225 | Can you verify if we have to design the structure to 150 square feet sign, or are we sizing the structure to actual sign area which are only the 3 signs shown on the structure. If we are sizing the structure to 150 square feet sign, we need to know the weight and the location, I have not seen this before , we usually size to actual loading. Are they saying as this structure type is applicable for sign area less than 150 square feet. Therefore we can still size to actual loading. Please verify. | The structure plan for S-45-0225 has been revised to eliminate that note. The updated plan sheet will be included in a forthcoming addendum. | Mike Coleman | 34 | 2021-10-28 11:06 | 2021-10-29 06:55
20211109 | 20211109009 | 9 | New Cable Barrier Items | The current listing of approved cable barrier systems by county does not show any approved systems for Ozaukee County. Can you please confirm which systems are approved for Ozaukee County? | Safence TL-3, 4 Cable and Brifen TL-3, 4 Cable | Jill Fehrman | 35 | 2021-10-28 13:12 | 2021-11-04 07:30
20211109 | 20211109009 | 9 | 643.1205.S Basic Traffic Queue Warning System | Is the intent of the Queue Warning System to be used only in stages 3 and 4 when traffic is in the counter-directional setup? There isn't much guidance other than the undistributed quantity of 300 days. Thanks | The quantity of 300 Days will be revised in a forthcoming addendum. The intent of the Basic Traffic Queue Warning System is to utilize one system on I-43 in each the northbound and southbound directions during all stages of construction. | Mike Coleman | 36 | 2021-11-01 15:50 | 2021-11-03 08:17
20211109 | 20211109009 | 9 | SPV.0045.1001 Truck Entering Warning System | Approximately how many of these systems will be required for the undistributed 3000 days for this item? | The quantity of 3000 Days was estimated using four systems (two for the northbound direction and two for the southbound direction). | Mike Coleman | 37 | 2021-11-01 16:00 | 2021-11-03 08:17
20211109 | 20211109009 | 9 | SPV.0045.1002 Combination Work Zone Speed Trailer | Approximately how many of these trailers will be required for the undistributed 3000 days for this item? | The quantity of 3000 Days was estimated using four systems (two for the northbound direction and two for the southbound direction). | Mike Coleman | 38 | 2021-11-01 16:01 | 2021-11-03 08:18
20211109 | 20211109009 | 9 | 0040 204.0109.S Removing Concrete Surface Partial Depth | It appears this Item of 0040 204.0109.S Removing Concrete Surface Partial Depth is completely Undisturbed, can the department give the contractor an idea where this will be used? Multiple stages? How deep? What is this item for? | The Removing Concrete Surface Partial Depth item and associated Special Provision article will be removed from the contract with a forthcoming addendum. | Jill Fehrman | 39 | 2021-11-02 10:10 | 2021-11-04 07:30
20211109 | 20211109009 | 9 | Compost | Where exactly is the compost to be placed and for what purpose? From the detail in the plan it looks like you place compost on the existing ground and then place medium riprap over the top of the compost? The specials state placing compost for infiltration basin. I don't see anything about an infiltration basin. The miscellaneous quantities show a large station range and the detail in the plan is poor. | Refer to Construction Details, page 50 of the plan set, for station range and location of use for Compost. As stated on the Construction Detail, Compost, Seed and Fertilizer is placed over riprap. Compost is used to infill riprap voids to improve establishment of vegetation along the Ulao Creek bank and maintain its long-term stability. Compost is not used with an infiltration basin. The Special Provisions will be revised accordingly with a forthcoming addendum. | Jill Fehrman | 40 | 2021-11-02 10:54 | 2021-11-04 07:31
20211109 | 20211109009 | 9 | Temporary Precast Trench Drain | The only spot it shows in the plan where it goes is in the temporary drainage plan. In the plan there are runs of temp precast trench drain that aren't attached to any structures. How is the supposed to drain anywhere? On page 467 it looks like 2 runs drain to nothing and on page 488 there looks to be 2 runs also that drain to nothing. Please explain. | Clarity on the intent of the precast trench drain drainage and connections, including the referenced pages, will be included in a forthcoming addendum. | Fred Schunke | 41 | 2021-11-02 14:18 | 2021-11-04 15:18
20211109 | 20211109009 | 9 | Backfill Controlled Low Strength | Why is there 700 CY of backfill controlled low strength in the emergency pavement repair items (page 1104)? What is this to be used for, nothing is shown in the plans? AGAIN the quantity seems unreasonably high. Also, you can't bid this as the same item used to abandon sewer runs in stage 4. Two totally different operations with two different prices. | This item will be removed from the table of pavement repair items. The quantity will be reduced accordingly in a forthcoming addendum, so the only use for this item will be with drainage pipes. | Jill Fehrman | 42 | 2021-11-03 10:33 | 2021-11-05 07:43
20211109 | 20211109009 | 9 | Anchored Temp Barrier | Can more info be provided on location of the anchored temp barrier bid quantities? Please provide stations or note on traffic plans where it is anticipated to be required. | Anchoring of temporary concrete barrier occurs during the stages shown in the Miscellaneous Quantities. It is generally used when adjacent to a dropoff greater than 3H:1V and the dropoff is less than 4 feet from the barrier. Locations of this nature have been approximated during stages 1B through 4A, with the predominant uses in stages 2 and 3A. | Jill Fehrman | 43 | 2021-11-04 12:04 | 2021-11-05 10:09
20211109 | 20211109009 | 9 | 628.2023 Erosion Mat II B | This type of erosion mat has been used very sparingly in the last several years due to the amount of light it blocks. Due to the quantity on this project and the price difference to Class I Type B, please confirm that the project intends to keep this quantity of coconut mat on the contract. | This item is regularly used successfully on WisDOT projects, and it will be used for this one. It is a higher-quality mat that is used for longer duration applications, which is whatâ€™s needed for this project. | Jill Fehrman | 44 | 2021-11-04 14:03 | 2021-11-05 08:16
20211109 | 20211109009 | 9 | SPV Article 20 - UPRR Company Requirements | Section E. of the subject SPV Article 20 indicates that the Union Pacific will charge for some or all of the construction reviews provided by the contractor and that the contractor shall bear 100% of the costs of the construction reviews. The contractor has no governance over the railroad or affiliation to agreements between the Department and the Railroad. How should the contractors price this work as the statement is vague. What does "some" or "all" mean? How does the contractor determine the length it will take for UP to review the submittals, (ie. will they do cursory reviews or complete engineering reviews - nothing is specified as to how these reviews would be conducted for various aspects of work). This section should be eliminated from the contract - please advise. |  |  | 45 | 2021-11-04 15:34
20211109 | 20211109009 | 9 | Article 81 - Backfill Slurry | Article 81 Backfill Slurry appears to indicate all storm sewer pipe and structure trenches get backfilled with slurry. However details on sheet 58 of the plans indicate several locations can be backfilled with granular backfill meeting spec section 209. Do all trenches get backfilled with backfill slurry incidental to the storm sewer pipe item? | Storm sewer structures and pipes at Highland Road are to be backfilled using Backfill Controlled Low Strength material to the limits as shown on sheet 58 of the plan set. Backfill material immediately above those locations will conform to Section 209 per Note 1 to the limits shown on the details. | Jill Fehrman | 46 | 2021-11-04 16:25 | 2021-11-05 10:12
20211109 | 20211109010 | 10 | B-40-500 Median Deck Reabr | Deck Plan sheet 8 of 20. The top Longitudinal Bars in the Median over the C/L Pier 2 are shown as 32 D402, should these be 32 D616? The Bill of Bars on sheet 9 of 20 show the correct quantity needed (146) all the way across the deck for stage 1 and 2. | The top longitudinal median bar at pier 2 shown on page 8 of 20 is labeled incorrectly. The bar is labeled D402, the correct bar label is D616. The bar is labeled correctly on the deck cross sections on pages 10 and 11 of 20. The bar mark is listed correctly in the bill of bars on sheet 9 on 20. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-10-19 19:02 | 2021-10-20 11:15
20211109 | 20211109010 | 10 | B-40-500 Structure Painting | Sheet 3 of the structure plans indicates that a temporary minimum clearance of 21' must be maintained above the railroad tracks. This leaves approximately 1' from bottom of girder to this required clearance. With the amount of train traffic on these lines per day, please advise on how this structure is supposed to be blasted and painted as this clearance requirement allows no room for a containment system to be installed. | A bid item and special provision will be added via addendum to address how to clean and coat the bottom flanges on Span 2 over the railroad prior to painting. | Mike Coleman | 2 | 2021-10-26 14:31 | 2021-11-03 06:55
20211109 | 20211109010 | 10 | Asphaltic Surface Thickness | What is the specified asphalt thickness for Item 40? | The plans show the asphalt it as VT (Variable Thickness) asphalt, the MQs were calculated using 3". | Jill Fehrman | 3 | 2021-11-04 11:39 | 2021-11-05 10:10
20211109 | 20211109016 | 16 | temporary pavement markings | Good morning, it appears there are quantities for temporary paint to cover 2 applications of edge lines (milled and lower layer), it does not appear there are quantities to cover any lane lines (milled or lower layer) or any temporary pavement markings on the surface layer. Please confirm this is correct and if you plan to add quantities for the milled and lower layer lane lines as well as the surface layer. Thank you. | The quantities do not account for all the layers. A forthcoming addendum will account for the necessary temporary edge lines and centerlines for milled, lower, and surface layers. | Mike Coleman | 1 | 2021-10-27 09:47 | 2021-10-29 06:53
20211109 | 20211109016 | 16 | Prepare Foundation for Asphalt Shoulders/ Base Aggregate Summary | In the base aggregate miscellaneous quantities under the "Remarks" it says to "remove 2" excess" in all outside shoulder areas that are being widened. Is the departments intent to have this material removed off the project or will it be incorporated into the shoulder per standard specification 211.3.5.1.2? There is currently no item to remove this material. |  |  | 2 | 2021-11-08 12:09
20211109 | 20211109017 | 17 | Lane Widths for Southbound turn lanes | The proposed typical section on sheet #8 calls out for (2) 12' Southbound STH 57 turn lanes. Sheet 14-16 in the plan details call out for (1) 12' and (1) 15' lane. Please verify the lane widths for the proposed Southbound turn lanes. | The proposed typical section on sheet 8 is incorrect, the dimension for the offset between the driving lane and the new right turn lane should be labeled as 15â€™. The plan details on sheets 14-16 are correct, the southbound right turn lane is offset 15â€™ from the driving lane and the northbound right turn lane is offset 12â€™ from the driving lane. | Mike Coleman | 1 | 2021-10-27 12:36 | 2021-11-01 06:58
20211109 | 20211109017 | 17 | Base section split | The proposed typical sections call for 6" of 1-1/4" base over 4" of 1-1/4 base. Is there a reason that the base section is split up or is the intent to have 10" of 1-14" base over 16" of select crushed material? | The base does not need to be split. Intent is to have 10â€ of 1-1/4â€ BAD over 16â€ select crushed. | Mike Coleman | 2 | 2021-10-27 12:41 | 2021-11-01 06:59
20211109 | 20211109017 | 17 | Intended plan for protecting the existing 6" longitudinal underdrain | What is the intended plan for protecting the existing 6" longitudinal underdrain that appears to be located within the proposed excavation? Based on the section of cut, there is going to be a high probability that the existing underdrain will be undermined to reach plan subgrade. | The 6â€ longitudinal underdrain doesnâ€™t need to be protected and can be removed if encountered. The existing underdrain on each end of the excavation limits will be daylighted to the ditch with a new outfall. There are items and quantities in the contract to account for new outfalls. Final locations of outfalls will be verified by the engineer. | Jill Fehrman | 3 | 2021-10-27 12:45 | 2021-11-04 07:49
20211109 | 20211109017 | 17 | Work days charged on Fridays | Does WisDOT plan to charge a work day for Fridays as the contractor will not be able to work more than 4 hours due to traffic control restrictions? | In accordance with standard spec 108.9.2, the department would charge a maximum of 1/2 working day on Fridays when the controlling operation requires a lane closure since the available time even with the traffic control restriction is from 4 to less than 8 hours. | Mike Coleman | 4 | 2021-10-27 12:48 | 2021-11-01 07:01
20211109 | 20211109017 | 17 | Culvert Pipes | There are few runs of pipe that are either coming in, coming out or between storm sewer structures (4' Manholes or 2x3 inlets) that called out in a plan as culvert pipes, not a storm sewer pipes. Pipe backfill requirements are different for culvert pipes vs storm sewer, which ones should be followed? | The pipes that are originating or terminating with a storm sewer structure should be following requirements for storm sewer pipes. An addendum will be developed to clarify the storm sewer pipes in the plan. | Mike Coleman | 5 | 2021-10-28 12:23 | 2021-11-01 07:21
20211109 | 20211109017 | 17 | Asphalt paving thickness | The typical sections show asphalt thicknesses that do not follow 460.3.2. Could the typicals be changed to follow the specifications? | The typical sections will be updated to show asphalt thickness on the shoulder that aligns with the standard specifications. | Jill Fehrman | 6 | 2021-11-01 09:53 | 2021-11-04 07:46
20211109 | 20211109018 | 18 | Construction Schedule | Could the Construction schedule developed during design be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/3qox9474ieyfr3kul9sf3d0ih54sbdcf or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-10-12 08:10 | 2021-10-13 06:32
20211109 | 20211109018 | 18 | Asphaltic Surface Butt Joint Detail and QTYs | The quantities for Removing Asphaltic Surface Butt Joints do not match the pay limits. The change in profile has the pay limit as 50' for mainline butt joint however it appears to be calculated at 2'. The change in profile detail shows just the surface for the last 50' at the butt joint however there is a 4" minimum at the existing pavement. Should this be 1 3/4" minimum as shown as the minimum at the pay limit length? | The 4â€ minimum depth in the detail is correct. It represents the proposed pavement depth. The 1 ï¿½â€ depth should be 2 ï¿½â€ as it represents the proposed milled surface depth. The quantities are incorrectly calculated with a 2â€™ pay limit. An addendum will be issued to revise the quantities to the correct 50â€™ pay limit. The butt joint detail will also be revised for milled surfaces with profile change. | Mike Coleman | 2 | 2021-10-14 07:17 | 2021-10-18 09:53
20211109 | 20211109018 | 18 | Temporary Shoring at C-5-1745 | From the site visit, it appears Temporary Shoring will be required at C-5-1745. Would the DOT provide for this bid item via addendum? | Any shoring related to the excavation for the proposed culvert extension would be incidental to the Excavation for Structures Culverts bid item. | Mike Coleman | 3 | 2021-10-14 13:02 | 2021-10-20 06:58
20211109 | 20211109018 | 18 | MGS Guardrail at B-05-262 | How does the MGS 3 attach to the W-Railing? Shouldn't there be a bid item for MGS Thrie Beam Approach on each corner coming off of the box culvert railing? | The item MGS Thrie Beam Transition will be added to the plan via addendum. | Mike Coleman | 4 | 2021-10-15 12:34 | 2021-10-20 06:58
20211109 | 20211109018 | 18 | Project Time frame | The working days on this project seem low compared to other similar sized projects. For example with the sample schedule paving is estimated quicker then what is realistic. With the size of project would the Department consider 50 working days? | The design team reviewed the sequence of construction operations and production rates in the contract time for completion and agrees that more time would be reasonable for this project. We feel 45 working days is realistic and will revise the contract time via addendum. An updated design schedule can be found at the following location: https://wisdot.box.com/s/3qox9474ieyfr3kul9sf3d0ih54sbdcf or can be accessed or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2021-10-25 07:21 | 2021-10-26 09:51
20211109 | 20211109018 | 18 | Guardrail Timeframe | There is a requirement for beam guard repairs to be done in 72 hours. Does that include placing the new rail or is this for the grading operations only? The 72 hour timeframe is impactable to remove, grade, shoulder, mill and place 2 lifts of asphalt and place the new rail. If the new rail is required in 72 hours then there will need to be an item added to adjust the rail after paving as there is a grade change in most areas of the job. | The timeframe is for the duration between when the existing guardrail is removed, and the new guardrail is placed. Reviewing the hazards and slopes being protected by the existing guardrail for this project, the department will allow up to 7 calendar days between removal of existing guardrail and installation of new guardrail. An item for adjusting the guardrail will not be added to the contract, the new guardrail should be set to the anticipated finished pavement height. Any final adjustments needed would be incidental to the guardrail item. | Mike Coleman | 6 | 2021-10-25 07:45 | 2021-10-26 09:51
20211109 | 20211109018 | 18 | culverts | There is a note on plan sheet 86 that says Sta 364+91 LT Tie Last 2 joints and another note 364+91 RT tie last Joint. I did not see any sort of bid item to cover this work. | An item will be added to cover the joint tie work at these locations. | Mike Coleman | 8 | 2021-10-27 10:34 | 2021-10-28 07:13
20211109 | 20211109018 | 18 | Roundabout closure | With the amount of work at the Roundabout would the department consider detouring traffic for 2 days? The first day to mill and the second to pave the roundabout. | The department would allow detouring traffic two days for the roundabout milling, paving, and pavement marking. An addendum will be issued to revise the roundabout detour language. | Jill Fehrman | 9 | 2021-11-01 07:53 | 2021-11-04 07:45
20211109 | 20211109019 | 19 | Preparation of foundation for asphaltic shoulders | The prosecution and progress in the special provisions states,â€ Replace aggregate shoulders with the existing shoulder material removed from the asphalt shoulder.â€ Could the item 305.0504S Hauling Excess Shoulder Material (CY) be added as the width of the existing shoulder and the in-slope of the ditch will not allow the material to stay on site? | Yes, item 305.0504.S Hauling Excess Shoulder Material (CY) will be added to the contract via a future addendum to cover any necessary hauling of excess shoulder material to other locations along the project. Disposal of excess shoulder material (to a location off the project) that canâ€™t be used on the project is already covered under the contract item 211.0400 Prepare Foundation for Asphaltic Shoulders per standard specification 211.3.6. | Mike Coleman | 1 | 2021-10-25 12:08 | 2021-10-28 10:05
20211109 | 20211109019 | 19 | Asphalt widening | Being a PWL asphalt project a test strip must be constructed prior to full production, but the 2 foot widening area should be constructed the day prior to paving mainline. Where is the tonnage for the widening in the test strip area being accounted for and paid as? | To help coordinate the timing of the paved shoulder widening as it relates to the test strip, the lower 2â€ of the paved shoulder widening will be revised in the plans to be item 465.0105 Asphaltic Surface, which does not require PWL. This change will be addressed as part of a future addendum. | Mike Coleman | 2 | 2021-10-25 12:12 | 2021-10-28 10:06
20211109 | 20211109019 | 19 | Construction Detail | Could the department provide a base thickness on the details on page 8? | Yes, the thickness of the base aggregate dense layer will be added to the details on page 8 as part of a future addendum. | Mike Coleman | 3 | 2021-10-27 10:51 | 2021-10-28 10:06
20211109 | 20211109019 | 19 | Cross Sections | Could the department provide cross sections for 442+74, 456+15, 537+06, 616+59, 135+80, 266+60, 387+77, 607+92, 224+18 and 571+17, showing existing vs requested slopes? | Cross sections will not be provided for these culvert locations, as no cross section or DTM data is available and all, but one, are to be replaced at the same length and elevations to match the existing slopes. The one exception is the culvert at station 571+17, which needs an additional section of pipe and apron endwall. A construction detail for this culvert location will be provided in a future addendum that will show existing and proposed slopes. | Mike Coleman | 4 | 2021-10-27 10:52 | 2021-10-28 10:08
20211109 | 20211109019 | 19 | Traffic | Under the traffic notes in the special provisions it states "Maintain at least a 10-foot wide paved portion of roadway..". Would the department consider changing the specials to state that patches are to be paved at the end of each day? | Yes, the phrase in the third paragraph under Article 4 Traffic that states, â€œâ€¦a 10-foot wide paved portionâ€¦,â€ will be removed and replaced with the phrase â€œâ€¦a 10-foot wide smooth and compacted base aggregate dense surface portionâ€¦,â€ as part of a future addendum. Also, as part of the addendum, the 8th paragraph under Article 3 Prosecution and Progress will be revised to require travel lanes at culvert replacement areas to be paved within 48 hours of beginning culvert removal and replacement operations. | Mike Coleman | 5 | 2021-10-27 11:03 | 2021-10-28 10:09
20211109 | 20211109019 | 19 | culverts | There is an item for Sealing pipe at Sta 479+90 . On plan sheet 20 there is a note saying that we are to plug the south end after removing the endwall, we are also supposed to locate the north end and pump in material. Is this trying to tell us we have to completely fill the entire pipe? Standard specs only require plugging both ends, not filling the entire pipe. What are we suppossed to all do for this item ?? | As part of a future addendum, the notes on plan sheets 20 and 44 will be corrected and the Sealing Pipes item/quantity will be replaced with a new SPV item called â€œFilling and Abandoning Culvert Pipe,â€ which will be paid by the cubic yard of cellular concrete material used to completely fill the culvert pipe. | Mike Coleman | 6 | 2021-10-27 11:22 | 2021-11-02 09:13
20211109 | 20211109019 | 19 | 72 hour milled surface | The special provisions state in part, "Do not allow a milled surface to remain exposed for a period greater than 72 hours... ". Due to the additional scope of work between the milling and mainline paving operations, 2 foot asphalt widening, would the department extend the time period to 96 hours? | Yes, for the first week of milling, paving, and PWL test strip operations only. The following sentence will be added to the fifth paragraph under Article 3 Prosecution and Progress as part of a future addendum: â€œThe 72-hour period may be increased to 96 hours for the first week of milling, paving, and PWL test strip operations only.â€ | Mike Coleman | 7 | 2021-10-27 13:10 | 2021-10-28 10:10
20211109 | 20211109019 | 19 | Culvert Pipe STA 479+90 | Plan sheet 44 says Replace Culvert Pipe at STA 479+90, Misc Quantities Sheet 32 Shows Sealing Pipe at STA 479+90, Special Provisions on page 2 under Prosecution and Progress Article states "Excavate to expose the buried end of pipe at Station 479+90 to be sealed. Pump concrete slurry in from the upstream end to ensure the pipe is fully sealed. Standard Specifications state under 204.3.3.3(3) "Under sealing pipes bid item, thoroughly clean the ends of the abandonded pipe, and seal them with brick, concrete block, or any grade of concrete under 501.3.1.3. We fill that itme of Flowable Fill or Backfill Controlled low strength by CY should be added to cover this work. | As part of a future addendum, the notes on plan sheets 20 and 44 will be corrected and the Sealing Pipes item/quantity will be replaced with a new SPV item called â€œFilling and Abandoning Culvert Pipe,â€ which will be paid by the cubic yard of cellular concrete material used to completely fill the culvert pipe. | Mike Coleman | 8 | 2021-10-27 16:34 | 2021-11-02 09:14
20211109 | 20211109019 | 19 | Question 5 Follow Up | Article 3 Prosecution and Progress includes a sentence that states, â€œTravel lanes at culvert replacement areas must be paved at the end of each workday.â€ With amount of traffic that STH 29 has it would be difficult to replace the pipe, perform transition cut/backfill, gravel and pave pipe areas in one day. Could the language be changed to "Travel lanes at culvert replacement areas must be paved at the end of each workweek"? | No. However, as part of a future addendum, the 8th paragraph under Article 3 Prosecution and Progress will be revised to require travel lanes at culvert replacement areas to be paved within 48 hours of beginning culvert removal and replacement operations. | Mike Coleman | 9 | 2021-10-28 12:39 | 2021-11-01 07:03
20211109 | 20211109020 | 20 | Shaping Shoulders | Looking at the bid items and details of proposed typical sections there is an item in the plan for Prep Foundation for Asphalt Shoulders, but shouldn't there also be an item for Shaping Shoulders? | The project plan is correct as shown. Prep foundation bid item is shown in areas where widening shoulder work is planned. The remaining shoulder work is covered for under the milling spec and/or the placing crushed aggregate spec. So shaping shoulder bid item is not needed. | Mike Coleman | 1 | 2021-10-08 15:35 | 2021-10-19 10:56
20211109 | 20211109020 | 20 | Asphaltic Surface Patching | In the plan there is an item for Asphaltic Surface Patching with an undistributed quantity of 200 Tons. Is intent to use this quantity for for distressed patching after the milled surface or is there a specific location that it will be used? | Yes, that is the intent â€“ to address areas identified after the milling. | Mike Coleman | 2 | 2021-10-11 11:46 | 2021-10-19 10:57
20211109 | 20211109020 | 20 | 646.6105 Stop Line Paint 18-Inch | Item 646.6105 Stop Line Paint 18-Inch; all other final pavement marking items on this project are Epoxy. Should the 18" Stop line also be Epoxy? Thanks | Please bid as shown. | Mike Coleman | 3 | 2021-10-14 15:40 | 2021-10-19 11:05
20211109 | 20211109020 | 20 | Asphalt Mow Strip | Please confirm that the mow strip limits will not fall into the MGS EAT area. Per the SDD's, only steel posts can be used with this mow strip. | Yes, the mow strip work will follow the SDD. Yes, only steel posts are used in mow strip. | Mike Coleman | 4 | 2021-10-15 09:51 | 2021-10-19 12:27
20211109 | 20211109020 | 20 | Structure B-39-57 Traffic Control | How will the traffic control be handled for the work operations on Structure B-39-57 is the intent to do half at a time with barrels/temp stoplights or work under flagging operations? | Yes, use daytime flagging operations to complete the work, this is noted on page 2, under Article 3 of the proposal. This is a relatively small structure and work area. We anticipate the work effort as follows: Day One: Milling deck Clean Place membrane Place first layer of asphalt Day Two: Final layer of asphalt Finish work | Jill Fehrman | 5 | 2021-11-01 12:02 | 2021-11-04 07:37
20211109 | 20211109020 | 20 | Asphaltic Surface Special Provision | In the Special Provision under item #15 Asphaltic Surface it states that it has to be 4LT HMA. Being that we are using it to pave The Cove Driveway and the Culvert Patches wouldn't it be better to use a 4MT? | 4 LT HMA is the minimum standard we need the Asphaltic Surface mix to meet. The region would not object if the contractor wanted to propose a change to use 4 MT HMA mix for these applications. | Jill Fehrman | 6 | 2021-11-02 14:04 | 2021-11-04 07:46
20211109 | 20211109020 | 20 | Sheet Membrane Waterproofing | There is not a domestic material for sheet membrane that meets the specifications in the proposal. In the past the material used was Mel-Dek. It does not meet Perms, or softening point. Is this material acceptable to use for this project? |  |  | 7 | 2021-11-04 09:34
20211109 | 20211109021 | 21 | Missing Bid Items | The new ground-mounted type I footings are missing the bid item 531.2024 for digging the footings. Please add the item and appropriate quantity. | An addendum will be issued to add the missing bid item. | Mike Coleman | 1 | 2021-10-15 09:58 | 2021-10-21 09:36
20211109 | 20211109021 | 21 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/okgkp5qwm585wvqr67rosq4msb61io7v or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-10-16 08:21 | 2021-10-21 09:43
20211109 | 20211109021 | 21 | Adjusting Steel Plate Beam Guard | With this quantity of adjusting, can you please clarify if the desired adjustment locations include adjusting EAT heights or Thrie Beam Approach heights? If so, how will the breakaway locations of EAT's and attachments to solid structures of the Thrie Beam Approach be handled? | The item and quantity of Adjusting Steel Plate Beam Guard is intended for entire runs of existing guardrail, including the end treatments. Profiles of the finished pavement surface will be transitioned to match existing bridge decks; therefore, no modifications of anchor assemblies are anticipated. If the required height adjustments to an existing Energy Absorbing Terminal would cause any component of the guardrail system to become unserviceable, then replacement of such components could be measured and paid for under the Replacing Material items included in the contract, as the engineer designates. | Mike Coleman | 3 | 2021-10-18 08:29 | 2021-10-21 09:44
20211109 | 20211109021 | 21 | 643.1205.S Basic Traffic Queue Warning System | Regarding the placement of item 643.1205.S Basic Traffic Queue Warning System, if there are two separate lane closures setup in the same direction, does each lane closure require their own Queue system? If they do, will they each be paid separately? Thanks | For these projects, if separate lane closures are utilized in the same direction for Interstate 94 traffic, only the first closure would require a Basic Traffic Queue Warning System. Subsequent lane closures in that same direction would be regular closures. | Mike Coleman | 4 | 2021-10-22 09:42 | 2021-10-26 09:54
20211109 | 20211109021 | 21 | Temporary Pavement Markings | Good morning. In looking at the temporary pavement markings, it does not appear there are any temporary paint quantities for the surface layer of IH94 with the exception of the ramps. What is the departments plan to delineate the lane and edge lines between paving and permanent pavement markings? On similar projects there have been enough temporary paint quantities to delineate both the lower layer and the upper layer. Will an addendum be issued to address this? Thank you. | Temporary paint quantities for the upper layer were included in the plan, but only for the lane line skips. We will proceed with adding the missing quantities for temporary edge lines through the addendum process. | Mike Coleman | 5 | 2021-10-26 07:33 | 2021-11-02 10:35
20211109 | 20211109021 | 21 | Minimum cement content for the various concrete repair and replacement items. | Should a minimum cement content be added for the various concrete repair and replacement items. No minimum is specified and a vary low cement content could be used. | The special provisions referenced only cover 6-hour mixes. If concrete is being placed during some timeframe on the project where these fast mixes are not required, then mix requirements would revert to standard specification requirements. There is no specific minimum cement content specified for 6-hour mixes. The contractor will need to use the amount of cement needed to achieve the required strength (2500 psi) in the required time while not exceeding the maximum W/C ratio. | Mike Coleman | 6 | 2021-10-31 13:37 | 2021-11-03 08:22
20211109 | 20211109021 | 21 | DBE Goal | This project has a DBE participation goal of 8%. This project primarily consists of concrete pavement repair, milling, HMA pavement, pavement marking, and traffic control. From experience with similar projects in this geographical area it will be difficult to achieve 8% DBE participation. Would the DOT be willing to review the DBE goal for this project? Thank you. | The contractor is to make every effort to attain the DBE Goal assigned to the proposal. If you are not able to attain the goal please follow the DT1202 process and submit your supplemental documentation of your efforts. A link to the DBE Tool Kit is provided below. https://wisdot.box.com/s/okgkp5qwm585wvqr67rosq4msb61io7v Or can be accessed on the HCCI November Bid Letting page under Supplemental Information | Jill Fehrman | 7 | 2021-11-01 16:36 | 2021-11-05 08:07
20211109 | 20211109022 | 22 | Article 8 - RR Protective Liability Insurance | It appears that per the plan, all required traffic control on STH 29 over the Soo Line RR is more than 50 feet from the Soo Line Railroad. Is this insurance coverage actually necessary? | ï¿½ 646.107 Railroad protective insurance. .. â€œâ€¦..highway construction projects located in whole or in part within railroad right-of-way, railroad protective liability insurance shall be purchased on behalf of the railroad by the contractorâ€ The project is within railroad right of way therefore the railroad protective liability is required. | Mike Coleman | 1 | 2021-10-27 09:41 | 2021-10-28 08:12
20211109 | 20211109022 | 22 | Guardrail Retrofits | What exactly is getting done for these items? There aren't any details nor the standard details in the plans. Is this more or less a salvage and reinstall of the thrie beam connections? New posts and panel required? Thanks | The intent is to remove, salvage and reinstall the existing steel thrie beam for the construction of the new concrete wing parapet. If posts are removed due to necessary excavations for the concrete wing parapet construction, replace the posts with new posts to the same configurations and dimensions as existing. | Mike Coleman | 2 | 2021-10-27 09:58 | 2021-10-28 12:48
20211109 | 20211109022 | 22 | Pigmented Surface Sealer Reseal | Plans state to apply to top and roadway face of the parapet. Surface preparation is included in the bid item "Pigmented Surface Sealer Reseal." Please define the extent or type of surface preparation necessary at these structures as part of this bid item. | As defined under Section 502.3.13 of the standard specifications. | Mike Coleman | 3 | 2021-10-28 13:42 | 2021-11-01 06:46
20211109 | 20211109024 | 24 | Excavation Common | Is the Bypass Removal Earthwork summary correct? It seems there would be 217CY of Fill and 1383 CY of Waste in that division for a net 1166 CY of waste, no borrow needed. | The earthwork calculation for the temporary bypass removal has been reviewed and a unit error was noticed in the quantity used for the unusable base. The bypass earthwork removal table has been corrected and an addendum has been prepared. The temporary bypass removal requires a small quantity of borrow, as the site of the temporary bypass should be restored to its original condition with the bypass removal. The base course and asphalt used in the bypass construction is not usable as fill to restore the bypass area to its original topographic condition. Please let us know if any additional information is needed. | Fred Schunke | 1 | 2021-11-02 15:53 | 2021-11-04 13:30
20211109 | 20211109025 | 25 | Cold Weather Epoxy and Regular Epoxy Item | Good morning. In looking at the pavement marking items, the project contains cold weather epoxy items for the long line markings but does not have an item to address the long line markings should a cold weather item not be needed. Will a regular epoxy item be added for the long line markings or is it the intent to use the cold weather item regardless of the conditions? Thank you. | Yes, standard epoxy pavement marking item(s) will be added to the plans and miscellaneous quantities through an â€œOn Timeâ€ addenda prior to the October 28th posting date. | Mike Coleman | 1 | 2021-10-12 11:07 | 2021-10-14 07:06
20211109 | 20211109025 | 25 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | Yes, the bid items as shown follow the most current FDM guidance for bidding of alternate pipe materials and the contactors will be able to bid these materials competitively. Please note that there is a large quantity of storm sewer pipe on the project that is above the 2-foot, and below the 11-foot bury depth guidance as listed in the FDM, so alternate pipe materials are not specified for these areas. We recommend bidding the storm sewer pipe as shown in the bidding documents and according to the bid items listed. | Mike Coleman | 2 | 2021-10-18 13:19 | 2021-10-20 12:57
20211109 | 20211109025 | 25 | 643.0920 Traffic Control Covering Signs Type II | Item 643.0920 Traffic Control Covering Signs Type II, the quantity in the miscellaneous quantities was calculated as "days" instead of as "each" (4 signs covered for a duration of 64 days). Please revise plan quantity for this item. Thanks | An addendum will be issued to correct the discrepancy for the Item 643.0920 Traffic Control Covering Signs II. | Mike Coleman | 3 | 2021-10-20 12:24 | 2021-10-26 09:43
20211109 | 20211109025 | 25 | Detour Signs and Fixed Message Signs | In the miscellaneous quantities table for detour signs on plan page 259, the stage duration for Stages 2, 3, and 4 are all set at 196 days each; instead of a total for all three of these stages of 189 days. This adds 36,666 days to the 643.0900 Traffic Control Signs item. Please revise the quantity for this item. Also, the Fixed Message Signs installed in Stage 2 for the Truck Detour remain in place for the duration of the stages, however the quantities show these FMS installed again in Stages 3 and 4, adding 84 square feet of FMS to the 643.1000 Traffic Control Fixed Message Sign item. Please revise the quantity for this item. Thanks | An addendum will be issued to correct the discrepancy for the Detour Signs and Fixed Message Signs quantities. | Mike Coleman | 4 | 2021-10-20 12:31 | 2021-10-26 09:44
20211109 | 20211109025 | 25 | Temporary Marking Line Tape 4-Inch (Black) | Stage 2 traffic control plans show the parking stall lines on Walnut Street to be covered with Temporary Marking Line Tape 4-Inch (Black); however there isn't an available product on the approved products list for 4-Inch Black removable tape. There are several approved products for 6" and 10" Black tape that are available for use. Please advise if 6-Inch Black Removable Tape should be used to cover these parking stall lines, and if so can an item be added for 649.0960 Temporary Marking Removable Mask Out Tape 6-Inch? Thanks | An addendum will be issued to correct the discrepancy for the Temporary Marking Line Tape 4-Inch (Black) item. | Mike Coleman | 5 | 2021-10-20 12:49 | 2021-10-26 09:44
20211109 | 20211109025 | 25 | Mix Type | The current cross section for mix show 3" of 4MT 58-34H on the upper lift and a higher end mix under that for the next two lifts with (2 -2.5" 5HT 58-28H). Would the state consider using all the same mix type for this job which would help reduce the cost if using a 4MT for all three lifts. | Yes, the plans will allow for one mix type for all three layers and this item Mix Type will be clarified stating such, through Addenda #2, which will be issued by 2:00 p.m. on Thursday, Nov. 4th. | Mike Coleman | 6 | 2021-11-01 10:43 | 2021-11-03 06:50
20211109 | 20211109026 | 26 | Temporary Markings | Good afternoon, with the milled surface able to be left for 72 hours, a CIR, and a leveling layer (in most areas), could you please check the temporary paint quantities as it does not appear to be enough quantity to cover 2, and sometimes 3 applications prior to the surface being applied. In addition, is the temporary epoxy item correct? typically it is close to matching the permanent quantity which, in this case, it is a bit higher. Thank you. | There are corrections for both the temporary marking line paint and temporary marking line epoxy quantities. The corrected quantity for the temporary line paint is 153,220 LF, and for the temporary epoxy it is 83,930 LF. An addendum will be issued regarding both of these items. | Mike Coleman | 1 | 2021-10-25 14:22 | 2021-10-28 10:01
20211109 | 20211109027 | 27 | Cold In-Place Recycling | The Cold In-Place Recycling (CIR) for this project is being bid under a special provision item, with a unique specification. The Balance of the CIR projects in this highway letting are being bid using bid item 327.1000.S and a uniform specification. Can this project be changed to the same specifications as the others? Thank You. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-10-22 11:57 | 2021-10-26 09:57
20211109 | 20211109027 | 27 | Shoulder Paving | The existing shoulder HMA depth on about 65-70% of the project has ~ 6.5 inches of existing asphalt and the proposed is only 1.75" total thickness. The question is are we putting enough strength back into this shoulder to even put a shoulder machine on for the CABC shoulders? Generally when we see thick pavement on the shoulders it is because there tends to be poor subsoils under them. Also the project has shoulder rumble strips ground into them which may likely go completely through the new shoulder. Is there a way to get more thickness on the new shoulder? | 1) The existing shoulder will be pulverized. This pulverized material along with the 1.75â€ HMA shoulder pavement will have sufficient strength to support shouldering operations and traffic in general. 2) Based on the operations needed to construct the proposed typical and compaction of the pulverized shoulder material, the actual thickness of the shoulder surface layer will vary between 1.75â€ and 2â€. | Mike Coleman | 2 | 2021-10-27 15:35 | 2021-10-28 12:51
20211109 | 20211109027 | 27 | Pulverizing Depth | What pulverizing depth is required? | A 4-5 inch pulverizing depth is required. | Mike Coleman | 3 | 2021-10-28 16:17 | 2021-11-01 07:30
20211109 | 20211109031 | 31 | Time frame and mix Type | Within the prosecution and progress section with the special provisions it states that the lower lift of HMA pavement needs to be placed within 48 hours and the surface lift of HMA need to be placed within 15 days of paving the lower lift. This requirement does not allow enough time to completely mill and place the first lift on the extent of the project thus requiring two separate phases to meet this time frame. Would the state consider a 4MT lower lift versus a 5MT lower lift which would be a cost savings? | After discussing this with the Region's pavement design engineer, we will be issuing an addendum to address the questions below. This addendum will: 1. Switch the binder bid type to 4MT pavement 2. Clarify that the milled surface shall be covered within 72 hours but removing any timing restrictions associated with covering the lower lift with the surface layer. | Mike Coleman | 1 | 2021-10-12 14:33 | 2021-10-18 09:43
20211109 | 20211109031 | 31 | Sheet Membrane Waterproofing | There is not a domestic material for sheet membrane that meets the specifications in the proposal. In the past the material used was Mel-Dek. It does not meet Perms, or softening point. Is this material acceptable to use for this project? |  |  | 2 | 2021-11-04 09:35
20211109 | 20211109032 | 32 | Shim Packs incidental to Non-Laminated bearing pads | Do the steel plates & shim need to be fabricated by steel fabricators off the approved list? If yes, which category would govern? - APPROVED FABRICATORS, FABRICATED BRIDGE COMPONENTS â€ STEEL BEARINGS - APPROVED FABRICATORS, LAMINATED ELASTOMERIC BEARINGS - APPROVED FABRICATORS, STEEL BRIDGE PRIMARY MEMBERS - Or other?? | The steel shim plates do not need to be fabricated by a steel fabricator from the Departmentâ€™s approved list for this project. Note that this exception only applies to the steel shim plates. Mill certifications for the steel shim plates shall still be provided to the Department. | Mike Coleman | 1 | 2021-10-25 15:44 | 2021-11-02 09:05
20211109 | 20211109035 | 35 | Type M Rail Post Spacing | On Structure Sheet 8 of 10, the initial rail post spacing dimensions aren't referenced to any specific point on the bridge. | In the notes on sheet 8 of 10, it specifically states: â€œRAIL POST SPACING IS MEASURED AT THE FRONT FACE OF BASE PLATESâ€ The reference line for laying out the rail is an arc that runs through the front face of the base plates. This reference line is located 14 3/8 inches in from the edge of the deck (2 5/8 inch edge of deck offset plus an 11 3/4 inch wide base plate). The reference points are where that reference line (arc) intersects the ends of the deck. | Mike Coleman | 1 | 2021-10-15 08:47 | 2021-10-20 11:49
20211109 | 20211109039 | 39 | Power Poles (Barron & Cumberland) | The specials detail that the power poles will be moved 10' and raised 10' prior to construction. From a site visit, it looks like these are new poles. Have these already been moved, or are they being moved another 10'? From the site visit, in the current location it seems the lines would be over the wing/ abutment corner and it will not be possible to maintain OSHA clearances for pile driving. Thanks much. | Yes, the poles have already been moved. Cumberland Municipal Utility (Electric) field verified the closet overhead line to the roadway is 10 feet from the edge of the existing bridge deck. Cumberland Municipal Utility (Electric) and Barron Electric Cooperative (Electric) have both indicated their overhead lines can be covered if construction means necessitate. | Fred Schunke | 1 | 2021-11-01 09:29 | 2021-11-04 13:35
20211109 | 20211109040 | 40 | Crystal Brook Creek Structure Removal | What is expected / allowed for line # 6, Removing Old Structure 678+12. This would be the culvert removal at Crystal Brook Creek where the proposed bridge will be built. How is the contractor going to grade the new streambed, remove existing pipe, place riprap, etc. Is a diversion needed? Can we work in the creek? Specials, plan sheets, possible bid items need to be added to explain / show what is allowed and expected. | Additional detail was added via Addendum #1. | Jill Fehrman | 1 | 2021-10-26 15:18 | 2021-11-05 07:52
20211109 | 20211109040 | 40 | Paving adjacent to Bridge | Will the department consider the asphalt paving connections to the bridge as part of the PWL specifications - currently shown this way? The paving on both sides of this bridge will be done at a completely different time as 95% of the job. It also may need to come out of a different plant site. Would the department allow for straight QMP for this section of paving? | We understand paving the new bridge approaches may be at a different time than mainline STH 70. Approximately 150â€™ either side of the bridge will be exempt from the PWL requirements. The department would allow QMP for this section. | Mike Coleman | 3 | 2021-11-01 10:56 | 2021-11-03 09:00
20211109 | 20211109040 | 40 | Size of Culvert Pipe Liners | Will bid line item 100, Culvert Pipe Liners (size) 01. 24-Inch, have an outside maximum diameter of 24â€ and an inside minimum diameter of 18â€? The plans and bid form have different sizes noted. The plan show the liner as 18â€. | The 24-inch size noted in the bid item title refers to the size of the existing pipe to be lined. The liner size specified in the plan sheets represents the designers verified liner size (inside diameter) that will fit inside the pipe to be lined and provide the required annular space for grouting. | Jill Fehrman | 4 | 2021-11-08 12:54 | 2021-11-08 12:55
20211109 | 20211109041 | 41 | Barrier System Grading Shaping Finishing | Can you please provide the estimate of quantities (common ex, borrow, salv topsoil, etc) associated with the Barrier System Grading Shaping Finishing item? | Estimated quantities will be added in the Beamguard section of the Miscellaneous Quantities in an upcoming addendum. | Mike Coleman | 1 | 2021-10-21 06:47 | 2021-10-22 07:35
20211109 | 20211109041 | 41 | Various Questions | Base Repair for CIR: - Is the asphaltic patching item for the asphaltic patching in the CIR item? - Will sawcutting be paid by the LF or is it truly incidental to the base repair item? Volumetric and Density Test Strips: - There is 4 volumetric test strips figured but only 1 mix type so should there only be 1 volumetric test strip? - For density test strips there is 4 in the quantity figured. Wondering if there should be 1 for the surface lift and 1 for the binder lift? Or is it possible to switch the binder lift to a leveling layer or QMP density since there is varying thicknesses throughout the entire binder lift. Also the targets for the binder lift vary based on paving over a milled surface or over a CIR base layer. Joint Density: - There is no joint density incentive item Prep of Foundation: - There is no prep of foundation for asphaltic paving item for prepping the milled surface after milling. The typical section references the item but there is no item. Traffic: - Page 3 â€“ For the milling and paving process needing an elevation of 2â€ or less is it allowable for the mill to match up every day and put ramps in at the ends for traffic? - Are the curb & gutter areas required to be filled back with asphalt each day or will that be allowed to be left at a 3.25â€ depth for the 72 hour period. | Base Repair for CIR: - Is the asphaltic patching item for the asphaltic patching in the CIR item? Asphaltic Patching item is incidental to Base Repair for CIR item per specifications. (Addendum - Iâ€™ll include a comment in the Miscellaneous Quantities stating â€œAsphaltic Surface Patching item for pothole/traffic pop-outs repairs, and temporary ramping at butt joints.â€ - Will sawcutting be paid by the LF or is it truly incidental to the base repair item? Sawcutting is incidental to Base Repair for CIR item per specifications. Volumetric and Density Test Strips: - There is 4 volumetric test strips figured but only 1 mix type so should there only be 1 volumetric test strip? Agreed, because the two projects are combined and only one asphalt mix type, 1 volumetric test strip is all that should be required. (Addendum â€“ Reduce the volumetric test strip to 1 for the 8190-00-72 Miscellaneous Quantities sheet and remove volumetric test strip from the 8620-00-73 Miscellaneous Quantities sheet). - For density test strips there is 4 in the quantity figured. Wondering if there should be 1 for the surface lift and 1 for the binder lift? Or is it possible to switch the binder lift to a leveling layer or QMP density since there is varying thicknesses throughout the entire binder lift. Also the targets for the binder lift vary based on paving over a milled surface or over a CIR base layer. Agreed, because the two projects are combined and the binder lifts vary in thickness, 1 density test strip is all that should be required. (Addendum â€“ Reduce the density test strip to 1 for the 8190-00-72 Miscellaneous Quantities sheet and remove the density test strips from the 8620-00-73 Miscellaneous Quantities sheet. Update table in MQ to call Density Acceptance for the binder layer as â€œAcceptance by ordinary compaction per 460.3.3.3â€.) Joint Density: - There is no joint density incentive item Agreed, incentive item needs to be added. (Addendum â€“ Add incentive item to estimate) Prep of Foundation: - There is no prep of foundation for asphaltic paving item for prepping the milled surface after milling. The typical section references the item but there is no item. Agreed, prep foundation for asphaltic paving is required in locations that do not have CIR treatment. (Addendum â€“ Add prep foundation for asphaltic paving item to the 8620-00-73 estimate) Traffic: - Page 3 - For the milling and paving process needing an elevation of 2â€ or less is it allowable for the mill to match up every day and put ramps in at the ends for traffic? This is acceptable, see comment below if elevation difference is greater than 2â€. - Are the curb & gutter areas required to be filled back with asphalt each day or will that be allowed to be left at a 3.25â€ depth for the 72 hour period. Per the traffic specifications, â€œDuring the milling and paving process, the maximum different in elevation between lanes or other adjacent concrete or asphalt shall be two inchesâ€. The concrete curb and gutter would fall in the â€œother adjacent concreteâ€. If WisDOT construction project manager agrees an urban shoulder closure could be utilized overnight for the 72 hour period. If this allows for a continuous binder layer paving operation I think it would be beneficial to the project. An addendum will be issued. | Mike Coleman | 2 | 2021-10-21 14:45 | 2021-10-25 08:34
20211109 | 20211109047 | 47 | Design Schedule | Would the Department be willing to share the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/7jq370lel73t2hd1vm2aoc9ge5182sc6 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-10-07 12:58 | 2021-10-11 07:47
20211109 | 20211109047 | 47 | Concrete Pavement Repair Longitudinal Joint, | Is there more construction detail for the concrete pavement repair longitudinal joint | A construction detail will be issued as part of an addenda. | Mike Coleman | 2 | 2021-10-15 15:11 | 2021-10-19 11:12
20211109 | 20211109047 | 47 | Culvert Liner | The culvert liner says 60". Is the existing pipe 60" or the proposed liner suppossed to be 60" Dia.? | Existing culverts requiring lining are twin 60-inch RCCP as shown on sheet 184. | Mike Coleman | 3 | 2021-10-27 16:39 | 2021-10-28 12:47
20211109 | 20211109047 | 47 | Storm Sewer RCCP Class III 18" | - There is a discrepancy between the storm sewer plans and bid items. Plans show storm sewer class III-B, bid item shows storm sewer RCCP Class III. Which one is it supposed to be? - on the north crossover from the slotted drain pipe to structure 3.0 why is there a 7 foot piece of pipe that drops nearly 5 feet, seems unnecessary? On plan it also show the 7 feet as "storm sewer class III-B special", is this supposed to be a separate bid item? - Also, instead of having the 7 feet of pipe drop 5 feet why can't you raise the 237 feet of storm sewer pipe, connect it directly to slotted drain pipe and connect to existing manhole nearly 5 feet higher than shown on plans? Why can't you have both pipe runs on page 44 of the plan higher in elevation where it connects to structure 3.0 so you aren't 9 feet in the ground at structure 3.0. Just like you show in the plan for the south crossover (page 43, not nearly as deep and makes much more sense) | â€¢ Answer: Install pipe per plan because this will be left in place permanently, and It is preferred to match the top of the pipe at the existing inlet. Most of the pipe could be installed before the median ditch point is raised to minimize excavation. Storm sewer pipe item number adjustment from 608.0318 to 608.3618 will be made in an addendum. | Mike Coleman | 4 | 2021-10-28 16:27 | 2021-11-03 06:48
20211109 | 20211109047 | 47 | culvert liner | The special provisions for culvert liners 60 inch list the ASTM designation for PVC pipe as ASTM 949 this ASTM spec appears to be one that spells out the requirements for pipe sizes 4-36 inchs, does not cover the liner size that would be needed on this project? So the contractor can not use PVC since complying with this spec would force us into not meeting the +/- 5% of flow spec? | The STSP language allows the contractor to provide culvert pipe liners made of several different materials. In reviewing the STSP, and for your information, we reviewed the ASTM Specifications in the special provision, and below is a list of the material that can be used and particular size requirements: â€¢ High-Density Polyethylene (HDPE) o Profile Wall Pipe - Can be used 10.5 inches to 132 inches o Solid Wall Pipe - Can be used 3.50 inches or larger â€¢ Polyvinylchloride (PVC) - Can be used 4 inches to 36-inches Also please see the Departmentâ€™s Approved product List for Culvert Pipe Liners referenced in the special provisions. | Jill Fehrman | 5 | 2021-11-05 09:09 | 2021-11-08 07:41