## qandasearchletting_results
Date: | 2022-09-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220913 | 20220913003 | 3 | Soil Borings | Please provide a copy of the soil boring report. | The Soils Report and Report Amendment can be found at the following location: https://wisdot.box.com/s/w9ibfrjyvnbx79do94pu4wgj69x34d8n or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-08-18 09:16 | 2022-08-18 11:58
20220913 | 20220913003 | 3 | Soils Report | It does not appear there is a soils report in the Contractor Data packet at this time on the HCCI website. Could the Department provide the Geotechnical Report for this project? | The Soils Report and Report Amendment can be found at the following location: https://wisdot.box.com/s/w9ibfrjyvnbx79do94pu4wgj69x34d8n or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-08-18 12:05 | 2022-08-18 12:08
20220913 | 20220913006 | 6 | Traffic Signal Controller | Can you please confirm what brand/type of traffic signal controller is being used at the intersection for this project? | The traffic signal controller will be an Econolite TS2. | Mike Coleman | 1 | 2022-08-10 10:12 | 2022-08-15 07:07
20220913 | 20220913006 | 6 | Structure Artwork | Can a .dwg file be provided for the proposed artwork and details for the graphics? | The structure plans include wall elevations of the proposed artwork and details of the graphics. Electronic format files showing the proposed artwork can be made available to the successful bidder if requested. | Mike Coleman | 2 | 2022-08-15 07:24 | 2022-08-15 07:26
20220913 | 20220913006 | 6 | Schedule, Soil Borings & Excel Earthwork Data | Can you provide the design Schedule, Soil Borings & Earthwork Data in Excel? | The Design Schedule, Soil Borings & Excel Earthwork Data can be found at the following location: https://wisdot.box.com/s/gmh42wdskcah9ry0c6ih5fnqe4gjnl8a or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2022-08-15 08:44 | 2022-08-16 05:45
20220913 | 20220913006 | 6 | SIGNAL MOUNTING HARDWARE | There is no proposal pay line number for signal mounting hardware for USH 14 & Pleasant View Rd, but there are signals lines 0636 - 0640. Can you please confirm if you want signal mounting hardware quoted for this intersection or not? | Bid item 658.5069 Signal Mounting Hardware (Pleasant View Road and USH 14) will be added via an upcoming addenda. | Mike Coleman | 4 | 2022-08-16 10:16 | 2022-08-18 12:45
20220913 | 20220913006 | 6 | 22. Public Convenience and Safety? | 22. Public Convenience and Safety says you can't work at night and in 3. Prosecution and Progress says multiple nights are available to install storm sewer crossings. I assuming we the Prosecution and Progress is right and 22. Public Convenience and Safety needs to me modified? | The article for Public Convenience and Safety states â€œDo not operate motorized construction equipment from 7:00 PM until the following 7:00 AM (Sunday night through Saturday morning) and from 7:00 PM until the following 10:00 AM (Saturday night to Sunday morning), unless prior written approval is obtained from the engineer.â€ which does allow for work at night as long as approval is obtained from the engineer. The section in the article Prosecution and Progress also states to â€œRequest approval from the engineer for all closures.â€ So the two articles are in agreement and state that engineer approval is required ahead of performing work at night for the installation of storm sewer crossings. | Mike Coleman | 5 | 2022-08-16 12:35 | 2022-08-17 06:09
20220913 | 20220913006 | 6 | Utility Conflicts | It appears multiple Utilities are going to be relocated during construction, some taking up to 120 days to complete there work. There is no way this project can be built in the specified schedule while waiting for the Utilities to be relocated during construction. Can the Utilities be relocated during the winter months before construction starts in the spring of 2023? Will the department allow additional time if the utilities are holding up construction work? | Understanding it is desirable for utilities to relocate ahead of construction, in this situation the depth of cut and fills along with the proposed rock cut necessitated the relocation of utilities during construction. The utility relocation work was coordinated to occur following completion of rough grading by the contractor for each stage. Contract time extensions will follow subsection 108.10 of the standard specifications. | Mike Coleman | 6 | 2022-08-16 12:41 | 2022-08-17 06:09
20220913 | 20220913006 | 6 | Traffic Control Narrative versus Traffic Control Plans | It appears that the narrative and the staging plans do not agree. Could the Department please verify which is to be followed? | In general it appears the Traffic article agrees with the drawings. If there is a discrepancy between documents, subsection 105.4 of the standard specifications will govern and the Special Provisions will take precedence over the Plans. | Mike Coleman | 7 | 2022-08-22 10:11 | 2022-08-26 08:40
20220913 | 20220913006 | 6 | Swallowtail Pond - Excavation | Currently Swallowtail's Pond excavation is under common excavation, which is not the appropriate bid item for his work. Swallowtail pond is an existing pond with 2-4' of water in it and the excavation is silty marsh material (not useable for embankments). Can this pond excavation be removed from the Common Excavation bid item and placed under Marsh Excavation which is the correct bid item? | The excavation required for the Swallowtail Pond will remain bid as Excavation Common. The Excavation Marsh bid item is to perform required excavation below the original ground level of marshes and swamps underlying proposed embankment. Within the Swallowtail Pond the proposed Excavation Common is used to lower the existing pond depth and will not have proposed embankment placed at this location. The earthwork summary table will be modified via an upcoming addenda to indicate all of the Excavation Common from Swallowtail Pond will be considered waste. | Mike Coleman | 8 | 2022-08-22 11:04 | 2022-08-26 08:41
20220913 | 20220913006 | 6 | Article 40. Embankment | Can a special bid item be created for the work specified in Article 40. Embankment (This special provision describes providing special compaction for embankment placed between Station 115+50 and Station 118+25.) vs making it incident? There is not a bid item for Embankment, so where should the contractor cover this incidental work? It would be helpful to create a special bid item for this work. Also 1 test per 150 cubic yards seems very excessive and not beneficial. That is about every 12 dump truck loads. Base Course under the Asphalt is tested every 3,000 ton which equals 1,500 CY, this seems more appropriate. Can the frequency be changed to 1 test per 1,500 cy regardless of the lifts it takes to achieve 1,500 cy. | The proposed embankment between Station 115+50 and Station 118+25 serves a dual purpose of roadway embankment and is considered a small dam for the outlet end of the Swallowtail Pond. Given the intended use the geotechnical consultant recommended the special compaction and testing requirements. The additional testing frequency follows the same testing frequency as MSE wall backfill as specified in Article 154 Section C.4.5. A separate SPV bid item for embankment at this location will be added via an upcoming addenda. | Mike Coleman | 9 | 2022-08-22 11:22 | 2022-08-26 08:44
20220913 | 20220913011 | 11 | Design Schedule | Please provide the Design Schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/nqxj4imvfxzqlfvp405dgghema9spooz or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-08-14 16:31 | 2022-08-15 08:35
20220913 | 20220913011 | 11 | Soil Borings | Please provide a copy of the soil boring report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/nqxj4imvfxzqlfvp405dgghema9spooz or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-08-16 15:10 | 2022-08-17 09:04
20220913 | 20220913011 | 11 | Topsoil and Salvaged Topsoil | Why are the quantities for Topsoil and Salvaged Topsoil identical? Will both items be paid? Are the Organic, Clay, Silt, Sand & Gravel requirements set forth in Article 22 of the Special Provisions necessary? This may require the manufacture and import of topsoil which will add substantial cost to the project. | Article 22 will be removed via addendum. | Mike Coleman | 3 | 2022-08-17 10:00 | 2022-08-24 10:25
20220913 | 20220913011 | 11 | Base Aggregate Items | Base Aggregate 1-1/4" is proposed at Sta 3+39 - 390+03 per the Table for Base Aggregate Items on Page 185 of plan. In addition to the detail for installation of culvert pipes on page 15 of plan, where else is this material going to be used? | Base Aggregate 1 ï¿½-inch is also being used in the widening area from 50+53 to 53+47, per the construction detail on page 13 of the plan. | Mike Coleman | 4 | 2022-08-17 10:06 | 2022-08-18 12:47
20220913 | 20220913012 | 12 | SIGNAL HEAD COLOR | In the proposal special provisions, page 20 has specs for traffic signal faces that state signal head housings shall be black. Just below that, specs for pedestrian signal faces state to use yellow housings. Please confirm if this is correct that signal head housings should be black and pedestrian housings should be yellow, or is this an error and all housings should be the same color black or yellow? | The traffic signal housings should be yellow for both the signal and ped heads and the backplates should be standard black. An addendum will be issued. | Mike Coleman | 1 | 2022-08-11 09:26 | 2022-08-16 13:22
20220913 | 20220913019 | 19 | 0086 516.0610.S Sheet Membrane Waterproofing for Top Slab (structure) 01. C-48-0025 | Good Morning, I see the specifications have for this item have been updated since last year. This will potentially allow a manufacturer to meet the specifications as written (they are running the independent tests now). However, of the manufacturer(s) who can potentially meet the material specification, none currently offer any "certification" program for installers. So currently, no contractor can meet that portion of the specification. Will the Department consider waiving this requirement? Additionally, due to COVD travel restrictions last year, The Department was amenable to "facetime" the manufacturer's representative during installation, as the manufacturer would not permit it's representatives to travel to job sites. Will the Department accept this as "having a manufacturer's representative on site" again this year? Thank you for your consideration. | Certification of the installation will be via the manufacturerâ€™s representative that is onsite during the installation. This representative must be familiar with the installation procedures of the waterproof membrane. The â€œcertificationâ€ as indicated in the last sentence of C.1 of the special provision is not a paper certification or class requirement, the intent is for the representative to certify installation was properly completed. As direct and extended observation is required for the representative to see the contractorâ€™s installation methods, the Department is not going to allow â€œfacetimeâ€ for the manufacturerâ€™s representative to review the work. Additionally, the APL list for Sheet Membrane Waterproofing for Buried Structures will be updated by the department in the near future. | Mike Coleman | 1 | 2022-08-17 09:02 | 2022-08-23 06:59
20220913 | 20220913028 | 28 | Photos | Are there photos available of the bridge maintenance issues? | Photos and photo log can be found at the following location: https://wisdot.box.com/s/br7n9qomqqswsc9eyrobto62bn1qugza or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-08-10 09:07 | 2022-08-10 09:14
20220913 | 20220913028 | 28 | DBE GAOL | We were not able to find any qualified DBE Companies to quote in whole or part of any scope of work on this contract last time this project bid. Since the scope stayed the same, were not going to have success in achieving the 2% DBE Goal. Can the DBE Goal be reduced to Zero (0.00%)? Factors on not receiving quotes is the lack of DBE companies in the geographical area of project plus the limited and very technical scope that no Certified DBE companies exist to quote. It would take a lot of stress out of the bidding process to eliminate the DBE goal on this project. Thank You for the consideration. | The DBE Utilization Engineer has reviewed your request. The DBE goal shall remain 2%. | Mike Coleman | 2 | 2022-08-16 20:07 | 2022-08-17 11:49
20220913 | 20220913006 | 6 | Swallowtail Pond Borings | It appears from the Swallowtail Pond plan sheets, borings were completed within the pond limits but they were not provided with the other Boring Data provided earlier. Please add these borings to the drop box. | The Geotech report for the Swallowtail Pond can be found at the following location: https://wisdot.box.com/s/gmh42wdskcah9ry0c6ih5fnqe4gjnl8a or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 10 | 2022-08-22 13:33 | 2022-08-26 09:19
20220913 | 20220913003 | 3 | Existing Underlying Concrete Pavement | The note on page 5 of the plan indicates the existing underlying concrete pavement may contain reinforcement. Is the existing reinforcement continuous steel? | Based on completed adjacent projects, it is anticipated that the concrete has continuous steel reinforcement. The exact limits of the steel reinforcement is unknown. Removal of steel reinforcement will be incidental to the concrete pavement removal as shown in the plans. | Mike Coleman | 3 | 2022-08-23 07:19 | 2022-08-24 07:33
20220913 | 20220913006 | 6 | Pond Liner Clay | Per the specials, the current liner requirements match WDNR Technical Standard 1001 Type A liner. Per the technical standard, High Density Polyethylene and Geosynthetic Clay Liners are listed as equivalents. Would the Department allow for an alternative liner for the Pond Liner Clay as long as it met the requirements for the WDNR 1001 Standard, Type A Liner? | Per guidance from the City of Madison, for this project the Department will not accept an alternative liner for the Pond Liner Clay bid item. | Mike Coleman | 11 | 2022-08-24 09:27 | 2022-08-26 09:28
20220913 | 20220913018 | 18 | Culvert Removal, Turbidity | What is the design intent for limiting the amount of sediment that may enter the active waterway during removal of the existing culvert at structure B-35-54? | Sediment control should be managed using turbidity barrier that is installed in the open bottom box culvert as shown in the plans. | Mike Coleman | 1 | 2022-08-24 15:37 | 2022-08-26 10:11
20220913 | 20220913022 | 22 | Protection Angle | Should the length of protection angle be 23'-1 1/8" since it normally does not extend through the wings? | The length shown on the plan is correct. The protection angle length shown on the plan does not extend into the wing tops when the skew of the bridge is accounted for. | Mike Coleman | 1 | 2022-08-24 16:00 | 2022-08-25 08:07
20220913 | 20220913006 | 6 | Railing Anchor Bolt Grade | Is an ASTM A193 Type 316 anchor bolt an acceptable substitute to the ASTM F593 Type 316 listed in 513.2.1(4)? | For this project and specific anchor bolt location, it is acceptable to substitute ASTM A193 Type 316 anchor bolt for the contract specified ASTM F593 Type 316 listed in standard spec 513.2.1(4). This substitution should be taken as an acceptance for this project and location only. An addendum will be issued to add the substitution. | Mike Coleman | 12 | 2022-08-24 16:30 | 2022-08-29 08:59
20220913 | 20220913003 | 3 | Continuous Steel Reinforcement | Is there additional information available regarding the size of the steel or as-builts depicting the pattern / spacing of the steel reinforcement? | No additional information is available regarding the size of the steel or pattern/spacing of the steel reinforcement. Bid as shown in the plans. Removal of the steel reinforcement will be incidental to the concrete pavement removal. | Mike Coleman | 4 | 2022-08-25 15:19 | 2022-08-29 08:57
20220913 | 20220913019 | 19 | Rubberized Membrane for the top of the box culvert | Will the Department's new APL for this membrane be issued prior to the letting? Two of the known manufacturers for this type of product indicated they cannot meet this specification. Both indicated that it seems the Department has written the specification around a particular product. Can you share what manufacturer or product you are basing your specification on? | A new spec that hasn't been released addresses this. An addendum will be issued to replace with the new specification. | Mike Coleman | 2 | 2022-08-26 07:02 | 2022-09-08 12:43
20220913 | 20220913012 | 12 | Design Schedule | Can the Design Schedule be provided? | ***the first schedule was incorrect. The latest version has been added. The design schedule can be found at the following location: https://wisdot.box.com/s/75sb4euwpi01ftyrrox4z458fxsbeatr or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-08-26 07:25 | 2022-08-29 10:23
20220913 | 20220913004 | 4 | Prosecution and Progress | What is the department's reasoning for not starting the work after August 1st, 2023? | Based on the FDMâ€™s percentage of probable working days for asphalt paving and the 40 working day contract, August 1, 2023 is the last day work could start before the project extending into November. The FDM does not recommend paving or painting in November. The quality of HMA pavement and pavement marking would diminish. | Mike Coleman | 1 | 2022-08-26 08:09 | 2022-08-29 08:56
20220913 | 20220913005 | 5 | Prosecution and Progress | Milling Operations If we bevel the centerline can we stay in one lane? | The centerline may be beveled at a 3:1 (H:V), but the HMA paving operations shall begin within 96 hours of the start of Removing Asphaltic Surface Milling operations. The contractor would be financially responsible for any additional traffic control items such as pavement marking, signs, etc. | Mike Coleman | 1 | 2022-08-26 08:12 | 2022-08-29 09:01
20220913 | 20220913006 | 6 | Spec Item 87 - McGraw Edison Luminaires | The factory has kicked back my request for pricing on these luminaires, stating they are not McGraw Edison part numbers. Can you verify the part numbers? Thank you! | The luminaires originally specified have been recently discontinued by the manufacturer. Replacement luminaires are being investigated and will be addressed via an upcoming addenda. | Mike Coleman | 13 | 2022-08-26 14:29 | 2022-09-01 10:48
20220913 | 20220913028 | 28 | FINISHING ROADWAY | WHAT DOES THE ITEM "FINISHING ROADWAY" ENTAIL ON THIS PROJECT? | Please refer to Standard Specifications section 213. 213.1 Description (1) This section describes destroying noxious weeds, cleaning out drainage structures installed under the contract, cleaning out material deposited in existing structures as a result of construction operations, removing and disposing of litter and debris, and final trimming and dressing required to neatly and satisfactorily restore and complete the entire roadway for any project or portion of a project where grading and drainage or structures are a part of the contract. (2) This section also describes destroying noxious weeds; removing and disposing of litter and debris; and the final shaping, finishing, trimming and dressing of shoulders, shoulder slopes and other portions of the roadway disturbed by contractor operations, on contracts for constructing base, or surface course, on any project or portions of a project where grading and roadway construction was or will be substantially completed under other contracts. | Mike Coleman | 3 | 2022-08-28 07:45 | 2022-08-29 10:25
20220913 | 20220913028 | 28 | EXISTING CLEARANCE AT PORTALS | WHAT IS THE EXISTING CLEARANCE AT TH PORTALS OF THE BRIDGE? | The minimum existing vertical clearance from the lowest horizontal strut to the crown of the roadway is approximately 18â€™-3â€. | Mike Coleman | 4 | 2022-08-28 18:52 | 2022-08-29 10:25
20220913 | 20220913015 | 15 | Line Item 0204, 4" grooved permanent tape | Good morning, this project butts up to project #16 on this letting. Project #16 calls for grooved contrast tape whereas this project calls for grooved tape (no contrast). Should the tape on this project be switched to contrast tape? Will an addendum be issued to make this change? Thank you. | An addendum is being issued to correct this. | Mike Coleman | 1 | 2022-08-29 08:14 | 2022-08-30 11:35
20220913 | 20220913005 | 5 | Temporary Paint Quantities | Good morning. It appears that there are quantities of temporary paint for the binder layer but not the milled surface. The milled surface can be left for 96 hours. What are the plans for guiding traffic on the milled surface? Will an addendum be issued to add temporary paint on the milled surface? Thank you. | The existing pavement thickness is 3â€. The milling depth is 3.5â€. There will be no milled surface. No Passing Zone signs will have to be installed while traffic is running on the base course. No addendum will be issued to add more temporary paint. | Mike Coleman | 2 | 2022-08-29 08:57 | 2022-09-01 10:44
20220913 | 20220913006 | 6 | B-13-892 Steel Truss Facade | Can the steel truss facade on sheet 764 standoff approximately 4-inches from the exterior face of the truss chord to allow for bolting of the facade plate to the truss? Due to painting requirements, the facade cannot be welded to the truss. | After further discussion with the city of Middleton and others, it has been determined the steel truss façade element will be eliminated from structure B-13-892. Revisions necessary to remove this bid item will be addressed via an upcoming addenda. | Mike Coleman | 14 | 2022-08-29 11:57 | 2022-09-01 10:47
20220913 | 20220913011 | 11 | Cleaning Culvert Pipes | Plan quantity for Cleaning Culvert Pipes is 13 each. A field visit to each location found 12 of the 13 locations have minor to moderate cleaning necessary for 18" to 30" RCP. The cleaning called out at Sta 241'A'+90 is a side by side double box culvert. Each culvert is 7'x7' in size and there is significant silt in the pipes and on the aprons. This is an active tributary to the Fox river. The pipes are approximately 100' long. Will special DNR permitting be required at this location? Will construction equipment be allowed to work in/from the creek bed? This location is very different from the other 12 locations. A special bid item should be considered. | No DNR permitting is required at this location, and the instream disturbance restrictions in the Prosecution and Progress apply specifically to this location. It is the intent at this location that only the west cell of the box culvert on the north side be cleaned, as it has exceeded the anticipated natural bottom of 1â€™. The other three ends are within the 1â€™ of silt build up that is anticipated for the natural bottom. Based on this limited area of clean out, we anticipate the work effort to be similar to the other culverts and therefore a separate bid item is not needed. | Mike Coleman | 5 | 2022-08-29 12:38 | 2022-08-30 09:34
20220913 | 20220913006 | 6 | MSE Walls in a Rock Cut | Why are there MSE Walls in a Rock Excavation Cut Section? Traditionally the rock slope is just left exposed vertically. The MSE walls look like they can be reduced by a lot in the Rock Sections. | Construction of an exposed rock face was reviewed and considered by the design team and geotechnical engineer as part of the design process. Several factors contributed to the design decision to provide retaining walls in lieu of a rock face. | Mike Coleman | 15 | 2022-08-29 12:56 | 2022-08-31 07:09
20220913 | 20220913006 | 6 | Rubberized Membrane Waterproofing for Structures PV3595 & PV3596 | The bid item for rubberized membrane waterproofing includes 34 SY for structures PV3595 & PV3596. Would it be acceptable to use products designed for this application like Mac Wrap or similar products? This would expedite the installation of the structures and backfilling process. | For rubberized membrane waterproofing for structures, only products from the approved products list as specified in subsection 516.2.3 of the standard specifications will be allowed. | Mike Coleman | 16 | 2022-08-30 10:40 | 2022-08-31 07:10
20220913 | 20220913006 | 6 | Swallowtail Pond | There has been history of contaminated soils in and around this pond. Has there been testing to confirm this material is "clean"? Or will there be the possibility of having to haul to a landfill (change in the work)? | Borings were completed and testing following NR 528 parameters was completed for the Swallowtail Pond location. The results of the testing confirmed the material to be excavated is â€œcleanâ€. | Mike Coleman | 17 | 2022-08-30 11:06 | 2022-08-31 07:11
20220913 | 20220913006 | 6 | Design Conversion Factors (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4", Base Aggregate Dense 1-1/4" and Select Crushed Material? | The following design conversion factors were used to develop quantities: Base Aggregate Dense 3/4-Inch: 2.1 tons/CY Base Aggregate Dense 1 1/4-Inch: 2.0 tons/CY Select Crushed Material: 1.9 Tons/CY | Mike Coleman | 18 | 2022-08-30 11:36 | 2022-08-31 07:12
20220913 | 20220913020 | 20 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2022-08-30 15:40 | 2022-09-01 10:46
20220913 | 20220913003 | 3 | DOT Right of Way | The DOT appears to have previously purchased property along the Whitewater Bypass for the future construction of an addition two lanes from Tri County Road to STH 59 / CTH P. If the Whitewater Bypass is expanded in the future, the placement of additional fill material may be required. Since this project contains excess material, would the Department allow the placement of fill material for the future expansion of the Whitewater Bypass? What would be the requirements for placing fill if permitted and at what locations? | Waste material shall be disposed of by the contractor following the requirements in the standards specifications, this contract, and as outlined in the ECIP process. | Mike Coleman | 5 | 2022-08-31 08:37 | 2022-09-07 09:52
20220913 | 20220913006 | 6 | Item # 0780 10" Live Tap | Will a stainless steel taping sleeve with a Ductile Iron flange be considered an equal to specified Ductile Iron Taping sleeve? | Per the City of Middleton stainless steel tapping sleeve with a ductile iron flange will not be accepted as an equal for this project. | Mike Coleman | 19 | 2022-08-31 08:48 | 2022-09-07 07:15
20220913 | 20220913010 | 10 | Railroad flagging | In the specials it mentions Railroad flagging, and Temporary grade crossing, is it the intention of the DOT that for Milling operations and Paving operations and guard rail operations that travel underneath the railroad bridge to perform this work will a rail road flagger be required. and if so does the contractor need to pay the Railroad for this service. | No flagging at the railroad is required in the DOT contract for the work shown in the plans. | Mike Coleman | 1 | 2022-08-31 16:58 | 2022-09-02 09:42
20220913 | 20220913028 | 28 | Scope | Are the suspender cables a part of the contract scope of the work? If so, what is their diameter. | Painting of the suspender cables is NOT included in the contract scope of work. | Mike Coleman | 5 | 2022-09-01 08:16 | 2022-09-02 06:34
20220913 | 20220913028 | 28 | Spot Painting | How large are the smallest areas in question regarding the internal spot painting of the Girders and the Arch and Strut cross Brace Portals? | The plan notes spot painting a total of 320 SF for the strut/cross brace portals. The conditions of all 22 of the strut locations are typical throughout with approximately 14.5 SF required at each location. | Mike Coleman | 6 | 2022-09-01 08:17 | 2022-09-06 10:39
20220913 | 20220913028 | 28 | Structure Repainting General Spec | On page 14 of 41 on the HIGHWAY WORK PROPOSAL, Paragraph 20 â€œSTRUCTURE REPAINTING GENERALâ€ Sub-Paragraph c.1 Repainting Methods states: DO not perform blasting, cleaning and paintingâ€¦â€¦.with prevailing winds in excess of 15 mph. Could there be a design calculation by our PE regarding the determination of the MPH for the project; in the alternate, would the department consider increasing the allowable/prevailing winds not to exceed 35 MPH in order for the State not to expend a lot of downtime work for unnecessary reasons, resulting in higher costs to the DOT? | WisDOT will entertain design calculations, stamped and signed by a registered PE in the State of Wisconsin, completed by the contractor to allow repainting operations to take place in prevailing winds exceeding 15 mph. The submitted calculations must meet all other provisions of the contract, shall include the loading conditions and where the loads will be transferred to the structure, what type of loading is being designed for (i.e., sustained wind, wind gusts, prevailing wind direction(s), etc.), the details of the confinement system and how it is to be connected to the structure, and the PEâ€™s assessment of the ability of the bridge to accommodate these loads. | Mike Coleman | 7 | 2022-09-01 08:20 | 2022-09-07 07:14
20220913 | 20220913006 | 6 | Valve Manholes | For the 10" and 12" RW valves in the valve vaults. Will the connection need to be Mechanical Joint or Flanged Joint. | The bid items Furnish & Install Valve 10-Inch, Item SPV.0060.52 and Furnish & Install Valve 12-Inch, Item SPV.0060.53. indicate valve ends shall be mechanical joint with rubber gasket. The bid Item 12-Inch Check Valve, 2 12-Inch Isolation Valves and Vault, Item SPV.0060.58. requires flanged joints associated with the check valve. | Mike Coleman | 20 | 2022-09-01 11:44 | 2022-09-08 07:00
20220913 | 20220913015 | 15 | Traffic - Lane Closure restrictions | Hello - please clarify the following language out of the Traffic section of the proposal: "All lane and shoulder closures shall be removed when work is not in progress. Place drums and other temporary traffic control on the outer edge of the shoulder when not in use." Does this mean that if the contractor is only working daylight hours that the lane closure needs to be removed daily when work is not in progress? | The lane closures can remain up during the times permitted by the contract documents. Closures are not required to be removed on a nightly basis if the contractor is only working during the day in the time frames permitted in the contract documents. | Mike Coleman | 2 | 2022-09-01 12:10 | 2022-09-06 11:57
20220913 | 20220913023 | 23 | Existing Spring | May the spring be diverted into a french drain directed into the ditch line? | This would be reviewed as a possibility during the ECIP review process. | Mike Coleman | 1 | 2022-09-02 09:23 | 2022-09-06 09:38
20220913 | 20220913020 | 20 | Abandoning Culvert Pipe | The abandoning culvert pipe detail in the plan shows Backfill Controlled Low Strength within the culvert. Is the Backfill Controlled Low Strength supposed to be incidental to the item or should there be a separate pay item for that material? | An addenda will be developed for this item. | Mike Coleman | 2 | 2022-09-06 09:16 | 2022-09-07 07:09
20220913 | 20220913019 | 19 | 4MT Lower Layer Option | For the mainline US 63 work there will be 3.25â€ of paving (1.75â€ lower and 1.5â€ upper). Would the DOT consider switching the lower lift from 5MT to 4MT? This will allow the contractor to provide a more economical bid to the department. This was previously done on STH 46, 8072-00-70. | Yes the Department will change the lower 1.75â€ layer of HMA on mainline USH 63 to 4MT58-34V. An addenda will be prepared for this change. | Mike Coleman | 3 | 2022-09-06 11:04 | 2022-09-08 06:56
20220913 | 20220913019 | 19 | Intersection Paving - PWL | Do to the construction staging of the project and needing to complete the pedestrian trail, 60th Ave intersection, and CTH A/F intersections first there will not be enough area/tonnage to complete a Volumetric test strip for the 5MT mixture specified at the intersection locations (Plan Sheet 2 â€“ Mixture Acceptance Table). PWL requirements will not be able to be meet. The DOT should consider switching the lower lifts for the 60th Ave and CTH A/F intersections to an Asphaltic Surface mixture with a note to provide a specific mix type (3MT or 4MT may work better for the lower lifts). The surface lift could remain under the PWL 5MT 58-34V mixtures as that work will be completed following the mainline US 63 work. | The Department will change the lower layer of HMA at the CTH A/F Intersection and the 60th Avenue intersection to 4MT58-34V with testing by the Department and remove the PWL requirement by the Contractor. | Mike Coleman | 4 | 2022-09-06 11:08 | 2022-09-08 12:45
20220913 | 20220913019 | 19 | Test Strip Quantity | There is only one density test strip noted for Item #50. There will need to be two density test strips, 1 per lift. If the lower layer is changed to a 4MT an additional volumetric test strip would be required. | The Department has changed the lower 1.75â€ layer of HMA on mainline USH 63 to 4MT58-34V. This change will also update the number of density test strips to 2 each and volumetric test strips to 2 each. An addenda will be provided. | Mike Coleman | 6 | 2022-09-06 11:26 | 2022-09-08 07:02
20220913 | 20220913019 | 19 | Interim Completion and Liquidated Damages â€“ Pedestrian Underpass C-48-0025: 35 Working Days | Can the department provide a schedule for the Pedestrian Underpass C-48-0025? There does not appear to be sufficient time to construct this structure in stages. Special provisions require a minimum concrete cure time of seven days before placing the primer for the membrane. Has the department taken the cure time into consideration for the 35 working days? Will the department consider additional time to construct this structure? | 10 working days will be added to the contract for the structure construction/interim completion via addenda. Additionally, 10 working days will be added to the overall contract. | Mike Coleman | 7 | 2022-09-06 11:27 | 2022-09-08 12:47
20220913 | 20220913019 | 19 | Culvert Patches | The mix specified for all culvert patches, is specified to be under Item #62, HMA Pavement 5MT 58-34V. With the minimal tonnage for this item and it being similar to other culvert patches on projects would the DOT consider changing this item to Asphaltic Surface Patching? You could also note in the specials to provide a 4MT 58-34S mixture or other specific mixture for all asphaltic surface patching but it would drop the QMP/testing requirements and costs. | The Department will change the lower 6â€ and middle 1.75â€ layer of 5MT58-34V at the culvert replacement locations to 4MT58-34V and also wave the PWL testing requirement at the culvert replacement locations. An addenda will be prepared for this change. | Mike Coleman | 8 | 2022-09-06 11:28 | 2022-09-08 07:01
20220913 | 20220913019 | 19 | Pedestrian Structure Patch | The mix specified over the new Pedestrian Trail, C-48-0025, is specified to be under Item #60, HMA Pavement 4MT 58-34S. With the minimal tonnage for this item and it being similar to other culvert patches would the DOT consider changing this item to Asphaltic Surface Patching? You could also note in the specials to provide a 4MT 58-34S mixture for all asphaltic surface patching but it would drop the QMP/testing requirements and costs. | The pedestrian trail mix will remain 4MT 58-34S standard bid item. | Mike Coleman | 9 | 2022-09-06 11:29 | 2022-09-08 12:48
20220913 | 20220913019 | 19 | Lane Closure/Work Restrictions | Under Traffic, Lane Closure and Work Restrictions work is not allowed from 12:01pm on Friday to 6:00AM on Monday between Memorial Day and Labor Day (Excluding the Pedestrian Underpass). The current project (1550-04-72/82) that joins this one does not have this restriction. Can the restriction be removed, or could an alternative route be signed and the restriction removed? | The Department recommends the lane closure restriction as noted in the Special Provisions be included during construction. No alternative route will be provided. | Mike Coleman | 10 | 2022-09-06 11:41 | 2022-09-08 06:59
20220913 | 20220913017 | 17 | Anti-Icing Overlay | There is a note on Sheet 67 in the General Notes that states "The existing concrete overlay & anti-icing overlay shall be removed from the bridge deck..." What are the details of this anti-icing overlay? From what I could determine, it was let for bridge around 2007 (Proj #1173-13-70). Can you please explain what the anti-icing overlay consists of? I could find no more mention of it in the plans or bid docs. | A copy of an anti-icing spec can be found at the following location: https://wisdot.box.com/s/i7pbgspe675lxhk9z95u2bffb4xldfgy or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-09-06 12:03 | 2022-09-09 10:24
20220913 | 20220913020 | 20 | Shaping Shoulders | The shaping shoulder quantity appears to be incorrect? Shaping shoulders is measured by the station along the centerline for each shoulder separately. | An addenda will be developed for this item. | Mike Coleman | 3 | 2022-09-06 12:05 | 2022-09-07 07:09
20220913 | 20220913020 | 20 | Temp Paint | Should a Temporary Marking Line Painting 4-Inch item be added for painting the milled surface and/or lower pavement layer during construction? | An addenda will be developed for this item. | Mike Coleman | 4 | 2022-09-06 12:08 | 2022-09-07 07:10
20220913 | 20220913025 | 25 | Lower Layer HMA Type | The plan requires 3.25â€ of paving (1.75â€ lower and 1.5â€ upper). The department may want to consider changing the lower lift from 5MT to 4MT. This would require an additional volumetric test strip. | The Region has considered this request and will issue an addendum to change the lower layer (1.75â€) to 4MT58-34V. An extra volumetric test strip will be added to the addendum as well. | Mike Coleman | 1 | 2022-09-06 13:12 | 2022-09-09 06:46
20220913 | 20220913025 | 25 | Paving Operations Restriction | Under Prosecution and Progress, Paving Operations it states that traffic may only travel on the milled surface up to 72 hours due to the thickness and condition of the milled surface. If the department expects a poor milled surface condition that can only hold up to traffic for 72 hours this should cause concerns with obtaining the required density on the lower pavement layer. Should the lower layer be a leveling layer to accommodate the condition of the milled surface? | The 72 hour requirement will reduce the risk of deterioration during construction and the Region feels the contractor will be able to achieve density. The lower layer will NOT be changed to a leveling layer. | Mike Coleman | 2 | 2022-09-06 13:36 | 2022-09-09 06:47
20220913 | 20220913028 | 28 | Scope of Work | Is there any changes to the scope of work on the current bid vs the June Letting? If yes, please list. Thank You. | There were no changes to the scope of work. Previous addendum items were incorporated into the plan and proposal. Clarification on work schedule was added to the Prosecution and Progress. | Mike Coleman | 8 | 2022-09-06 18:04 | 2022-09-07 09:51
20220913 | 20220913012 | 12 | Pavement Marking Quantities | Good morning, Could you please review the quantity of 50,671'for the contrast skips? It appears this is a road length quantity rather than the skip length quantity. If this is indeed a skewed quantity, will an addendum be issued to correct this? Thank you. | An addendum will be issued to correct the quantities. | Mike Coleman | 3 | 2022-09-07 10:10 | 2022-09-08 12:49
20220913 | 20220913028 | 28 | Hazardous waste disposal cost | Does WISDOT pay for the disposal of hazardous waste generated on this project? | The state has an exclusive mandatory use contract with a private waste management contractor to transport and dispose of hazardous waste. | Mike Coleman | 9 | 2022-09-07 10:22 | 2022-09-07 10:47
20220913 | 20220913019 | 19 | Common Excavation | The misc quantities for common excavation within 1550-02-76 has quantities listed for the culvert replacements. It appears in the cross sections that the common excavation for the culvert replacements is the material directly above the culverts. Is that material really going to be paid as common excavation? | An addendum will be issued to correct this. | Mike Coleman | 11 | 2022-09-07 12:37 | 2022-09-08 12:50
20220913 | 20220913028 | 28 | Drawing No 130 Part A | On page 2 of 4 â€“ Drawing No 130 shows the General Notes depicting the structural repainting With an estimated total of 59,700 SF. The break down total beneath it shows the same SF., However it does not include the Tie Girder . Further down (under AMS STANDARD 595a) it mentions #25240 Blue Exterior ARCH,TIE GIRDER, FLOOR BEAM ENDS AND EXTERIOR STRINGERSâ€¦â€¦. Are the Tie Girders a part of the exterior scope as well? | External tie girder painting includes the following items as noted on sheet 2 of 4 (plan sheet 130): â€¢ Repainting Recycled Abrasive o Floor beam to Tie Girder Connections â€¢ Structural Overcoating Cleaning and Priming o Floor beam to tie girder gusset connections | Mike Coleman | 10 | 2022-09-07 13:46 | 2022-09-09 07:27
20220913 | 20220913028 | 28 | Drawing No 130 Part B | On page 2 of 4 â€“ Drawing No 130 shows the General Notes depicting the structural repainting With an estimated total of 59,700 SF. The break down total beneath it shows the same SF., However it does not include the Tie Girder . Further down (under AMS STANDARD 595a) it mentions #27925 White (Interior Arch and Tie Girder). As it stands, Could you provide as built drawings showing the interior Stiffeners and /or Diaphragms for an accurate take off? In the alternate, could you provide a SF. allowance as per the aforementioned SF. estimates? | The as-built plans can be found at the following location: https://wisdot.box.com/s/br7n9qomqqswsc9eyrobto62bn1qugza or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 11 | 2022-09-07 13:47 | 2022-09-09 07:26
20220913 | 20220913022 | 22 | Cofferdam? | Would the Department consider allowing excavation for the channel under the bridge to be performed using Turbidity barrier on each side of the excavation first, and then flipping the turbidity barrier to seal the section of channel being abandoned/filled in? The cofferdam item could then be eliminated, and allow the grading contractor to perform the majority of the road work prior to bridge construction. It would further facilitate using the excavated materials (after a brief on site stockpile) to be placed back as fill in the slopes upstream and down stream. If this cannot be done, then all of that material will have to be trucked away to a commercial site and then trucked back in. our fear is that this would be less efficient and more expensive. | This would be a change from what the DNR has approved for the site. Given that the project letting is less than a week away, I think the contractor will need to bid the project as shown with the cofferdam. Potential changes to a different system for protecting water quality could be entertained during the ECIP review process, but is not guaranteed to be acceptable. | Mike Coleman | 2 | 2022-09-07 14:15 | 2022-09-08 12:44
20220913 | 20220913020 | 20 | Shaping Shoulders | It appears in addendum 2 the shaping shoulders item was eliminated instead of correcting the quantity. The item is needed for shaping the shoulders after milling and before paving to ensure proper drainage. | After review of the Facilities Development Manual and the Standard Specifications, it was determined that this item was not needed for this project. FDM Chapter 19-5-3 Section 3.2 â€“ â€œShaping Shoulders bid item is not needed to maintain drainage for milling, or pulverizing operations as standard specification for those items address maintaining drainage. Generally, Shaping Shoulders is not needed on projects where new base aggregate is being placed on existing shoulders.â€ Under the Removing Asphaltic Surface Milling, Item 204.0120, Section 204.3.2.2.2(5) of the standard specifications it states â€œGrade shoulders adjacent to milled areas by the end of each work day to provide positive drainage of the pavement.â€ | Mike Coleman | 5 | 2022-09-07 19:47 | 2022-09-08 12:39
20220913 | 20220913021 | 21 | Item 203.0260 - Structure Removal Minimal Debris | With the updated standard specification for Minimal Debris, is it the designers intent that this cast in place girder bridge, removed in stages, be allowed to drop safely in large pieces and remove the large pieces or is it the designers intent to provide an extensive removal plan of false decking the stream, sawcutting the structure, provide for slurry containment and utilize large lifting equipment to meet the currently used bid item specification? |  |  | 1 | 2022-09-08 08:05
20220913 | 20220913008 | 8 | Article 8. Blanchard's Cricket Frog | Is the mowing, trimming, and/or hand clipping that is necessary in this Article incidental to the contract or is there a missing SPV for this work? | Work associated with this article does not have a bid item. The work is incidental to the contract. | Mike Coleman | 1 | 2022-09-08 08:48 | 2022-09-09 11:18
20220913 | 20220913014 | 14 | Earthwork Table | For the C-20-0163 culvert the earthwork table states that the salvaged unuseable pavement is included in the cut although the salvaged unuseable pavement number is higher than the cut number. Can you review and explain the earthwork table? Thank you | In the Common Excavation column, the salvaged/unusable pavement material was inadvertently left off. A new earthwork table will be available at the pre-construction meeting. | Mike Coleman | 1 | 2022-09-09 07:35 | 2022-09-12 11:43
20220913 | 20220913015 | 15 | Over-mill | The centerline joint on the traffic control typical section show an over-mill of the centerline being 3' max. What is the intent? | The expectation is that the contractor will need to complete milling operations so that any centerline joint deterioration can be repaired. If the centerline joint is in good condition the over-mill distance needs to only be what is required to construct the notched wedge joint. | Mike Coleman | 3 | 2022-09-09 07:56 | 2022-09-09 08:12
20220913 | 20220913015 | 15 | dowel bar locations | Is there any info on the percentage of dowel bar locations that required repairs prior to paving based on the current project under construction which is similar in nature? | On the current project similar in nature of work, the amount of dowel bars that are requiring patching/repairs has been around 50% or less than the original plan quantity for work completed to date. However, this is percentage is not assumed to be representative of what will be encountered on the advertised project for proposal #15. | Mike Coleman | 4 | 2022-09-09 08:10 | 2022-09-09 08:13
20220913 | 20220913019 | 19 | OH Power Line at Station 177+10 | The proposal and plan show an Excel OH power line at 177+10 and indicate no conflicts are anticipated yet there are temporary shoring installation requirements that would appear to be in conflict with this line and cannot be installed while maintaining the required safety distance with an energized power line. What was the designers intention for this location? Can the line be temporarily relocated of de-energized? |  |  | 12 | 2022-09-09 08:59
20220913 | 20220913006 | 6 | MSE Walls in rock areas | What are you requiring for a base psi under the retaining walls? | Refer to Section B.3.2 of the special provision for â€œWall Concrete Mechanically Stabilized Earthâ€ for requirements related to the concrete leveling pad under the wall. Refer to the â€œWall External & Overall Stability Evaluationâ€ table in the retaining wall drawings for the Factored Bearing Resistance of the subgrade below the wall. | Mike Coleman | 21 | 2022-09-09 09:37 | 2022-09-09 14:37
20220913 | 20220913006 | 6 | Rock Excavation within Structure Excavation Zone of walls | Does the rock within the structure excavation get paid under the Rock Excavation item or is it to be included within the Wall item? | Rock excavation is anticipated for retaining walls R-13-366 and R-13-367. All excavation for the retaining walls (including rock) is included in the retaining wall bid item â€œWall Concrete Panel Mechanically Stabilized Earthâ€ as noted on the structure plans. | Mike Coleman | 22 | 2022-09-09 09:55 | 2022-09-09 14:38
20220913 | 20220913020 | 20 | Barrier System Grading Shaping Finishing | Are cross sections available for the Barrier System Grading Shaping Finishing item? | There are no cross-sections for the area associated with the Barrier System Grading Shaping Finishing item. This will be based on the SDDâ€™s for the guardrail. | Mike Coleman | 6 | 2022-09-10 10:21 | 2022-09-12 10:09
20220913 | 20220913017 | 17 | Temporary Crash Cushion total | The Temporary Crash Cushion total on page 14 in the plan set show 2, but the actual plans call for 4. Why are there only 2 in the line items? Is this a mistake? | The miscellaneous quantities indicate: â€œStage 1 Crash Cushions Temporary will be reused during stage 2.â€ | Mike Coleman | 2 | 2022-09-12 11:25 | 2022-09-12 11:44
20220913 | 20220913029 | 29 | 1 1/4-Inch Diameter Cored Holes, Item SPV.0060.01. - ASBI Certification | The Specification for this item calls out "Grouting operations shall be supervised, inspected and documented by qualified technician(s) and/or engineer(s) who have received training and certification under the ASBI Grout Certification Program." All training classes for this course for 2022 have already been held and no more will be available until 2023. Would a Post Tensioning Institute (PTI) Grout Certification be an acceptable substitute for the ASBI Grout Certification? |  |  | 1 | 2022-09-12 11:46