## qandasearchletting_results
Date: | 2023-08-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230808 | 20230808001 | 1 | Adjusting Inlet Covers | Per the construction details, paving rings are to be placed on the inlets that are called out to be adjusted. Can the Department provide the existing casting dimension or the WisDOT Casting Type that are currently poured into the concrete? | The inlet covers installed on inlets in front of the barrier wall with the previous project were Type â€œVâ€. The Standard Detail Drawing for the Type V inlet cover from the asbuilt can be found at the following location. Page #9 of the as-let plans show â€˜Detail of Inlet Adjustments at Barrierâ€™. Type â€œVâ€ is also shown on this detail. https://wisdot.box.com/s/y4kkm8g2n3xnsmjxrr2ak9kao3ipt1qn or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-07-31 13:40 | 2023-08-01 07:32
20230808 | 20230808001 | 1 | Existing Rumble Strips | There is no item to remove the existing rumble strips. Typically, there are items to remove the rumble strips via "mill and fill" to avoid the rumbles reflecting into shoulder and subsequent lanes during paving operations. Can the Department add items to remove the existing rumble strips? | No additional items will be added to the project to remove the existing rumble strips for staging or reflective cracking purposes. | Mike Coleman | 2 | 2023-07-31 13:43 | 2023-08-01 07:34
20230808 | 20230808002 | 2 | Geo Report | Is there a Geo Tech Report available? | The soils report can be found at the following location: https://wisdot.box.com/s/086e8i5457hfk089xelmgi8jjw9u2w47 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-07-11 12:21 | 2023-07-12 05:56
20230808 | 20230808002 | 2 | APPENDIX D - PROJECT SIGNS | How are the APPENDIX D - PROJECT SIGNS paid for? Can't find the pay item for this work? Can a pay item be added if their in not one? | A bid item will be added via addendum. | Mike Coleman | 2 | 2023-07-18 11:04 | 2023-07-26 12:38
20230808 | 20230808002 | 2 | UTILITIES | 1. is AY McDonald approved to be used as an equal to for water service brass? (corporations stops, curb stops, and couplings) 2. What T-Bolts should be used with EBAA Megalugs, Stainless Steel, Cor-Blue, or Cor-Ten? | 1. The City of Baraboo has indicated that Ford would be the second choice. 2. The City of Baraboo has indicated that Cor-Blue should be used. | Mike Coleman | 3 | 2023-07-26 09:08 | 2023-07-26 12:40
20230808 | 20230808002 | 2 | Design Conversion Factors | What design conversion factors were used on these items of work: Base Aggregate 3/4", Base Aggregate 1-1/4" and Select Crushed? | A conversion factor of 2.1 was used for Base Aggregate Dense 3/4-Inch. A conversion factor of 2.0 was used for Base Aggregate Dense 1 1/4-Inch. A conversion factor of 1.9 was used for Select Crushed Material. | Mike Coleman | 4 | 2023-07-27 06:41 | 2023-07-27 09:26
20230808 | 20230808002 | 2 | MGS Thrie Beam Connection | It appears that at station 33+48.22, the new MGS Thrie Beam Transition will be attaching to an existing retaining wall pier. What is the expectation of how to attach the guardrail to this? Also, will payment for this attachment be incidental to the guardrail or will an SPV be written to cover this attachment? | The intent is for the new thrie beam to attach to the existing retaining wall pier in the same fashion as the Thrie Beam Connection to Bridge Parapet With Square Ends detail shown on SDD 14B45-05D. The intent is for the payment to be incidental to bid item 614.2500 MGS Thrie Beam Transition. | Mike Coleman | 5 | 2023-07-31 09:28 | 2023-07-31 13:39
20230808 | 20230808002 | 2 | Follow-Up to MGS Thrie Beam Connection | The concern to the previous answer is that the wall pier looks to be abnormally thick. It is certainly much thicker than the barrier wall or parapet wall that is depicted in SDD 14B45-05D. The ability to drill through this thickness, including rebar issues, may be quite limited with equipment that is able to drill that depth and cut through any rebar that is encountered. Would the department consider an alternative of some sort to bolting all the way through this concrete block? | The contractor can pursue an alternative connection/anchorage, but that alternative connection/anchorage would have to be approved by the guardrail manufacturer for it to be acceptable to ensure that safety and the integrity of the connection and guardrail is maintained. The alternative would also have to be maintainable, so the connection can easily be replaced as needed or if the guardrail got damaged. | Mike Coleman | 6 | 2023-07-31 14:13 | 2023-08-01 12:11
20230808 | 20230808002 | 2 | Alternative Product | Can we submit our luminaire for review and consideration for the item SPV.0060.97? If so, is there anyway we can attach files here? Thank you! | Electrical components are only used if they are on the EQPL: https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/tools/prods/qpl.aspx You need to submit your product to get on the list. We donâ€™t accept products on a project by project basis. | Mike Coleman | 7 | 2023-08-03 17:09 | 2023-08-04 14:08
20230808 | 20230808004 | 4 | Bill of bars illegible | The bill of bars for the west abutment, superstructure and parapet seem to be distorted and difficult to read. Could these be revised? | An addendum will be issued to replace those pages. | Mike Coleman | 1 | 2023-07-13 14:39 | 2023-07-24 11:56
20230808 | 20230808004 | 4 | Pay Limits of Structure Backfill, Type A | ON sheet 32 of the plans in the elevation view near the west abutment of Bridge B-22-301 there is a note: "FILL VOIDS BELOW RIPRAP WITH BACKFILL STRUCTURE TYPE A, AS NEEDED". Is this backfill included in the "Pay Limits"? | No. Pay limits of backfill are shown and described on sheet 2 of the structure plans. | Mike Coleman | 2 | 2023-07-14 09:34 | 2023-07-24 11:59
20230808 | 20230808004 | 4 | HMA Paving | Given the small quantity, will the DOT consider switching the 3LT and 4 LT HMA pavement to Asphaltic Surface? | An addendum will be issued to change from LT to asphaltic surface. | Mike Coleman | 3 | 2023-07-19 12:45 | 2023-08-01 07:45
20230808 | 20230808005 | 5 | Soil Borings | Are there soil borings available for this job? | The soil borings can be found at the following location: https://wisdot.box.com/s/086e8i5457hfk089xelmgi8jjw9u2w47 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-07-11 09:39 | 2023-07-11 13:21
20230808 | 20230808005 | 5 | Project Schedule | Could the proposed project schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/086e8i5457hfk089xelmgi8jjw9u2w47 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-07-11 10:17 | 2023-07-11 13:08
20230808 | 20230808005 | 5 | CAD Files | Are there CAD files available for this project? | This is a local program project. On local program projects, there is no requirement for contractor data packets. 2D files can be provided after award. | Mike Coleman | 3 | 2023-07-13 15:38 | 2023-07-24 10:52
20230808 | 20230808005 | 5 | Select Borrow for Marsh Backfill | Specials do not state it but is there an acceptable alternative to a granular material for marsh backfill? Other specs have allowed the substitute of Select Crushed Material conforming to standard spec. 312 for select borrow. | Please bid the project as shown in the specials. | Mike Coleman | 4 | 2023-07-17 10:57 | 2023-07-25 14:00
20230808 | 20230808005 | 5 | Select Borrow | During the prebid meeting, it was stated that the select borrow would need to be under 8% of the total sample, not passing the #4 sieve like the specials state. Is this the intent? | Bid the project as the specials are written. | Mike Coleman | 5 | 2023-07-18 13:25 | 2023-07-25 07:54
20230808 | 20230808005 | 5 | Helical Pile Questions | Please provide the unfactored load per pile. What is the allowable deflection criteria at the top of helical pile? For design of bracing and helical pile shaft, Will there be any lateral load to consider per pile or per bent? | 1. As stated in Article 58. Helical Pile, item SPV.0060.07, section B.1 Design Requirements: â€œDesign the Helical Piles to meet the loads provided by the boardwalk designer . . .â€ 2. Limit deflection values at the top of the helical pile to ï¿½-inch unless a lower value is required by the designer of the boardwalk. 3. As stated in Article 58. Helical Pile, item SPV.0060.07, section B.1 Design Requirements: â€œDesign the Helical Piles to meet the loads provided by the boardwalk designer . . .â€ | Mike Coleman | 6 | 2023-07-20 07:22 | 2023-07-25 07:18
20230808 | 20230808005 | 5 | Helical Pile Design Safety Factor | Will forgoing the proof testing of Helical Anchors be considered if a higher safety Factor is used. If so please advise on desired safety factor to be used. | As stated in Article 58. Helical Pile, item SPV.0060.07, section B.1 Design Requirements: â€œIf static load tests are not performed, a minimum factor of safety of 2.5 shall be used in determining the allowable capacity of the piles.â€ | Mike Coleman | 7 | 2023-07-20 20:49 | 2023-07-25 07:16
20230808 | 20230808005 | 5 | Temporary Shoring Left In Place | Could you please verify that good, used material can be utilized for the Left In Place shoring? | As long as it is in good condition and meets the requirements of the specâ€™s, we do not have an issue with the use of used material. | Mike Coleman | 10 | 2023-07-26 13:41 | 2023-07-27 09:27
20230808 | 20230808005 | 5 | Design Conversion Factors | What design conversion factors were used on these items of work: Base Aggregate 3/4", Base Aggregate 1-1/4" and Select Crushed? | Design conversion factors as follows: Base Aggregate Dense ï¿½-Inch used 2 tons/CY Base Aggregate Dense 1 1/4-Inch used 2 tons/CY Select Crush Material used 1.8 tons/CY | Mike Coleman | 11 | 2023-07-27 06:46 | 2023-07-27 09:25
20230808 | 20230808005 | 5 | Marsh Excavation and Select Borrow backfill | 1. Will the Marsh Excavation need to be dewatered completely before the placement of Select Borrow? 2. Are there compaction requirements for the Select Borrow, i.e. does the material need to be placed in lifts and have density requirements? 3. What is the method of measurement for the Select Borrow? | 1. No â€“ up to contractors means and methods. 2. No density requirements follow standard specifications 207.3 for placement and compaction. 3. Follow standard spec 208.4 for measurement. | Mike Coleman | 12 | 2023-07-27 09:34 | 2023-07-31 09:56
20230808 | 20230808005 | 5 | 48. Select Borrow Geogrid, Item SPV.0035.01 | In specials it says this item will be measure by the cubic yard, acceptably completed. Then in the plans it is expanded by 30%, which used means its measured in the borrow pit. How is the item going to be paid? | Item will be measured and paid according to Standard spec 208.4, which allows measurement in original position, in vehicles or final position based on engineerâ€™s judgement. | Mike Coleman | 13 | 2023-07-28 10:33 | 2023-07-31 06:57
20230808 | 20230808005 | 5 | 75. Excavation, Hauling, and Disposal of Contaminated Soil, Item SPV.0195.01 | Please provide a profile along with a full lab analytics of this Contaminated Soil. Without that we canâ€™t provide pricing for this item of work. | The soil was previously profiled and deemed acceptable for disposal at the Dane County Landfill. For bidding purposes, the soil should be assumed to be disposed of at Dane County Landfill. The Phase 3 for the site can be found at the following location: https://wisdot.box.com/s/086e8i5457hfk089xelmgi8jjw9u2w47 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 14 | 2023-08-01 09:23 | 2023-08-03 10:54
20230808 | 20230808005 | 5 | Answer to Question #13 - 48. Select Borrow Geogrid, Item SPV.0035.01 | "Item will be measured and paid according to Standard spec 208.4, which allows measurement in original position, in vehicles or final position based on engineerâ€™s judgement." We understand it can be measured many different ways, but the contractor needs to know how this item will be measured before the bid to determine the price for this item. Please specify now the engineers judgment of measurement. | Usually, it's measured by the project team in the field based on the spec. However, the project team could choose to use any of the methods available in the spec book. Please bid the project as it is written in the spec | Mike Coleman | 15 | 2023-08-01 09:27 | 2023-08-02 08:14
20230808 | 20230808005 | 5 | Property at CTH K and CTH M | Is the county property at the intersection of K and M available to the contractor for staging/stockpiling/etc? Dane County said that was a question that needed to be asked through this portal. | We will permit the use of the property with a permit to work in highway right of way. Our preference would be that the use of this site be outside of the CTH M contract. | Mike Coleman | 16 | 2023-08-02 09:48 | 2023-08-03 06:16
20230808 | 20230808005 | 5 | Temporary Shoring Left In Place Article 74 | This bid item is listed as temporary shoring left in place but the article states that "the proposed retaining walls must be appropriately designed to resist lateral earth and water pressures, as well as any surcharge loads, for the life of the structures." Being that this item is essentially being used as a permanent structure, would the department please provide the design for this wall to the bidders? | The sheet piling is to be designed by the contractor. The details are shown in the plan details and cross sections and the necessary design parameters are in the special provision. | Mike Coleman | 17 | 2023-08-02 11:16 | 2023-08-03 11:02
20230808 | 20230808005 | 5 | Select Borrow / Select Borrow Geogrid | Please define the definition of "granular" in Article 33 and 48 of the Special Provisions. |  |  | 18 | 2023-08-02 14:36
20230808 | 20230808005 | 5 | Select Borrow | What are the pay limits for Select Borrow? Are we to figure backfilling the marsh exc to subgrade or to 1 foot above or ??? Looking for the pay limits. | Please follow construction details on page 17 which state to extend select borrow 1-ft above existing ground elevation. Select Borrow Geogrid bid item as shown on page 18 is required at partial marsh excavation locations and will be backfilled to subgrade elevation. | Mike Coleman | 19 | 2023-08-07 08:07 | 2023-08-07 09:48
20230808 | 20230808006 | 6 | Schedule - | Could the Department provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/l70h44bpxdzmzebexfvumxlgb2ukzav3 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-07-11 10:16 | 2023-07-24 10:43
20230808 | 20230808006 | 6 | Beat Seat Extension | The dimensions for the removal of the existing abutment for the beam seat extension on structures B-40-253 & B-40-254 are extremely vague. Please clarify the removal limits for the beam seat extension. | The removal limits shown in the abutment cross section indicate removal of unsound concrete on the abutment face. Those areas are also shown as hatched shapes in the abutment elevation view and will be verified in the field. Where existing concrete is sound, no removal is required. | Mike Coleman | 2 | 2023-07-20 13:11 | 2023-07-24 12:00
20230808 | 20230808006 | 6 | Painting | Please clarify differences in pay items "Preparation and Coating of Top Flanges (structure)" and "Structure Repainting Recycled Abrasive (structure)." |  |  | 3 | 2023-08-01 11:53
20230808 | 20230808006 | 6 | Painting | Does the pay item, "Preparation and Coating of Top Flanges (structure)" mean to paint the top faces of the beams? If so, tops of beam are touching the underside of bridge deck. Please clarify. |  |  | 6 | 2023-08-01 11:57
20230808 | 20230808006 | 6 | Painting | Please confirm this contract calls for the cleaning and painting of all structural steel on four bridges and cleaning and painting of only specified bearings on two bridges. |  |  | 7 | 2023-08-01 11:58
20230808 | 20230808007 | 7 | Design Conversion Factors | What design conversion factors were used on these items of work: Base Aggregate 1-1/4" and Breaker Run? | Base Aggregate Dense 1-1/4â€ = 2.0 tons/CY Breaker Run = 1.8 tons/CY | Mike Coleman | 1 | 2023-07-27 06:48 | 2023-07-27 10:05
20230808 | 20230808007 | 7 | Backfill for the S32A Concrete Barrier | How is the department paying for the S32A concrete barrier wall backfill? | Backfill will consist of Base Aggregate Dense 1 ï¿½-inch. The typical section and quantities will be revised via Addendum. | Mike Coleman | 2 | 2023-07-31 12:54 | 2023-08-02 10:26
20230808 | 20230808007 | 7 | Foundation for Sign Structure S-40-3098 | The bid document bid item is calling for an MC-III foundation. It's shown as a 2-chord structure. Please advise on how to bid this item. | The bid item 531.5130 FOUNDATION SINGLE-SHAFT TYPE MC-III (STRUCTURE) will be revised to bid item 531.5330 FOUNDATION SINGLE-SHAFT TYPE TC-III (STRUCTURE) via addendum. | Mike Coleman | 3 | 2023-07-31 13:52 | 2023-08-02 10:27
20230808 | 20230808008 | 8 | Project Schedule | Could the proposed project schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/w3rug29bkoy877swr7uohjs8ro5poaxy or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-07-11 10:19 | 2023-07-11 13:15
20230808 | 20230808008 | 8 | Soil Borings | Would the department be able to supply the soil borings for the project? | The soils report can be found at the following location: https://wisdot.box.com/s/w3rug29bkoy877swr7uohjs8ro5poaxy or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-07-19 06:59 | 2023-07-24 13:11
20230808 | 20230808008 | 8 | Earthwork Tables | Could an excel copy of the earthwork data tables on pages 497 to 516 be made available? | Earthwork tables cannot be provided in EXCEL format. | Mike Coleman | 3 | 2023-07-21 10:22 | 2023-07-24 13:13
20230808 | 20230808008 | 8 | Job #8 Aug 2023 letting | Per sheet 215 addenum 1 the 9"concrete pavement quantity is wrong due to a miscalculation I found. Station 159+46 to 192+00 EB should be 9,400 s.y. not 3,403 s.y. Please advise. | The quantity for Station 159+46 to 192+00 EB should be 9,403 SY. An addendum will follow to address this. | Mike Coleman | 4 | 2023-07-27 10:52 | 2023-07-27 11:47
20230808 | 20230808008 | 8 | Bid items 653.0140, 653.0105 | The 12" pullboxes that are in the plan have a side pull for the wire, we all know this is next to impossible to do a 24" box is better for installation and future maintenance. Why in 2023 have we gone back to using the steel pullboxes instead of the poly boxes? Poly boxes last much longer than the steel. | Six Pull Boxes Steel 12x24-Inch will be switched to Pull Boxes Steel 24x42-Inch. The pull boxes will not be switched to poly boxes based on input from the region that will maintain the pull boxes. An addendum will follow addressing changes to the pull boxes. | Mike Coleman | 5 | 2023-08-02 07:18 | 2023-08-03 11:01
20230808 | 20230808008 | 8 | Rock | It is belived that rock will be encountered at around 6 ft depth or so, how will compensation for this be handled when drilling the deeper bases such as Type 10 and Type 13? | Rock will be considered incidental to the Concrete Bases Type 10 and Concrete Bases Type 13 items. | Mike Coleman | 6 | 2023-08-02 07:21 | 2023-08-03 10:55
20230808 | 20230808008 | 8 | Rock Excavation | Will the Department waive the quality requirements, when utilizing the Rock Excavation from within the right of way, as base course or select crushed? | The Department will NOT waive the quality requirements for the rock excavation. The ledge rock contains sandstone seams within the portion that is to be excavated. | Mike Coleman | 7 | 2023-08-02 14:31 | 2023-08-03 08:02
20230808 | 20230808008 | 8 | Structure Excavation | If rock is encountered with the the structure excavation, will the rock excavation be paid under the excavation rock item? | If rock is encountered with the structure excavation, the excavation of the rock is part of the Excavation for Structures Culverts item. Rock excavation for the structures will not be paid for under the excavation rock item. | Mike Coleman | 8 | 2023-08-03 17:24 | 2023-08-04 09:21
20230808 | 20230808008 | 8 | Railroad Flagging | If work is being done adjacent to the railroad, will the Department be adding the Flagging Reimbursement item? | The answer is â€œnoâ€ to the contractor. STSP 107-026 was added correctly. RR Flagging is incidental. This Railroad at the STH 15 east of STH 45 crossing has not charged very many days of flagging and has made special arrangements with the highway contractor. If the contractor wants more information on these arrangements, they should call the flagging contact in the specials and or the highway contractor on the other project. | Mike Coleman | 9 | 2023-08-04 15:32 | 2023-08-07 09:41
20230808 | 20230808011 | 11 | Crack & Damage Survey | QTY for C&D is usually (1 each for the entire project) This project has 23 each. I am counting 30-35 business/residences on the project that are front facing STH 13 (Per the SPV) Do you have a list of the address for the 23 that need to be done or was this an error by putting in a number of surveys that need to be done? | The 23 locations for the Crack and Damage Survey are listed in the plan set. They are listed on the Miscellaneous Quantity Sheet, page 156. | Mike Coleman | 1 | 2023-07-28 10:02 | 2023-07-31 10:52
20230808 | 20230808011 | 11 | milling/butt joints | Can you please provide more detail on the locations to be milled around the detour area. Only details found on the plans are on Sheets 123 and 131. I also saw no detail for the butt joints, please provide detail on how those are to be quantified and paid. | No detail was included because the milling operation is replacing the same amount of pavement, 2â€, with no transition area â€“ butt joint required is a 2ft max â€“ cross mill operation across the full width street. Detail showing this can be provided at pre-con. Butt joint quantity is included and paid for in sy. Located along the area not receiving new pavement at the beginning of construction. W Bigelow from existing STH 13 to 8th (CTH C) and at the abutting side streets. Additional Quantities from the end of the new paving at Holman road along Washington Avenue up to STH 13 on the detour route. These quantities will occur after the STH 13 project is complete and traffic is back on STH 13. | Mike Coleman | 2 | 2023-07-31 14:58 | 2023-08-04 07:34
20230808 | 20230808011 | 11 | On-the-Job Training Graduate at $5.00/HR | The description for this bid item is $5.00/HR but the locked unit price in the AASHTOWare Project Bids file has it at $4.00/HR? | Since this is currently locked in the bid price of $4/hr and should have been $5/hr, this can easily be taken care of with a CCO in the field. | Mike Coleman | 3 | 2023-08-03 22:47 | 2023-08-04 09:20
20230808 | 20230808012 | 12 | Road Closure/Detour | Is the detour required in 2023 and 2024? The Special Provisions reference opening a road closure by an Interim Completion Date in both 2023 and 2024, but the Misc. Qty's state that Type II covers only have one cycle. If the detour is required in both years please review the Traffic Control Misc. Qty table. Thanks | The detour is not required 2023, it is only required in 2024 for the STH 113 Curve Reconstruction work (from Station 202+10 to Station 220+50). This is planned to be clarified in the Special Provisions with an addenda. | Mike Coleman | 1 | 2023-07-26 11:25 | 2023-07-26 13:28
20230808 | 20230808012 | 12 | Temporary Pavement Marking Item | Should the temporary pavement marking item shown as 643.3120 Temporary Marking Line Epoxy 4-inch Yellow actually be item 643.3105 (Temporary Marking Line Paint 4-inch)? The temp paint item would be used on the milled surface and lower layer of asphalt and the existing item 646.4520 Marking Line Same-Day Epoxy 4-inch Yellow would be used on surface. |  |  | 2 | 2023-08-04 15:07