## qandasearchletting_results
Date: | 2023-11-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20231114 | 20231114001 | 1 | milling quantity | Please review the milling quantity. It appears quantity is based upon milling 10 feet wide on the outside shoulders and 6 feet wide on the median shoulders. Typical sections Show 8 feet for outside shoulders and 4 feet for median shoulders. Which dimensions will be used? | The milling item was reviewed and determined to be the incorrect quantity. Typical sections are correct. An addendum will be issued to correct the quantity. | Mike Coleman | 1 | 2023-10-19 07:52 | 2023-10-25 06:24
20231114 | 20231114001 | 1 | asphalt shoulders at guardrail | Looking at similar past projects in this general area, it appears that guardrail sections and ramp gore areas which a milling machine would not easily access without special effort have been skipped. Will this continue to be allowed for this project? | The areas of concern will be milled as part of this project. Skipping may have been allowed on other projects due to upcoming scheduled projects in those areas. An addendum will be issued to clarify gore area quantities in the westbound lanes of Exit 92. | Mike Coleman | 2 | 2023-10-19 07:53 | 2023-10-25 06:25
20231114 | 20231114002 | 2 | Earthwork Data Table Notes | Could the department please provide the Notes for the Earthwork Data tables beginning on sheet 179? The table references Notes 1, 2, 3, and 8. Thank you. | The earthwork data notes can be found at the following location: https://wisdot.box.com/s/l1nd4qj5qxxecandfccxqfh708e7zfa2 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-01 12:05 | 2023-11-09 15:05
20231114 | 20231114004 | 4 | Storm Sewer and Culvert Items | Would the Department be opposed to issuing an addendum to allow for Class IIIA or Class IIIB culvert bid items to â€œClass III-A and Class III-B items â€¦ to introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inchesâ€ (FDM 13 â€“ 15.2 par. 3) | The Department does not plan to issue an addendum for Class IIIA or Class IIIB culvert pipes on this project. | Mike Coleman | 1 | 2023-10-27 14:20 | 2023-11-02 11:10
20231114 | 20231114004 | 4 | Boring Logs | Has the Department performed any subsurface explorations at any of the culvert structures? If so, could the boring logs be provided for any exploration that was performed. | The road cores can be found at the following location: https://wisdot.box.com/s/xv0aljx5ph22ysw3pe07kdznd7552fon or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-11-08 07:00 | 2023-11-08 11:53
20231114 | 20231114005 | 5 | Research and Locate | I would assume the creator of the Plat would not be able to do the work for Item SPV.0060 Special 03 Research and Locate Existing Land Parcel Monuments LINE 200. Being that the DOT has already paid the plat creator to research and Locate Land Parcel Monuments. | After communicating internally with the DOT SWR Plat Coordinator about this, they felt there was no issues with the plat creator doing the work for â€˜Item SPV.0060 Special 03 Research and Locate Existing Land Parcel Monuments LINE 200â€™. It was figured that there would be savings in the project effort since they have the materials, information, and awareness already rather than having another party perform this work. | Mike Coleman | 1 | 2023-11-05 08:38 | 2023-11-10 10:05
20231114 | 20231114005 | 5 | research and locate | There would be a savings if Jewell did the work but it would not be equal for other contractors doing the work. The items should be eliminated and the state could just hire Jewell to do the work outside of the construction. if the State wants the savings of the work already being paid for. |  |  | 2 | 2023-11-10 10:40
20231114 | 20231114008 | 8 | Adjusting and Replacing Guardrail Items | It appears to us that these bid items are being used in EAT's. The FDM expressly forbids using these standard bid items for this purpose. Will the Department please change these items to SPV's or describe exactly which posts, panels, hardware, and blocks need adjustment or replacement so the contractor can accurately bid this work? | We will be issuing an addenda to clarify this work. | Mike Coleman | 1 | 2023-10-26 11:26 | 2023-10-31 07:00
20231114 | 20231114009 | 9 | Adjusting Guardrail Areas | It appears that there are EAT areas being called out for adjustments in the plan with post replacement quantities also given. As the bid items for adjusting guardrail and replacing posts and blocks cannot include EAT components, please clarify if the intent of the project is to adjust EAT's. If so, please include the separate bid items for adjusting EAT's. |  |  | 1 | 2023-11-09 10:08
20231114 | 20231114009 | 9 | Milling and Paving Operations | In the prosecution and progress it states that the milled surface can be be exposed for 48 hours, what is the significance behind that? Being that the A.A.D.T is so low could it be left open longer than 48 hours? Past projects that are similar size have had a higher A.A.D.T with the same structure type and has had a longer duration between the Milling and Paving. A longer duration between the 2 operations would increase the distance between 2 work zones and would be safer for the traveling public. |  |  | 2 | 2023-11-09 15:34
20231114 | 20231114009 | 9 | Design Schedule | Would the the department be willing to share the design schedule for the project? |  |  | 3 | 2023-11-09 15:35
20231114 | 20231114009 | 9 | Construction Details on Sheet 40 & 41 | In the prosecution and progress it states 48 hours between milling and paving and in the plan on sheet 40 & 41 it shows that you the plan is to mill one side and then pave the lower lift before milling the adjacent lane. If you mill one side you will have a 4" drop off of for 48 hours due and that causes safety concerns to the traveling public. Shouldn't the mill have to match up the lanes everyday to the same elevation to avoid this potential hazard. |  |  | 4 | 2023-11-09 15:40
20231114 | 20231114009 | 9 | A.A.D.T Traffic Volume | Being that A.A.D.T is only around 1400 would DOT be open to closing the roadway down and detouring the project to help the operations move more efficiently? |  |  | 5 | 2023-11-09 15:42
20231114 | 20231114012 | 12 | Traffic Requirements | In the plan it shows the project is closed to thru traffic. Why in the special provisions does it state the entire project needs to be built basically half at a time using flagging operations? There is a section of road that is a complete reconstruct and a new structure is being built too. Is this correct? Please explain in greater detail. | Maintaining a 12-foot lane with flagging operations was specified in the Traffic Management Plan (TMP). However, maintaining a 12-foot lane with flagging operations is only applicable within the pavement replacement section (which is most of the project length). It is not applicable within the approximately 1-mile reconstruction section (the special provisions will need to be modified to state this) and it is not applicable at structure B-11-66 (the special provisions already state this). | Mike Coleman | 1 | 2023-10-13 09:47 | 2023-10-16 07:53
20231114 | 20231114012 | 12 | Soil Borings | Is a soil boring report available? | The boring logs can be found at the following location: https://wisdot.box.com/s/w68qfsiz9223lwhk77117gflbl75ezn6 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-10-19 13:29 | 2023-10-23 11:39
20231114 | 20231114012 | 12 | Conversion Rates | What are the conversion rates utilized in the plan for base aggregates and select crushed? | The material unit weights that were used are per FDM 14-15 Table 10.4: â€¢ Base Aggregate Dense 3/4-Inch: 2.1 TON/CY â€¢ Base Aggregate Dense 1 1/4-Inch: 2.0 TON/CY â€¢ Select Crushed Material: 1.9 TON/CY | Mike Coleman | 3 | 2023-10-19 13:40 | 2023-10-23 07:18
20231114 | 20231114012 | 12 | Culvert Pipe Install | For the culvert pipe replacements on the mainline and sideroads that are outside the reconstruction section of the project is it allowed to close the road down to install the culvert pipe? Some are deep installations and one is very deep (sta. 155+01). Please advise. | An addendum will be submitted to address the question about culvert pipe installation outside of the reconstruction section. | Mike Coleman | 4 | 2023-10-23 11:20 | 2023-10-31 06:59
20231114 | 20231114012 | 12 | Removing Asphaltic Surface | What is the reason for having a removing asphaltic surface item (103,100 SY) and not a removing asphaltic surface milling item for this quantity? | Since this is a pavement replacement project with a short reconstruction section, Removing Asphaltic Surface item is specified to allow the contractor to determine means and methods of pavement surface removal. | Mike Coleman | 5 | 2023-10-23 11:51 | 2023-10-26 12:24
20231114 | 20231114012 | 12 | Design Schedule | Can the Department provide the Design Schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/w68qfsiz9223lwhk77117gflbl75ezn6 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2023-10-24 09:14 | 2023-10-25 06:28
20231114 | 20231114012 | 12 | Railroad Right of Entry | SPV article 7. Railroad Insurance & Coordination, paragraph A.7 indicates the contractor is required to obtain a Right of Entry from the UPRR at no cost to the contractor. Also included in Article 7 is a Maintenance Consent Letter requiring the contractor to fill out a contractor endorsement with an administration fee of $1,025, as a condition to entering UPRR property. Is a there a difference between the Right of Entry and Maintenance Consent Letter, contractor endorsement? |  |  | 7 | 2023-11-10 10:55
20231114 | 20231114014 | 14 | SEQUENCE OF OPERATIONS CHART & CONTROLLER | For the plans traffic signals section, the intersections are listed, but there is no sequence of operations chart listed (normally listed right after the intersection signals page). Also, there is conflicting information between the specifications and plans as to which traffic signal controller should be used. Please confirm. Thank you. | The City of Sun Prairie have updated their standard traffic signal controller as the one they used to specify is no longer manufactured. An addendum will be issued to update Special Provision Article 23 and the four impacted plan sheets. An addendum will be issued to include the updated sequence of operations chart for the city of Sun Prairie controlled intersections, Davison Dr and Thompson Road. The sequence of operations chart was not included for the state-owned traffic signal installation at USH 151 & STH 19 because the state will maintain control of the timing & operations through construction. If it were included, it would be watermarked FOR INFORMATION ONLY. | Mike Coleman | 1 | 2023-10-10 15:37 | 2023-10-12 14:03
20231114 | 20231114014 | 14 | SPV.0060 Special 11 and 12 | Camera spec'd isn't a pan/tilt/zoom camera but the spec reads that it should be. Please clarify. Thanks |  |  | 2 | 2023-11-09 15:38
20231114 | 20231114015 | 15 | Lane/Ramp Closure Time Restrictions | Are there any time restrictions for the lane and ramp closures? Are the Kilbourn ramp closures allowed to remain in place for the duration of the work or do they need to be opened during peak hours? Are the single lane closures on Howell Ave allowed to remain in place for the duration of the work or do they need to be removed during peak hours? Currently there are not any restrictions in the Special Provisions. | There are no time restrictions for the lane and ramp closures. Kilbourn ramp closures will remain in place for the duration of work. Howell lane closures will remain in place for the duration of work. (Because the closure is only a single lane there are no restriction needed for peak hours). | Mike Coleman | 1 | 2023-10-26 16:49 | 2023-11-01 06:15
20231114 | 20231114015 | 15 | AGI32 | Can I please have access to the AGI photometric files so we can perform light level calculations? | The Agi evaluations and Civil 3D files can be found at the following location: https://wisdot.box.com/s/yitl5q13vh4pd625con235yi8xsawkgq or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-11-02 11:58 | 2023-11-06 09:03
20231114 | 20231114015 | 15 | AGI file | I need access to the tunnel topology as depicted in the AGI32 files that were used as the basis of design. Previous link sent in response to this request did not contain that information. Where can I obtain the .agi files? | The tunnel lighting AGI files can be found at the following location: https://wisdot.box.com/s/yitl5q13vh4pd625con235yi8xsawkgq or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-11-06 15:13 | 2023-11-07 13:40
20231114 | 20231114016 | 16 | C-45-21 Hydraulic Data | Please provide the hydraulic data for box culvert C-45-21. Thanks | WisDOT does not prepare hydraulic calculations for wingwall replacements. The original culvert construction was in 1967 and the as-builts do not show any hydraulic data and WisDOT does not have any on record. | Mike Coleman | 1 | 2023-10-25 10:24 | 2023-11-08 08:28
20231114 | 20231114016 | 16 | Special Provision | Can the 3/4" DSB for aggregate shoulders be installed during daytime off peak hours with single lane closures in place or does this work need to be performed under full closures in Phase 2 also? | If I am understanding the specs correctly, I do not see an issue with the ï¿½â€ being installed during daytime off peak hours with single lane closures as the proposed drop off is 2â€ and is not within 8â€™ of the existing travelled way. Per 305.3.3.3, Provide and maintain signing and other traffic protection and control devices, as specified in 643, until completing shoulder construction to the required cross-section and flush with the asphaltic pavement or surfacing. | Mike Coleman | 3 | 2023-11-06 10:16 | 2023-11-07 06:32
20231114 | 20231114016 | 16 | HMA Paving | Will the Department allow a full closure of NB & SB for paving on the 2 separate weekends? In other areas with the same echelon paving requirements, the Department has allowed a "weekend blitz" of Friday night thru Monday am to complete the binder in one weekend and the surface on a different weekend. As it is specified now, the milling crews and paving crews will only have 5-6 hours of production each night. The benefits would include less transverse joints, less impact to travelling public (less full closures) and cost savings to the Department. |  |  | 4 | 2023-11-07 09:54
20231114 | 20231114018 | 18 | Driveway milling and paving | Where the plans call for "grind driveway" will this be paid under item 8, "Removing Asphaltic Surface Butt Joints"? What is the milling depth? Will the Department add a item for paving driveways? If not, how will this work be paid? | Please remove 1-3/4" from driveways marked as "grind driveway," to be paid under "Removing Asphaltic Surface Butt Joints." Replace with 1-3/4" of HMA Pavement, paid for as "HMA Pavement 4 MT 58-28 S." | Mike Coleman | 1 | 2023-10-24 15:11 | 2023-11-02 11:16
20231114 | 20231114018 | 18 | Milling depth | Under item 10, "Removing asphaltic surface milling" is the intend to mill a consistent 3" from the surface? Or remove asphalt down to the concrete base? If milling into concrete, will a separate item for milling concrete be added? | The existing asphaltic surface thickness varies as shown in the Typical Section, the intent is to mill to the concrete base. | Mike Coleman | 2 | 2023-10-24 15:15 | 2023-11-02 11:17
20231114 | 20231114018 | 18 | Surveillance and Care Cycles | Is a quantity of 1 each accurate? Generally, we see this quantity as an each for each visit in the growing season. | Please use a quantity of 10 to account for each visit in the growing season. An addendum will be issued. | Mike Coleman | 3 | 2023-10-26 11:23 | 2023-11-02 11:18
20231114 | 20231114018 | 18 | Removal and Restoration at Storm Sewer Pipe Trenches and at Storm Sewer Structures | It seems that most/all of the proposed storm sewer and associated catch basins/mh's are in locations of existing concrete pavement. Will bid items for sawing concrete pavement, removing concrete pavement, base patching concrete, drilled tie bars, drilled dowel bars be paid in addition to the LF of 12" rcp c5, catch basins, and mh's? | These quantities are included in the MQ tables as "undistributed" for the items listed below, with the exception of the curb & gutter removal/replacement for the new Catch Basins, quantities for these are included by segment as they were to be replaced regardless of sewer work. | Mike Coleman | 4 | 2023-11-06 10:16 | 2023-11-09 06:40
20231114 | 20231114018 | 18 | 4-FT Manholes | The table on page 233 indicates a new 4-FT Manhole for Str's 168 & 194. Str depth is only shown for Str 168. Page 57 of the plan shows Str 168 with dashed lines and Str 166 with bold solid lines. On page 61 Str 194 is shown with bold solid lines. Can you clarify which two structures are to be installed as new 4-FT Manholes? Can you also give a Str depth for the two new 4-FT Manholes? | Both Structures 168 and 194 are new 4-FT Manholes. Structure 166 is an existing structure that will remain in place. The drainage table information is correct for both structures 166 and 168. The depth of new Structure 194 is missing from the drainage table, but can be calculated from the rim elevation of 111.70 and the outgoing pipe invert at 98.78. This calculation gives a depth of 12.92 feet. | Mike Coleman | 5 | 2023-11-06 10:39 | 2023-11-09 06:41
20231114 | 20231114019 | 19 | Design Schedule | Can the Department provide the Design Schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/gf0qsqg61okd1k7tv62w7nsocnhjn4x5 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-10-10 16:00 | 2023-10-11 08:51
20231114 | 20231114019 | 19 | Stream Work at C-64-91 | On Sheet 11 of the plan, it states "refer to Maintaining Drainage Special Provision". Was this left out of the Specials? How is new stream construction paid for? Only mentions pumping incidental to the construction of the culvert. | The Maintaining Drainage provision is under the Erosion Control Article, which also discusses some dewatering requirements. The new stream construction was broken down into individual pay items required to construct it. So there are items like common excavation for excavating the new channel, and Riprap Light to line the channel. There is no lump sum item intended for â€œChannel Constructionâ€. | Mike Coleman | 2 | 2023-11-07 15:04 | 2023-11-08 14:42
20231114 | 20231114019 | 19 | C-64-91 | Can the box culvert C-64-91 be pre-cast, or is the Department requiring Cast-in-place? | There is not enough cover over the box for a precast option at this location and so a precast option was not stated in the general notes of the structure plan for that reason. A precast option will not be allowed here. | Mike Coleman | 3 | 2023-11-08 10:25 | 2023-11-08 14:47
20231114 | 20231114020 | 20 | Schedule | Could the Department please provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/ggayl8wrt90dhovy8fy4bxva2nxv1v7k or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-10-25 10:30 | 2023-10-25 12:13
20231114 | 20231114021 | 21 | Existing Pavement Marking Removal | Good Morning, The Special Provisions state that the existing pavement markings be removed immediately preceding the diamond grinding operations. Why would this be necessary prior to diamond grinding? Wouldn't the diamond grinding operation remove the existing marking? | Language was included to ensure pavement markings were not removed too far in advance of diamond grinding operations. There is both grooved in tape and epoxy markings along I 41. The assumption was made that contractor would not want to leave tape on the surface prior to diamond grinding. So, the quantity provided for removal was for existing grooved tape. It was assumed that any painted pavement markings could remain on the surface and would be removed by the diamond grinding operation, so this was not quantified as a bid item. Marking Removal Line bid items included in the contract were specifically for staging operations only. If the contractor feels that they can remove all pavement markings through diamond grinding operations, they should bid accordingly based on their proposed means and methods. | Mike Coleman | 1 | 2023-10-26 09:17 | 2023-10-26 12:25
20231114 | 20231114021 | 21 | Asphlatic Surface Temporary | On Sheet 137 there is a note that says, during asphalt slab replacement areas, temporary asphalt is needed for phasing purposes. It is also noted that it is to be agreed upon by the engineer and contractor on the extents of the limits. Can this be quantified and added to an asphaltic surface temporary item so the contractor can accurately bid this scope of work? | Asphaltic Surface Temporary cannot be quantified. Contractor means and methods will dictate the quantity of Asphaltic Surface Temporary required. Contractor to estimate quantity based on anticipated space required for new pavement construction and bid work as incidental to bid item 415.1110 Concrete Pavement HES 11-Inch. | Mike Coleman | 2 | 2023-10-26 13:25 | 2023-10-31 07:06
20231114 | 20231114021 | 21 | High Friction Surface Treatment removal | Is the cost of the removal of the existing HFST to be included in the placement of the new HFST. There is a line item for the Removal of the existing polymer overlay. | The item Removing Polymer Overlay bid item is for removal of the existing HFST on the southbound Green Bay Road bridge (B-70-0131). The overlay on the northbound Green Bay Road bridge (B-70-0132) will come off with deck removal. Diamond grinding is sufficient to remove the existing overlay on the roadway. Preparation of roadway surface after diamond grinding and prior to new HFST application is covered under the Resin Binder High Friction Surface Treatment bid item. | Mike Coleman | 3 | 2023-10-30 15:44 | 2023-10-31 11:05
20231114 | 20231114021 | 21 | B-70-406 Jacking | To complete the jacking specified at pier 4 of the B-70-406 structure will the department allow holes to be core drilled through the pier cap for the installation of brackets and associated thru bolts? | The SPV bid item for Reset Existing Bearings requires the contractor to submit plans and obtain prior approval from the engineer for the method of raising and supporting the superstructure. As is stated in the SPV, the contractor is responsible for performing this work in a way that does not damage the existing structure. The method of raising the superstructure is to be submitted by the contractor and will be reviewed after the contract is awarded by the project staff. | Mike Coleman | 4 | 2023-10-31 09:15 | 2023-11-02 11:20
20231114 | 20231114021 | 21 | Schedule | Please provide a copy of the construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/pxoi7ksal34walxqy32n035d0ll3s1pa or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2023-10-31 14:25 | 2023-11-01 08:58
20231114 | 20231114021 | 21 | Temporary Support B-70-132 | Design standards require the designer to provide at least one feasible/constructible concept in the plans. Please provide the designers concept for the temporary support of B-70-132. | The Temporary Support item is intended to be a contractor-designed temporary support system. As stated in the SPV article, all dead, live, and construction loading conditions shall be determined by the contractor, and the contractor is required to submit plans for the proposed system. For responsibilities of the design engineer, reference WisDOT Bridge Manual chapter 40, page 30, which does not state the design engineer is required to provide concepts in the plans. | Mike Coleman | 6 | 2023-10-31 16:25 | 2023-11-06 09:05
20231114 | 20231114021 | 21 | Special Provisions Section 6 Traffic - Work Zone Restrictions | Will removals and pavement repair/replacement activities be allowed during the single lane closure times (prior to double lane closures) as long as the drums remain outside the open lane of travel? | Traffic control devices are required to be installed a minimum of 2â€™ shy of the edge of the live lane of traffic. All construction activities are required to occur behind the traffic control device installed. | Mike Coleman | 7 | 2023-11-02 12:31 | 2023-11-06 09:06
20231114 | 20231114021 | 21 | Superstructure Transverse Bar and Bar Coupler Quantity | On Drawing 589, Stage 3B calls for 1,760 Pcs. of Bar Mark S505. It seems that this is double the quantity required. On Drawing 582, in the plan view it calls for 880 Pcs. Please verify. | The bar mark quantity for S505 is correct as shown in the plans. There are 439 spaces each, top and bottom, and due to the curve and varying deck width, each line of S505 bars consists of two bars with a 2â€™-7â€ lap. | Mike Coleman | 8 | 2023-11-03 14:47 | 2023-11-06 15:09
20231114 | 20231114021 | 21 | Temporary Support B-70-132 Follow Up to question 6 DOT Response | The Bridge Manual Chapter 40, Page 30 indicates the Temporary Support bid item is intended to be used when the designer has determined there is a viable path forward through a temporary support system. If the Department is not willing to place this path forward in the plans, will the department provide what the designers viable path forward is? Moreover, Chapter 40, Page 30 indicates that temporary overhangs supporting traffic operations shall be evaluated by the designer. Can the department provide the calculations/load determinations from the designer in this evaluation process? | It is intentional to not place details for the temporary support system on the plans as to allow the system to be contractor-designed. The contractor is responsible for performing calculations and load determinations for the temporary support system. All dead, live, and construction loading conditions shall be determined by the contractor. | Mike Coleman | 9 | 2023-11-06 15:11 | 2023-11-08 08:27
20231114 | 20231114021 | 21 | Temp Support SPV.0060.03 | The special provisions "Section C Construction" indicates conformance with Standard Spec 526.3.4. This specification section indicates that a third party inspection of the temporary support is required using form DT2007 and using a Department approved active team leader. is this third party inspection the intent of the Department. If so, can the Department provide a list of the approved third party certified active team leaders for this inspection. (The HSI site doesn't appear to have an active directory for team leaders, it only has documents related to being certified to be an inspection team leader) | A third-party inspection of the temporary support with a Department-approved active team leader is not required for the temporary support. Construct the temporary support system conforming to standard spec 526.3.4(1) and 526.3.4(3). | Mike Coleman | 10 | 2023-11-06 15:25 | 2023-11-08 08:26
20231114 | 20231114021 | 21 | Bridge Deck Crack Sealing | On B-70-130 there is a line item for 650' of Bridge Deck Crack Sealing. This bridge already has a Polymer Overlay and there items to remove and replace 28sy of Polymer Overlay, typically the polymer overlay will seal up the cracks. Was line item intended for a different bridge? Seems like a lot of deck crack sealing in 28sy area. | We are going to be issuing an addendum for an update in plan quantities for the Bridge Deck Crack Sealing item applicable to structures B-70-129 and B-70-130. | Mike Coleman | 12 | 2023-11-07 14:11 | 2023-11-09 06:50
20231114 | 20231114021 | 21 | BDM Beach Road Lane Closure | Will a lane closure be allowed on BDM Beach Road enabling access to pier 4 of the B-70-406 structure? | Sheet 309 indicates that any work which requires the closure of a single lane on Lake Butte Des Morts Beach Road will be completed under a flagging operation in accordance with Standard Detail Drawings. | Mike Coleman | 13 | 2023-11-08 11:09 | 2023-11-09 06:50
20231114 | 20231114022 | 22 | Project Start Restriction | SPV Article 3 states the project is to begin work no earlier than June 17, 2023. Is this date supposed to be 2024? | Yes, this date should be June 17, 2024. An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-10-16 14:34 | 2023-10-17 08:08
20231114 | 20231114022 | 22 | Frost Heave Patches HMA | Would the department consider changing the HMA for the frost heave patches from 3MT/4MT to the asphaltic surface item? | The department is requiring the specified 3 MT and 4MT mixes at the frost heave areas. The department would like to see the mixes conform to the quality management program specified under 460.2.8 and any density testing. | Mike Coleman | 2 | 2023-11-08 12:08 | 2023-11-08 15:06
20231114 | 20231114023 | 23 | Working Days | Per the Specials Detours may not be concurrent, and the curb and gutter work that has to occur in Stage 2 has 5 sub-phases that take about 5 days each phase. Could the Department add 8 working days to the contract. | Most curb ramp work does not require to happen under detour. Curb ramps can be done during the duration of the project under shoulder closures. This intent is shown under â€œConcrete Curb and Gutter and Pedestrian Curb Rampsâ€ article. | Mike Coleman | 1 | 2023-11-02 12:46 | 2023-11-06 08:58
20231114 | 20231114024 | 24 | Salvage and Reinstall Traffic Signal Controller | Line 38 of the specials states Salvage and Reinstall Traffic Signal Controller. Please confirm what model of controller is currently in use for this? ie. Eagle/EPAC, Econolite, McCain, etc. Thank you. | The traffic controller is a Yunex Traffic m60. | Mike Coleman | 1 | 2023-10-13 12:58 | 2023-10-17 06:37
20231114 | 20231114024 | 24 | Boring Logs | Are boring logs available? | The boring logs can be found at the following location: https://wisdot.box.com/s/m12mtp6yaiaob9c3ms02vq7z83b7f0kb or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-11-07 14:53 | 2023-11-09 15:10
20231114 | 20231114025 | 25 | Class IV Storm Sewer Bid Items | Would the Department be opposed to issuing an addendum to allow for Class IIIB storm sewer bid items â€œto introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inchesâ€ (FDM 13 â€“ 15.2 par. 3) Much of the current design includes Class IV storm inside and outside ROW with sufficient cover for Class IIIB items. | Due to the depth of the pavement structure, the majority of the project does not meet required subgrade cover for alterative materials. The remaining segments of storm sewer that may meet cover requirements were individual short runs and per FDM 13-1-17.3.1 there is not an expectation to switch back and forth between materials. | Mike Coleman | 1 | 2023-10-27 14:56 | 2023-11-02 07:24
20231114 | 20231114025 | 25 | Rock Probes | Can the rock probes performed by the DOT be made available to the contractors? | The rock probes can be found at the following location: https://wisdot.box.com/s/zdqx98cmavzvzppvmbr9vo3f9jnem299 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-10-31 12:14 | 2023-11-02 07:22
20231114 | 20231114025 | 25 | Schedule | Would the Department provide their construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/zdqx98cmavzvzppvmbr9vo3f9jnem299 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-11-06 09:54 | 2023-11-07 07:25
20231114 | 20231114025 | 25 | Staging | The PWL Mixture Table on sheet 86 calls out the mixture testing for the RAB (STA 1186+55 to 1195+15) as Acceptance Testing by the Department; Not eligible for Incentive or Disincentive. Should this be listed as PWL Incentive Air Voids HMA Pavement 460.2010 ? The staging called out in the Prosecution and Progress on page 3 states, Stage 1A must be completed before starting Stage 1B. It also states Stage 2 should be completed concurrently with Stages 1A & 1B. Will the department allow Stage 2 to be completed during the construction of Stage 1A but prior to the placement of any HMA within Stage 1A? This will allow the contractor to have enough 4MT for the test strips to be performed in advance of paving the RAB. Stage 1A does not have sufficient quantity of 4MT to perform the volumetrics test strip. | PWL Mixture Table will be updated and appropriate density incentive item will be added by addendum. PWL will not apply to paving during stage 1A & 1B and not be dependent on when stage 2 is paved. | Mike Coleman | 4 | 2023-11-08 11:36 | 2023-11-09 15:11
20231114 | 20231114026 | 26 | Storm Sewer | Would the Department be opposed to issuing an addendum to allow for Class IIIB storm sewer bid items â€œto introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inchesâ€ (FDM 13 â€“ 15.2 par. 3) Much of the current design includes Class IV storm inside and outside ROW with sufficient cover for Class IIIB items. | An addendum will be issued to change the following runs of storm sewer pipe to Class III-B: INL 12.1 â€“ AEW 12.0, MH 12.3 â€“ INL 6.2, and INL 6.1 â€“ MH 6.0. | Mike Coleman | 1 | 2023-10-17 17:01 | 2023-10-19 12:51
20231114 | 20231114026 | 26 | Boring Logs | Are boring logs available? |  |  | 2 | 2023-11-10 09:19
20231114 | 20231114027 | 27 | Line item 0008 - Replace wet reflective epoxy - 6" | Good morning, are the existing markings and groove able to accept 6" wide markings under this item or will a new groove (presumably current markings are 4") be required to accommodate the new 6" wide markings? If a new (wider) groove is required, will an addendum be issued to address this? Thank you. | This item is so that we would get the right beads in the groove if there is an existing groove. The contractor will not need to groove the old epoxy out or make the groove any wider just retrace but use the correct beads. We anticipate 1â€ of this marking to be out of the groove when finished. | Mike Coleman | 1 | 2023-11-06 10:23 | 2023-11-08 14:51
20231114 | 20231114028 | 28 | Curb Locations and Elevations | Will there be any additional information provided for the curb locations and elevations, such as what you would normally find in a paving detail, station and offset detail, or plan detail? I realize there is an intersection detail and curb ramp detail, and the cross sections can be used, but that would still be missing key points like taper points, high points, low points, etc. | An addendum will issued to provide additional curb & gutter grade and layout information. | Mike Coleman | 1 | 2023-10-13 10:59 | 2023-10-18 10:54
20231114 | 20231114028 | 28 | Design Schedule | Can the department provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/9dezbo4x5v9c2wrp1fii35i0cs3pkl3s or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-10-25 13:49 | 2023-10-26 09:14
20231114 | 20231114028 | 28 | Paving Limits for Stage 1B | Will the temporary lane configuration for traffic in Stage 1B from STA 402+00 to 414+00 (as shown on sheet 34) for Stage 1B Pavement Replacement allow for paving to the reference line? If not, then is it the department's intent for the paving limits of Stage 1B to end at the crown point? | The intent is to pave to the crown point in Stage 1B. | Mike Coleman | 3 | 2023-10-31 12:45 | 2023-11-02 11:19
20231114 | 20231114028 | 28 | Asphaltic Surface Patching & Asphaltic Curb | The Construction Detail on Sheet 9 shows Asphaltic Surface Patching in the Roadway, with Asphaltic Curb adjacent to a Temporary Pedestrian Surface/Curb Ramp. The Traffic Control Sheet for Stage 1A, shows the location of Temporary Pedestrian Surface Asphalt, but does not indicate any roadway patching to match the construction detail. Could the department clarify which bid items are necessary in the work locations in shown Stage 1A? | Roadway patching will be required per the Construction Detail. The miscellaneous quantities tables show the bid items necessary to construct the Stage 1A temporary pedestrian curb ramp and asphaltic curb. | Mike Coleman | 4 | 2023-10-31 12:48 | 2023-11-02 07:27
20231114 | 20231114029 | 29 | Leveling course of Asphalt. | Given the requirements of PWL on the project would the Department change the yield of the 4 LT item from 227 pounds per square yard to 290 pounds per square yard allowing for a 0.75 inch leveling course and an 1.75 inch surface course? This would allow for a more uniform cross-section and make it more suitable for the PWL spec. | A 2" surface course is desired for this project. | Mike Coleman | 1 | 2023-11-02 12:14 | 2023-11-06 08:56
20231114 | 20231114031 | 31 | Design Schedule | Can the department provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/a6f7v71t6bvylfehht1rugxfta7664lc or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-10-25 13:48 | 2023-10-26 09:17
20231114 | 20231114031 | 31 | Additional Working Days | Based on the amount of grading work in the project and the necessary time needed to complete the infiltration trench, culvert replacements/repair, and the ditch grading and shaping, would the department consider adding 8 working days to the contract to allow for more time to complete these three operations before pavement resurfacing begins? A percentage of the infiltration trench installation, culvert repairs (liners and joint sealing), and ditch grading may be completed during or after pavement resurfacing, however the contractor has a concern with working on or from a newly surfaced roadway and causing damage to the surface. | The department will issue an addendum to add 5 working days to the project. | Mike Coleman | 2 | 2023-10-26 15:08 | 2023-10-30 08:20
20231114 | 20231114031 | 31 | Construction Base Staking | Based on the size, location, and geometry of the Culvert C-004224 removal and replacement shown on Sheet 38 of the plans near Lolly Coogan Lane, will the department add Construction Base Staking to reestablish the correct grades and elevations for the full depth asphalt replacement? | After reviewing the bid items included and area being disturbed, the department will not add Construction Base Staking. The intent is to replace the pavement grades in-kind and the base should be graded to fit field conditions. Transfer of horizontal layout is part of the Construction Staking Supplemental Control and Construction Staking Resurfacing Reference bid items. The culvert transition detail only applies to the mainline portion of the culvert replacement. The culvert may be trenched within the town road. | Mike Coleman | 3 | 2023-10-30 11:35 | 2023-11-02 11:13
20231114 | 20231114032 | 32 | Replace wet reflective epoxy - 6" | Good afternoon, are the existing markings and groove able to accept 6" wide markings under this item or will a new groove (presumably current markings are 4") be required to accommodate the new 6" wide markings? If a new (wider) groove is required, will an addendum be issued to address this? Thank you. | No grooving necessary. We will be placing 6-inch wet reflective epoxy in the existing groove. | Mike Coleman | 1 | 2023-11-06 15:21 | 2023-11-08 09:04
20231114 | 20231114032 | 32 | Wet reflective epoxy | On plan sheet 8 it is listing standard wet reflective epoxy 6" for IH 94. I do not see a bid item for this in the proposal. The standard wet reflective quantities (646.2040) are part of the total for replace wet reflective marking item (646.2041.S) on sheet 17. Will a clarification or addendum be issued to address this? Thank you. |  |  | 2 | 2023-11-06 15:55
20231114 | 20231114034 | 34 | 20231114034 - Plans Document | The plans indicate that the existing static scales is to be re-used, Could you please confirm , what is the make and model of the static scale and indicator that we are to be interfacing with. | A new scale was installed in a refurbished scale pit. It was commissioned in September 2023. Static Scale: Manufacturer: Fairbanks Model: PLT2600100312HWY Indicator: Manufacturer: Fairbanks Model: FB4000 | Mike Coleman | 1 | 2023-10-31 07:27 | 2023-11-01 06:13
20231114 | 20231114034 | 34 | Pavement Marking | Good Morning. It appears as though the Grooved Permanent Tape item is overstated. Should the Grooved Permanent Tape be utilized for the Lane Lines? | The grooved permanent tape IS overstated. The grooved permanent tape should be used for lane lines and grooved wet reflective epoxy 6-inch should be used for edge lines. An addendum will be issued to correct this. | Mike Coleman | 2 | 2023-10-31 10:16 | 2023-10-31 12:11
20231114 | 20231114034 | 34 | Drilling Shaft - 24 Inch | Should there be an item for drilling the footings for the Type I Signs? | Yes, 29 LF of Drilling Shaft (24-inch) will be added via addendum. | Mike Coleman | 3 | 2023-11-07 07:52 | 2023-11-07 13:41
20231114 | 20231114034 | 34 | Fill Existing Rumble Strip | â€œFill Existing Rumble Stripâ€ - One way to complete this is to reheat the top of the asphalt shoulder adding new mix as need and roll flush. Is this allowed? Would milling this shoulder and repaving be a better option? | Yes, that would be allowed as long as tack was utilized also. Mill and re-paving is not necessary but could be proposed as a no cost alternative to the project engineer once the contract is awarded if desired. | Mike Coleman | 4 | 2023-11-08 11:34 | 2023-11-08 14:24
20231114 | 20231114034 | 34 | GEOTECHNICAL Report | Please provide the GEOTECHNICAL Report. | The Geotech report can be found at the following location: https://wisdot.box.com/s/why5urt52ifq2iy7i4uqf6x394e8hl57 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 5 | 2023-11-09 12:52 | 2023-11-10 10:00
20231114 | 20231114035 | 35 | High Friction Surface Treatment | Call 21 in the same letting has a high friction specification that allows for semi-automated application of HFST. This has been the typical spec with WisDOT and the application methodology utilized by most contractors performing this work. The above project has a specification that specifically calls for a fully automatic system. Is the specification for High Friction Surface Treatment not standard across WisDOT? Will a semi-automated application (one which automatically mixes and proportions the epoxy but spreads it to width with a notched squeegee) be permitted on this project? Thank you | An addenda will be issued that will remove the requirement to use fully automated application of the HFST. | Mike Coleman | 1 | 2023-10-30 13:18 | 2023-11-06 09:07
20231114 | 20231114035 | 35 | Epoxy Placement - 2 questions due to size | If the surface is prepared correctly, the weather and moisture content is acceptable, the epoxy is mixed accurately, aggregate is placed prior to polymerization for good embedment and retainage, and proper cure windows are followed then the overlay will perform as desired. If this is not acceptable then shouldn't the full automated equipment be on the bridge deck as well and the use of squeegees and hand placement be forbidden. It doesnâ€™t make sense to perform the same process and allow for different methods because one is a road, and one is a bridge with 2 layers. The requirement for both should be to utilize the necessary means and methods to install the product so that it performs as intended. | An addenda will be issued that will remove the requirement to use fully automated application of the HFST | Mike Coleman | 2 | 2023-10-30 14:42 | 2023-11-06 09:09
20231114 | 20231114035 | 35 | Epoxy Placement - 2 Part Question due to size | Part 1 Please reference the specifications for high friction surface and high friction polymer overlay. Both processes utilize the same materials but 1 is a single application for enhancing friction and the other is a 2 layer for waterproofing but also friction enhancement. The High friction surface requires a fully automated machine (specifically mentioning that the use of squeegees is not allowed but when itâ€™s not possible for the fully automated equipment i.e. tapers it is ok then?) but on the bridge deck a semi-automated machine (use of squeegees required for proper mill thickness and applications as coating have required) can but used as the fully automated machine is not practical and for the most part not possible. Can the same equipment be allowed for the bridge deck be used for the roadway? At the end of the day the methods on installation do not affect the performance of the new surface. | An addenda will be issued that will remove the requirement to use fully automated application of the HFST. | Mike Coleman | 3 | 2023-10-30 14:43 | 2023-11-06 09:08
20231114 | 20231114036 | 36 | 646.9300 Marking Removal Special Marking | 646.9300 Bid Quantity and EOQ shows (100) EACH, however the Misc. Qty table on page 61 shows (4) EA. This quantity matches up with plan sheet 47. I don't see where the other (96) Special Markings are that need to be removed, either in the plans or in the Miscellaneous Quantities. EOQ for plan 8220-00-76 does not show this item. Can this be reviewed and adjusted if needed? Thanks | 4 each is the correct answer. An addendum will be issued to correct the quantity. | Mike Coleman | 1 | 2023-10-26 15:01 | 2023-10-30 13:13
20231114 | 20231114036 | 36 | Storm sewer - 3' inlets | The Type H casting specified for the 3' storm inlets will not fit on this size structure. Will a different size structure or casting be revised? | The structure will be revised to a 2x3 inlet in an upcoming addendum. | Mike Coleman | 2 | 2023-11-02 07:13 | 2023-11-02 11:12
20231114 | 20231114036 | 36 | Repair Wall Modular Block Gravity R-60-001 | According to block manufacturers listed on the APL, they no longer make a beveled block to match the existing wall. Does the department have any information regarding who the block manufacturer was and the shop drawings/design files for the wall? | Please bid the closest currently-available alternative from the APL and use the plan item & quantity. | Mike Coleman | 3 | 2023-11-03 10:50 | 2023-11-10 10:21
20231114 | 20231114036 | 36 | Repair Wall Modular Block Gravity R-60-001 | The MQs show only the top course and cap block will be replaced throughout the wall. Looking at the wall, it seems in several locations courses below the top course have deteriorated more than the top course. Please confirm that the department's intent is to only replace the top course and the caps throughout the existing wall. | Please bid the closest currently-available alternative from the APL and use the plan item & quantity. | Mike Coleman | 4 | 2023-11-03 11:02 | 2023-11-10 10:22
20231114 | 20231114036 | 36 | Traffic control | Stage 3 work includes milling and paving, the last sentence of stage 3 says (flagging is not permitted on multi-lane portion of STH 13) There also is not a TC plan showing a bidirectional closure for this stage, the majority of this section is 11' lanes and would not accommodate a single lane closure due to width. to complicate this further it also says no centerline edge drop off can exist overnight. The mill is roughly 1.5' wider than what is being milled, We Think there needs to be a quantity of drums added to the job to route traffic in one half of the job for the day using flaggers to execute a single lane closure during work hours. More direction on how the DOT is envisioning this stage being built would be helpful thank you. |  |  | 5 | 2023-11-06 08:51
20231114 | 20231114036 | 36 | radius widening | Sheet 14 has a typical showing 7" of 5MT going into the curb radius widening areas, We suggest this get changed to lower lifts paid Asphaltic surface and spec a 3 mix for the lower layers. Not 4 lifts of 5MT |  |  | 6 | 2023-11-06 08:55
20231114 | 20231114036 | 36 | Traffic Control | In conjunction with the previous traffic control question, in the special provisions where it states a difference in centerline can not exist overnight, that can be accommodated in the 2 lane sections. Once the operation gets into the 4 lane, as was previously stated drums and barricades will need to be used to work in outside/inside lanes, but how would it be feasible to mill and pave both layers of asphalt in a day to not have a centerline difference? |  |  | 7 | 2023-11-06 15:27
20231114 | 20231114036 | 36 | Item 0064, Type C2 Railing | Item 0064, Type C2 Railing, 513.8011 â€“ Can you provide the railing details such as joint connections or single two post panels, height, paint color and the materials needed if changed from the standard? |  |  | 8 | 2023-11-08 13:11
20231114 | 20231114036 | 36 | Covering Signs | Sheet 47 shows 2 Overhead Signs that need to be covered, shouldn't these be paid as Covering Type I Signs? Only Covering Type II Signs are listed as bid items. | The overhead signs in question are Type II signs mounted on a Cantilever Mast Arm Sign Bridge and are covered under the existing bid items as shown in the plans. | Mike Coleman | 9 | 2023-11-09 15:16 | 2023-11-10 10:06
20231114 | 20231114037 | 37 | Item #204.0115 Removing Asphaltic Surface Butt Joints, | Could the Department please confirm the pay limits for the asphalt butt joints on this project. Sheets 6 and 7 of the plans suggest that the pay limits for butt joints on Mainline, Side Roads and Private Entrances is 2' by the width of the road. Is that correct? If the 2' is the correct length then could the Misc Quantities found on sheet 42 of the plans be confirmed as accurate. Thanks | The details shown on plan sheets 6 and 7 and associated miscellaneous quantities will be corrected and updated as part of an upcoming addendum. | Mike Coleman | 1 | 2023-10-19 17:08 | 2023-10-25 06:25
20231114 | 20231114037 | 37 | Reattach Existing Pipe | There are 3 locations that have notes in the plans to reattach existing pipe. Should there be Salvage and Reinstall items? Thanks | Yes. As part of an upcoming addendum, additional notes and items/quantities will be added to the plan and proposal to clarify the proposed work. | Mike Coleman | 2 | 2023-10-30 07:38 | 2023-11-01 13:28
20231114 | 20231114037 | 37 | Asphaltic Surface Driveways and Field Entrances Bid Qty | Can you please review the qty's listed under this item 465.0120? | The design team reviewed the quantity for Asphaltic Surface Driveways and Field Entrances that was provided in Addendum 1 and confirmed that the quantity was, indeed, in error. The quantity for that item will be corrected with an upcoming addendum. | Mike Coleman | 3 | 2023-11-08 11:24 | 2023-11-09 15:07
20231114 | 20231114037 | 37 | Shaping Shoulders Item | Should there be a shaping shoulders item? | The item of shaping shoulders is not necessary. A quantity of Base Aggregate Dense ï¿½-Inch has been provided in the miscellaneous quantities as shown in the proposed typical section. Work associated with constructing and shaping the shoulders is incidental to the Base Aggregate Dense ï¿½-Inch item. | Mike Coleman | 4 | 2023-11-08 11:26 | 2023-11-09 14:58
20231114 | 20231114038 | 38 | Is there a bid item for Temporary Traffic Signals for project 7180-00-78 |  | No, there is not a bid item for Temporary Traffic Signals for project 7180-00-78. The bid item â€œDriveway Assistance Device System 7180-00-78â€ covers payment for the complete system consisting of temporary traffic signals, driveway assistance devices, and system communications. | Mike Coleman | 1 | 2023-10-18 15:17 | 2023-10-19 10:30
20231114 | 20231114038 | 38 | Access/easement and traffic control | How did the department intend to remove and construct wall R-47-40 within the easement and available work zone as it currently exists? Drilling and installation of the soil nails, placement of falsework for the existing bridge protection, placement of forms & pouring of the CIP face, protection of the existing building just to name the major issues. There are also concerns about the stability of the existing stone retaining wall during the drilling and installation of the soil nail portion of the wall. Single lane traffic, controlled by temporary stop lights (similar to stage 2 wall R-47-41) will be required to give the contractor a work zone (south bound lane of STH 35) to access and build this project and to reduce risk to traffic (the traveling public). | The Department does not determine means and methods for the contractor. The project is complex and requires construction within tight constraints. As stated in item â€œSPV.0165.01 Soil Nail Retaining Walls R-47-40â€, the soil nail wall is contractor designed and requires the contactor to design a stable wall system. Equipment is available that can fit in the space between the Old Creamery Building and R-47-40 that uses short strokes to drill the soil nails. Access is provided to the bottom of the wall from the parking lot on the southwest side of the building. Access is also provided from the top side of the wall with daytime flagging operations as stated in the special provisions. | Mike Coleman | 2 | 2023-10-26 14:11 | 2023-10-31 07:09
20231114 | 20231114038 | 38 | Asphaltic Surface | The departement may want to consider changing the 51 tons of 4MT 58-34S to an Asphaltic Surface item. The HMA Type and Asphalt Cement type can be specified if wanted as an SPV or part of the the job specific specifications. | The department has decided to keep the bid item as currently shown on the plans. | Mike Coleman | 3 | 2023-10-30 07:31 | 2023-11-01 13:30
20231114 | 20231114038 | 38 | Excavation for Structures R-47-40 - missing | There is a note on the general notes page of structure R-47-40 page 96 or sheet 3 of 13 structure plans - "The existing ground line shall be the upper limits of excavation for structure". There should be a bid item for excavation for structures R-47-40. Excavation will be required for the construction of the base of the wall and the installation of the underdrain. | The bid item â€œSPV.0165.01 - Soil Nail Retaining Walls R-47-40â€ covers payment for excavation for the wall. Per the payment section of the SPV: Payment is full compensation for providing designs, submittals, labor, tools, equipment and soil nail wall materials, excavating, hauling and removing excavated materials, installing soil nails, grouting, shotcreting and supplying wall drainage systems and any incidentals necessary to construct soil nail walls. No additional payment will be made and no extension of completion date or time will be allowed for repairing property damage, over excavations or unstable excavations, unacceptable test nails or thicker shotcrete or concrete facing. The bid item â€œ612.0406 â€“ Pile Underdrain Wrapped 6-Inchâ€ is full compensation for providing the underdrain; and for excavating and backfilling. | Mike Coleman | 4 | 2023-10-30 10:58 | 2023-10-31 07:10
20231114 | 20231114038 | 38 | utilities | Will Xcel Energy's pole be relocated prior to mid-March in order to be in compliance with the clearing dates for the NLEB? Where will the new pole be located? | The pole will be relocated twice: Phase 1 (Temporary pole location during construction) - Approx. 30' west of existing pole location (STA 14+70) (close to the corner of the existing building) Phase 2 (Permanent pole location) - Approx 22' SE of existing pole location (STA 15+10) The initial pole relocation to its temporary location is anticipated to occur January 2024 and will be in compliance with the clearing dates for the NLEB. The second pole relocation to its permanent location will occur after the site is to the final grade and will not require tree clearing. | Mike Coleman | 5 | 2023-10-31 11:04 | 2023-11-02 07:26
20231114 | 20231114038 | 38 | Existing wall R-47-30 Removal | Is the existing wall allowed to be removed in entirety? Stabilizing the top portion and removing the bottom of a gravity wall could still create unsafe conditions. | The Department will not determine means and methods for the removal of existing wall and construction of the new wall. As stated as SPV.0060.08 â€“ Temporary Excavation Support, â€œthe contractor shall remove as little as possible of the existing wall as needed for construction.â€ Contractor must comply with the protection requirements stated in SPV.0060.08 â€“ Temporary Excavation Support. | Mike Coleman | 6 | 2023-11-07 12:11 | 2023-11-09 06:39
20231114 | 20231114038 | 38 | Existing Structure R-47-40 | The existing wall is unstable with clear signs of movement along the wall. Given the parameters of the working area shown on sheet 15 and 16, the soil nail wall is intended to be constructed from below the wall as there is not enough room without a lane closure for "over the shoulder" construction. Given drilling is intended to take place below the wall while introducing vibrations in a confined area, the wall would not be able to be constructed safely from below. To construct the wall as shown in the plan safely, a temporary lane closure would be required. |  |  | 7 | 2023-11-08 16:23
20231114 | 20231114038 | 38 | Existing Structure R-47-40 Access | It was noted in a previous question that there is equipment that can fit between existing wall and the building to utilizing a â€œshort stroke drill mastâ€, this is not a typical drill that is readily available and would likely need to be custom and/or introduce usage of a wagon style drill. Support equipment for a wagon drill (i.e. forklift and manlift) and any equipment with a 20ft reach would not fit between wall and building. It is our opinion that constructing the wall as intended would require lane closure above the existing wall. |  |  | 8 | 2023-11-08 16:25
20231114 | 20231114038 | 38 | Geotech Report | Will the DOT provide a copy of the Geotech report? There has not been any response from the listed contact on page 44 of the special provisions. |  |  | 9 | 2023-11-08 16:25
20231114 | 20231114039 | 39 | Guardrail Replacement | In 2019 under SP#7650-01-62 the department updated all of the guardrail on this project to MGS standards along with Grading, Shaping, and Finishing for barrier systems and also installed asphalt mow strips. Please confirm that the slopes and guardrail will be reconstructed under this project as well. | Yes. The bridge is being widened requiring some of the guardrail/shoulders/slopes to be widened out to match. Decision was made during design to fully replace the shoulders and guardrail. | Mike Coleman | 1 | 2023-10-30 06:11 | 2023-10-30 11:06
20231114 | 20231114039 | 39 | Asphaltic Surface | The department may want to consider changing the 4MT 58-34S item to an Asphaltic Surface item. The mix type and asphalt cement type can be specified as part of an SPV if desired. | The Region would prefer to stay with the mix that is currently specified. | Mike Coleman | 2 | 2023-10-30 07:35 | 2023-10-30 11:10
20231114 | 20231114040 | 40 | Finishing Roadway | There is not a Finishing Roadway item on this project. The department may want to add the item. | An addendum will be issued to add the item. | Mike Coleman | 1 | 2023-10-30 08:52 | 2023-10-31 07:05
20231114 | 20231114040 | 40 | Base Aggregate Dense 3/4-Inch | The project includes 50 tons of 3/4" Base. This quantity seems low and may want to be reviewed. | Since we are removing 2 in. of HMA and replacing it with 2 in. of HMA, no additional Base Aggregate Dense should be technically needed. I included the 50 tons in case additional material would be needed in conjunction with the â€œShaping Shouldersâ€ bid item. | Mike Coleman | 2 | 2023-10-30 08:56 | 2023-10-30 10:47
20231114 | 20231114041 | 41 | PROPOSAL SCHEDULE OF ITEMS LINE NUMBER 0352 | Line number 0352 is listed as a Qty 22 each for the Traffic Signal Face 3 Section. The plans on page 91 show a Qty of 20 signals 3 section & a Qty of 2 signals 4 section. Can you please confirm which is correct? | The plans on Page 91 are correct, and we are missing the bid item for the 4 section face. The bid item for the 4 section face will be added via addendum. | Mike Coleman | 1 | 2023-10-24 13:13 | 2023-10-26 07:35
20231114 | 20231114041 | 41 | Curb & Gutter Staking | The quantity of curb and gutter staking appears to include the 36-Inch Type A curb and gutter. The Standard Specifications state in Section 650.4 that Construction Staking Curb Gutter and Curb & Gutter will not be measured when adjacent to concrete pavement. Will the department pay for the Type A curb and gutter staking along with the concrete pavement staking? | Per the Standard Specifications the 36-Inch Type A curb & gutter will not be measured for payment under the Construction Staking Curb Gutter and Curb & Gutter item. The quantity of Construction Staking Curb Gutter and Curb & Gutter in the Proposal and Miscellaneous Quantities is incorrect, and will be corrected by addendum. | Mike Coleman | 2 | 2023-11-07 20:06 | 2023-11-08 11:49
20231114 | 20231114042 | 42 | Culvert Replacements | Since STH 64 will be closed to through traffic and will have full closures at the Hay Creek and Otter Creek structures, is it possible to utilize a full closure for any of the culvert replacements, specifically the 3-4 deeper replacements? | Full closure of the roadway at the culvert replacements is acceptable if culvert replacements are completed in a manner to maintain access to commercial and private entrances during construction. Emergency services should also be made aware of the schedule to complete the work and locations of expected full closures for culvert work. | Mike Coleman | 1 | 2023-11-08 13:17 | 2023-11-09 14:53
20231114 | 20231114043 | 43 | Floor Drain Substitution | In the past it has been difficult to procure Floor Drains Type GC within a reasonable time for bridge construction. Would it be acceptable to substitute a Floor Drain Type 'H'? | While the drains and hydraulic capacity are very similar (TYPE GC vs TYPE H), the Type H drain has 8â€ studs around the frame. With the back of the frame set 6â€ in from the face of the parapet, and 1.25â€™ from the face of the parapet to the edge of deck, there is only 1â€ clear from the edge of the deck to the end of the stud. This raises maintenance concerns and could result in spalling of the edge of deck at the drain locations. Please plan to use the Type GC drain as called out in the plans. | Mike Coleman | 1 | 2023-10-18 14:27 | 2023-10-19 12:28
20231114 | 20231114043 | 43 | HMA | Due to the small quantity, can the department change the pay item of HMA to Asphaltic Surface with a special provision to provide 4MT 58-34S? | An addendum will be issued to change to asphaltic surface. | Mike Coleman | 2 | 2023-10-26 07:45 | 2023-10-27 09:53
20231114 | 20231114043 | 43 | Painting Clarification | Notes on sheet 2 of the bridge plans call out painting all bearings but under the paint details on sheet 3 it only mentions painting the abutment bearings. Do all bearings at the piers need to be painted as well? |  |  | 3 | 2023-11-08 10:13
20231114 | 20231114044 | 44 | 643.3120 Temporary Epoxy 4-Inch | Can 4" Temporary Removable Tape be used instead of 4" Temporary Epoxy in this application? Temporary Epoxy typically isn't used for short term use (16 days). Thanks | An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-10-26 09:47 | 2023-11-02 07:10
20231114 | 20231114045 | 45 | Removing Asphaltic Surface | Removing of asphalt driveways for new tie-ins is not included in the quantity under â€œRemoving Asphaltic Surfaceâ€. How is removal of existing asphalt driveways/prep for asphalt paving being paid for? | This work was originally included in the quantity for Removing Asphaltic Surface Milling. This has been revised and moved to the Removing Asphaltic Surface item to allow the contractor more flexibility in how the material is removed. An addendum will be issued. | Mike Coleman | 1 | 2023-11-08 11:40 | 2023-11-09 06:43
20231114 | 20231114045 | 45 | Culvert Patching | Several culverts are being removed/replaced on the project, but there is no quantity for base course or asphalt patching in these areas? | Base course quantities/details have been updated to address this question. Culvert replacements are in the area where CTH X is closed and detoured, no asphaltic surface is required for the patches. An addendum will be issued | Mike Coleman | 2 | 2023-11-08 11:42 | 2023-11-09 06:45
20231114 | 20231114045 | 45 | Removing Aspahltic Surface. | I do not believe the addendum was correct as this qty was placed in the milling item. Please confirm. This work was originally included in the quantity for Removing Asphaltic Surface Milling. This has been revised and moved to the Removing Asphaltic Surface item to allow the contractor more flexibility in how the material is removed. An addendum will be issued. |  |  | 3 | 2023-11-09 09:35
20231114 | 20231114046 | 46 | North Leg Gore | On the north leg of CTH A sheet 15 shows the cross slope as 0 percent in the gore area. The slope draining lengthwise appears to also be minimal - 0.3% towards the RAB. This may want to be reviewed to improve drainage. | Thanks for the question. The intent is to have positive drainage through the gore, and we will update sheet 15 and the x-sections and provide an addendum to be inserted into the plans. | Mike Coleman | 1 | 2023-10-30 10:05 | 2023-10-30 13:02
20231114 | 20231114046 | 46 | Construction Staking - Subgrade, Base & Slope | It appears the quantities for Subgrade, Base and Slope staking does not show that CTH A has a northbound and southbound roadway which would be paid separately. The same would apply to McCutcheon Road which does not include quantities for a westbound and eastbound roadway. | After reviewing the 2023 WisDOT Standard Specification, we believe we are correct in the way we measured quantities for items: â€¢ 650.4500 Construction Staking Subgrade â€¢ 650.5000 Construction Staking Base â€¢ 650.9920 Construction Staking Slope Stakes. The spec reads these items should be measured by linear foot along each roadway centerline. This project is a rural 2-lane, undivided roadway with a splitter island for a section of each leg. We don't believe the contractor should be paid double as these are not divided roadways. This project will also be constructed as full closure and will not require multiple stages for construction staking. We also looked at several other roundabout projects in different parts of the state and verified that the staking items in question were measured similarly to how we measured them on CTH A & McCutchen Road project. | Mike Coleman | 2 | 2023-11-07 21:50 | 2023-11-08 14:54
20231114 | 20231114047 | 47 | Asphaltic Patching | 1. The contract includes Base Patching Asphaltic as well as Distressed Milling/Asphaltic Surface. How will the engineer determine which item(s) will be used? It seems as though it may be simpler to eliminate one or the other to avoid confusion and future arguments. 2. What is the anticipated depth of the Base Patching Asphaltic? | 1. â€œBase Patching Asphalticâ€ will be used where indicated in the plans, which is adjacent to â€œBase Patching Concreteâ€ where signal loops are being installed and the full depth of asphalt needs to be removed and replaced. â€œRemoving Distressed Pavement Millingâ€ is an undistributed item included for large areas that may need an additional 2 inches of milling to get to solid pavement after the initial milling operation is complete. These items require a different level of effort to remove the asphalt as well as having different standards for how pavement material is placed back in. The Engineer should be able to distinguish where each operation is appropriate so the â€œRemoving Distressed Pavement Millingâ€ item will remain in the project. 2. The existing asphalt shoulder and right turn lanes varies from 6.75 to 9 inches deep. With a 4-inch mill across the shoulder/turn lane, that leaves between 2.75 and 5 inches of remaining asphalt left to be removed and patched. Due to the potential variations in existing asphalt depth, the quantity in the plan conservatively estimates this depth to be 5 inches. | Mike Coleman | 1 | 2023-10-18 07:18 | 2023-10-24 11:28
20231114 | 20231114047 | 47 | Temporary Asphaltic Surface (Temp Crossover) | On sheet 2 of the Plan; in the "HMA PAVEMENT LAYERS AND GRADATION" table, the temp crossover asphaltic surface temporary is listed as a 2 lift 4" pavement composed of 2.25" & 1.75". Is there any reason why this could not be constructed as a 4" single lift pavement following WISDOT 460.3.2. | The temporary crossover pavement may be placed in a 4â€ single lift as allowed by Standard Spec 460.3.2. An addendum will be issued to revise the general notes page. | Mike Coleman | 2 | 2023-10-19 08:39 | 2023-10-24 11:31
20231114 | 20231114047 | 47 | Full Depth Asphaltic Patches STA 15+50EB - 37+00EB | On sheet 10 of the plan there is a note that reads "FULL DEPTH ASPHALT PATCHES ON STH 190 EB FROM STA 15+50EB TO STA. 37+00EB WILL BE PAID UNDER THE REMOVING CONCRETE BID ITEM". What patches is this note pertaining to? | In 2022, Waukesha County installed asphalt base patches on STH 190 EB from STA 15+50EB to STA 37+00EB. For ease of quantifying during construction, the removal of these asphaltic patches has been included in the Removing Concrete Pavement quantity. The estimated total area of these asphaltic patches is approximately 575 SY. | Mike Coleman | 3 | 2023-10-19 08:44 | 2023-10-24 11:33
20231114 | 20231114047 | 47 | Temp Cross-Over | Is there a typical section for the East and West temporary cross overs? |  |  | 4 | 2023-11-02 12:32
20231114 | 20231114047 | 47 | Base Patching | Does the item Removing Pavement for Base Patching (cy) include the full depth removal for Base Patching Concrete HES (cy), Concrete Pavement Repair (sy), and Concrete Pavement Replacement (sy)? | The Removing Pavement for Base Patching item only includes the full depth removals for the Base Patching Concrete HES and Base Patching Asphaltic items. The Concrete Pavement Repair and Concrete Pavement Replacement items include removing existing pavements and excavated materials. | Mike Coleman | 5 | 2023-11-06 07:03 | 2023-11-06 15:11
20231114 | 20231114047 | 47 | Base Patching | If the Removing Pavement for Base Patching item (1071 cy) includes the full depth removals for the Base Patching Concrete HES (571 cy) and Base Patching Asphaltic item (124 ton), why are the volume totals not equivalent to Removing Pavement for Base Patching? | Addendum #1 revised the quantity of Removing Pavement for Base Patching from 1071 CY to 628 CY. | Mike Coleman | 6 | 2023-11-07 07:46 | 2023-11-08 08:24
20231114 | 20231114047 | 47 | Intersection Closures | Per the Special Provisions Article 3 â€œInterim Completion and Liquidated Damages- Stage 2â€¦.â€, Contractors are allowed to close left turn lane movements at non-consecutive intersections for 7 day periods. Furthermore, in Article 4 â€œSTH 190 and side road right-turn and left-turn lanes are to remain open during peak hours unless specifically mentioned within this article. Do these statements allow for nighttime milling and paving operations thru intersections on the mainline and shoulders with short term closure/flagging operations during off peak hours? The reason behind the question is if the only time a contractor can mill and pave is by not closing left turn lanes or intersection at consecutive intersections, there will be approximately 15-20 transverse joints and a large amount of mobilization costs added to the contract for both operations. |  |  | 7 | 2023-11-08 07:34
20231114 | 20231114048 | 48 | missing information | are the rims and inverts available for the following items: manhole 6 ft diameter 1 each inlets 4 ft diameter 1 each inlets 2x3 ft 5 each also the pipe sizes needed for these manholes and inlet connections are not listed. | An addendum will be published to provide the missing information. | Mike Coleman | 1 | 2023-10-31 16:32 | 2023-11-02 11:21
20231114 | 20231114048 | 48 | storm sewer | Are rim and invert elevations available for Items 611.2006, 611.3004 and 611.3230? Also are the pipe diameters and inverts available for the existing storm sewer for these locations of the same items? | An addendum will be published to provide the missing information. | Mike Coleman | 2 | 2023-11-02 09:20 | 2023-11-02 13:38